NHS England - East

Health and Justice Commissioning

Evaluation of health information and advice through in-cell television

Contents

Introduction	2

Background	2

Content and scope of reports	2

Deliverables	3

Timetable	3

Price and Payment Terms	3

Evaluation and Scoring	4

# Introduction

NHS England wishes to understand the effectiveness of various pieces of work which have recently been initiated including the provision of health information and advice through broadcasting on in-cell television .  We are seeking to appoint an independent provider who can propose an appropriate way to evaluate the service, do the evaluation, and provide answers to the questions given.   methods of evaluation.

# Background

A piece of work  has recently been initiated to communicate health messages to prisoners while they are in their cells. Prisoners spend significant periods of time in their cells and as a result, watch many hours of television.  Television is therefore potentially a powerful way of communicating with prisoners, and offers the opportunity to repeat health messages over a long period.    NHS England has commissioned a provider of in-cell broadcasting to develop two ‘programmes’ which address health issues (mental health/coping while in prison,  and testing and treatment for hepatitis). The evaluation will ascertain whether the provision of health messages through in-cell TV broadcasting influences service users. The provider of the evaluation must aim to engage with at least 2 prisons where the content is broadcast, and one where it is not to ensure that the questions do not influence the responses (i.e. that the respondents prompt them to give positive answers even though they have not actually viewed the material).

The prisons where the content is broad cast are as follows:

HMP Bedford

HMP Bure

HMP Chelmsford

HMP Hollesley Bay

HMP Littlehey

HMP Norwich

HMP Peterborough

HMP Warren Hill

HMP Wayland

HMP Whitemoor		(locations and addresses available on the internet)

The control prison must be either HMP Highpoint or HMP The Mount. Introductions to all prisons will be made by NHS England.

# Content and scope of report

Bidders must aim to survey at least 25% of all service users being released at each prison during the period Oct- Nov-Dec 2018 in all 3 prisons.

The report must provide the following:

- A review of any published literature relating to the use of in-cell broadcasting (may include radio and television)  which considers how likely this medium is to be effective in disseminating messages to prisoners.

- The design and implementation of a survey of prisoners in at least 2 prisons where the material is broadcast, and one where it is not, which includes the following questions:

  - Did the Service User (SU) see any material relating to coping or BBV (to be operated across 3 prisons, one of which does not broadcast the material, to act as a control)

  - Did the SU act engage with a health service at any point in the following 3 months?

  - What did the SU recall about the in-cell TV broadcast? (free text reponse)

  - What comments do you have about using in-cell TV for health information? (free text response)

  - Record other effects as observed

- Operation of a focus group in each of the 3 prisons which asks the same questions as above, records remarks and undertakes a qualitative analysis of them.

# Deliverables

The provider of the report must provide both an initial draft and a final draft of the report  in Word. This allows comments to be made within the text of the initial draft, and also allows extraction of the text from the final draft for insertion into other documents. The initial and final drafts must be delivered to claire.weston2@nhs.net  in Word format.

# Timetable

The opportunity will be advertised to any potential provider in August 2018 and bids must be submitted by 17.00 on 7/9 2018 to emma.giles3@nhs.net .  NHS England will notify all bidders of the outcome within 1 week of this date. Bidders should request a receipt of their bid, and if this is not received by 17.00 on 10/9/18, they should contact  Emma Giles to request this.

The successful bidder must be in a position to begin work upon being appointed, and to complete the initial draft by 15/12/18. Comments will be provided within 1 week and a final draft should be provided by 15/01/19.

Bidders are expected to notify the commissioner of progress towards delivery of the initial and final drafts.

# Price and Payment Terms

The maximum value of acceptable bids is £10 000 (net of VAT).  Any bid which does not clearly state the price for the report will be rejected.  In formulating the bid price, bidders are asked to show their daily rate and the number of days consumed in each element of the preparation of the report.

Interested parties are requested to advise Commissioners of their fully inclusive price for undertaking the report to the specification set out in this document.   Should the report fail to fully meet the requirements of the service specification or deadline (unless due to factors outside of the Provider’s control) NHS England reserves the right to withhold up to 10% of the total contract value when paying the final invoice.  NHS England terms and condition will be applied.  No payment will be made for part completion of the report.

## Evaluation and Scoring

- Please submit a bid using the template completing each section.

- Please provide details of similar evaluations which you have previously undertaken including the date completed, and be prepared to provide these documents to NHS England on request.

- Please ensure that the bid to provide your report is the same name as the author of the report.  The purchase order will be raised in the name of the bidder and the invoice must correspond to the name on the purchase order and the bid.

Applications will evaluated and scored as follows:

Scoring Methodology

| 0 | The Provider is unable to fulfil the requirement or no response is received |
| --- | --- |
| 1 | The Provider is only able to partly fulfil the requirement |
| 2 | The Provider is able to fulfil the requirement |
| 3 | The Provider exceeds fulfilment of the requirement |

| Quality – weighted at 60% of total score |  |  |
| --- | --- | --- |
| The Provider has demonstrated that: |  |  |
| Review Deliverables | - All the objectives and products contained within the specification will be delivered. |  |
|  | - Comprehensive and suitable methodologies are proposed for all aspects of the evaluation, with the rationale for each. |  |
|  | - A suitable methodology and rationale will be adopted to operate focus groups |  |
|  | - Project challenges have been identified and suitable mitigations proposed. |  |
| Capability | - Experience of undertaking a similar piece of work, delivered to timescale. |  |
|  | - The availability of suitably competent staff who have relevant experience |  |
|  | - An understanding and application of, data confidentiality and information governance issues. |  |
|  | - They can deliver the report within the project deadline with a realistic timetable. |  |
| Price – Weighted at 40% of total score |  |  |
| Price |  | Price will be evaluated by the bid with the lowest score scoring 100 and all other bidder prices being expressed as an inverse proportion. For example, where maximum value for an opportunity is £60 000 Bid A – Price £30,000 = scores 100 Bid B – Price £40,000 = scores 75 Bid C - Price £50,000 = scores 60 Bid D – Price £60,000 = scores 50 |

Checklist for bidders

This check list may be helpful in developing your bid but may not be exhaustive:

- Each bid states        ‘Evaluation of in-cell TV + [bidder name]’       as a foot note on each page

- Each bid is page numbered

- Price for the bid has been provided, is net of VAT and is not subject to any proposed discounting.

- Each bid excludes the cost of making a presentation to NHS England on the findings

- Each bid states that the report will be delivered in Word.

- Each bid states the daily rate for the author and any associates  and the number of days consumed in each element of the task

- Each bid comes from the same organisation as the organisation which will submit the invoice for the report once complete, and the name of the invoicing organisation is clearly given.

-ends-