**Clarification Question**

Contract Reference: C21-0482-1589

Title:A review of disaster resilience work programmes in the inhabited UK Overseas Territories in the context of nature-based solutions

**Question.**

We note exact dates are to be agreed at start up meeting based on Contractor and JNCC availability.  What is the scope to extend the report deadline for component 1 and by how much?

**Answer: Revised timetable below for delivery of the contract outputs are set out below. Exact dates are to be agreed at start-up meeting.**

|  |  |
| --- | --- |
| **Milestones** | **Provisional dates** |
| Start-up meeting (UK) | Week commencing 27 September 2021 |
| 1. Draft report on Component 1
 | 29 November 2021 |
| 1. Draft report on Component 2 and 3
 | 12 January 2022 |
| 1. Final report
 | 04 February, 2022 |
| 1. Project sign off
 | 14 February 2022 |