## Instructions
Instructions for DIO's BIM Maturity Assessment Tool (BMAT)
1. The questions should be answered in full by the end of each project stage, looking back over that stage.
2. The questions should be answered collectively by the project team, with the DIO Project Manager having the final say if there is disagreement.
3. The questions are the same for each project stage and therefore at early stages many of the answers will be 'No' - the intention is to show maturity growing throughout the project stages.
4. If at a given project stage the question is 'not applicable' then the answer given should be 'No'.
5. It would only be possible to score 100% at the end of Stage 6.
6. Where a team member does not agree with the answer given, the table at the bottom of each project stage gives them the opportunity to state their concerns.
7. Other team members do not have to agree with the written statements given, as long as the party making the statement is prepared to put their name to it.

## Stage 1
DIO BIM Maturity Assessment Tool (BMAT) | [7 empty] | V1.0
Project name: | [7 empty] | project name
Project reference number: | [7 empty] | ???
Completed by: | [7 empty] | Names & Roles
Date completed: | [7 empty] | date
These questions aim to measure overall BIM maturity on a project, firstly BIM Level 2 and then also programme (4D) and costs (5D) BIM tools, in order to help measure
the benefits of BIM adoption; some questions relate to the Employer and some relate to the Supplier, so that their separate BIM maturity can be measured.
Project BIM Maturity | [7 empty] | 0%
Client BIM Delivery | [7 empty] | 0%
Supplier BIM Delivery | [7 empty] | 0%
| BIM Maturity Project Score | 0% |  | 0
|  | Achieved (Yes/No) |  | Score | Client Score | Supplier Score
1 | BIM Procurement / Employer Engagement | 0% |  | 0 | 0% |  |  | Information about the questions:
Confirm BIM and information delivery is appropriately defined in the context of the project.
a | The Employers Information Requirements (EIR) document has been issued for the project. | [5 empty] | Yes
b | The Information Delivery Plan (IDP) is comprehensive providing sufficient general & specific employer information requirements for the plan of work stage for the supplier to deliver to. | [5 empty] | No
c | The IDP has been adequately defined in the context of the project, detailing the deliverables, formats, Level of Definition (both Level of Detail and Level of Information) for the work stage to be contractually adopted.
d | Project specific Government Soft Landings (GSL) requirements have been provided, including defined outcome measurement, for a defined post operational evaluation process.
e | Where specific BIM surveys are required by the Employer, the purpose, format and extent of the surveys has been made clear in the EIR (for example point cloud surveys).
f | The Employer has a nominated Information Manager for the project?
g | If required (see PAS1192-5), the Employer has a nominated Security Manager for the project? | [6 empty] | If not required the answer is Yes.
2 | BIM Delivery | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm the suppliers have adequately defined their BIM and information delivery and are delivering to meet the Employer requirement.
a | The supplier has delivered BIM processes as described in the BIM Execution Plan (BEP). | [6 empty] | This looks back at the completed stage.
b | The BIM Execution Plan (BEP) is comprehensive, providing sufficient information about how the EIR and IDP are to be delivered at all project stages. | [6 empty] | This looks forwards towards the next stage.
c | A comprehensive Master Information Delivery Plan (MIDP) has been provided, that confirms delivery in response to the entire IDP. | [6 empty] | The stage at which supplier produces a MIDP will differ depending on how the project is procured.
d | The supplier has a nominated Information Manager for the project.
e | The information security requirements are being adhered to and aligned to the general project security requirements.
f | Surveys have been carried out in the format and to the extent described in the EIR/IDP.
g | Design management coordination and optimisation is being carried out as described in the BEP.
h | Commissioning has been or is planned to be supplied as described in the BEP.
i | O&M information has been or is planned to be supplied as described in the BEP.
j | Health & Safety information has been or is planned to be supplied as described in the BEP.
k | The supplier has provided information exchanges as required by the EIR/IDP and as detailed in the suppliers BEP/MIDP.
l | The supplier has provided published stage information exchanges complete with COBie data as defined in the EIR.
3 | Data, Verification and Validation | 0% |  | 0 | 0% | 0% |  | Information about the questions:
Confirm information, files and data, is being delivered, verified and validated, to enable the Employer to contractually rely on the information at the appropriate stages, for appropriate purposes.
a | Information and Data security policy is detailed in the Post BEP in line with the EIR and it is being applied. | [6 empty] | The answer to this question will depend on the stage at which the supplier is appointed.
b | Data is being provided in COBie to BS1192-4.
c | Published information: files and data has been verified (complete) & validated (correct) by the supplier prior to receipt into the Employer's Common Data Enivironment (CDE).
d | Published information: files and data received is being validated (complete) by the employer on receipt into the Employer's CDE.
e | Employer information verification issues are being reported back to the supplier. | [6 empty] | If no issues then answer is Yes. Please note that data validation is not a task carried out by the Employer.
4 | Collaborative working | 0% |  | 0 | 0% | 0% |  | Information about the questions:
Confirm that information is being used effectively to promote collaborative working within the supplier project team and with appropriate stakeholders.
a | The Employer CDE has been used throughout the appropriate stages of project by the supplier to PAS1192-3. | [6 empty] | This depends on the Employer providing a CDE so it is currently an Employer score.
b | A Supplier CDE has been used throughout the appropriate stages of the project by the supplier to PAS1192-2. | [6 empty] | This includes operating a CDE on the Employers behalf.
c | Iterative clash detection and mitigation processes are clearly set out and are being adhered to.
d | Risks are being identified and mitigated by using BIM processes, including, but not limited to, stakeholder engagement and clash detection.
e | The resolved coordinated BIM is being comprehensively referenced for site construction information.
5 | Visualisation / Stakeholder Engagement | 0% |  | 0 | 0% | 0% |  | Information about the questions:
Confirm that information, models & visualisations, are being effectively used to promote broad engagement and understanding.
a | Regular team reviews are taking place, including with the client team, clearly using an interactive federated model/data.
b | Use of federated model/data to present visualisation has taken place with stakeholders and benefits have been identified.
c | The federated model/data is being used as part of GSL processes by the supplier.
d | The federated model/data is being used as part of GSL processes by the employer/FM provider.
6 | Discipline based model authoring | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm information authorship and provenance is being used, promoted, maintained and tracked throughout the project lifecycle.
a | Federated discipline based models have been provided with a stage appropriate data sets.
b | The current model reflects the current design intent or as-built condition, as appropriate.
c | Buildability reviews have been carried out using the federated/discipline models.
d | All drawings and documents are also managed and accessible via the supplier and employer CDE.
e | Lower tier suppliers play an appropriate part in model authoring / content.
7 | Construction | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm the best use of BIM and information is being effectively used in the construction phase of a project.
a | Modelling based planning / efficient construction process is has been undertaken. | [6 empty] | 4D BIM is not a requirement of DIO BIM Level 2, but it is recognised that a project will benefit from it.
b | Visual scheduling / sequencing has been carried out.
c | Model use for safety planning in pre-construction and construction.
d | Model use for testing and commissioning.
e | O&M Manual referenced to the model as a minimum & included in the MIDP.
8 | Model based estimating and change management | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm that BIM and information is being effectively used to support cost, carbon and programme management.
a | Model use for cost estimating. | [6 empty] | 5D BIM is not a requirement of DIO BIM Level 2, but it is recognised that a project will benefit from it.
b | Model use for quantity take off.
c | Model use change management / value engineering, including proposed design enhancements and what-if scenario cost impacts/assessments
d | Model use detailed estimating, focusing detail on the parts that have a high risk.
Comments:
No. | Comment | Question No. | Author
1
2
3
4
5
6
7
8
9
10
Note: Please include comments that are relevant to the Yes/No scoring only.

## Stage 2
DIO BIM Maturity Assessment Tool (BMAT) | [7 empty] | V1.0
Project name: | [7 empty] | project name
Project reference number: | [7 empty] | ???
Completed by: | [7 empty] | Names & Roles
Date completed: | [7 empty] | date
These questions aim to measure overall BIM maturity on a project, firstly BIM Level 2 and then also programme (4D) and costs (5D) BIM tools, in order to help measure
the benefits of BIM adoption; some questions relate to the Employer and some relate to the Supplier, so that their separate BIM maturity can be measured.
Project BIM Maturity | [7 empty] | 0%
Client BIM Delivery | [7 empty] | 0%
Supplier BIM Delivery | [7 empty] | 0%
| BIM Maturity Project Score | 0% |  | 0
|  | Achieved (Yes/No) |  | Score | Client Score | Supplier Score
1 | BIM Procurement / Employer Engagement | 0% |  | 0 | 0% |  |  | Information about the questions:
Confirm BIM and information delivery is appropriately defined in the context of the project.
a | The Employers Information Requirements (EIR) document has been issued for the project. | [5 empty] | Yes
b | The Information Delivery Plan (IDP) is comprehensive providing sufficient general & specific employer information requirements for the plan of work stage for the supplier to deliver to. | [5 empty] | No
c | The IDP has been adequately defined in the context of the project, detailing the deliverables, formats, Level of Definition (both Level of Detail and Level of Information) for the work stage to be contractually adopted.
d | Project specific Government Soft Landings (GSL) requirements have been provided, including defined outcome measurement, for a defined post operational evaluation process.
e | Where specific BIM surveys are required by the Employer, the purpose, format and extent of the surveys has been made clear in the EIR (for example point cloud surveys).
f | The Employer has a nominated Information Manager for the project?
g | If required (see PAS1192-5), the Employer has a nominated Security Manager for the project? | [6 empty] | If not required the answer is Yes.
2 | BIM Delivery | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm the suppliers have adequately defined their BIM and information delivery and are delivering to meet the Employer requirement.
a | The supplier has delivered BIM processes as described in the BIM Execution Plan (BEP). | [6 empty] | This looks back at the completed stage.
b | The BIM Execution Plan (BEP) is comprehensive, providing sufficient information about how the EIR and IDP are to be delivered at all project stages. | [6 empty] | This looks forwards towards the next stage.
c | A comprehensive Master Information Delivery Plan (MIDP) has been provided, that confirms delivery in response to the entire IDP. | [6 empty] | The stage at which supplier produces a MIDP will differ depending on how the project is procured.
d | The supplier has a nominated Information Manager for the project.
e | The information security requirements are being adhered to and aligned to the general project security requirements.
f | Surveys have been carried out in the format and to the extent described in the EIR/IDP.
g | Design management coordination and optimisation is being carried out as described in the BEP.
h | Commissioning has been or is planned to be supplied as described in the BEP.
i | O&M information has been or is planned to be supplied as described in the BEP.
j | Health & Safety information has been or is planned to be supplied as described in the BEP.
k | The supplier has provided information exchanges as required by the EIR/IDP and as detailed in the suppliers BEP/MIDP.
l | The supplier has provided published stage information exchanges complete with COBie data as defined in the EIR.
3 | Data, Verification and Validation | 0% |  | 0 | 0% | 0% |  | Information about the questions:
Confirm information, files and data, is being delivered, verified and validated, to enable the Employer to contractually rely on the information at the appropriate stages, for appropriate purposes.
a | Information and Data security policy is detailed in the Post BEP in line with the EIR and it is being applied. | [6 empty] | The answer to this question will depend on the stage at which the supplier is appointed.
b | Data is being provided in COBie to BS1192-4.
c | Published information: files and data has been verified (complete) & validated (correct) by the supplier prior to receipt into the Employer's CDE.
d | Published information: files and data received is being validated (complete) by the employer on receipt into the Employer's CDE.
e | Employer information verification issues are being reported back to the supplier. | [6 empty] | If no issues then answer is Yes. Please note that data validation is not a task carried out by the Employer.
4 | Collaborative working | 0% |  | 0 | 0% | 0% |  | Information about the questions:
Confirm that information is being used effectively to promote collaborative working within the supplier project team and with appropriate stakeholders.
a | The Employer CDE has been used throughout the appropriate stages of project by the supplier to PAS1192-3. | [6 empty] | This depends on the Employer providing a CDE so it is currently an Employer score.
b | A Supplier CDE has been used throughout the appropriate stages of the project by the supplier to PAS1192-2. | [6 empty] | This includes operating a CDE on the Employers behalf.
c | Iterative clash detection and mitigation processes are clearly set out and are being adhered to.
d | Risks are being identified and mitigated by using BIM processes, including, but not limited to, stakeholder engagement and clash detection.
e | The resolved coordinated BIM is being comprehensively referenced for site construction information.
5 | Visualisation / Stakeholder Engagement | 0% |  | 0 | 0% | 0% |  | Information about the questions:
Confirm that information, models & visualisations, are being effectively used to promote broad engagement and understanding.
a | Regular team reviews are taking place, including with the client team, clearly using an interactive federated model/data.
b | Use of federated model/data to present visualisation has taken place with stakeholders and benefits have been identified.
c | The federated model/data is being used as part of GSL processes by the supplier.
d | The federated model/data is being used as part of GSL processes by the employer/FM provider.
6 | Discipline based model authoring | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm information authorship and provenance is being used, promoted, maintained and tracked throughout the project lifecycle.
a | Federated discipline based models have been provided with a stage appropriate data sets.
b | The current model reflects the current design intent or as-built condition, as appropriate.
c | Buildability reviews have been carried out using the federated/discipline models.
d | All drawings and documents are also managed and accessible via the supplier and employer CDE.
e | Lower tier suppliers play an appropriate part in model authoring / content.
7 | Construction | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm the best use of BIM and information is being effectively used in the construction phase of a project.
a | Modelling based planning / efficient construction process is has been undertaken. | [6 empty] | 4D BIM is not a requirement of DIO BIM Level 2, but it is recognised that a project will benefit from it.
b | Visual scheduling / sequencing has been carried out.
c | Model use for safety planning in pre-construction and construction.
d | Model use for testing and commissioning.
e | O&M Manual referenced to the model as a minimum & included in the MIDP.
8 | Model based estimating and change management | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm that BIM and information is being effectively used to support cost, carbon and programme management.
a | Model use for cost estimating. | [6 empty] | 5D BIM is not a requirement of DIO BIM Level 2, but it is recognised that a project will benefit from it.
b | Model use for quantity take off.
c | Model use change management / value engineering, including proposed design enhancements and what-if scenario cost impacts/assessments
d | Model use detailed estimating, focusing detail on the parts that have a high risk.
Comments:
No. | Comment | Question No. | Author
1
2
3
4
5
6
7
8
9
10
Note: Please include comments that are relevant to the Yes/No scoring only.

## Stage 3
DIO BIM Maturity Assessment Tool (BMAT) | [7 empty] | V1.0
Project name: | [7 empty] | project name
Project reference number: | [7 empty] | ???
Completed by: | [7 empty] | Names & Roles
Date completed: | [7 empty] | date
These questions aim to measure overall BIM maturity on a project, firstly BIM Level 2 and then also programme (4D) and costs (5D) BIM tools, in order to help measure
the benefits of BIM adoption; some questions relate to the Employer and some relate to the Supplier, so that their separate BIM maturity can be measured.
Project BIM Maturity | [7 empty] | 0%
Client BIM Delivery | [7 empty] | 0%
Supplier BIM Delivery | [7 empty] | 0%
| BIM Maturity Project Score | 0% |  | 0
|  | Achieved (Yes/No) |  | Score | Client Score | Supplier Score
1 | BIM Procurement / Employer Engagement | 0% |  | 0 | 0% |  |  | Information about the questions:
Confirm BIM and information delivery is appropriately defined in the context of the project.
a | The Employers Information Requirements (EIR) document has been issued for the project. | [5 empty] | Yes
b | The Information Delivery Plan (IDP) is comprehensive providing sufficient general & specific employer information requirements for the plan of work stage for the supplier to deliver to. | [5 empty] | No
c | The IDP has been adequately defined in the context of the project, detailing the deliverables, formats, Level of Definition (both Level of Detail and Level of Information) for the work stage to be contractually adopted. | [6 empty] | It should be noted that EIR may require revision prior to going out to tender.
d | Project specific Government Soft Landings (GSL) requirements have been provided, including defined outcome measurement, for a defined post operational evaluation process.
e | Where specific BIM surveys are required by the Employer, the purpose, format and extent of the surveys has been made clear in the EIR (for example point cloud surveys).
f | The Employer has a nominated Information Manager for the project?
g | If required (see PAS1192-5), the Employer has a nominated Security Manager for the project? | [6 empty] | If not required the answer is Yes.
2 | BIM Delivery | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm the suppliers have adequately defined their BIM and information delivery and are delivering to meet the Employer requirement.
a | The supplier has delivered BIM processes as described in the BIM Execution Plan (BEP). | [6 empty] | This looks back at the completed stage.
b | The BIM Execution Plan (BEP) is comprehensive, providing sufficient information about how the EIR and IDP are to be delivered at all project stages. | [6 empty] | This looks forwards towards the next stage.
c | A comprehensive Master Information Delivery Plan (MIDP) has been provided, that confirms delivery in response to the entire IDP. | [6 empty] | The stage at which supplier produces a MIDP will differ depending on how the project is procured.
d | The supplier has a nominated Information Manager for the project.
e | The information security requirements are being adhered to and aligned to the general project security requirements.
f | Surveys have been carried out in the format and to the extent described in the EIR/IDP.
g | Design management coordination and optimisation is being carried out as described in the BEP.
h | Commissioning has been or is planned to be supplied as described in the BEP. | [6 empty] | Normally occurs in Stage 5
i | O&M information has been or is planned to be supplied as described in the BEP. | [6 empty] | Normally occurs in Stage 5
j | Health & Safety information has been or is planned to be supplied as described in the BEP.
k | The supplier has provided information exchanges as required by the EIR/IDP and as detailed in the suppliers BEP/MIDP. | [6 empty] | The supplier at this stage is deemed to be the PSP and his supply chain.
l | The supplier has provided published stage information exchanges complete with COBie data as defined in the EIR. | [6 empty] | The supplier at this stage is deemed to be the PSP and his supply chain.
3 | Data, Verification and Validation | 0% |  | 0 | 0% | 0% |  | Information about the questions:
Confirm information, files and data, is being delivered, verified and validated, to enable the Employer to contractually rely on the information at the appropriate stages, for appropriate purposes.
a | Information and Data security policy is detailed in the Post BEP in line with the EIR and it is being applied. | [6 empty] | The answer to this question will depend on the stage at which the supplier is appointed. This refers to the PSP's post BEP.
b | Data is being provided in COBie to BS1192-4.
c | Published information: files and data has been verified (complete) & validated (correct) by the supplier prior to receipt into the Employer's CDE. | [6 empty] | Assumes supplier at this stage is the PSP and/or their supply chain
d | Published information: files and data received is being validated (complete) by the employer on receipt into the Employer's CDE. | [6 empty] | Assumes supplier at this stage is the PSP and/or their supply chain
e | Employer information verification issues are being reported back to the supplier. | [6 empty] | If no issues then answer is Yes. Please note that data validation is not a task carried out by the Employer.
4 | Collaborative working | 0% |  | 0 | 0% | 0% |  | Information about the questions:
Confirm that information is being used effectively to promote collaborative working within the supplier project team and with appropriate stakeholders.
a | The Employer CDE has been used throughout the appropriate stages of project by the supplier to PAS1192-3. | [6 empty] | This depends on the Employer providing a CDE so it is currently an Employer score.
b | A Supplier CDE has been used throughout the appropriate stages of the project by the supplier to PAS1192-2. | [6 empty] | This includes operating a CDE on the Employers behalf.
c | Iterative clash detection and mitigation processes are clearly set out and are being adhered to.
d | Risks are being identified and mitigated by using BIM processes, including, but not limited to, stakeholder engagement and clash detection.
e | The resolved coordinated BIM is being comprehensively referenced for site construction information. | [6 empty] | It is assumed this will take place from Stage 5 onwards.
5 | Visualisation / Stakeholder Engagement | 0% |  | 0 | 0% | 0% |  | Information about the questions:
Confirm that information, models & visualisations, are being effectively used to promote broad engagement and understanding.
a | Regular team reviews are taking place, including with the client team, clearly using an interactive federated model/data.
b | Use of federated model/data to present visualisation has taken place with stakeholders and benefits have been identified.
c | The federated model/data is being used as part of GSL processes by the supplier.
d | The federated model/data is being used as part of GSL processes by the employer/FM provider.
6 | Discipline based model authoring | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm information authorship and provenance is being used, promoted, maintained and tracked throughout the project lifecycle.
a | Federated discipline based models have been provided with a stage appropriate data sets.
b | The current model reflects the current design intent or as-built condition, as appropriate.
c | Buildability reviews have been carried out using the federated/discipline models. | [6 empty] | It is assumed this will take place from Stage 4 onwards.
d | All drawings and documents are also managed and accessible via the supplier and employer CDE.
e | Lower tier suppliers play an appropriate part in model authoring / content. | [6 empty] | It is assumed this will take place from Stage 4 onwards, once the Constructor is the supplier.
7 | Construction | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm the best use of BIM and information is being effectively used in the construction phase of a project.
a | Modelling based planning / efficient construction process is has been undertaken. | [6 empty] | It is assumed this will take place from Stage 4 onwards.
b | Visual scheduling / sequencing has been carried out. | [6 empty] | It is assumed this will take place from Stage 4 onwards.
c | Model use for safety planning in pre-construction and construction. | [6 empty] | It is assumed this will take place from Stage 4 onwards.
d | Model use for testing and commissioning.
e | O&M Manual referenced to the model as a minimum & included in the MIDP. | [6 empty] | It is assumed this will take place from Stage 6 onwards.
8 | Model based estimating and change management | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm that BIM and information is being effectively used to support cost, carbon and programme management.
a | Model use for cost estimating. | [6 empty] | This target answer will remain No because it is optional and not part of the BIM Level 2 standards. However the project will be deemed more mature if the answer is Yes.
b | Model use for quantity take off. | [6 empty] | This target answer will remain No because it is optional and not part of the BIM Level 2 standards. However the project will be deemed more mature if the answer is Yes.
c | Model use change management / value engineering, including proposed design enhancements and what-if scenario cost impacts/assessments
d | Model use detailed estimating, focusing detail on the parts that have a high risk. | [6 empty] | This target answer will remain No because it is optional and not part of the BIM Level 2 standards. However the project will be deemed more mature if the answer is Yes.
Comments:
No. | Comment | Question No. | Author
1
2
3
4
5
6
7
8
9
10
Note: Please include comments that are relevant to the Yes/No scoring only.

## Stage 4
DIO BIM Maturity Assessment Tool (BMAT) | [7 empty] | V1.0
Project name: | [7 empty] | project name
Project reference number: | [7 empty] | ???
Completed by: | [7 empty] | Names & Roles
Date completed: | [7 empty] | date
These questions aim to measure overall BIM maturity on a project, firstly BIM Level 2 and then also programme (4D) and costs (5D) BIM tools, in order to help measure
the benefits of BIM adoption; some questions relate to the Employer and some relate to the Supplier, so that their separate BIM maturity can be measured.
Project BIM Maturity | [7 empty] | 0%
Client BIM Delivery | [7 empty] | 0%
Supplier BIM Delivery | [7 empty] | 0%
| BIM Maturity Project Score | 0% |  | 0
|  | Achieved (Yes/No) |  | Score | Client Score | Supplier Score
1 | BIM Procurement / Employer Engagement | 0% |  | 0 | 0% |  |  | Information about the questions:
Confirm BIM and information delivery is appropriately defined in the context of the project.
a | The Employers Information Requirements (EIR) document has been issued for the project. | [5 empty] | Yes
b | The Information Delivery Plan (IDP) is comprehensive providing sufficient general & specific employer information requirements for the plan of work stage for the supplier to deliver to. | [5 empty] | No
c | The IDP has been adequately defined in the context of the project, detailing the deliverables, formats, Level of Definition (both Level of Detail and Level of Information) for the work stage to be contractually adopted. | [6 empty] | It should be noted that EIR may require revision prior to going out to tender.
d | Project specific Government Soft Landings (GSL) requirements have been provided, including defined outcome measurement, for a defined post operational evaluation process.
e | Where specific BIM surveys are required by the Employer, the purpose, format and extent of the surveys has been made clear in the EIR (for example point cloud surveys).
f | The Employer has a nominated Information Manager for the project?
g | If required (see PAS1192-5), the Employer has a nominated Security Manager for the project? | [6 empty] | If not required the answer is Yes.
2 | BIM Delivery | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm the suppliers have adequately defined their BIM and information delivery and are delivering to meet the Employer requirement.
a | The supplier has delivered BIM processes as described in the BIM Execution Plan (BEP). | [6 empty] | This looks back at the completed stage.
b | The BIM Execution Plan (BEP) is comprehensive, providing sufficient information about how the EIR and IDP are to be delivered at all project stages. | [6 empty] | This looks forwards towards the next stage.
c | A comprehensive Master Information Delivery Plan (MIDP) has been provided, that confirms delivery in response to the entire IDP. | [6 empty] | The stage at which supplier produces a MIDP will differ depending on how the project is procured. Post Constructor contract award the constructor MIDP should have been produced.
d | The supplier has a nominated Information Manager for the project.
e | The information security requirements are being adhered to and aligned to the general project security requirements.
f | Surveys have been carried out in the format and to the extent described in the EIR/IDP.
g | Design management coordination and optimisation is being carried out as described in the BEP.
h | Commissioning has been or is planned to be supplied as described in the BEP. | [6 empty] | Normally occurs in Stage 5
i | O&M information has been or is planned to be supplied as described in the BEP. | [6 empty] | Normally occurs in Stage 5
j | Health & Safety information has been or is planned to be supplied as described in the BEP.
k | The supplier has provided information exchanges as required by the EIR/IDP and as detailed in the suppliers BEP/MIDP.
l | The supplier has provided published stage information exchanges complete with COBie data as defined in the EIR.
3 | Data, Verification and Validation | 0% |  | 0 | 0% | 0% |  | Information about the questions:
Confirm information, files and data, is being delivered, verified and validated, to enable the Employer to contractually rely on the information at the appropriate stages, for appropriate purposes.
a | Information and Data security policy is detailed in the Post BEP in line with the EIR and it is being applied. | [6 empty] | The answer to this question will depend on the stage at which the supplier is appointed.
b | Data is being provided in COBie to BS1192-4.
c | Published information: files and data has been verified (complete) & validated (correct) by the supplier prior to receipt into the Employer's CDE.
d | Published information: files and data received is being validated (complete) by the employer on receipt into the Employer's CDE.
e | Employer information verification issues are being reported back to the supplier. | [6 empty] | If no issues then answer is Yes. Please note that data validation at this stage is carried out by the PSP.
4 | Collaborative working | 0% |  | 0 | 0% | 0% |  | Information about the questions:
Confirm that information is being used effectively to promote collaborative working within the supplier project team and with appropriate stakeholders.
a | The Employer CDE has been used throughout the appropriate stages of project by the supplier to PAS1192-3. | [6 empty] | This depends on the Employer providing a CDE so it is currently an Employer score.
b | A Supplier CDE has been used throughout the appropriate stages of the project by the supplier to PAS1192-2. | [6 empty] | This includes operating a CDE on the Employers behalf.
c | Iterative clash detection and mitigation processes are clearly set out and are being adhered to.
d | Risks are being identified and mitigated by using BIM processes, including, but not limited to, stakeholder engagement and clash detection.
e | The resolved coordinated BIM is being comprehensively referenced for site construction information. | [6 empty] | It is assumed this will take place from Stage 5 onwards.
5 | Visualisation / Stakeholder Engagement | 0% |  | 0 | 0% | 0% |  | Information about the questions:
Confirm that information, models & visualisations, are being effectively used to promote broad engagement and understanding.
a | Regular team reviews are taking place, including with the client team, clearly using an interactive federated model/data.
b | Use of federated model/data to present visualisation has taken place with stakeholders and benefits have been identified.
c | The federated model/data is being used as part of GSL processes by the supplier.
d | The federated model/data is being used as part of GSL processes by the employer/FM provider.
6 | Discipline based model authoring | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm information authorship and provenance is being used, promoted, maintained and tracked throughout the project lifecycle.
a | Federated discipline based models have been provided with a stage appropriate data sets.
b | The current model reflects the current design intent or as-built condition, as appropriate.
c | Buildability reviews have been carried out using the federated/discipline models.
d | All drawings and documents are also managed and accessible via the supplier and employer CDE.
e | Lower tier suppliers play an appropriate part in model authoring / content.
7 | Construction | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm the best use of BIM and information is being effectively used in the construction phase of a project.
a | Modelling based planning / efficient construction process is has been undertaken.
b | Visual scheduling / sequencing has been carried out.
c | Model use for safety planning in pre-construction and construction.
d | Model use for testing and commissioning.
e | O&M Manual referenced to the model as a minimum & included in the MIDP. | [6 empty] | It is assumed this will take place from Stage 6 onwards.
8 | Model based estimating and change management | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm that BIM and information is being effectively used to support cost, carbon and programme management.
a | Model use for cost estimating. | [6 empty] | This target answer will remain No because it is optional and not part of the BIM Level 2 standards. However the project will be deemed more mature if the answer is Yes.
b | Model use for quantity take off. | [6 empty] | This target answer will remain No because it is optional and not part of the BIM Level 2 standards. However the project will be deemed more mature if the answer is Yes.
c | Model use change management / value engineering, including proposed design enhancements and what-if scenario cost impacts/assessments
d | Model use detailed estimating, focusing detail on the parts that have a high risk. | [6 empty] | This target answer will remain No because it is optional and not part of the BIM Level 2 standards. However the project will be deemed more mature if the answer is Yes.
Comments:
No. | Comment | Question No. | Author
1
2
3
4
5
6
7
8
9
10
Note: Please include comments that are relevant to the Yes/No scoring only.

## Stage 5
DIO BIM Maturity Assessment Tool (BMAT) | [7 empty] | V1.0
Project name: | [7 empty] | project name
Project reference number: | [7 empty] | ???
Completed by: | [7 empty] | Names & Roles
Date completed: | [7 empty] | date
These questions aim to measure overall BIM maturity on a project, firstly BIM Level 2 and then also programme (4D) and costs (5D) BIM tools, in order to help measure
the benefits of BIM adoption; some questions relate to the Employer and some relate to the Supplier, so that their separate BIM maturity can be measured.
Project BIM Maturity | [7 empty] | 0%
Client BIM Delivery | [7 empty] | 0%
Supplier BIM Delivery | [7 empty] | 0%
| BIM Maturity Project Score | 0% |  | 0
|  | Achieved (Yes/No) |  | Score | Client Score | Supplier Score
1 | BIM Procurement / Employer Engagement | 0% |  | 0 | 0% |  |  | Information about the questions:
Confirm BIM and information delivery is appropriately defined in the context of the project.
a | The Employers Information Requirements (EIR) document has been issued for the project. | [5 empty] | Yes
b | The Information Delivery Plan (IDP) is comprehensive providing sufficient general & specific employer information requirements for the plan of work stage for the supplier to deliver to. | [5 empty] | No
c | The IDP has been adequately defined in the context of the project, detailing the deliverables, formats, Level of Definition (both Level of Detail and Level of Information) for the work stage to be contractually adopted.
d | Project specific Government Soft Landings (GSL) requirements have been provided, including defined outcome measurement, for a defined post operational evaluation process.
e | Where specific BIM surveys are required by the Employer, the purpose, format and extent of the surveys has been made clear in the EIR (for example point cloud surveys).
f | The Employer has a nominated Information Manager for the project?
g | If required (see PAS1192-5), the Employer has a nominated Security Manager for the project? | [6 empty] | If not required the answer is Yes.
2 | BIM Delivery | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm the suppliers have adequately defined their BIM and information delivery and are delivering to meet the Employer requirement.
a | The supplier has delivered BIM processes as described in the BIM Execution Plan (BEP). | [6 empty] | This looks back at the completed stage.
b | The BIM Execution Plan (BEP) is comprehensive, providing sufficient information about how the EIR and IDP are to be delivered at all project stages. | [6 empty] | This looks forwards towards the next stage.
c | A comprehensive Master Information Delivery Plan (MIDP) has been provided, that confirms delivery in response to the entire IDP. | [6 empty] | The stage at which supplier produces a MIDP will differ depending on how the project is procured.
d | The supplier has a nominated Information Manager for the project.
e | The information security requirements are being adhered to and aligned to the general project security requirements.
f | Surveys have been carried out in the format and to the extent described in the EIR/IDP.
g | Design management coordination and optimisation is being carried out as described in the BEP.
h | Commissioning has been or is planned to be supplied as described in the BEP.
i | O&M information has been or is planned to be supplied as described in the BEP.
j | Health & Safety information has been or is planned to be supplied as described in the BEP.
k | The supplier has provided information exchanges as required by the EIR/IDP and as detailed in the suppliers BEP/MIDP.
l | The supplier has provided published stage information exchanges complete with COBie data as defined in the EIR.
3 | Data, Verification and Validation | 0% |  | 0 | 0% | 0% |  | Information about the questions:
Confirm information, files and data, is being delivered, verified and validated, to enable the Employer to contractually rely on the information at the appropriate stages, for appropriate purposes.
a | Information and Data security policy is detailed in the Post BEP in line with the EIR and it is being applied.
b | Data is being provided in COBie to BS1192-4.
c | Published information: files and data has been verified (complete) & validated (correct) by the supplier prior to receipt into the Employer's CDE.
d | Published information: files and data received is being validated (complete) by the employer on receipt into the Employer's CDE.
e | Employer information verification issues are being reported back to the supplier. | [6 empty] | If no issues then answer is Yes. Please note that data validation at this stage is carried out by the PSP.
4 | Collaborative working | 0% |  | 0 | 0% | 0% |  | Information about the questions:
Confirm that information is being used effectively to promote collaborative working within the supplier project team and with appropriate stakeholders.
a | The Employer CDE has been used throughout the appropriate stages of project by the supplier to PAS1192-3. | [6 empty] | This depends on the Employer providing a CDE so it is currently an Employer score.
b | A Supplier CDE has been used throughout the appropriate stages of the project by the supplier to PAS1192-2. | [6 empty] | This includes operating a CDE on the Employers behalf.
c | Iterative clash detection and mitigation processes are clearly set out and are being adhered to.
d | Risks are being identified and mitigated by using BIM processes, including, but not limited to, stakeholder engagement and clash detection.
e | The resolved coordinated BIM is being comprehensively referenced for site construction information.
5 | Visualisation / Stakeholder Engagement | 0% |  | 0 | 0% | 0% |  | Information about the questions:
Confirm that information, models & visualisations, are being effectively used to promote broad engagement and understanding.
a | Regular team reviews are taking place, including with the client team, clearly using an interactive federated model/data.
b | Use of federated model/data to present visualisation has taken place with stakeholders and benefits have been identified.
c | The federated model/data is being used as part of GSL processes by the supplier.
d | The federated model/data is being used as part of GSL processes by the employer/FM provider.
6 | Discipline based model authoring | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm information authorship and provenance is being used, promoted, maintained and tracked throughout the project lifecycle.
a | Federated discipline based models have been provided with a stage appropriate data sets.
b | The current model reflects the current design intent or as-built condition, as appropriate.
c | Buildability reviews have been carried out using the federated/discipline models.
d | All drawings and documents are also managed and accessible via the supplier and employer CDE.
e | Lower tier suppliers play an appropriate part in model authoring / content.
7 | Construction | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm the best use of BIM and information is being effectively used in the construction phase of a project.
a | Modelling based planning / efficient construction process is has been undertaken.
b | Visual scheduling / sequencing has been carried out.
c | Model use for safety planning in pre-construction and construction.
d | Model use for testing and commissioning.
e | O&M Manual referenced to the model as a minimum & included in the MIDP. | [6 empty] | It is assumed this will take place from Stage 6 onwards.
8 | Model based estimating and change management | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm that BIM and information is being effectively used to support cost, carbon and programme management.
a | Model use for cost estimating. | [6 empty] | This target answer will remain No because it is optional and not part of the BIM Level 2 standards. However the project will be deemed more mature if the answer is Yes.
b | Model use for quantity take off. | [6 empty] | This target answer will remain No because it is optional and not part of the BIM Level 2 standards. However the project will be deemed more mature if the answer is Yes.
c | Model use change management / value engineering, including proposed design enhancements and what-if scenario cost impacts/assessments
d | Model use detailed estimating, focusing detail on the parts that have a high risk. | [6 empty] | This target answer will remain No because it is optional and not part of the BIM Level 2 standards. However the project will be deemed more mature if the answer is Yes.
Comments:
No. | Comment | Question No. | Author
1
2
3
4
5
6
7
8
9
10
Note: Please include comments that are relevant to the Yes/No scoring only.

## Stage 6
DIO BIM Maturity Assessment Tool (BMAT) | [7 empty] | V1.0
Project name: | [7 empty] | project name
Project reference number: | [7 empty] | ???
Completed by: | [7 empty] | Names & Roles
Date completed: | [7 empty] | date
These questions aim to measure overall BIM maturity on a project, firstly BIM Level 2 and then also programme (4D) and costs (5D) BIM tools, in order to help measure
the benefits of BIM adoption; some questions relate to the Employer and some relate to the Supplier, so that their separate BIM maturity can be measured.
Project BIM Maturity | [7 empty] | 0%
Client BIM Delivery | [7 empty] | 0%
Supplier BIM Delivery | [7 empty] | 0%
| BIM Maturity Project Score | 0% |  | 0
|  | Achieved (Yes/No) |  | Score | Client Score | Supplier Score
1 | BIM Procurement / Employer Engagement | 0% |  | 0 | 0% |  |  | Information about the questions:
Confirm BIM and information delivery is appropriately defined in the context of the project.
a | The Employers Information Requirements (EIR) document has been issued for the project. | [5 empty] | Yes
b | The Information Delivery Plan (IDP) is comprehensive providing sufficient general & specific employer information requirements for the plan of work stage for the supplier to deliver to. | [5 empty] | No
c | The IDP has been adequately defined in the context of the project, detailing the deliverables, formats, Level of Definition (both Level of Detail and Level of Information) for the work stage to be contractually adopted.
d | Project specific Government Soft Landings (GSL) requirements have been provided, including defined outcome measurement, for a defined post operational evaluation process.
e | Where specific BIM surveys are required by the Employer, the purpose, format and extent of the surveys has been made clear in the EIR (for example point cloud surveys).
f | The Employer has a nominated Information Manager for the project?
g | If required (see PAS1192-5), the Employer has a nominated Security Manager for the project? | [6 empty] | If not required the answer is Yes.
2 | BIM Delivery | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm the suppliers have adequately defined their BIM and information delivery and are delivering to meet the Employer requirement.
a | The supplier has delivered BIM processes as described in the BIM Execution Plan (BEP). | [6 empty] | This looks back at the completed stage.
b | The BIM Execution Plan (BEP) is comprehensive, providing sufficient information about how the EIR and IDP are to be delivered at all project stages. | [6 empty] | This looks forwards towards the next stage.
c | A comprehensive Master Information Delivery Plan (MIDP) has been provided, that confirms delivery in response to the entire IDP. | [6 empty] | The stage at which supplier produces a MIDP will differ depending on how the project is procured.
d | The supplier has a nominated Information Manager for the project.
e | The information security requirements are being adhered to and aligned to the general project security requirements.
f | Surveys have been carried out in the format and to the extent described in the EIR/IDP.
g | Design management coordination and optimisation is being carried out as described in the BEP.
h | Commissioning has been or is planned to be supplied as described in the BEP.
i | O&M information has been or is planned to be supplied as described in the BEP.
j | Health & Safety information has been or is planned to be supplied as described in the BEP.
k | The supplier has provided information exchanges as required by the EIR/IDP and as detailed in the suppliers BEP/MIDP.
l | The supplier has provided published stage information exchanges complete with COBie data as defined in the EIR.
3 | Data, Verification and Validation | 0% |  | 0 | 0% | 0% |  | Information about the questions:
Confirm information, files and data, is being delivered, verified and validated, to enable the Employer to contractually rely on the information at the appropriate stages, for appropriate purposes.
a | Information and Data security policy is detailed in the Post BEP in line with the EIR and it is being applied.
b | Data is being provided in COBie to BS1192-4.
c | Published information: files and data has been verified (complete) & validated (correct) by the supplier prior to receipt into the Employer's CDE.
d | Published information: files and data received is being validated (complete) by the employer on receipt into the Employer's CDE.
e | Employer information verification issues are being reported back to the supplier. | [6 empty] | If no issues then answer is Yes. Please note that data validation at this stage is carried out by the PSP.
4 | Collaborative working | 0% |  | 0 | 0% | 0% |  | Information about the questions:
Confirm that information is being used effectively to promote collaborative working within the supplier project team and with appropriate stakeholders.
a | The Employer CDE has been used throughout the appropriate stages of project by the supplier to PAS1192-3. | [6 empty] | This depends on the Employer providing a CDE so it is currently an Employer score.
b | A Supplier CDE has been used throughout the appropriate stages of the project by the supplier to PAS1192-2. | [6 empty] | This includes operating a CDE on the Employers behalf.
c | Iterative clash detection and mitigation processes are clearly set out and are being adhered to.
d | Risks are being identified and mitigated by using BIM processes, including, but not limited to, stakeholder engagement and clash detection.
e | The resolved coordinated BIM is being comprehensively referenced for site construction information.
5 | Visualisation / Stakeholder Engagement | 0% |  | 0 | 0% | 0% |  | Information about the questions:
Confirm that information, models & visualisations, are being effectively used to promote broad engagement and understanding.
a | Regular team reviews are taking place, including with the client team, clearly using an interactive federated model/data.
b | Use of federated model/data to present visualisation has taken place with stakeholders and benefits have been identified.
c | The federated model/data is being used as part of GSL processes by the supplier.
d | The federated model/data is being used as part of GSL processes by the employer/FM provider.
6 | Discipline based model authoring | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm information authorship and provenance is being used, promoted, maintained and tracked throughout the project lifecycle.
a | Federated discipline based models have been provided with a stage appropriate data sets.
b | The current model reflects the current design intent or as-built condition, as appropriate.
c | Buildability reviews have been carried out using the federated/discipline models.
d | All drawings and documents are also managed and accessible via the supplier and employer CDE.
e | Lower tier suppliers play an appropriate part in model authoring / content.
7 | Construction | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm the best use of BIM and information is being effectively used in the construction phase of a project.
a | Modelling based planning / efficient construction process is has been undertaken.
b | Visual scheduling / sequencing has been carried out.
c | Model use for safety planning in pre-construction and construction.
d | Model use for testing and commissioning.
e | O&M Manual referenced to the model as a minimum & included in the MIDP.
8 | Model based estimating and change management | 0% |  | 0 |  | 0% |  | Information about the questions:
Confirm that BIM and information is being effectively used to support cost, carbon and programme management.
a | Model use for cost estimating. | [6 empty] | This target answer will remain No because it is optional and not part of the BIM Level 2 standards. However the project will be deemed more mature if the answer is Yes.
b | Model use for quantity take off. | [6 empty] | This target answer will remain No because it is optional and not part of the BIM Level 2 standards. However the project will be deemed more mature if the answer is Yes.
c | Model use change management / value engineering, including proposed design enhancements and what-if scenario cost impacts/assessments
d | Model use detailed estimating, focusing detail on the parts that have a high risk. | [6 empty] | This target answer will remain No because it is optional and not part of the BIM Level 2 standards. However the project will be deemed more mature if the answer is Yes.
Comments:
No. | Comment | Question No. | Author
1
2
3
4
5
6
7
8
9
10
Note: Please include comments that are relevant to the Yes/No scoring only.

## Trends
DIO BIM Maturity Assessment Tool (BMAT) - Trends Graph | V1.0
Project name: | project name
Project reference: | ???