DPS SCHEDULE 4: LETTER OF APPOINTMENT AND CONTRACT TERMS

  - Letter of Appointment

Dear Sirs,

This letter of Appointment is issued in accordance with the provisions of the DPS Agreement (RM6018) between CCS and the Supplier dated 18th May 2018.

Capitalised terms and expressions used in this letter have the same meanings as in the Contract Terms unless the context otherwise requires.

| Order Number: | CCCO18A17 |
| --- | --- |
| From: | The Ministry of Housing, Communities and Local Government ("Customer") |
| To: | Market & Opinion Research International Limited (Trading as Ipsos MORI) ("Supplier") |

| Effective Date: | 31/05/2018 |
| --- | --- |
| Expiry Date: | End date of Initial Period 30/05/2020 End date of Maximum Extension Period 30/05/2021 Minimum written notice to Supplier in respect of extension:31st December 2020 |

| Services required: | Set out in Section 2, Part B (Specification) of the DPS Agreement and refined by: The Customer’s Project Specification attached at Annex A and the Supplier’s Proposal attached at Annex B. |
| --- | --- |

| Key Individuals: | ## ‘Redacted Text’ Market & Opinion Research International Limited (Trading as Ipsos MORI) ## ‘Redacted Text’ The Ministry of Housing, Communities and Local Government |
| --- | --- |

| Contract Charges (including any applicable discount(s), but excluding VAT): | Year 1 and 2: £624,098 |
| --- | --- |
| Insurance Requirements | N/A |
| Customer billing address for invoicing: | ## Ministry of Housing, Communities & Local Government ## Invoice Processing team ## Finance Shared Services Division ## ‘Redacted Text’ |

| Alternative and/or additional provisions (including Schedule 6 (Additional clauses)): | The Supplier will seek to refine the methodological approach following the scoping phase to ensure that the proposed activities best meets the Authority’s needs within the available budget. |
| --- | --- |

FORMATION OF CONTRACT

BY SIGNING AND RETURNING THIS LETTER OF APPOINTMENT (which may be done by electronic means) the Supplier agrees to enter a Contract with the Customer to provide the Services in accordance with the terms of this letter and the Contract Terms.

The Parties hereby acknowledge and agree that they have read this letter and the Contract Terms.

The Parties hereby acknowledge and agree that this Contract shall be formed when the Customer acknowledges (which may be done by electronic means) the receipt of the signed copy of this letter from the Supplier within two (2) Working Days from such receipt

## For and on behalf of the Supplier:                          ‘Redacted Text’

## ‘Redacted Text’

Name and Title:

Signature:

Date:

Annex A

Customer Project Specification

To be determined by the Customer at Call for Competition stage

## THE REQUIREMENT

## To answer the questions the Supplier will, following a feasibility stage, design and implement a multi-stranded evaluation. The Supplier will conduct a design and feasibility stage, which will develop a comprehensive programme that can be delivered over the life of the evaluation.

## Design and feasibility stage

## For the CBA and Impact evaluation section the Authority will work with the Supplier to agree up to 30 sites from a longer list to include in the evaluation. In selecting 30 sites, the Authority will likely focus on those projects where funding was agreed late 2017, January 2018 or later, to allow for pre and post data collection.

## In terms of scoping and feasibility stage, the Supplier will establish, for the range of CMF projects considered, the most robust means of assessing impact over the two year period of the scheme and the most robust methodological approaches that the Authority can use to evaluate impact of these projects in a consistent way and taking into account appropriate counterfactuals  . While the Authority knows that Randomised Control Trials are unlikely to be viable in many localities, the Supplier will explore the range of other quasi-experimental approaches that may be viable and appropriate to use.

## Similarly, for the CBA element, the Supplier will be required to explore the extent to which the selected CMF schemes are suitable for CBA analysis.  Not every aspect of all schemes will be suitable. For example, for cohesion initiatives the intended longer term outcomes are primarily social – for example improved civic engagement, wellbeing – currently lack clear monetisable benefits, whereas aspects of service delivery designed to address the fallout from poor cohesion are potentially more measureable.

## The Supplier will consider how costs and benefits can be captured for different types of schemes.

## For the chosen CMF areas, potential options to deliver CBA analysis include working with local analysts (either in-house or with appointed local evaluators) to develop cost benefit models or to provide the support to the project as part of this contract. The role of the national evaluator could be a combination of offering guidance; or a more active role in collecting data and conducting analysis. The key will be to ensure consistency across the selected sites.

## For the remaining three elements of the national evaluation (establishing and sharing good practice, learning about the nature of migration pressures in local areas, exploring resident benefits) the Supplier shall use the feasibility stage to develop potential methods and produce a series of costed options. Potential methodologies for each are discussed in the relevant sections below.

## The scoping and feasibility stage will last 4-6 weeks and result in a costed proposal with options that the Authority will consider to move to phase 2. The Authority will convene a steering group comprising policy and analysis specialists that will advise on the final approach.

## Proposed Methods

## Following the scoping phase the different elements of the evaluation which will be delivered for the remainder of the contract will be as follows:

## Exploring CBA of different CMF project by themes;

## Exploring the impact of and ‘what works’ for selected schemes types using the optimal method(s) proposed by the Supplier as part of the feasibility phase. This will include developing a measurement framework to improve consistency in the metrics used for particular types of projects. There will be overlaps with the evaluation of the Integrated Communities area programme.

## Resident benefits – defining and explaining and measuring these across different places and different interventions where CMF interventions are rolled out.  This will include how local areas capture resident views and perceptions regarding migration;

## The evaluation of Integrated communities area programme will also include surveys of local residents.  The Supplier shall consider how the survey elements of the two evaluations can be linked;

## Identifying and spreading evidence-based good practice (e.g. via action learning sets);

## Improving the quality of migration data projects (Understanding the local Migration data landscape and the ways that data are collected, combined and available for policy and programme planning use).

## Cost benefit analysis

## In previous programmes CBA was found to have been an excellent way of encouraging projects to organise their thinking through logic modelling, and enabling the identification and quantification of predicted impacts through a systematic process. The Authority endorsed the use of the ‘New Economy Model’ of CBA as fit for purpose for most service transformation type projects.  The model can be found here [link], and a user friendly guide was produced by Locality as part of the support to the 2014-15 Our Place programme.  This can be found here [link].  The New Economy methodology has been scrutinised by experts and forms the basis of the 2014 Annex to the HM Treasury Green Book on Cost Benefit Analysis for Local Partnerships [link].

## For the CMF, every funded CMF proposal was based around an initial bid, the structure of which covered the main elements of a logic model – nature of the problem, proposed solution, costs/benefits and expected outcomes. Of the 30 CMF sites that the Authority will short list, the Supplier will work on the assumption that CBA analysis will be feasible in 15 sites. This assumption can then be tested during the feasibility stage.

## Exploring effectiveness/what works for selected scheme types using the most robust methods possible

## Alongside the CBA development work discussed above, the Supplier will establish the potential impact for a sample of projects (assume 15 for the purposes of developing a tender, which can then be tested in the feasibility stage).

## The Supplier will use the appropriate methods identified during the scoping and feasibility stages. Alongside capturing impacting through different methodologies, qualitative methods should be used to explore process questions (for example effective partnership working).

## This will involve extensive fieldwork during two phases, early in the evaluation (approximately summer 2018) and towards the end of the evaluation period.  The scoping phases discussed below will firm up the volume of fieldwork required.

## Exploring Resident Benefits

## A key element of the CMF is clear identifiable benefits to the resident community. From the analysis of CMF bids received it is clear that the direct beneficiaries of the majority of CMF funded activities are migrant communities – for example, through receipt of ESOL classes, rogue landlord activities.

## Some of the anticipated benefits to residents of CMF schemes are indirect or secondary: for example through improved community cohesion and increased some social mixing. Direct benefits to resident communities can include improvement to public realm (e.g. reduction in poor housing, rough sleeping) and less pressure on public services. There could also changes to residents’ perceptions of the impact of high, recent migration.

## It is important that the external evaluation systematically captures how residents have benefited from schemes across projects and areas where appropriate. The external evaluation should also support local areas in how to measure resident benefits – how to establish a link between the funded activities and impact on the wider community.

## In terms of methodology, there are a number of ways which the Suppliers can answer these questions. The Authority would welcome innovative proposals that can be tested during the scoping and feasibility stage. Potential options include:

## The CBA and what works elements discussed above will include an assessment of resident benefits in fiscal and economic terms;

## Through resident surveys in a sample of local areas. The evaluation of the Integration Strategy Area Programme will include local surveys of residents’ attitudes to integration and cohesion. The Supplier will investigate using the results of these surveys in the CMF evaluation, and/or replicating the survey in other areas;

## Some local authorities will have run their own surveys, seeking residents’ views on questions related to integration and cohesion. Where these surveys are sufficiently robust the results can be used to inform the national evaluation. A more likely scenario is that where a sample of local areas are planning to run local surveys over the course of their CMF project, the Supplier can ensure consistency in terms of questions and metrics; Local surveys can be supplemented by qualitative interviewing with residents The feasibility stage should explore to what extent community views are likely to change over the life of a CMF project.

## One of the Action Learning Sets (ALS) discussed below can also focus on how local areas are measuring resident benefits and how these can be related to CMF activity; and identifying good practice relating to reducing pressure on public services and related resident benefits.

## Identifying and spreading best practice

## The 100+ projects funded through the CMF represent a significant test bed for establishing good practice for how local areas can mitigate (and even benefit from) the impact of high and unexpected migration.

## There are a number of different ways in which Suppliers could capture this. One potential option is to run a number (10) of ALS for specific topics (e.g. Working with particular communities; implementing a particular type of initiative; measuring resident benefits; how to improve the availability and use of local migration data) over the course of the two year evaluation.

## The Authority are open to other suggestions from Suppliers, based on previous successful experience of identify and sharing good practice in other areas of public policy.

## Understanding the Local Migration data Landscape

## A key purpose of the CMF is to learn more about the nature of the problems and tensions related to high and unexpected increases in migration in local areas. Alongside this, the CMF is an opportunity to explore how local areas identify migration pressures, and the strengths and limitations of available data sources and data sharing arrangements.

## Components of this are as follows:

## Use the CMF to explore the impact of migration on local areas. Examples could include the experiences of Czech and Slovak Roma communities in urban areas in South Yorkshire; the experiences of young asylum seekers; exploring in detail what the schemes under the umbrella of ‘rogue landlord’ tell the Authority bout the nature of exploitation (e.g. links to modern day slavery). The specific topics to be explored will be agreed with the Supplier during the feasibility stage.

## For the chosen topics, explore the relationship between the new migrant community and the resident community, impact on service pressures, positive impact on labour market; and to explore the range of policy responses and programmes that have been developed in response and how these vary according to problem definition.

## As part of this, assess how local authorities know about local patterns of migration and recommend how these could be improved. For example: what national and local data sources do they use? These could be data from administrative sources, bespoke data collections and intelligence from local partners. How robust are the data sources and how could they be improved? For example, what data are missing? How can data be shared and pooled to give a richer insight into the stocks and flows of migrant communities in local areas (below Local Authority level if possible).

## The Supplier will produce recommendations such as; how could data and intelligence be improved and timelier?  What could national, local government and other stakeholders who maintain administrative data do better?

## In terms of methodology, the Authority would welcome innovative proposals but Suppliers may consider a combination of the following and/or other methods proposed:

## The different components of the evaluation discussed above (CBA, qualitative theory based approaches, spreading best practice) will all increase knowledge of the nature of migration and service pressures.

## Qualitative interviews with key stakeholders in the sample of 30 projects that are also the focus of CBA/impact

## In addition, of the CMF bids funded, £1.1m has been allocated to bids specifically looking to improve the quality of data sharing and intelligence; and a further bids have this as a major component. The Supplier shall work with a sample of these projects to identify good practice in data sharing (e.g. how barriers to data sharing are overcome), how data analysis is used to inform practice, and how national datasets can be improved (we will explore how the ONS and other national data holders can be involved in this element of the work). An option would be to bring some of these bids together as part of an ALS.

Annex B

Supplier Proposal

## ‘Redacted Text’

  - Contract Terms

As a guide, to what extent can projects (or part of projects) be evaluated on the Maryland scale [link to NAO 2013 study and the HMT Magenta book].  For some CMF schemes Realistic evaluation approaches maybe appropriate (See Westhorpe, G (2014) Methods Lab, Realist Impact Evaluation, ODI, Australian Foreign Affairs, BetterEvaluation; and Pawson, R, and Tilley, N, (1997) Realistic Evaluation, Sage

https://www.gov.uk/government/consultations/integrated-communities-strategy-green-paper