## Sheet1
Shedule of Works: Justinian House, Spitfire Close, Huntingdon. PE29 6XY
item | Works Description | Cost: Unit (£) | Cost: Construction (£)
Preliminaries, Site and General Pricing Notes
1 | Please Note: Any works not noted in the schedule but identified on the drawings must be identified/added prior to return of the tender documents. Those items on the drawings but not added to the schedule will be deemed to have been included in your overall tender price.
Contractor to price for all prelims as necessary to cover the duration of the works, estimated to be an 8 week programme. Contractor to ensure costs allow for : Acting as Principal Contractor under CDM Regulation 2015, as no pre tender/ construction phase Health and Safety Plan has been prepared.
Demolitions
Remove Sink, base units etc in Ground Floor Kitchen as noted in drawing 07-Rev B
Partitions
Install new partitions as noted on drawings 07-Rev B, 11-Rev B and 15-Rev B. Note! Contractor to check ceiling conditions and ensure that head restraint appropriate for specific locations
Type 1 - Unrated
Type 2 - Fire Rated Non Acoustic
Type 3 - Fire Rated and Acoustic
Doors
Provide new doors, frames and specific ironmongery as noted on drawings 07-Rev B, 11-Rev B and 15-Rev B
Allow provisional sum to attend on Security Specialist works to main entrance door.
Joinery
Provide shelving and spur support brackets as indicated on drawings 07-Rev B, 11-Rev B and 15-Rev B
Provide new reception countertop, upper level and support as noted in drawing 07-Rev B. Note! Contractor to provide Trust with drawings for approval prior ro placing any orders with sub contractors
Kitchen Installation
Refer to drawings 07-Rev B, 11-Rev B and 15-Rev B and allow for new kitchenette installations, including units, tiling, plumbing and drainage
Ground Floor installation
First Floor installation
Second Floor installation
Supply and fit 3No Calomax Kudos water boilers, including services. Ensure that no duplication of electrical costs and if covered elsewhere specifically stated so.
Ceilings
Provide acoustic insulation bags above existing ceilings as indicated on drawings 10-Rev B and 14-Rev B
Electrical and Data
Contractor to liaise with both data and electrical contractors and ensure any BWIC and fire stopping/ compartment works are allowed for, ensuring a compliant installation on handover.
Main Contractor to : Manage all works, programming, test/ commissioning and sign off of the Electrical Contractor's works, all to handover on the same date as main works. Allow either a fixed fee or confirm percentage to manage as required. Note that Electrical Contractor separately appointed by the Trust.
Main Contractor to : Manage all works, programming, test/ commissioning and sign off of the Data/ IT Contractor's works, all to handover on the same date as main works. Allow either a fixed fee or confirm percentage to manage as required. Note that Data/ ITContractor separately appointed by the Trust.
TOTAL (£)