# Annex A

| Title of Project | 0922S survey imagery analysis |
| --- | --- |
| Date and Time for Return of Bids | 31st October 2022 @ time |
| Contract Reference Number | C22-600-1675 |
| Address for Bid Submission | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND BIDS DIRECTLY TO TOM TANGYE, DAVID REYNOLDS OR JNCC VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the number below; (00 44 1733 866 988) |
| Contacts for Technical Information relating to this Project Specification | Joint Nature Conservation Committee Name: Tom Tangye Email: tom.tangye@jncc.gov.uk Telephone: 01733 866944 OR Joint Nature Conservation Committee Name: David Reynolds Email: David.Reynolds@jncc.gov.uk Telephone:: +44 (0)1733 943167 |
| Contact for all Queries Regarding the Procurement Procedure (Technical and Administration) | Finance and Planning Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk |
| Proposed Start Date | 7/11/2022 |
| Proposed End Date | 27/02/2023 |

0922S West Shetland Shelf MPA survey epibenthic imagery analysis specification

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Aims	3

3.	Project Background	3

4.	Project Objectives	5

5.	Project Objectives: Detailed Tasks	6

5.1.	Analysis of video data	6

5.2.	Analysis of stills data	8

6.	Quality Assurance	10

7.	Outputs	12

8.	Product Specification	13

9.	Dissemination	14

10.	Timescale	14

11.	Health and Safety	14

12.	Project Management	15

13.	Instructions for Bid Submission	15

14.	Evaluation Criteria	16

15.	Payment	17

16.	Additional Requirements	17

17.	References	18

Appendix A: BIIGLE protocol (adapted from Cefas BIIGLE protocol)	18

Appendix B: Non-indigenous species (after Curtis et al, 2020)	19

Appendix C: Representative images of Each Survey Box	21

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation

Our role is to provide scientific evidence, information, and advice to inform decisions to  protect the natural environment. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally, by:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/

## Project Aims

JNCC wishes to commission a contract to undertake the analysis of seabed imagery (still images and video) collected on the 0922S survey from drop frame camera (DC).

Video and still images from 86 stations will be analysed; tenderers should provide quotes outlined in Table 1:

More detailed metadata will be provided and information from logs and the survey report. There are also representative images from each station from the 0922S WSS survey shown in Annex C.

## Project Background

JNCC and Marine Scotland Science (MSS) have conducted a survey aboard MRV Scotia (0922S) to gather evidence to monitor West Shetland Shelf Nature Conservation MPA (WSS) and inform assessment of condition of the designated features of the site.

WSS was designated in July 2014 to protect the Offshore Subtidal Sands and Gravels habitat feature (OSSG). The site has an area of 4,083 km2, a depth range of 70 - 150 m, and is located to the north of Scotland in offshore waters (Figure 1). More information on WSS can be found in the JNCC site information centre.

The 0922S survey departed from Aberdeen on the 20th July 2022 and ended on the 03rd August 2022. The primary survey objective, related to seabed imagery, was to acquire video and still images for the purposes of MPA feature monitoring.

Imagery was collected with a drop camera (DC) system. The DC was equipped with a high-definition video camera and a separate still image camera unit, in a planar (downwards facing) orientation inside the frame. The stills camera was fitted with a four-spot (green) laser-scaling device with a 67 mm spacing.

The aim of the 0922S survey is to acquire robust investigative monitoring (Type Three) of the offshore circalittoral sands and to acquire robust sentinel monitoring (Type One) of the offshore circalittoral course sediment dataset within WSS to contribute to the development of a monitoring timeseries for WSS. This will monitor the rate in the direction of change in the condition of the MPA features can be inferred in the long-term.

Camera stations were positioned using an equidistant grid in four survey boxes (labelled A, F, G and H as shown in Figure 1). At each station there was a ~15 minute deployment of the drop camera or to collect up to 80 still images. Some stations ran over due to ocean swell to acquire the needed 80 still images.

The following instruments were mounted to the drop frame:

- SubC 1 Alpha video camera (HD video recorded internally).

- Standard definition Kongsberg digital camera (10MP) with; dedicated flash unit for still images capture (camera-controlled topside, images recorded internally), and primary TV observation and topside recording to DVD

- 4 SEALED lamps for illumination

- 2 reference spot lasers (67 mm separation)

- Valeport CTD

- Ultra-short Baseline (USBL) acoustic positioning beacon

Table 1. Imagery for analysis

| Imagery | No. stations | No. still images per station | No. still images in total | Total Length of Video (hh:mm) |
| --- | --- | --- | --- | --- |
| Video | 86 |  |  | 23:00 |
| Stills | 71 15 | 40 Ranging ~25 – 39 | 2840 493 Total 3,333 |  |

Still images with a field of view (FOV) of between ~0.8 - 1.2 m2 have been selected at random from DC transects to be analysed.

Locations of the camera stations sampled at WSS are shown in Figure 1.

Access to the imagery via BIIGLE will be provided on request to aid in the tendering process (available from October 2022) and more detailed metadata will be provided to the successful contractor following contract award.

Figure 1. Locations of camera stations sampled and completed at WSS during 0922S survey

The following will be supplied to the successful contractor:

Access to BIIGLE project with all stills, video and label trees (from October 2022)

Associated metadata

Draft Cruise Report

Epibiota Quality Assurance Framework Proforma spreadsheets

## Project Objectives

To meet the overall aims of this project (Section 2), the objectives are:

JNCC wishes to commission a contract to undertake the analysis of seabed imagery (still images and video) collected on the 0922S survey.

- The Tenderers are to provide a quote for:

  - All 86 video stations and still images (3,333 images from 86 stations)

- The successful contractor will undertake the analysis as set out below and adhering to the NMBAQC Epibiota interpretation guidelines (Turner et al, 20161).

- High level review of imagery should be conducted as outlined in Section 3.1 of Turner et. al., 2016.

- If an image quality level of zero is given, then no further review of seabed substrate or fauna is required.

- The successful contractor will use BIIGLE2 to annotate video and still images as described below and in Appendix A. JNCC will set up the BIIGLE project to be used prior to the contract beginning. During the start-up meeting JNCC will provide guidance on use of BIIGLE if needed.

- Some information, where specified, may be recorded directly into the proformas provided but the majority will be recorded in BIIGLE first and used to populate the proforma.

- Taxonomic, broad-scale habitat and biotope image reference collections are required

- The successful contractor should ensure that still image and video references used in analysis outputs are identical to those used in the naming of the original media, to enable future reconciliation between data and media. If identical naming is not possible, a suitable alternative should be sought with JNCC (e.g. a lookup table, or closely similar naming)3.

- The successful contractor will produce a brief analysis report.

Any deviation from this methodology should be approved in writing by the project officer.

The analysis method for video is described in section 5.1 and the method for stills in section 5.2.

## Project Objectives: Detailed Tasks

  - Analysis of video data

Video should be analysed in BIIGLE using the label trees shown in Table 2. A high-level review should be conducted as described in section 2.1 of Turner et al (2016). Annotations can be added to videos as either tier 1 or tier 2 annotations depending on the label tree used. More details on the video annotation tiers and how they should be applied are provided in Appendix A.

Video will be analysed to extract the following information (all information should be recorded using the provided BIIGLE label trees, unless specified otherwise):

- Video should be segmented into areas of continuous broadscale seabed habitat type (detailed in step 2) greater than or equal to 5 m along transect distance; JNCC will provide positional information for this purpose. The segment label tree should be used to delineate these segments and labels from other trees should be attached to each segment using the “add label” tool in BIIGLE.

- The Marine Habitat Classification of Britain and Ireland (v 15.03) will be used, and a new segment should be started if the habitat classification changes.

  - Marine habitat classification of Britain and Ireland4. Initially this label tree should be used to assign broad-scale habitats, that is up to level 3 of the hierarchy (e.g. Sublittoral sands and muddy sands).

- Each segment will be assigned image quality scores using labels from the following two label trees. Further analysis of video segments will be dependent on the image quality score. For example, if a segment is given a score of zero, no further analysis should be carried out for that segment.

  - NMBAQC image quality, a summary of these scores is shown in Table 3 and described in more detail in section 2.1 of Turner et al (2016).

  - JNCC image quality, a summary of these labels is shown in Table 4.

- Use the Priority Marine Feature (PMF) label tree to identify any habitat segments containing the PMF habitats and/or species as listed in NatureScot, 20165.

- Identify evidence of anthropogenic impacts on the seabed:

  - Use the litter label tree to record the presence of litter using the categories listed in Annex 5.1 of the Joint Research Centres Guidance on Monitoring of Marine Litter in European Seas6.

  - Use the Anthropogenic label tree to annotate trawl marks or anthropogenic impacts other than litter. This will not be a complete label tree and new labels may need to be added to the label tree.

- Use the biotope label tree to assign biotopes, up to level 6 of the Marine habitat classification of Britain and Ireland hierarchy and in accordance with Parry (2019)7.

A reference collection of representative images must be provided for each discreet habitat and biotope identified.

Table 2. Label trees for video annotation and the annotation type which should be used for each label tree

| Video analysis label tree | Video annotation type |
| --- | --- |
| Segment | Tier 1 |
| Marine habitat classification of Britain and Ireland (v 15.03) | Tier 1 |
| JNCC image quality | Tier 1 |
| NMBAQC image quality | Tier 1 |
| Priority Marine Features | Tier 1 |
| Biotope | Tier 1 |
| Litter | Tier 2 |
| Anthropogenic | Tier 2 |

Table 3. Summary of NMBAQC image quality categories (Turner et al, 2016)

Table 4. JNCC image quality categories

| - Imagery quality level | - Description |
| --- | --- |
| - Fauna | - Most fauna can be identified (e.g. including smaller taxa such as brittlestars etc.) |
| - Conspicuous fauna | - Large and conspicuous fauna can be identified (e.g. sponges, soft corals etc.) |
| - Substrate | - The substrate type can be identified, but the fauna cannot (e.g. the water column is obscured / the camera is too high off the seabed) |
| - Zero | - No visibility of the seabed, substrate cannot be identified. |

  - Analysis of stills data

Stills should be analysed in BIIGLE using the label trees shown in Table 5. Annotations should be added to stills as either tier 1 or tier 2 labels depending on the label tree used. Some tier 1 labels may be added directly into the proforma (see below). More details on the still annotation types and how they should be applied are provided in Appendix A.

Table 5. Label trees for stills annotation and the annotation type which should be used for each label tree

| Stills analysis label tree | Stills annotation type |
| --- | --- |
| NMBAQC image quality | Tier 1 |
| JNCC image quality | Tier 1 |
| Substrate | Tier 1 |
| Biota | Tier 2 |
| Laser points | Tier 2 |
| Litter | Tier 2 |
| Anthropogenic | Tier 2 |

Stills will be analysed to extract the following information:

- Each still will be assigned image quality scores using labels from the following two label trees. Further analysis of the still image will be dependent on the image quality score. For example, if a still image is given a score of ‘very poor’ and ‘substrate’, no taxonomic identification should be carried out for that still image.

  - NMBAQC image quality, a summary of these scores is shown in Table 3 and described in more detail in section 2.1 of Turner et al 2016.

  - JNCC image quality, a summary of these labels is shown in Table 4.

- Identification and enumeration of epifauna. Annotations made using the Biota label tree. For each still image being analysed, identify, and quantify all8:

  - Solitary and/or erect epifaunal species present.

  - Bioturbation traces using counts (achieved by using the point annotation tool within BIIGLE).

  - Colonial and/or encrusting epifaunal species present as far as possible (using percentage cover (achieved by using the polygon, magic wand, or brush tools within BIIGLE).

- Record substrate type and Faunal Turf cover to nearest 10% directly to proforma.

- Use laser points label tree to annotate lasers and calculate image area in BIIGLE. Analysts are not to use the automated laser detection tool in BIIGLE.

- Identify evidence of anthropogenic impacts on the seabed:

  - Use the litter label tree to record the presence of litter using the categories listed in Annex 5.1 of the Joint Research Centres Guidance on Monitoring of Marine Litter in European Seas6

  - Use the Anthropogenic label tree to annotate trawl marks or anthropogenic impacts other than litter. Note, new labels may need to be added to the label tree.

- Any comments from the analyst which are considered of importance should be recorded directly to proforma.

A reference collection of representative images must be provided with one image for each species/ morphospecies identified.

- Quality Assurance

Following award of the contract, and dependent on the evaluation scores they achieve, unsuccessful bidders may be invited to undertake the independent external QA aspects of this project. Please indicate in your tender if you do not wish to be considered for this work.

Note external QA analysis may be undertaken at same time as primary analysis if preferred by successful contractor and suitable process is agreed with JNCC at start-up meeting.

Internal Quality Assurance process for imagery analysis

A minimum of 10% of still images and video analysed are to be subject to an internal QA process.

Tenderers must demonstrate their internal Quality Control (QC) system, which includes routine checks of data and analysis.

QC of data and analysis is where data are re-checked and compared against the original and compared to an expected standard/ limit of error/ deviation from the original.  It is also where electronic records (in spreadsheets or databases) are checked against the data on the original field/laboratory datasheets.  This measures the repeatability of the method of analysis and data entry, and highlights factors such as inter-worker variability.  QC must also include details of remedial action in cases where expected standards/limits are not met.

Internal QC must be undertaken by a staff member other than the staff member who conducted the original analysis.

External Quality Assurance process for still images

Ten percent of still images analysed are to be subject to an independent external QA process.

The following steps will be adhered to:

- Images to be quality assured will be selected by JNCC

- The auditing analysts receive the imagery data from JNCC and project level identifications (i.e. substrate and taxonomic image reference collections) from the original analyst. Abundance data are not provided to the auditing analysts, to ensure auditing analyst enumeration is undertaken blind

- The auditing analysts complete the image analysis for selected images as described above

- The results are sent to JNCC and original analysts

- The auditing analysts complete the JNCC image analysis comparison proforma spreadsheet

- JNCC, the original and the auditing analysts meet to resolve any discrepancies in taxa identification and enumeration to the satisfaction of all parties.

Any remedial action required following the QA process must be completed within an agreed timeframe at no extra cost to the project.

All remedial action taken, and associated rationale, are to be recorded and provided as outputs of this contract. The contract shall not be deemed complete until this external Quality Assurance step has been completed successfully.

| Party | To provide | Format |
| --- | --- | --- |
| JNCC | Image analysis comparison proforma spreadsheet template and review of completed image analysis comparison proforma spreadsheet | MS Excel spreadsheet MS Word Document |
| Original analyst | Results of audit and review of completed image analysis comparison proforma spreadsheet and summary of all remedial action taken, and associated rationale | MS Excel spreadsheet MS Word Document |
| Auditing analyst | Completed image analysis comparison proforma spreadsheet, review of completed image analysis comparison proforma spreadsheet | MS Excel spreadsheet MS Word Document |

External Quality Assurance process for video analysis

Ten percent of video transects analysed are to be subject to an independent external QA process.

The following steps will be adhered to:

- Video to be quality assured will be selected by JNCC;

- The auditing analysts receive the video data from JNCC and project level identifications (i.e. image taxonomic reference collections) from the original analyst. Abundance data are not provided to the auditing analysts, to ensure auditing analyst enumeration is undertaken blind;

- The auditing analysts complete the video analysis for selected video transects as described above.

- The results are sent to JNCC and original analysts.

- The auditing analysts complete the JNCC video analysis comparison proforma spreadsheet.

- JNCC, the original and the auditing analysts meet to resolve any discrepancies in taxa identification and broad-scale habitat/biotope assignment to the satisfaction of all parties.

Any remedial action required following the QA process must be completed within an agreed timeframe at no extra cost to the project.

All remedial action taken, and associated rationale, are to be agreed with JNCC before being implemented, recorded and provided as outputs of this contract. The contract shall not be deemed complete until this external Quality Assurance step has been completed successfully.

| Party | To provide | Format |
| --- | --- | --- |
| JNCC | Video analysis comparison proforma spreadsheet template and review of completed video analysis comparison proforma spreadsheet | MS Excel spreadsheet MS Word Document |
| Original analyst | Results of audit and review of completed video analysis comparison proforma spreadsheet and summary of all remedial action taken, and associated rationale | MS Excel spreadsheet MS Word Document |
| Auditing analyst | Completed video analysis comparison proforma spreadsheet, review of completed video analysis comparison proforma spreadsheet | MS Excel spreadsheet MS Word Document |

## Outputs

Any products or outputs submitted to JNCC [for publication] should adhere to JNCC’s house-style and should be produced in an accessible format (see product specification for more information).

JNCC require the successful contractor to provide analysis results in the MEDIN compliant Big Picture Quality Assurance Framework MS Excel proforma spreadsheets9.

Please note the Final Report must adhere to the JNCC report template and house style (will be provided to successful contractor at start-up meeting).

The report should be no longer than 10,000 words including all tables and appendices.

The report should be provided electronically via email as a Microsoft Word document, and will include the following sections:

- Methodology

- Results

- Details of all QA work undertaken, and any remedial action deemed necessary.

| Output/deliverable | Format |
| --- | --- |
| Imagery analysis results | Completed Epibiota Quality Assurance Framework Proforma spreadsheets BIIGLE CSV reports: Image Label report, “Full” Annotation Report” “Annotation Area Report” Video Annotation Report |
| Comparison of analysis and independent analysis and reconciliation | Excel spreadsheet |
| Reference collection of images for each taxon identified and metadata spreadsheet. Taxa to be highlighted in image (e.g. using a boundary box) | Still image files labelled with StnCode and taxon they represent |
| Reference collection of video clips for each broad-scale habitat and biotope identified and metadata spreadsheet | Screen grab or short video files labelled with StnCode and biotope they represent |
| Final Report | Document |

## Product Specification

JNCC is committed to making its publicly available resources and documents accessible, in accordance with the Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.

Making material accessible means making sure it can be used by as many people as possible.  This includes those with:

- impaired vision

- motor difficulties

- cognitive impairments or learning disabilities

- deafness or impaired hearing

The outputs and material that JNCC publishes should be compliant with the Web Content Accessibility Guidelines version 2.1 AA standard.

To meet this standard, all reports and other documentation which are to be made publicly available must adhere to JNCC’s house-style (to be provided) and be produced using a JNCC template (to be provided), unless otherwise stated. All reports (draft and final) should be provided electronically via email both as a Microsoft Word document and an Adobe PDF.

Copies of documentation associated with case studies should be provided in electronic format with an associated reference catalogue.

For any other outputs or products which are to be made publicly available through JNCC, evidence regarding how the accessibility standard will be reached should be included.

(Note for author if research project/contract: see EQA Policy Appendix 4 (Communicating Evidence Quality). Ensure that data management and storage requirements are stipulated taking into account relevant policy for data access. See https://jncc.gov.uk/about-jncc/corporate-information/evidence-quality-assurance/

## Dissemination

The products/outputs produced under this contract will be a JNCC product and shall not be published or disseminated without the written permission of JNCC. Outputs may at some point be published on the JNCC website and all material supplied as part of this contract shall remain copyright of JNCC. The findings from this contract will also be made available to staff within JNCC, the UK country nature conservation bodies (Marine Scotland, Nature Scot).

## Timescale

Provisional dates for delivery of the contact outputs are set out below. Exact dates are to be agreed at the start-up meeting based on Contractor and JNCC staff availability.

| Output | Provisional Date |
| --- | --- |
| Start-up meeting | TBC |
| Interim meeting to discuss any issues or resolve questions, after the analysis of 10 camera stations has been completed. | WC 28/11/2022 |
| Completion of analysis and reporting, provision of draft deliverables to JNCC and external QA samples to external QA analyst(s) | 27/02/2023 |
| Completion external QA and remedial action (if necessary) | 13/03/2023 |
| Wash-up meeting | 20/03/2023 |

In agreeing exact dates please note that the potential for work under this contract to be funded into 2022/23 is subject to availability of funds.

## Health and Safety

The successful bidder is expected to follow appropriate Health & Safety procedures including adhering to JNCC’s policy on safeguarding. For further information  https://jncc.gov.uk/about-jncc/corporate-information/safeguarding/ and to be able to undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by the JNCC H&S Advisor).

Any incidents occurring within the contract period should be immediately reported to JNCC.

## Project Management

The successful Contractor shall nominate a project manager who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Name: Tom Tangye

Email: tom.tangye@jncc.gov.uk

Telephone: +44 (0)1733 866944

Name: David Reynolds

Email:  david.reynolds@jncc.gov.uk

Telephone: +44 (0)1733 943167

## Instructions for Bid Submission

The bid submission should include the following:

A brief summary of the bidder’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract and delivering the detailed tasks identified within each objective. This should be sufficiently detailed to allow assessment against the evaluation criteria (Section 14);

A detailed project plan (including Gantt chart) with proposed work programme and an estimate of time required to achieve each objective;

A draft Table of Contents for the final report;

Details of Quality Control procedures to be followed (note for author if research project/contract: see EQA Policy Appendix 112 (Bias, Conflicting Evidence and Uncertainty) and EQU Policy Appendix 312 (Quality Assurance of Expert Knowledge and Opinion):

Details of the bidder’s own internal Quality Management System;

Details of the Project Team including their roles and experience, an estimate of their time input into each task and CVs of all personnel who will be involved in the contract/project;

Availability of the Project Team for a start-up meeting by Teams

Overall quote for the contract to include:

  - Day rates for all members of the Project Team;

  - Rates for attending start-up, interim and final meetings in Peterborough or Aberdeen (costs for travel and accommodation are attached, and should be used. These rates are analogous to the civil service rates).

  - Costs and time allocation should be clearly allocated to specific tasks within this contract/project; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and if so, provide their VAT registration number.

The following documentation:

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates;

  - Copies of any appropriate risk assessments; and

  - Copies of any environmental policies should you have them.

In addition, note that the bid submission should provide sufficient information to allow assessment against the evaluation criteria outlined in Section 14.

## Evaluation Criteria

JNCC is not bound to accept the lowest priced or any bid. Having the technical expertise and experience to complete the work to a high standard and being able to complete it within the timescale are of the essence for this contract.

The bid evaluation will be undertaken by a panel consisting of JNCC only

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Maximum Score | Score |
| --- | --- | --- | --- |
| 1. Quality of Bid (50% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal particularly work programme and deliverables | 10 |  |
|  | Understanding of, and relevance to, the requirements in particular the adequacy of outputs | 10 |  |
|  | Soundness and logicality of methods | 5 |  |
|  | Realism and measurability of outputs | 5 |  |
|  | Evidence provided of how accessibility standards will be met | 5 |  |
|  | Identification and proposed solutions to potential risks/issues | 5 |  |
|  | Serious weaknesses which threaten success | 5 |  |
|  | Probability of success | 5 |  |
|  | Sub Total | 50 |  |
| 2. Details of Contractor (20% of the total for the three assessment categories) |  |  |  |
|  | Expertise, experience, and balance of team | 9 |  |
|  | Risks if important team members drop out | 5 |  |
|  | Adequacy of subcontractors if any | 6 |  |
|  | Sub Total | 20 |  |
| 3. Cost (30% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation what does presentation mean here in relation to cost? | 10 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 6 |  |
|  | Appropriateness of ratio of senior to junior staff time | 6 |  |
|  | Clarity of each team member’s contribution and value added | 8 |  |
|  | Sub Total | 30 |  |
| Total Score |  | 100 |  |

## Payment

Unless a payment schedule is stated in your submission and agreed by JNCC project manager. Payment will be made on completion of the objectives following the submission of invoice(s) and based on the satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key outputs.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates/fees given.

The bidder is expected to supply all necessary equipment, software, licences, etc. to carry out the obligations required under the contract.

## References

1  http://www.nmbaqcs.org/media/1643/nmbaqc_epibiota_interpretation_guidelines_final.pdf & http://www.nmbaqcs.org/scheme-components/epibiota/epibiota-quality-assurance-framework-and-documents/

2 https://www.biigle.de/

3 Copy-Paste from the original material is preferred, to avoid typos. Note if changes are made a lookup table is essential, as it takes a lot of time to write and check the code for matching strings when combining attributes from different files.

4 https://mhc.jncc.gov.uk/

5 https://www.nature.scot/professional-advice/protected-areas-and-species/priority-marine-features-scotlands-seas

6 https://mcc.jrc.ec.europa.eu/documents/201702074014.pdf

7 Parry, M.E.V. 2015. Guidance on Assigning Benthic Biotopes using EUNIS or the Marine Habitat Classification of Britain and Ireland JNCC report No. 546 JNCC

8 Please note that a mixture of point and area annotations should not be used for a single taxon. i.e. if Alcyonium digitatum is considered colonial it should be labelled as such in all cases.

9 http://www.nmbaqcs.org/scheme-components/epibiota/epibiota-quality-assurance-framework-and-documents/

10 http://randd.defra.gov.uk/Document.aspx?Document=13892_ME5215Objective2-Monitoring.pdf

11 https://hub.jncc.gov.uk/assets/1684dd5e-36e3-4969-852f-4541c82240eb

12 EQA Policy https://jncc.gov.uk/about-jncc/corporate-information/evidence-quality-assurance/

## Appendix A: BIIGLE protocol (adapted from Cefas BIIGLE protocol)

- A BIIGLE account (with editor privileges) will be created for the successful contractor, if one does not already exist, which will allow for annotations to be added to each image.

- Images will be stored on a remote volume which JNCC, MSS and the successful contractor will have access to.

- The contractor will not have access to the volume following completion of the contract.

The Annotation Process (video)

There are two forms of video annotation:

- Tier 1 Video Metadata (multi-frame annotations for transect / segment metadata)

  - The entire video transect should be viewed at up to 4x speed on the first review. During this review, the video will be annotated to identify segments, whereupon any time that a change in BSH (of greater than 5 m in length – see fix to point data) is noted, the appropriate segment will be changed using a whole frame annotation:

    - Using the “Start a Whole Frame Annotation H” tool, “open” the first annotation by clicking on the button or pressing H whilst viewing the desired start frame.

    - This annotation is now open until you click again to create a “closing point” (i.e. at the EOL or change of habitat). N.B.  you can switch between open annotations, so you don’t have to scroll through the video until the habitat / substrate etc. changes.

    - Make sure that the next segment starts on the same frame as the previous one ended. This avoids gaps or overlaps. Care should also be taken to ensure there are no gaps at the start and end of the video.

Once a segment has been delineated, additional whole frame labels (for other Tier 1 labels such as image quality and BSH) should be attached to the segments using the “add label tool”. using the add label tool will ensure the start and end points are the same for all labels given to a segment.

- Tier 2 - Video Litter and or Anthropogenic Annotations (single frame annotations for faunal abundance)

  - These are point annotations.

  - When litter or marine debris is seen, pause the video and select the correct label from the MPA Imagery Litter and or Anthropogenic Annotations analysis label trees.

  - Using the “Start a Point Annotation A” tool place the annotation by clicking on a point at the centre.

  - No “Closing point” is needed, simply click the “Tick” mark above the point tool – this finishes the single frame annotation.

Ensure that no multi-frame annotations are used for faunal annotations, as this will confuse the analysis process (such annotations are useful for tracking mobile fauna such as fish)

### Report downloading

BIIGLE allows admin users to download “Annotation Reports”. These are CSV documents which contain, line by line the: image ID, file name, annotation tag labels, exact tag position within the image (pixel x and y), BIIGLE user ID.

- It is from these reports that the final dataset will be compiled.

- The contractor can request a report to be generated as required for data management tracking purposes.

## Appendix B: Non-indigenous species (after Curtis et al, 2020)

Taxa listed as non-indigenous species (present and horizon) which have been selected for

assessment of Good Environmental Status in GB waters under MSFD Descriptor 2 (Stebbing et al.

2014)10.

Additional taxa listed as non-indigenous species in the JNCC ‘Non-native marine species in British waters: a review and directory’ report by Eno et al. (1997)11 which have not been selected for assessment of Good Environmental Status in GB waters under MSFD.

## Appendix C: Representative images of Each Survey Box

Box A

| Station name & description | Image 1 (Start) | Image 2 (Middle) | Image 3 (End) |
| --- | --- | --- | --- |
| 0922S_WSS_Box_A_DC_A001_S060_A1 Sand |  |  |  |
| 0922S_WSS_Box_A_DC_A003_S188_A1 Coarse sand and shells Sand |  |  |  |
| 0922S_WSS_Box_A_DC_A010_S193_A1 Sand |  |  |  |
| Box F |  |  |  |
| 0922S_WSS_DC_F021_S171_A1 Sand |  |  |  |
| 0922S_WSS_DC_F016_S176_A1 Sand |  |  |  |
| 0922S_WSS_DC_F014_S178 Sand |  |  |  |
| Box H |  |  |  |
| 0922S_WSS_DC_H027_S149_A1 Sand, coarse, cobbles |  |  |  |
| 0922S_WSS_DC_H019_S137_A1 Sand, cobbles, gravel, shells |  |  |  |
| 0922S_WSS_DC_H009_S136_A1 Sand with cobbles, gravel, and shells |  |  |  |
| Box G |  |  |  |
| 0922S_WSS_G002_S005_DC_A1 Cobble at first, sand and shell |  |  |  |
| 0922S_WSS_G019_S018_DC_A1 Sand/coarse sand and shells |  |  |  |
| 0922S_WSS_G028_S025_DC_A1 Sand |  |  |  |