| Contract Management Guidance – Template #10 CHANGE CONTROL FORM- Extensions – v. 5 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Contract Name: | Provision of Consultancy for the Grenfell Tower Inquiry |  |  |  | Contract Ref. No. | CCS Reference: CCCC17A75 (Variation Ref: CCCC17A75-01) |  |
|  |  |  | CLIENT CHANGE NOTICE (CCN) |  |  |  |  |
| CCN 1 REDACTED Grenfell Tower Inquiry CCN Reference: Initiated by: Date CCN Raised by relevant party: 17th November 2017 Cabinet Office Source of change: |  |  |  |  |  |  |  |
| STAGE 1 – CLIENT |  |  |  |  |  |  |  |
| Summary of proposals/ requirements : | This is a variation to the Contract between the Cabinet Office and KPMG LLP. The Terms and Conditions of the Contract apply but with the following amendments: - Extension of time only for 3 months until 16th February 2018. |  |  |  |  |  |  |
| Proposed payment: |  | In line with the existing terms and conditions of Contract. |  |  |  |  |  |
| Required delivery date, with rationale: |  |  |  | In line with the existing terms and conditions of Contract and the new proposed implementation plan and milestones detailed within Annex A. |  |  |  |
| 17/11/2017 REDACTED REDACTED Change authorised to proceed to Stage 2 (Customer organisation representative): Signature Print Name & Position Date 17/11/2017 REDACTED REDACTED Change authorised to proceed to Stage 2 (CCS representative) Signature Print Name & Position Date |  |  |  |  |  |  |  |
| STAGE 2 – SUPPLIER |  |  |  |  |  |  |  |
| Comments/ caveats on requested change: |  |  |  |  |  |  |  |
| Anticipated period from CCN being authorised by customer to start of related provision Anticipated implementation period, if any |  |  |  |  |  |  |  |
| Craig Masters Date: 17/11/2017 REDACTED Signed (Supplier Representative): REDACTED Change authorised to proceed to Stage 4 (CCS): REDACTED 17/11/2017 Signature Print Name & Position Date |  |  |  |  |  |  |  |
| STAGE 3 – CLARIFICATIONS |  |  |  |  |  |  |  |
| Clarification/ queries to supplier regarding Date: their proposals: Supplier response Date: |  |  |  |  |  |  |  |
| STAGE 4 - CUSTOMER CCN SIGN-OFF TO PROCEED TO IMPLEMENTATION |  |  |  |  |  |  |  |
| Variation Withdrawn |  |  |  |  |  |  |  |
| By signing below, unless CCN is withdrawn, the Cabinet Office agrees to pay the KPMG LLP the costs detailed in Stage 1, by deadlines agreed with the supplier, or as defined in the contract. |  |  |  |  |  |  |  |
| 23/11/17 REDACTED REDACTED Signed (Customer Representative): Date Print Name & Position Signature Change authorised to proceed to implementation (CCS): 23/11/2017 REDACTED REDACTED Date Print Name & Position Signature |  |  |  |  |  |  |  |
| STAGE 5 - CCN COMPLETION SIGN-OFF |  |  |  |  |  |  |  |
| I confirm that the provision required under the CCN commenced in accordance with the customer requirements and supplier proposals in this CCN. |  |  |  |  |  |  |  |
| Date provision required under the CCN commenced: Date Signed by Customer: 23/11/17 20/11/17 REDACTED REDACTED Signed (Customer representative): Print Name & Position |  |  |  |  |  |  |  |