## Sheet1
Highways England Confirmation of Task Order |  |  |  |  | Redacted under Section 40 and Section 43 of the FOI Act (2000)
Confidential and Commercially Sensitive Information which shall not be disclosed to third parties
Supplier: | Atkins
Project Title: | Brexit Banners – second batch of 12 sites
Contract Ref. | 2589 | CPA No.: | Redacted |  | BPA No.: | Border Readiness
PIN Description: | Border Readiness | Sub Pin: | Redacted |  | PIN No.: | Redacted
HE Reference: | SE 42 19/20ATK | HE Ordering Officer: |  |  | Redacted
Consultant Ref: | 5165058.602 | Consultant Contact: |  |  | Redacted
Start & End Date: | 22/10/2019 - 31/01/2020 | CTO Authorisation No.
Task Overview
Please see "Highways England Confirmation of Task Order_banners 2nd batch_draft final3" emailed 15/10/2019 for Introduction & History and Information Available. Redacted e-mail of 11 October confirmed that this CTO should be costed on the full 12 sites being required. It is possible that the Government may seek more sites – these would need to be captured by an additional CTO. Methodology Utilising the experience gained from the previous three sites, we envisage the key tasks to deliver the three applications to be: •Review various background documents and supporting information relating to the proposals provided by HE. •Skype meetings and ongoing liaison with HE in order to ensure we understand the proposals and have access to the relevant information. •Prepare application form and cover letter for each submission including local policy review and provision of justification for proposed works. •Receipt and review of photomontages / drawings for each submission. •Compile / assemble each application. •Raise fee required to accompany each submission. •Review and internal sign off. •Submission to each Council via Planning Portal (on-line submission). •Seek urgent confirmation from relevant Council that each application is validated the day following submission. •Post application submission, we have allowed for liaison with the planning authority, such as providing clarifications which they are third party consultees may have and reviewing draft committee report and conditions. Assumptions •This CTO assumes that the submissions (for 12 sites only) will all be finalised by mid October. •Our ability to meet deliverables depends on any outstanding specifications or details to be received as timely as possible. Atkins Planners will liaise regularly with Redacted (the HE single point of contact) to ensure that expectations are being met and any impacts on deliverable cost and/or programme are discussed. Any liaison with HE’s contractors is not anticipated and may require additional budget. •Supporting documents and specifications are provided by Highways England. •Atkins will submit the 12 consents; and have estimated time required to support the applications during the determination period, for example negotiate with the planning authority, responding the third party concerns. This estimate includes 6 hours of Redacted, 6 hours of Redacted and 36 hours of Redacted. •No post determination time has been included in the CTO, apart from receipt, and review of decision notice, with provision of a copy to HE. •No meetings other than telecons. No face to face meetings with LPA currently proposed. •Due to demanding timeframes, no pre-application meetings with the LPA have been allowed for, no site visits have been allowed for. In the event that site visits for face to face meeting are required this will be subject to additional scope. •Atkins assumes that the design and specification for each sign would be the same as that for Ashford, or if there were any revisions, these would be provided to Atkins by close of play on 7 October for the next batch of submissions. •Two signs are to be affixed to each bridge / structure – one facing the direction of traffic either side of the bridge. •Applications will be submitted via the Planning Portal (hard copies sent via the post would not be required). •Each application would be approved by the planning authority – we have not allowed for any appeals in the event of a refusal or the non-determination of an application. •Attendance at planning committees will not be required.
Task Objectives and Milestones
Outcome: 12 advertisement consent applications to be submitted to Reigate and Banstead, Canterbury, Sevenoaks and Epping Councils. Milestone: Support until the 12 applications have been determined i.e. by end Jan 20 at the latest. Milestones are continuously changing and to be agreed with Redacted. It is acknowledged that the deadline is challenging and that there are risks that achieving the deadlines is dependent on the various identified information becoming available.
Task Outcomes
Task Outcomes: Highways England is seen to be proactive in supporting Brexit preparations sustainable development whilst protecting the Secretary of State's interests in the four listed Councils and the wider SRN.
Project Risk and Management
Although the risks are better understood following submission of the previous three Ashford application sites, HE acknowledge that this task remains a “rapidly changing and demanding requirement”: •Given the challenging programme and evolving parameters, there is a risk that the applications will not gain approval to programme. Accordingly, it should be clarified that Atkins are acting as Agent for Highways England and, whilst providing professional planning and spatial planning advice in support of the applications, are proceeding following the procedures and requirements as set out by Highways England. •Information provided by Highways England including supporting documents, process for application and requirements are assumed to be fit for purpose. Highways England are responsible for final sign off of the content for each application and the background / supporting information (such as suitability and safety of the design, contractor’s specifications and materials to be used). •There is a risk that all available information is not submitted and that deadlines are not met. •There is a prospect that we would fall short on financial KPI’s and requested that this situation in taken account in subsequent assessment of task performance. •Our estimate is based on the information provided in communications to date, our experience of undertaking the submissions to date and the identified documentation we anticipate is required to submit the planning application. Any further information or iteration of comments / review or delay to the programme of delivery could incur additional costs. •Any further work or additional sites beyond the hours stated and any additional budget requirements will be discussed immediately with HE and agreed prior to the additional work being undertaken. •The named staff on this task is indicative only, the challenging programme uncertainty may require other staff. •Confirmation of final banner design for each location is required by return in order to complete deliverables. Delay in receipt could affect programme. •Atkins will commence work on all 12 sites and unless indicated otherwise by Redacted there is a risk that should a site not require submission then may result in abortive work. •The determination period time requirements are estimated and this time may or may not be required. This estimate includes 6 hours of Redacted, 6 hours of Redacted and 36 hours of Redacted. Management: •Contract Management – Redacted •Project Director – Redacted •PM / Contract Co-ordinator – Redacted •Planning Review - Redacted •Planning Lead – Redacted
Project Title: | Brexit Banners – second batch of 12 sites |  |  |  | HE Reference: | SE 42 19/20ATK
HE Project Sponsor | Sign: |  | Print Name: |  |  | Date:
Management Approver: | Sign: |  | Print Name: |  |  | Date:
Contractual Approval: |  |  | Print Name: |  |  | Date:
Fee Type: | Time Online
Notification of Non Conflict: | Redacted has signed the notification of non conflict or management of conflict for this task
Task History Record | Fee Estimate for the Task set out in this CTO | Invoiced Amount/Estimate this Financial Year |  | Date CTO Confirmed | Fee Amount Requested | HE Sponsor
SE 42 19/20ATK | 13826.78 | 0 |  |  | 13826.78 | Redacted
Fee Estimate / Fee Requested for the scope on this CTO |  |  |  |  | 13826.78
Carry over Amount from previous financial year |  |  |  |  | 0
Previously Invoiced Amount |  |  |  |  | 0
Cumulative Project Fee Estimate (this financial year) |  |  |  |  | 13826.78
Total Project Fee Estimate |  |  |  |  | 13826.78
Name | Grade | Hours |  | Hourly Rate | (£)
Redacted | Principal Planner / Engineer | 8 | @ | Redacted | Redacted
Redacted | Principal Planner / Engineer | 28 | @ | Redacted | Redacted
Redacted | Director | 10 | @ | Redacted | Redacted
Redacted | Assistant Planner/ Engineer | 42 | @ | Redacted | Redacted
Redacted | Director | 16 | @ | Redacted | Redacted
Redacted | Assistant Planner/ Engineer | 8 | @ | Redacted | Redacted
Redacted | Director | 6 | @ | Redacted | Redacted
Redacted | Assistant Planner/ Engineer | 18 | @ | Redacted | Redacted
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
Date Produced: | 2019-10-18 |  | Works Total |  | 8282.78
Confidential and commercially sensitive information which shall not be disclosed to third parties |  |  | Planning Fees |  | 5544
|  |  | Sub Total |  | 13826.78
|  |  | Expenses |  | 0
COMMERCIAL RESTRICTED / FINANCE FILE ONLY |  |  | Total |  | 13826.78