| Document Properties |  |
| --- | --- |
| Document Author |  |
| # Document Owner | # Mike Sturgeon |
| # Organisation | # Education Funding Agency |
| # Title | # JCT Intermediate Building Contract 2011 with contractor’s design |
| Version Date | # March 2015 |
| This Contract is to be used without amendment or derogation save for the deletion of footnotes and completion of items in square brackets. The form has been fixed under the Regional Contractors Framework restricted procedure. The EFA accepts no liability whatsoever for any expense, liability, loss, claim or proceedings arising from reliance placed upon the Contract. It is not a replacement for independent, specialist advice and the Employer should ensure that they take appropriate legal and technical advice in using this template document particularly with regard to the complexity and cost of the Works required. |  |

DATED										20

(1) [SCHOOL]

- and -

(2) [CONTRACTOR]

|  | CONTRACT relating to [ ] incorporating the conditions of the JCT Intermediate Building Contract 2011 Edition, with contractor's design |  |
| --- | --- | --- |

This CONTRACT is made on 	20

BETWEEN:

(1) 	[SCHOOL] (company number                     ) whose registered office is situated at                     ("Employer"); and

(2) 	[CONTRACTOR] (company number                     ) whose registered office is situated at                      ("Contractor").

RECITALS:

First	The Employer is desirous of carrying out [the construction] [the refurbishment] of [                    ] ("Works") and has had drawings and bills of quantities or a specification or work schedules prepared which show and describe the work to be done.

Second	The Works include the design and construction of

(“the Contractor’s Designed Portion”);

Third	The drawings are numbered/listed in

annexed to this Contract ("Contract Drawings") 

and have for identification been signed or initialled by or on behalf of each Party.

Fourth	The Employer has supplied to the Contractor:

the Bills of Quantities;

the Specification;4

the Work Schedules;4

other documents showing or describing or otherwise stating his requirements for the design and construction of the Contractor’s Designed Portion (“the Employer’s Requirements”);

particulars of the Intermediate Named Sub-Contract Tender & Agreement ICSub/NAM (comprising a certified copy of the tender for work included in the Bills of Quantities, Specification or Work Schedules for pricing by the Contractor and for which the Contractor is required under clause 3.7 to employ a named person, together with the Intermediate Named Sub-Contract Invitation to Tender and Tender (ICSub/NAM/IT and ICSub/NAM/T) as completed and the Tender Documents referred to in them.

Fifth	The Contractor has:

priced the Bills of Quantities/Specification/Work Schedules (as priced, "Priced Document"), the total of such pricing being the Contract Sum stated in Article 2 ("Pricing Option A"); or

stated the sum he will require for carrying out the Works shown on the Contract Drawings and described in the Specification, that sum being the Contract Sum stated in Article 2, and has supplied to the Employer a Contract Sum Analysis in accordance with the stated requirements of the Employer or a Schedule of Rates on which that sum is based ("Priced Document") ("Pricing Option B"),

and has provided the Employer with the priced schedule of activities annexed to this Contract ("Activity Schedule");

the Priced Documents, the Priced Activity Schedule, where provided, and (where Pricing Option B applies) the (unpriced) Specification have each for identification been signed or initialled by or on behalf of each Party.

Sixth	In response to the Employer's Requirements the Contractor has supplied to the Employer:

documents showing and describing the Contractor's proposals for the design and construction of the Contractor's Designed Portion ("Contractor's Proposals"); and

an analysis of the portion of the Contract Sum relating to the Contractor's Designed Portion ("CDP Analysis").

Seventh	The Employer has examined the Contractor's Proposals and, subject to the Conditions, is satisfied that they appear to meet the Employer's Requirements.  The Employer's Requirements, the Contractor's Proposals and the CDP Analysis have each for identification been signed or initialled by or on behalf of each Party and particulars of each are given in the Contract Particulars.

Eighth	For the purposes of the Construction Industry Scheme (CIS) under the Finance Act 2004, the status of the Employer is, as at the Base Date, that stated in the Contract Particulars.

Ninth	Not used.

Tenth	The extent of the application of the Construction (Design and Management) Regulations 2015 ("CDM Regulations") to the Works is stated in the Contract Particulars.

Eleventh	The division of the Works into Sections is shown in the Bill of Quantities/Specification/ Work Schedules and/or or the Contract Drawings or in such other documents as are identified in the Contract Particulars.

Twelfth	Where so stated in the Contract Particulars, this Contract is supplemented by the Framework Agreement identified in those Particulars.

Thirteenth The Supplemental Provisions identified in the Contract Particulars apply.

ARTICLES:

IT IS HEREBY AGREED as follows:

# CONTRACTOR'S OBLIGATIONS

For the consideration hereinafter mentioned the Contractor will upon and subject to the Contract Documents carry out and complete the Works shown upon, described by or referred to in those Contract Documents and in accordance with them.

# CONTRACT SUM

The Employer will pay to the Contractor the VAT exclusive sum of [                    pounds] (£                    ) ("Contract Sum") or such other sum as shall become payable hereunder at the times and in the manner specified in the Conditions.

# ARCHITECT/CONTRACT ADMINISTRATOR

The term "Architect/Contract Administrator" in the Conditions shall mean [                    ] or, in the event of his death or ceasing to be the Architect/Contract Administrator for the purpose of this Contract, such other person as the Employer shall nominate within a reasonable time but in any case no later than 14 days after such death or cessation for that purpose, not being a person to whom the Contractor no later than seven days after such nomination shall object for reasons considered to be sufficient a person appointed pursuant to the procedures under this Contract relevant to the resolution of disputes or differences.  Provided always that no person subsequently appointed to be the Architect/Contract Administrator under this Contract shall be entitled to disregard or overrule any certificate or opinion or decision or approval or instruction given or expressed by the Architect/Contract Administrator for the time being.

# QUANTITY SURVEYOR

The term “Quantity Surveyor” in the Conditions shall mean [                    ] or, in the event of the death of the Quantity Surveyor or his ceasing to be the Quantity Surveyor such other person as the Employer shall appoint.

# PRINCIPAL DESIGNER

The term “Principal Designer” in the Conditions shall mean [                    ] or, in the event of the death of the Principal Designer or his ceasing to be the Principal Designer such other person as the Employer shall appoint as the Principal Designer pursuant to the CDM Regulations.

# PRINCIPAL CONTRACTOR

The term "Principal Contractor" in the Conditions shall mean the Contractor, or in the event of his ceasing to be the Principal Contractor such other person as the Employer shall appoint as the Principal Contractor pursuant to of the CDM Regulations.

# ADJUDICATION

If any dispute or difference arises under this Contract either Party may refer it to adjudication in accordance with clause 9.2.

# LEGAL PROCEEDINGS

Subject to Article 7, if any dispute or difference as to any matter or thing of whatsoever nature arising under this Contract or in connection therewith shall arise between the Parties either during the progress or after the completion or abandonment of the Works or after the determination of the employment of the Contractor it shall be determined by legal proceedings and the English Courts shall have jurisdiction.

# SCHEDULE OF AMENDMENTS

The Conditions of the JCT Intermediate Building Contract with contractor’s design 2011 (“ICD2011”) are intended to be and are hereby incorporated into and amended and supplemented by the Schedule of Amendments contained in Appendix A to this Contract and this Contract shall be read and construed accordingly. In the case of inconsistency between the Schedule of Amendments and any other term of this Contract, the Schedule of Amendments shall prevail.

# COLLATERAL WARRANTIES: THE CONTRACTOR

## The Contractor shall execute and deliver to the Employer within 14 days of a written request from the Employer a Deed or Deeds of Collateral Warranty in the form of Schedule 3 to this Contract with only such amendments as the Employer may approve in favour of:

### any organisation providing finance in connection with the whole or any part of the Works;

### any purchaser of the whole or any part of the Works;

### any organisation providing finance to a purchaser of the whole or any part of the Works;

### any tenant of the whole or any part of the Works;

### any organisation providing finance to a tenant of the whole or any part of the Works;

### any freeholder or landlord of the Site (where this is not the Employer); and

### the Governing Body of [the School] and

### [specify any other interested parties here]

## Should the collateral warranties from the Contractor not be delivered to the Employer within 14 days of a written request from the Employer then the Employer shall be entitled to withhold all future payments to the Contractor until such time as the relevant collateral warranties have been provided to the Employer.

# COLLATERAL WARRANTIES: SUB-CONTRACTORS

## In this Article 11 ‘Specified Sub-contractors’ means any sub-contractor or supplier of the Contractor for the following elements of the Works:

[Ground improvement works]

[Piling]

[Structural steel frame/roof structure]

[Pre-cast concrete floors/stairs]

[Profile metal cladding/roofing]

[Mechanical services]

[Electrical services]

[Fenestration] and

[Lifts].

## Each of the Specified Sub-contractors shall be appointed by deed, and within seven days of the appointment of a Specified Sub-contractor the Contractor shall supply a complete copy of the sub-contract to the Employer.

## The Contractor shall procure that every Specified Sub-contractor shall provide to the Employer a Deed or Deeds of collateral warranty in the form as set out in Schedule 3 to this Contract with only such amendments as the Employer may approve in favour of:

### the Employer;

### any organisation providing finance in connection with the whole or any part of the Works;

### any purchaser of the whole or any part of the Works;

### any organisation providing finance to a purchaser of the whole or any part of the Works;

### any tenant of the whole or any part of the Works;

### any organisation providing finance to a tenant of the whole or any part of the Works;

### any freeholder or landlord of the Site (where this is not the Employer);

### the Governing Body of [the School] and;

### [specify any other interested parties here]

## The Contractor shall procure that every Specified Sub-contractor shall take out and maintain £[1,000,000] ([one] million pounds) of professional indemnity or product liability insurance (or subject to the written agreement of the Employer, such agreement not to be unreasonably withheld or delayed, a level of cover that is commercially reasonable subject to the value and nature of the sub-contract package) for the period required by clause 3.1 of the Specified Sub-contractor collateral warranty.

## Should the collateral warranties from the Specified Sub-contractors not be delivered to the Employer within 14 days of a written request from the Employer then the Employer will be entitled to withhold all future payments to the Contractor in respect of that particular Specified Sub-contractor’s work until such time as the relevant collateral warranty has been delivered.

## The Employer’s right to withhold payment under sub-clause 11.5 shall not apply once the Contractor satisfies its obligations under Article 11.

## If the Contractor terminates the employment of any Specified Sub-contractor, he shall forthwith give notice in writing to the Employer of such event and, as soon as practicable, appoint or employ a substitute whose identity shall first be approved by the Employer (such approval not to be unreasonably withheld or delayed).  The Contractor shall procure the execution by such substitute Specified Sub-Contractors, of collateral warranty agreements on like terms to those provided for in this Article 11 upon the appointment or engagement of any such substitute Specified Sub-Contractors and deliver the same forthwith to the Employer."

# DESIGN CONSULTANTS

## [The Employer has appointed the following consultants for the purposes of the Works:-

### list the consultants to be appointed by the employer and novated to the Contractor;

### (together the “Novated Consultants”).

## [Within 7 days of executing this Contract or receiving a written request from the Employer (whichever is earlier), the Contractor shall enter into a deed of novation with the Novated Consultants in the form set out in Schedule 7].

## Within 21 days of executing this Contract, the Contractor shall appoint the following consultants (or such other consultants as the Employer shall approve) for the purposes of the Works:

## [Architect];

## [Mechanical and Electrical];

## [Civil and Structural];

## [list any other consultants appointed by the Contractor]

## (together the “Design Consultants”)

## The Design Consultants shall be appointed by deed, such terms to be approved by the Employer (acting reasonably).

## Within seven days of the appointment of each Design Consultant the Contractor shall supply to the Employer a completed certified copy of the Design Consultant’s deed of appointment.

## The Contractor shall not dismiss any of the Design Consultants or vary the terms of their appointment without the written approval of the Employer.

## If the employment of any consultant is terminated before the completion of the services allocated to him, the Contractor shall as soon as is practicable but on seven days’ notice to the Employer appoint another consultant to complete those services (save any consultant to whom the Employer shall make reasonable objection in writing).  The foregoing provisions of this Article 12 shall apply to such replacement consultant, mutatis mutandis.

## The Contractor shall procure that every Design Consultant shall provide to the Employer a deed or deeds of collateral warranty in the form set out in Schedule 3 of  this Contract with only such amendments as the Employer may approve in favour of:

### the Employer;

### any organisation providing finance in connection with the whole or any part of the Works;

### any purchaser of the whole or any part of the Works;

### any organisation providing finance to a purchaser of the whole or any part of the Works;

### any tenant of the whole or any part of the Works;

### any organisation providing finance to a tenant of the whole or any part of the Works;

### any freeholder or landlord of the Site (where this is not the Employer);

### the Governing Body of [the School] and;

### [specify any other interested parties here]

## Should the collateral warranties from the Design Consultants not be delivered to the Employer within 14 days of a written request from the Employer then the Employer will be entitled to withhold all future payments to the Contractor in respect of that particular Design Consultant’s work until such time as the relevant warranty has been delivered.

## The Employer’s right to withhold payment under Article 12.9 shall not apply once the Contractor satisfies its obligations under this Article 12.

# PARENT COMPANY GUARANTEE

The Contractor shall procure the execution and delivery to the Employer by its parent company, within 14 days of a written request from the Employer, of a parent company guarantee, in the form set out at Schedule 3 to this Contract with only such amendments as the Employer may approve.

CONTRACT PARTICULARS

|  | Contract Particulars |  |
| --- | --- | --- |
|  | Note: An asterisk (*) indicates text that is to be deleted as appropriate |  |
|  | Part 1: General |  |
| Clause etc. | Subject |  |
| Fourth Recital | Employer's Requirements (State reference numbers and dates or other identifiers of documents in which these are contained). |  |
| Sixth Recital | Contractor's Proposals (State reference numbers and dates or other identifiers of documents in which these are contained).19 |  |
| Sixth Recital | CDP Analysis (State reference numbers and dates or other identifiers of documents in which these are contained). |  |
| Eighth Recital and clause 4.5 | Construction Industry Scheme (CIS) | Employer at the Base Date * is a 'contractor'/is not a 'contractor' for the purposes of the CIS |
| Tenth Recital | CDM Regulations | The project * is/is not notifiable |
| Eleventh Recital | Description of Sections (if any) (If not shown or described in the Bills of Quantities/Specification/Work Schedules or the Contract Drawings, state the reference numbers and dates or other identifiers of documents in which they are shown).19 |  |
| Twelfth Recital | Framework Agreement (if applicable) (State date, title and parties) | EFA Regional Contractors Framework Agreement [Sector [ ]] made between Secretary of State for Education and Contractor dated [ ]. |
| Thirteenth Recital and Schedule 5 | Supplemental Provisions (Where neither entry against an item below is deleted, the relevant paragraph applies.) |  |
|  | Collaborative working | Paragraph 1 applies |
|  | Health and safety | Paragraph 2 applies |
|  | Cost savings and value improvements | Paragraph 3 applies |
|  | Sustainable development and environmental considerations | Paragraph 4 applies |
|  | Performance Indicators and monitoring | Paragraph 5 * applies/does not apply |
|  | Notification and negotiation of disputes | Paragraph 6 applies |
|  | Where paragraph 6 applies, the respective nominees of the Parties are | Employer's nominee |
|  |  | Contractor's nominee |
|  |  | or such replacement as each Party may notify to the other from time to time |
|  | Arbitration | Clauses 9.3 to 9.8 (Arbitration) Do not apply |
| 1.1 | Base Date |  |
| 1.1 | Date for Completion of the Works (where completion by Sections does not apply) |  |
|  | Sections: Dates for Completion of Sections | Section : |
|  |  | Section : |
|  |  | Section : |
| 1.7 | Addresses for service of notices by the Parties (If none is stated, the address in each case, unless and until otherwise agreed and subject to clause 1.7.3, shall be that shown at the commencement of the Agreement) | Employer (Fax Number) |
|  |  | Contractor |
|  |  | (Fax Number) |
| 2.4 | Date of Possession of the Site (where possession by Sections does not apply) |  |
|  | Sections: Dates of Possession of Sections 22 | Section : 20 |
|  |  | Section : 20 |
|  |  | Section : 20 |
| 2.5 | Deferment of possession of the Site (where possession by Sections does not apply) | Clause 2.5 * applies/does not apply Maximum period of deferment (if less than 6 weeks) is …………………………………….. |
|  | Sections: deferment of possession of Sections | Clause 2.5 * applies/does not apply Maximum period of deferment (if less than 6 weeks) is |
|  |  | Section : 20 |
|  |  | Section : 20 |
|  |  | Section : 20 |
| 2.23.2 | Liquidated damages (where completion by Sections does not apply) | at the rate of £ per |
|  | Sections: rate of liquidated damages for each Section 23 | Section : £ per week or part thereof |
|  |  | Section : £ per week or part thereof |
|  |  | Section : £ per week or part thereof |
| 2.29 | Sections: Section Sums 23 | Section : £ |
|  |  | Section : £ |
|  |  | Section : £ |
| 2.30 | Rectification Period | 12 months from the date of Practical Completion of the Works |
|  | Sections: Rectification Periods 23 | Section : 12 months |
|  |  | Section : 12 months |
|  |  | Section : 12 months from the date of Practical Completion of each Section |
| 4.6 | Advance payment | Clause 4.6 does not apply |
| 4.6 | Advance Payment Bond | An advance payment bond is not required |
| 4.7.1 | Interim payments - due dates (If no date is stated, the first due date is one month after the Date of Possession.) | The first due date is: |
|  |  | and thereafter the same date in each month or the nearest Business Day in that month |
| 4.8.1 | Interim payments - percentages of value |  |
|  | Where the Works, or those works in a Section, have not achieved Practical Completion, the percentage of total value in respect of the works that have not achieved practical completion is (The percentage is 95 per cent unless a different rate is stated). | per cent |
|  | Where the Works, or those works in a Section, have achieved Practical Completion, the percentage in respect of the completed works is (The percentage is 97½ per cent unless a different rate is stated). | per cent |
| 4.9.4 | Listed items - uniquely identified (Delete the entry if no bond is required.) | * For uniquely identified Listed Items a bond in respect of payment for such items is required for £ |
| 4.9.5 | Listed Items - not uniquely identified (Delete the entry if clause 4.9.5 does not apply.) | * For Listed Items that are not uniquely identified a bond in respect of payment for such items is required for £ |
| 4.15 and Schedule 4 | Contribution, levy and tax fluctuations Percentage addition for Fluctuations Option, paragraph 12 | Do not apply per cent |
| 6.4.1.2 | Contractor's insurance - injury to persons or property Insurance cover (for any one occurrence or series of occurrences arising out of one event) | £ |
| 6.5.1 | Insurance - liability of Employer (Not required unless it is stated that it may be required and the minimum amount of indemnity is stated) | Insurance * may be required/is not required Minimum amount of indemnity for any one occurrence or series of occurrences arising out of one event £ |
| 6.7 and Schedule 1 | Insurance of the Works - Insurance Options | Schedule 1: * Insurance Option A applies/ * Insurance Option B applies/ * Insurance Option C applies |
| 6.7 and Schedule 1 Insurance Option A (paragraphs A.1 and A.3, B (paragraph B1) or C (paragraph C.2) | Percentage to cover professional fees (If no other percentage is stated, it shall be 15 per cent.) | per cent |
| 6.7 and Schedule 1 Insurance Option A (paragraph A.3) | Annual renewal date of insurance (as supplied by the Contractor) |  |
| 6.10 and Schedule 1 | Terrorism Cover - details of the required cover (State reference numbers and dates or other identifiers of documents setting out the requirements. Unless otherwise stated, Pool Re Cover is required.) |  |
| 6.12 | Joint Fire Code | The Joint Fire Code * applies/does not apply |
|  | If the Joint Fire Code applies, state whether the insurer under Schedule 1, Insurance Option A, B or C (paragraph C.2) has specified that the Works are a "Large Project": | * Yes/No |
| 6.15 | Joint Fire Code - amendments/revisions (The cost shall be borne by the Contractor unless otherwise stated.) | The cost, if any, of compliance with amendment(s) or revision(s) to the Joint Fire Code shall be borne by * the Employer/the Contractor |
| 6.16 | Contractor's Designed Portion (CDP) Professional Indemnity insurance |  |
|  | Level of cover (If an alternative is not selected the amount shall relate to claims or series of claims arriving out of one event. A period of insurance for these purposes shall be one year unless otherwise stated.) | Amount of indemnity required * relates to claims or series of claims arising out of one event/ * is the aggregate amount for any one period of insurance |
|  |  | and is £ |
|  | Level of cover for pollution/contamination claims | £ |
|  | Expiry of required period of CDP Professional Indemnity insurance is | 12 years |
| 8.9.2 | Period of suspension (If none is stated, the period is 2 months). |  |
| 8.11.1.1 to 8.11.1.5 | Period of suspension (If none is stated, the period is 2 months). |  |
| 9.2.1 | Adjudication | President or a Vice-President or Chairman or a Vice-Chairman of The Royal Institution of Chartered Surveyors |
|  | Nominating body - where no Adjudicator is named or where the named Adjudicator is unwilling or unable to act (whenever that is established) (Where an Adjudicator is not named and a nominator has not been selected, the nominator shall be the nominator- listed opposite selected by the Party requiring the reference to adjudication). | Royal Institution of Chartered Surveyors |
| 9.4.1 | Arbitration - appointer of Arbitrator (and of any replacement) | Does not apply |

| Executed as a deed, but not delivered until the first date specified on page 1, by [ ] by a director in the presence of a witness: |  | )))) | Signature |  |
| --- | --- | --- | --- | --- |
|  |  |  | Name (block capitals) |  |
|  |  |  |  | Director |
| Witness signature |  |  |  |  |
| Witness name |  |  |  |  |
| (block capitals) |  |  |  |  |
| Witness address |  |  |  |  |

| Executed as a deed, but not delivered until the first date specified on page 1, by [ ] by a director in the presence of a witness: |  | )))) | Signature |  |
| --- | --- | --- | --- | --- |
|  |  |  | Name (block capitals) |  |
|  |  |  |  | Director |
| Witness signature |  |  |  |  |
| Witness name |  |  |  |  |
| (block capitals) |  |  |  |  |
| Witness address |  |  |  |  |

APPENDIX A

Schedule of Amendments to Conditions of Contract

CONDITIONS

Section 1	Definitions and Interpretation

1.1	Definitions

Amend existing definitions and insert new definitions, as follows:

"Asbo: an anti-social behaviour order as defined in the Crime and Disorder Act 1998."

  - “Associated Person: a person is an associated person if they:-

  - (a) perform services or works for or on behalf of the Contractor and that shall include but not be limited to any Sub-Contractor, Supplier, agent or subsidiary of the Contractor;

  - (b)	the capacity in which such services or works may be performed is irrelevant;

  - (c)	whether a person performs services or works for or on behalf of the Contractor, in relation to this Contract or any other contract, shall be determined by reference to all relevant circumstances and not solely by reference to the nature of a person’s relationship with the Contractor;

(d) a person who is an employee of the Contractor shall be deemed to perform services or   works for the Contractor."

"Barred List: the barred lists provided for under the Safeguarding Vulnerable Groups Act 2006 as amended by the Protection of Freedoms Act 2012 (as may be amended or re-enacted from time to time)."

"CDM Co-ordinator: delete.”

"CDM Planning Period: delete.”

"CDM Regulations: the Construction (Design and Management) Regulations 2015 and any modification or replacement of the same".

"Construction Phase Plan: the plan prepared by the Principal Contractor under the CDM Regulations in order to comply with regulation 12, including any updates and revisions."

"Contract: the Articles, Contract Documents, Conditions, Schedule of Amendments and any other document forming part of this contract.”

"Convictions: other than in relation to any minor road traffic offences, any previous or pending prosecutions, convictions, cautions and binding overs (including any spent convictions as contemplated by section 1(1) of the Rehabilitation of Offenders Act 1974 by virtue of the exemptions specified in Part II of Schedule 1 of the Rehabilitation of Offenders Act 1974 (Exemptions) Order 1975 (SI 1975/1023) or any replacement or amendment to that Order)."

"Design Consultants: has the meaning given to it in Article 11.3."

“Disclosure and Barring Scheme: the disclosure and barring scheme operated by the Disclosure and Barring Service.”

“Disclosure and Barring Service: the non-departmental public body established pursuant to the Protection of Freedoms Act 2012.”

"DPA: the Data Protection Act 1998."

"Educational Services: the provision of teaching and pastoral support for school age children, the provision of careers advice, liaison with parents and guardians of pupils and the carrying on of extra-curricular activities for pupils and the use of educational accommodation by the local community."

  - "Funder": delete.

"Good Building Practice: all BSI Group and other appropriate standards and codes of practice and proven up-to-date practices that are in force at the date of this Contract, applicable to the UK construction industry and relevant to the Works."

"Named Employee: has the meaning set out in clause 2.35.1 of this Contract."

"Practical Completion: a stage of completeness of the Works which allows the Property to be occupied and used and in which

there are no apparent deficiencies or defects and no incomplete items of work which would or could

compromise the health and safety of persons entering and/or occupying the Property; and/or

given their cumulative number and/or nature, have more than a trivial impact on the beneficial occupation and use of the Property, by reason of their rectification or completion; and

the Site has been substantially cleared of all temporary buildings, builders' plant and equipment, unused materials and rubbish

provided that where the Contract Documents expressly state that the commissioning, testing and/or adjustment of any mechanical or electrical services installations forming part of the Works is to be completed before practical completion of the Works is to be regarded for the purposes of this Contract as achieved, then the Works shall not be considered to have achieved practical completion for the purposes of this Contract until such commissioning testing and/or adjustment is completed as the Contract Documents require."

“Principal Designer: the person named in Article 5 or any successor appointed by the Employer.”

"Programme: the programme for the carrying out and completion of the Works in accordance with the terms of the Contract."

"Prohibited Acts:

offering, promising, giving or proposing to give to any servant of the Employer any gift or consideration of any kind as an inducement or reward:

for doing or not doing (or for having done or not having done) any act in relation to the obtaining or performance of this Contract or any other contract with the Employer; or

for showing or not showing favour or disfavour to any person in relation to this Contract or any other contract with the Employer;

entering into this Contract or any other contract with the Employer in connection with which commission has been paid or has been agreed to be paid by the Contractor or on its behalf, or to its knowledge, unless before the relevant contract is entered into particulars of any such commission and of the terms and conditions of any such contract for the payment thereof have been disclosed in writing to the Employer;

committing any offence:

under the Bribery Act 2010;

under legislation creating offences in respect of fraudulent acts; or

at common law in respect of fraudulent acts in relation to this Contract or any other contract with the Employer; or

defrauding or attempting to defraud or conspiring to defraud the Employer."

"Property: the property comprised of the completed Works."

"Purchaser: delete."

"Schedule of Amendments: the schedule of additional amendments, modifications and changes to the Conditions as set out in this Appendix A."

"Sensitive Works: the carrying out of any part of the Works (including the making good of any defects) in or on any part or parts of the Site which may allow direct access to premises occupied or used or likely to be occupied or used, during the course of the Works (including the making good of any defects) by pupils attending a school."

"Site"                      [address/description] upon which the Works are to be carried out [and the extent of which is shown, for identification purposes only, edged red on the plan annexed at schedule 6] and all references in the Contract to "the site" shall be read and construed as references to "the Site."

"Sub-Contractor: any person engaged as an independent contractor by the Contractor to carry out and complete all or any part of the Works."

"Supplier: any person engaged by the Contractor to provide goods or materials required by the Contractor for incorporation into the Works or any part thereof."

"Tenant: delete."

1.6	Contracts (Rights of Third Parties) Act 1999

Delete and insert a new clause as follows:

"A person who is not a party to this Contract will have no right under the Contracts (Rights of Third Parties) Act 1999 to enforce any term of this Contract.  This clause does not affect any right or remedy of any person which exists or is available otherwise than pursuant to that Act."

1.9	Effect of Final Certificate

1.9.1

1.9.1.1	Delete and insert:

"that all terms of the Contract which require an amount to be added to or deducted from the Contract Sum or an adjustment to be made to the Contract Sum have been complied with, save where in any computation there has been any accidental inclusion or exclusion of any work, materials or goods or any arithmetical error (in which event, the Final Certificate shall have effect as conclusive evidence as to all other computations)".

1.10	Effect of certificates other than Final Certificate

In line 1, delete "Save as stated in clause 1.9 no" and insert "No".

Section 2	Carrying out the Works

2.1	General obligations

2.1.3 delete “regulations 11, 12 and 18 of”.

Insert new clause 2.1.4 as follows:

"2.1.4

2.1.4.1	The Contractor shall, at all times, take all reasonable steps to reduce and prevent any public or private nuisance (including, without limitation, any such nuisance caused by noxious fumes, noisy working operations or the deposit of any material or debris on the public highway) or other interference with the rights of any adjoining or neighbouring landowner, tenant or occupier or any statutory undertaker arising out of the carrying out of the Works or of any obligation pursuant to clause 2.30 and shall assist the Employer in defending any action or proceedings which may be instituted in relation thereto.

2.1.4.2	The Employer shall, if so requested by the Contractor, supply to the Contractor in such time as may be reasonable, having regard to the time and nature of any such request, any relevant information in the possession of the Employer relating to the rights of such third parties.

2.1.4.3	The Contractor shall be responsible for and shall be liable to the Employer from and against any and all reasonably foreseeable and direct expenses, liabilities, losses, claims and proceedings whatsoever resulting from any such nuisance or interference, save only where such nuisance or interference is the consequence of an instruction of the Employer.

2.1.4.4	Without prejudice to the Contractor’s obligations under clause 2.1.4.1 the Contractor shall ensure that there is no trespass on or over any adjoining or neighbouring property arising out of or in the course of or caused by the carrying out of the Works or of any obligation pursuant to clause 2.30.

2.1.4.5	If the carrying out of the Works or of any obligation pursuant to clause 2.30 is likely to necessitate any interference (including without limitation, the oversailing of tower crane jibs) with the rights of adjoining or neighbouring owners or occupiers, then the Contractor shall, at no cost to the Employer, obtain the prior written agreement of such owners and/or occupiers thereto, and such agreement shall be subject to the approval of the Employer before execution.  The Contractor shall comply in every respect with any conditions contained in any such agreement."

Insert new clause 2.1.5 as follows:

"2.1.5

2.1.5.1	The Contractor has been afforded the opportunity to inspect the physical and other conditions (including sub-surface conditions) of the Site and its surrounds and the available means of access to and egress from the Site and shall be deemed to have fully acquainted himself with the same and to have obtained all necessary information concerning any associated risks, contingencies and other circumstances that may influence or affect the execution of the Works.  No failure on the part of the Contractor to discover or foresee any such condition, risk, contingency or circumstance (whether or not the same ought reasonably to have been discovered or foreseen) nor any misunderstanding in respect of any matter affecting the Site and its surrounds and the available means of access thereto shall relieve the Contractor from any risks or obligations imposed on or undertaken by him, nor shall the Contractor be entitled to an addition to the Contract Sum or to an adjustment of the Completion Date.

2.1.5.2	The Contractor may at his own risk and expense rely upon and use any survey, report or other document prepared by or on behalf of the Employer regarding any such matter as is referred to in this clause 2.1.5, but the Employer makes no representation or warranty as to the accuracy or completeness of any such survey, report or document or any representation or statement contained therein.  The Employer shall have no liability arising out of or in relation to any such survey, report or document or from any representation or statement."

Insert new clause 2.1.6 as follows:

"2.1.6	No inspection, test, review, consent, notice, permission, payment, certificate or other approval made or given by or on behalf of the Employer under the Contract, or any failure to make or give the same, shall relieve the Contractor in whole or in part of any of his obligations or liabilities under this Contract, whether by way of contribution or otherwise".

2.2	Materials, goods and workmanship

2.2.1	Delete the second sentence and substitute with:

"Unless otherwise specified in the Contract Documents or agreed between the Parties:

2.2.1.1	all materials and goods for the Works shall be new, appropriate for use in the Works, of a satisfactory quality and fit for the purpose or purposes stated or otherwise reasonably to be inferred from the Contract Documents; and

2.2.1.2	workmanship for the Works shall be of a satisfactory quality and standard appropriate for the Works."

Insert a new clause 2.2.3 as follows:

"2.2.3	The Contractor shall not specify or approve for use, use or permit to be used in connection with the Works any materials which at the time of specification or use (as the case may be):

2.2.3.1	are known to be deleterious (either to health and safety or to the durability of the Works); or

2.2.3.2	contravene any relevant standard or code of practice issued from time to time by the BSI Group or under a European directive relating to standards or Good Building Practice; or

2.2.3.3	do not accord with the guidelines contained in the edition of the publication Good Practice in Selection of Construction Materials (British Council for Offices (BCO)), current at the date of specification or use."

2.4	Date of possession - progress

At the end of the clause, after "clause 2.25", insert ", clause 2.4A".

Insert a new clause 2.4A as follows:

2.4A	"Upon any determination of the Contractor's employment under Section 8 or if this Contract is otherwise determined, repudiated or discharged, the Contractor shall, notwithstanding that the validity of such determination, repudiation or discharge may be disputed by the Contractor (and unless the Employer otherwise agrees in writing), immediately carry out all instructions of the Employer with regard to the conclusion of work on the Site, the delivery to the Employer of all Contractor's Design Documents (whether or not in the course of preparation or production), the protection of the Works and any goods and materials for the Works, the safe and orderly removal of all plant, equipment and other items belonging to the Contractor and the Contractor shall vacate the Site and deliver to the Employer possession of the Site and of the Works in a neat and tidy condition."

2.7	Work not forming part of the Contract

Delete the clause and replace with the following:

"2.7.1	The Contractor shall permit the execution of work not forming part of this Contract by the Employer and/or any persons authorised or licensed by the Employer to carry out such work on those parts of the Site in the Contractor's possession (including statutory undertakers and any other authorities).  The Contractor shall at any time allow the Employer and/or any such persons to re-enter the Site for the purposes of executing such work or to install any goods, equipment or other articles for fitting out.  Provided always that the Employer shall use all reasonable endeavours to procure that the execution of such work does not obstruct, interfere with or delay the Contractor in carrying out the Works.

2.7.2	The Contractor shall use all reasonable endeavours not to interfere with or impede the progress of any works being carried out by the Employer and/or any person authorised or licensed by the Employer to carry out such works and shall observe all reasonable requirements of the same in relation to the carrying out of such works.

2.7.3	Each person referred to in this clause 2.7 shall, for the purposes of clauses 6.1 to 6.3 be deemed to be a person for whom the Employer is responsible and not to be a sub-contractor of the Contractor.

2.7.4	The execution of any work referred to in this clause 2.7 shall not in any way be deemed to be or treated as taking possession of part or parts of the Works by the Employer as referred to in clause 2.25 and the provisions of clauses 2.25 to 2.29 shall not apply to the execution of such work."

2.8	Contract Documents

Insert new clause 2.8.4 as follows:

"2.8.4	If the employment of the Contractor under this Contract is terminated for any reason, the Contractor will forthwith deliver to the Employer two copies of the Contractor's Design Documents."

2.10 Construction Information

2.10.2 delete “regulations 11, 12 and 18 of”.

2.11	Further drawings, details and instructions

Insert new clause 2.11.4 as follows:

"2.11.4	Where under this Contract the Contractor is to provide to the Architect/Contract Administrator drawings details or other documents (including any such drawings details or other documents to be supplied to the Contractor by its Sub-Contractors and/or Suppliers) for review comment on and/or approval by the Architect/Contract Administrator the Contractor shall provide such drawings details or other documents to the Architect/Contract Administrator in sufficient time to allow the Architect/Contract Administrator to properly review comment on and/or approve the same without any delay being caused to the carrying out of the Works."

2.14 Instructions – additions to Contract Sum, exceptions

2.14.2 delete “regulations 11, 12 and 18 of”.

2.17	Materials and goods - on Site

In lines 2 and 3, delete "such consent not to be unreasonably delayed or withheld".

2.19	Notice of delay - extensions

2.19.1	In lines 5 and 6 after "save where these Conditions expressly provide otherwise", insert "and provided that the Contractor has made reasonable and proper efforts to mitigate such delay and the effects of such delay".

2.21	Practical Completion, Lateness and Liquidated Damages

In line 2, after "achieved", insert "and the Works have or a Section has reached a stage of completeness in which there are no apparent deficiencies or defects in the Works or a Section and no incomplete works and the Site of the Works has been substantially cleared of all temporary buildings, builders' plant and equipment unused materials and rubbish".

2.22	Certificate of non-completion

In line 2, after "to that effect." insert a new second sentence as follows:

"Such certificate shall (unless cancelled as hereinafter provided or revised in proceedings pursuant to Article 7) be conclusive and binding on the Contractor until final ascertainment or agreement between the Parties as to the matters to which it relates."

2.27	Defects etc. - Relevant Part

At the end of clause 2.27 insert as follows:

"Provided that the Architect/Contract Administrator shall not be required to issue such certificate any earlier than 14 days after the end of the Rectification Period applicable to such Relevant Part"

2.30	Rectification

In line 1, after "which" insert "remain at Practical Completion of the Works or such Section or which".

In line 3, after "this Contract", insert "or to frost occurring before Practical Completion of the Works or a Section".

In line 4, after "be made good by the Contractor", insert "to the satisfaction of the Architect/Contract Administrator and as soon as practicable following the delivery to him of particulars of such defects (and if the Architect/Contract Administrator so directs, outside the normal working hours of the Contractor)".

Insert, at the end of the clause, the following new final sentence:

"If the Contractor fails to remedy any defect, shrinkage or other fault or complete any outstanding item of work which he is required to remedy or complete within a reasonable time of receipt of an instruction to do so, the Employer shall be entitled to employ or pay others to remedy the outstanding items and the reasonable and proper costs thereof shall be a debt payable by the Contractor to the Employer."

2.31	Certificate of making good

At the end of the clause insert as follows:

"Provided that the Architect/Contract Administrator shall not be required to issue any certificate to that effect any earlier than 14 days after the end of the relevant Rectification Period."

CDP Design Work

2.32	As-built Drawings

Renumber clause 2.32 as 2.32.1 and insert new clause 2.32.2 as follows:

"2.32.2	Notwithstanding any provision to the contrary in this Contract, the Contractor shall not be entitled to any payment of the Retention that would (but for this provision) become due and payable under this Contract until the provisions of clause 2.32.1 have been complied with."

2.33	Copyright and use

2.33.1	In line 1 delete "Subject to all monies due and payable under this Contract to the Contractor having been paid, the" and insert "The".

On line 4 after "maintenance," insert "extension".

Insert new clauses 2.33.3, 2.33.4 and 2.33.5 as follows:

2.33.3	The Contractor warrants to the Employer that the use by the Employer of any of the Contractor's Design Documents for any purpose provided for in clause 2.33.1 will not infringe the rights of any third party in relation to the same.

2.33.4	If the employment of the Contractor under this Contract is terminated the Contractor hereby agrees that the licence in respect of the Contractor's Design Documents granted pursuant to clause 2.33.1 shall continue in all respects and shall not be affected by such termination, and the Contractor shall when requested in writing to do so by the Employer deliver up forthwith to the Employer two copies of the Contractor's Documents.

2.33.5	The Contractor warrants to the Employer and undertakes to procure that his Sub-Contractors and Suppliers shall waive any rights the Contractor, the Sub-Contractors and/or Suppliers may have pursuant to Section 80 of the Copyright, Designs and Patents Act 1988."

2.34	Design liabilities and limitation

Delete the clause and replace with the following:

"2.34.1	The Contractor warrants and undertakes to the Employer that:

2.34.1.1	he has exercised and will continue to exercise in the design of the CDP Works the skill, care and diligence reasonably to be expected of a properly qualified and competent professional architect or, as the case may be, other appropriate professional designer experienced in the design of works of a similar size, scope and complexity as the CDP Works;

2.34.1.2	he is responsible for the entire design of the CDP Works including any design contained in the Employer's Requirements (and will notify the Employer if the Employer's Requirements are inadequate or inconsistent immediately upon such inadequacy or inconsistency becoming apparent), all design contained in the Contractor's Proposals and all design which he prepares or has prepared on his behalf by the Contractor's Consultants or any Sub-Contractors;

2.34.1.3	the design of the CDP Works and of each part of the CDP Works will, when completed, comply with any performance-related requirement included or referred to in the Contract Documents and all Statutory Requirements; and

2.34.1.4	the various elements of the design of the CDP Works will be properly co-ordinated and integrated one with another and with the Works and, in this regard, he will at all times co-operate and liaise with the consultants appointed by the Employer.

2.34.2	The Contractor shall not be excused liability for breach of any of the warranties set out in clause 2.34.1 by reason of the fact that he may have exercised all due skill, care and diligence in the selection of the persons to whom he delegated his responsibilities."

2.34.3	The aggregate liability of the Contractor to the Employer for any matters arising in connection with the performance of its obligations under this Contract shall not except as set out below at clause 2.34.4 exceed [one and a half times contract sum].

2.34.4	The Contractor shall not exclude or restrict its liability for any of the following and no liability for the same shall be taken into account in determining whether the limit of liability under clause 2.34.3 has been reached or exceeded:

2.34.4.1	payments made by the Contractor to the extent corresponding payments are either received by the Contractor pursuant to insurance policies required to be effected and maintained by the Contractor in accordance with clause 6 of this Contract (other than professional indemnity insurance) or would have been received but for the failure of the Contractor to maintain such policies in accordance with clause 6 of this Contract or to make a claim under such policies;

2.34.4.2	the Contractor’s liability under clause 2.23;

2.34.4.3	the Contractor’s liability in the event he abandons the Works;

2.34.4.4	the Contractor’s liability in the event of any fraud, wilful misconduct of direct employees of the Contractor or of its Design Consultants, Sub-Contractors or Suppliers, in each case to the extent employed directed by the Contractor, fraudulent misrepresentation, abandonment, corruption or criminal, conduct on the part of the Contractor;

2.34.4.5	the Contractor’s liability in respect of any employer’s liability; and

2.34.4.6	the Contractor’s liability in respect of personal injury or death.

Insert new clause 2.35 as follows:

"2.35	Disclosure and Barring Service

2.35.1	The Contractor shall procure that in respect of all potential staff or persons (including Sub-Contractors) who will be carrying out any Sensitive Works (each a "Named Employee") before a Named Employee begins to attend the Site to perform any Sensitive Works:

2.35.1.1	each Named Employee is questioned as to whether he or she has any Convictions or Asbos;

2.35.1.2	the results are obtained of a check of the most extensive available kind made with the Disclosure and Barring Service  in respect of each Named Employee;

2.35.1.3	(to the extent permitted by law a copy of the results of the checks as referred to in clause 2.35.1.2 are notified to the Employer.

2.35.2	The Contractor shall procure that:

2.35.2.1	no person who appears on a Barred List following the results of a Disclosure and Barring Service check shall be employed or engaged in the performance of the Sensitive Works; and

2.35.2.2	it shall and shall procure that all Sub-Contractors shall comply with all reporting requirements to the Disclosure and Barring Service.

2.35.3	The Contractor shall procure that no person who discloses any Convictions or Asbos, or who is found to have any Convictions following the results of a Disclosure and Barring Service check, is employed or engaged in carrying out any part of any Sensitive Works without the Employer's prior written consent (such consent not to be unreasonably withheld or delayed).

2.35.4	Insofar as permitted by law, the Contractor shall procure that the Employer is kept advised at all times of any member of staff or employee of any Sub-Contractor engaged in the provision of the Sensitive Works who:

2.35.4.1	is engaged in the carrying out of any Sensitive Works; or

2.35.4.2	subsequent to his/her commencement of employment as a member of staff  receives a Conviction or Asbo which become known to the Contractor or any Sub-Contractor or whose previous Convictions or Asbos which become known to the Contractor (or any employee of the Contractor involved in the provision of the Sensitive Works) or any Sub-Contractor; or

2.35.4.3	in respect of whom information is referred to the Disclosure and Barring Service pursuant to the Disclosure and Barring Scheme; or

2.35.4.4	the Disclosure and Barring Service is "minded to bar" or who is placed on a barred list pursuant to the Disclosure and Barring Scheme which become known to the Contractor or a Sub-Contractor.

2.35.5	In the event that any member of staff of the Contractor or any employee of any Sub-Contractor is added to a Barred List, the Contractor shall procure that such member of staff is removed from the Site and shall cease to be engaged in the Sensitive Works.

2.35.6	Save to the extent prescribed otherwise pursuant to the  Disclosure and Barring Service, this clause 2.35 shall not apply to those individuals who shall be required by the Contractor to attend on the Site to provide emergency reactive services. In the case of such individuals, the Contractor shall ensure that such individuals are accompanied at all times while on each Site by a member of the Contractor's staff who has been properly employed or engaged in accordance with this clause 2.35."

Insert new clause 2.36 as follows:

"2.36	Conduct of Staff and Security Arrangements

2.36.1	Whilst engaged at the Site the Contractor shall and shall procure that its staff and the staff of any Sub-Contractor shall comply with any Employer's policies relating to the conduct of staff and security arrangements.

2.36.2	The Employer (acting reasonably) may:

2.36.2.1	instruct the Contractor that disciplinary action is taken against any employee of the Contractor or any Sub-Contractor involved in the provision of the Works (in accordance with the terms and conditions of employment of the employee concerned) where such employee misconducts himself or is incompetent or negligent in his duties (in which case the Employer shall cooperate with any disciplinary proceedings and shall be advised in writing of the outcome); or

2.36.2.2	where the Employer has reasonable grounds for considering that the presence or conduct of an employee at any location relevant to the performance of the Works is undesirable, require the exclusion of the relevant employee from the relevant location(s)."

Insert new clause 2.37 as follows:

"2.37	Admission to the Sites

2.37.1	Subject to the remainder of this paragraph 2.37.1, the Contractor shall at least twenty (20) Business Days before the date on which the Contractor first carries out any Sensitive Works provide the Employer with a written list of the names and addresses of all employees or other persons who it expects may require admission to the Site in connection with the carrying out of any Sensitive Works, specifying the capacities in which those employees or other persons are concerned with any Sensitive Works and giving such other particulars as the Employer may require. The Contractor shall update this information as and when any such individuals are replaced or complemented by others, not less than twenty (20) Business Days before their inclusion. The decision of the Employer on whether any person is to be refused admission to the Site shall be final and conclusive and the Employer shall not be obliged to give reasons for its decision.

2.37.2	Where the Contractor is unable (acting reasonably) to comply with paragraph 2.37.1 by the time period specified in it then the Contractor shall comply with its obligations under that clause as soon as reasonably practicable and by no later than the end of the day on which the relevant individual first goes on Site. Until such time as the Contractor has complied with its obligations in respect of that individual, they shall at all times be accompanied on Site by a member of the Contractor's staff who has been properly notified to the Employer in accordance with paragraph 2.37.1.

2.37.3	This paragraph 2.37 shall not apply to those individuals who shall be required by the Contractor to attend on the Site to provide emergency reactive services. In the case of such individuals, the Contractor shall ensure that such individuals are accompanied at all times while on Site by a member of the Contractor's staff who has been properly notified to the Employer in accordance with paragraph 2.37.1."

Insert new clause 2.38 as follows:

"2.38	Refusal of Admission

The Employer reserves the right to refuse to admit to the Site any person employed or engaged by the Contractor or any Sub-Contractor, whose admission would, in the opinion of the Employer, present a risk to themselves or any pupil, or to the Employer's property and shall not be obliged to give any reasons for such refusal."

Insert new clause 2.39 as follows:

"2.39	Decision to Refuse Admission

The decision of the Employer as to whether any person is to be refused admission to the Site pursuant to paragraph 2.39 shall be final and conclusive."

Insert new clause 2.40 as follows:

"2.40	Removal from Sites

The Contractor shall comply with and/or procure compliance with any notice issued by the Employer from time to time requiring the removal from the Site of any person employed thereon who in the opinion of the Employer acting reasonably is not acceptable on the grounds of risk to themselves or any pupil, or any Employer related party or property and that such persons shall not be employed again in connection with the Works without the written consent of the Employer."

Insert new clause 2.41 as follows:

"2.41	Minimising Disruption to the Provision of Educational Services

Insofar as the carrying out of the Works affects or may affect the provision of Educational Services at the School, the Contractor shall procure that (subject to the terms of this Contract) the Works are carried out:

2.41.1	so as to minimise any disruption to the provision of Educational Services; and

2.41.2	so as to ensure that no disruption is caused during the carrying out of examinations at the School during any examination period; and

2.41.3	in compliance, to the extent reasonably practicable, with the Programme."

Insert a new clause 2.42 as follows:

"2.42	Not used

Insert a new clause 2.43 as follows:

"2.43	Operations on Site

2.43.1	The Contractor shall provide to the Architect/Contract Administrator if and as the Architect/Contract Administrator requests in writing, details of the Contractor's proposals for the means of access to the Site during the construction period, vehicle parking facilities on Site, loading and unloading areas for materials, site compounds, temporary warning and direction signs on adjacent highways and any other similar information as to the Contractor's working arrangements.  If necessary the Contractor shall amend such details to obtain the approval of the local planning authority or other relevant public authority having jurisdiction with respect to the Works.

2.43.2	The Contractor shall be wholly responsible for the design, adequacy, stability and safety of all temporary works required in and about the construction of the Works, save insofar as it is provided in any Contract Document that the design of any temporary works is to be provided by any member of the Employer's design team, in which case the Contractor shall not be responsible for the production or the adequacy of such design.

2.43.3	In and about the execution of the Works the Contractor shall maintain and not cause any interference to any support enjoyed by any adjoining land or any structures, other than any structures which are to be demolished as part of the Works.

2.43.4	The Contractor shall:

2.43.4.1	keep all enclosures around the Site clear of graffiti, posters and other unauthorised attachments, so far as is practicable;

2.43.4.2	implement measures for the regulation of traffic to and from the Site including wheel-washing procedures and street cleaning and comply with any requirements of the police or highway authorities with regard to local traffic arriving at and departing from the Site;

2.43.4.3	obtain for itself any licences required to oversail any land outside the Site boundaries; and

2.43.4.4	make good or meet the cost of making good all damage caused to roads, footpaths and property adjoining the Site and to any services, arising from the carrying out of the Works."

Insert a new clause 2.44 as follows:

"2.44	As-built data and energy performance

2.44.1	At or before Practical Completion of the Works or any Section, provide to the Employer an energy performance certificate and a recommendation report for the Works or Section, in conformity with regulation 29 of the Building Regulations 2010 and any modification or replacement of the same.

2.44.2	At or before Practical Completion of the Works or any Section, the Contractor shall without charge provide to the Architect/Contract Administrator such draft as-built or final issue drawings, specifications and other details (in three copies) and draft service manuals (in three copies) as are specified in the Contract Documents, containing sufficient information to enable the Works or such Section to be properly maintained and operated.

2.44.3	Within four weeks after Practical Completion of the whole of the Works, the Contractor shall without charge provide to the Architect/Contract Administrator three copies of all such as-built or final issue drawings, specifications and other details and service manuals as are specified in the Contract Documents."

Insert a new clause 2.45 as follows:

"2.45	Duty of confidentiality

The Parties shall treat the details of this Contract and any information made available in relation thereto as private and confidential and neither of them shall publish or disclose the same of any particulars thereof (save in so far as may be necessary for the purposes of the Contract or as expressly required by any statutory or legal obligation) without the previous consent of the other, provided that nothing in this clause shall prevent the publication or disclosure of any such information that has come within the public domain otherwise than by breach of this clause."

Insert a new clause 2.46 as follows:

"2.46	Data Protection

The Contractor shall comply with the DPA and any other applicable data protection legislation and agrees to use all reasonable efforts to assist the Employer in complying with the DPA."

Insert a new clause 2.47 as follows:

"2.47	Audit

For the purposes of the examination and certification of the Employer’s accounts the Contractor agrees to make available for examination such documents as he or it may reasonably require which are owned, held or otherwise within the control of the Contractor should be provided to the Employer at the Employer's request."

Insert a new clause 2.48 as follows:

"2.48	Exploitation of information

The Contractor shall not make use of this Contract or any information issued or provided by or on behalf of the Employer in connection with this Contract otherwise than for the purposes of this Contract, except with the written consent of the Employer."

Insert a new clause 2.49 as follows:

"2.49	Freedom of information

The Contractor acknowledges that the Employer may be subject to the requirements of the FOIA and the Environmental Information Regulations and shall facilitate the Employer's compliance with its information disclosure requirements and the Contractor shall provide the Employer with a copy of all such information, in the form that the Employer requires, as soon as practicable and in any event within ten (10) Business Days (or such other period as the Employer, acting reasonably, may specify) of the Employer request.

Insert a new clause 2.50 as follows:

"2.50	General

2.50.1	In relation to all Personal Data, the Contractor shall at all times comply with the DPA as a data controller if necessary, including maintaining a valid and up to date registration or notification under the DPA covering the data processing to be performed in connection with the Works.

2.50.2	The Contractor and any Sub-Contractor shall only undertake processing of Personal Data reasonably required in connection with the Works and shall not transfer any Personal Data to any country or territory outside the European Economic Area."

Insert a new clause 2.51 as follows:

"2.51	Corrupt gifts and fraud

The Contractor warrants that in entering into this Contract it has not committed any Prohibited Act."

Insert a new clause 2.52 as follows:

"2.52	Termination for corrupt gifts and fraud

2.52.1	If the Contractor or Associated Person or any of its or their agents or shareholders commits any Prohibited Act, the Employer shall be entitled to act in accordance with the provisions of this clause 2.52.

2.52.2	Notwithstanding clauses 2.52.3 to 2.52.6 if a Prohibited Act is committed by the Contractor or by an Associated Person not acting independently of the Contractor or by an employee not acting independently of the Contractor, the Employer may terminate this Contract by giving notice to the Contractor.

2.52.3	If the Prohibited Act is committed by an employee of the Contractor or Associated Person acting independently of the Contractor, the Employer may give notice to the Contractor of termination and the Contractor's employment under this Contract will terminate unless, within 20 Business Days of receipt of such notice, the Contractor terminates the employee's or Associated Person’s employment and demonstrates to the reasonable satisfaction of the Employer that the employee or Associated Person was acting independently of the Contractor and (if necessary) procures the carrying out of such part of the Works by another person.

2.52.4	If the Prohibited Act is committed by a Sub-Contractor of the Contractor or by an employee of that Sub-Contractor not acting independently of that Sub-Contractor, the Employer may give notice to the Contractor of termination and the Contractor's employment under this Contract will terminate, unless within 20 Business Days of receipt of such notice the Contractor terminates the relevant subcontract and demonstrates to the reasonable satisfaction of the Employer that the Sub-Contractor was acting independently of the Contractor and procures the carrying out of such part of the Works by another person.

2.52.5	If the Prohibited Act is committed by an employee of a Sub-Contractor of the Contractor acting independently of that Sub-Contractor, the Employer may give notice to the Contractor of termination and the Contractor's employment under this Contract will terminate, unless within 20 Business Days of receipt of such notice the Sub-Contractor terminates the employee's employment and demonstrates to the reasonable satisfaction of the Employer that the employee was acting independently of the Sub-Contractor and (if necessary) procures the carrying out of such part of the Works by another person.

2.52.6	If the Prohibited Act is committed by any other persons not specified in clauses 2.52.2 to 2.52.5, the Employer may give notice to the Contractor of termination and the Contractor's employment under this Contract will terminate, unless within 20 Business Days of receipt of such notice the Contractor procures the termination of such person's employment and of the appointment of their employer (where not employed by the Contractor or the Sub-Contractors) and (if necessary) procures the carrying out of such part of the Works by another person.

2.52.7	Any notice of termination under this clause 2.52 shall specify:

2.52.7.1	the nature of the Prohibited Act;

2.52.7.2	the identity of the party whom the Employer believes has committed the Prohibited Act; and

2.52.7.3	the date on which this Contract will terminate, in accordance with the applicable provision of this clause.

2.52.8	In this clause 2.52 the expression "not acting independently of" (when used in relation to the Contractor or Sub-Contractors) means and shall be construed as acting with the authority of or knowledge of any one or more of the directors of the Contractor or any of its Sub-Contractors."

Insert a new clause 2.53 as follows:

"2.53	Programme

2.53.1	The Contractor shall produce the Programme to the Employer prior to the Date of Possession (or, if there are Sections, prior to the first of the Dates of Possession) and shall thereafter revise the Programme as appropriate from time to time (and if and whenever there is any material delay to the execution of the Works) so as to minimise or avoid any anticipated delay or disruption to the carrying out of the Works, and shall provide the Employer with the revised Programme.

2.53.2	Each month the Contractor shall report to the Employer in writing comparing the progress of the Works with the Programme current at that time, and promptly advise the Employer of any delay or disruption to the Works, setting out the measures he is taking or proposes to take to minimise or make good such delay or disruption."

Section 3	Control of the Works

3.4	Delete this clause.

3.8 Compliance with instructions

3.8.2 delete “regulations 11, 12 and 18 of.”

3.18 Undertakings to comply

Delete the final sentence of the opening paragraph of clause 3.18 from “Without limitation” to “notifiable” (inclusive). Replace the existing full stop after “CDM Regulations” with a colon.

3.18.1 delete “CDM Co-ordinator” and replace with “Principal Designer”.

3.18.2 In every case it appears in this clause delete “CDM Co-ordinator” and replace with “Principal Designer”.

3.18.2 In every case it appears in this clause delete “CDM Co-ordinator” and replace with “Principal Designer”.

3.18.4 In every case it appears in this clause delete “CDM Co-ordinator” and replace with “Principal Designer”.

3.18.5 Insert new clause: “where the Contractor is not the Principal Designer but is the Principal Contractor and the Principal Designer’s appointment concludes before practical completion of the Works, the Contractor shall review, update and revise the health and safety file in accordance with regulations 12(8) to 12(10) of the CDM Regulations without charge.

3.19 Appointment of successors

Delete “CDM Co-ordinator” and replace with “Principal Designer”.

Section 4	Payment

4.1	Work included in Contract Sum

4.1.2	At the beginning of the clause, delete "Where" and insert "Subject to the provisions of clauses 2.1 and 2.2, where".

4.8	Interim payments - amounts due

4.8.1.2	After "casualties", insert "and in respect of which the Contractor has provided the Architect/Contract Administrator with reasonable proof that the property in such materials or goods is vested in him and that no Sub-Contractor or Supplier (of any tier) has validly retained title to the same".

4.11	Interim payments - final date and amount

4.11.1	Insert “28 days” in lieu of “14 days” in line 1

4.11.6	At the end of the clause insert as follows:

"The Parties agree that this clause 4.11.6 constitutes a substantial remedy for late payment of any sum payable under this Contract in accordance with the provisions of s8(2) of the Late Payment of Commercial Debts (Interest) Act 1998."

Insert new clause 4.11.8 as follows:

"4.11.8	The issue by or on behalf of the Employer of any written notice pursuant to this clause 4.11 or the payment of any amount by the Employer to the Contractor pursuant to this clause 4.11 shall not constitute or imply or be evidence of the Employer's approval or acceptance of any design, work, materials or equipment forming part of the Works or any Section."

4.12	Pay Less Notices and general provisions

4.12.3	In line 3, after "clause 4.7.2", delete the words "shall be fiduciary as trustee for the Contractor (but without obligation to invest) and the Contractor's beneficial interest therein shall be subject only" (in line 4) and insert "shall not be fiduciary as trustee for the Contractor or any Sub-Contractor or Supplier, and shall be subject".

4.15	Contribution, levy and tax fluctuations

Insert a second sentence, as follows:

"Unless any of the Fluctuation Options is stated (in the Contract Particulars) to apply, the Contract Sum and the sums contained in the Contract Sum Analysis shall be deemed to allow for all price fluctuations (whether occurring before or after the Base Date)."

Loss and Expense

4.17	Disturbance of regular progress

Renumber clause 4.17 as clause 4.17.1

In line 1, delete "If" and insert "Subject to clause 4.17.2, if"

Insert new clause 4.17.2 as follows:

"4.17.2	The Contractor:

4.17.2.1	shall advise the Architect/Contract Administrator of all measures that are necessary to avoid or minimise the delay and the consequences of such measures on the Programme and the Contractor shall take all steps to avoid or minimise such delay;

4.17.2.2	shall not be entitled to any addition of any amount to the Contract Sum or to any other financial adjustment under this clause 4.17 to the extent that the same is due to any breach of this Contract by the Contractor or any negligence or default of the Contractor, the Design Consultants or any Sub-Contractor or Supplier for whom the Contractor is responsible under this Contract, or their respective servants or agents; and

4.17.2.3	shall constantly use best endeavours to prevent or minimise any disruption to the regular progress of the Works and each Section as aforesaid and to mitigate any loss and/or expense incurred by him".

4.19	Reservation of Contractor's Rights and Remedies

Delete and replace with:

"Save to the extent that the Contractor is entitled to reimbursement of the same under any other provision of this Contract, the Contractor's rights under this Contract to payment in respect of any loss or expense suffered or sustained by the Contractor because the regular progress of the Works or any Section or any part thereof has been affected by any act or omission of the Employer or anyone to whom the Employer is responsible under this Contract are fully set out in clauses 4.17 and 4.18, and no other rights whatsoever of the Contractor in relation thereto shall be implied as terms of this Contract.  Further, but without prejudice to the foregoing, the Employer shall have no liability whatsoever to the Contractor at common law for damages in respect of any such loss or expense".

Section 5	Variations

5.1	Definition of Variations

5.1.2.3	After "limitations of working hours" insert:

"(except where the Architect/Contract Administrator requires the Contractor during the Rectification Period to remedy any defect, shrinkage or other fault outside the normal working hours of the Contractor)".

5.2	Valuation of Variations and provisional sum work

At the end of this clause insert:

"Provided that there shall be no addition to the Contract Sum in respect of any Variation to the extent that the same is required by reason of any breach of this Contract by the Contractor or any negligence or default of the Contractor, or his servants or agents, the Design Consultants or any Sub-Contractor or Supplier or their respective servants or agents save where a Variation is necessary as a result of the occurrence of a Specified Peril which is covered by the Specified Perils insurance policy taken out pursuant to clause 6 of this Contract."

Section 6	Injury, Damage and Insurance

6.1	Liability of Contractor - personal injury or death

In line 3, after "the Works", insert "(including the performance of any obligation pursuant to clause 2.30)".

6.2	Liability of Contractor - injury or damage to property

In line 3, after "the Works", insert "(including the performance of any obligation pursuant to clause 2.30)".

6.7	Insurance Options

Insert a new second sentence as follows:

"In this Section 6 and in Options A, Option B or Option C all references to 'full reinstatement value' are to be read as references to 'full reinstatement cost. The application of Options A, Option B or Option C (as the case may be) shall not affect the responsibility of the Contractor under this Contract for any loss or damage not insured by any Joint Names Policy described therein".

6.8	Related Definitions

In the definition of Joint Names Policy, after “Contractor” insert:

“and any one or more third persons specified in writing by the Employer to the Contractor, being persons having or acquiring an interest in or an organisation providing finance in connection with  the site or the Works”.

Section 7	Assignment, Third Party Rights and Collateral Warranties

Assignment

7.1	Delete the whole of Section 7 and substitute with:

“7.1	The Contractor may not assign or charge the benefit of this Contract or any right arising under it without the written consent of the Employer.

7.2	The Employer’s rights under this Contract may be assigned without the consent of the Contractor:

1	as security to any organisation providing finance in connection with the Works (and such rights may be re-assigned on redemption);

2	by absolute assignment to any Group Company;

3	by absolute assignment on two other occasions only.

7.3	The Contractor shall not be entitled to contend that any person to whom this Contract is assigned in accordance with clause 7.2 is precluded form recovering under this Contract any loss incurred by such assignee resulting from any breach of this Contract (whenever happening), by reason that such person is an assignee and not a named promisee under this Contract”.

Section 8	Termination

Termination by Employer

8.4	Default by Contractor

Insert new clause 8.4.1.6:

"8.4.1.6	fails to provide any of the collateral warranties, and/or parent company guarantee, as required by Articles 10 to 13 of this Contract."

Insolvency of Contractor

8.5.1	Delete and substitute:

- "If the Contractor is or becomes Insolvent, the Contractor shall so notify the Employer forthwith and either Party may at any time by notice to the other, terminate the Contractor's employment under this Contract."

8.5.2	In line 1, delete "the Employer" and substitute "either Party".

8.5.3.2	In line 2, delete "suspended" and substitute "terminated".

8.6	Corruption

In line 3, after "acting or his behalf", insert "or an Associated Person".

8.7	Consequences of termination under clauses 8.4 to 8.6

8.7.2.1 	In line 1, delete "when required by the Architect/Contract Administrator to do so (but not before),".

8.7.2.3	In line 1, delete "if so required by the Employer (or by the Architect/Contract Administrator on his behalf) within 14 days of the date of termination,".

8.7.4	Insert at the end of clause 8.7.4:

- "Provided that if the Employer elects not to procure the completion of the Works, then the amount to be allowed under clause 8.7.4.3 shall be the portion of the Contract Sum earned by the Contractor.

Section 9	Settlement of Disputes

9.2	Adjudication

Insert new clauses 9.2.3 and 9.2.4 as follows:

9.2.3	"the Adjudicator shall have power to determine more than one dispute under this Contract at the same time; and

9.2.4	at the same time as he gives any decision, the Adjudicator shall give reasons for the decision in writing."

Arbitration

Delete clauses 9.3 to 9.8 inclusive.

Schedules

Schedule 3	Forms of Bonds

Delete the heading and replace with:

Schedule 3	Forms of Guarantee and Collateral Warranties

Insert

Schedule 6	Site Plan

Schedule 7	Deed of Novation

Schedule 3	Forms of Guarantee and Collateral Warranties

Part 1 – Contractor’s Collateral Warranty

DATED							20[   ]

[CONTRACTOR]

and

[BENEFICIARY]

and

[EMPLOYER]

Draft [   ]: [Date]

CONTRACTOR’S [PURCHASER/FUNDER/TENANT] COLLATERAL WARRANTY

[description]

CONTENTS

.

1.	Building Obligations	45

2.	Prohibited Materials	46

3.	Professional Indemnity Insurance	46

4.	[Step In Rights]	47

5.	[Beneficiary’s Rights In Relation To The Building Contract]	48

6.	[Contractor’s Position]	48

7.	Assignment	48

8.	Copyright	48

9.	Extraneous Rights	49

10.	Contracts (Rights Of Third Parties) Act 1999	49

11.	Expiry Of Warranty	49

12.	Service Of Notice	50

13.	Governing Law And Interpretation	50

THIS DEED is made	20[     ]

BETWEEN:

(1)	[		] (CRN [		]) whose registered office is at [		] (‘Contractor’); and

(2)	[		] (CRN [		]) whose registered office is at [		] (‘Beneficiary’)[; and]

[(3)	[		] (CRN [		]) whose registered office is at [		] (‘Employer’)].

WHEREAS:

(A)	By an agreement in writing made [date] (‘Building Contract’) the Contractor agreed with [the Employer/[			] ([			]) whose registered office is at [			](‘Employer’)] to design, construct and complete [give details] upon land at [address] (‘the Development’, which expression means the said land and the works constructed or to be constructed on it or either of them as the case shall require).

(B)	[The Beneficiary is a funder of the Development.

or

The Beneficiary is the purchaser of [the premises known as [give details] (‘Premises’) forming part of] the Development.

or

The Beneficiary has taken or agreed to take a lease of [the premises known as [give details] (‘Premises’) forming part of] the Development.]

NOW THIS DEED WITNESSES in consideration of the sum of £1.00 paid by the Beneficiary, receipt of which the Contractor acknowledges, as follows:

- Building obligations

  - The Contractor undertakes with and warrants to the Beneficiary that the Contractor has carried out and completed and will carry out and complete the Contract Works with all due diligence, in accordance with and subject to the terms of the Building Contract, and has observed and performed and will observe and perform all of its duties and obligations expressed in or arising out of the Building Contract and (without qualification to or derogation from the foregoing) has exercised and will exercise all reasonable skill and care and diligence in and about the execution of the Contract Works to be expected from a contractor experienced in constructing developments of a similar nature, value, complexity and timescale to the Development.

  - The Contractor shall have no liability under Clause 1.1 of this Deed that is greater or of longer duration that it would have had and shall be entitled in any action or proceedings by the Beneficiary to raise equivalent rights in defence of liability (except for set-off or counterclaim) if in lieu of this Deed the Beneficiary had been a party to the Building Contract as joint employer.

  - Without derogation from Clause 1.1 and to the extent that under the Building Contract the Contractor takes responsibility for the design of the Contract Works or the selection of goods, materials, plant and equipment for incorporation in the Contract Works, the Contractor warrants that the same have been and will be designed and selected with all the reasonable skill and care set out in Clause 1.1.

- Prohibited materials

The Contractor warrants that it will not specify or use or approve the specification for use by others of any products or materials not in conformity with (save where they exceed) relevant British or European standards or codes of practice or which are generally known in the construction industry at the time of use to be deleterious to health and safety or to the durability of buildings and/or other structures and/or finishes and/or plant and machinery in the particular circumstances in which they are specified to be used.

- Professional indemnity insurance

  - The Contractor shall maintain professional indemnity insurance covering (inter alia) all its design liability hereunder upon customary and usual terms and conditions prevailing for the time being in the insurance market, and with reputable insurers lawfully carrying on such insurance business in the United Kingdom, in an amount of not less than £[                    ] ([                    ] million pounds) for any one occurrence or series of occurrences arising out of any one event for a period beginning now and ending 12 years after the date of Practical Completion of the Development, provided always that such insurance is available at commercially reasonable rates.  The said terms and conditions shall not include any term or condition to the effect that the Contractor must discharge any liability before being entitled to recover from the insurers, or any other term or condition which might adversely affect the rights of any person to recover from the insurers pursuant to the Third Parties (Rights Against Insurers) Act 1930, or any amendment or re-enactment thereof.  The Contractor shall not, without the prior approval in writing of the Beneficiary, settle or compromise with the insurers any claim which the Contractor may have against the insurers and which relates to a claim by the Beneficiary against the Contractor, or by any act or omission lose or prejudice the Contractor's right to make or proceed with such a claim against the insurers.

  - Any increased or additional premium required by insurers by reason of the Contractor's own claims record or other acts, omissions, matters or things particular to the Contractor shall be deemed to be within commercially reasonable rates.

  - The Contractor shall immediately inform the Beneficiary if such insurance ceases to be available at commercially reasonable rates in order that the Contractor and the Beneficiary can discuss means of best protecting the respective positions of the Beneficiary and the Contractor in respect of the Development in the absence of such insurance.

  - The Contractor shall fully co-operate with any measures reasonably required by the Beneficiary, including (without limitation) completing any proposals for insurance and associated documents, maintaining such insurance at rates above commercially reasonable rates if the Beneficiary undertakes in writing to reimburse the Contractor in respect of the net cost of such insurance to the Contractor above commercially reasonable rates or, if the Beneficiary effects such insurance at rates at or above commercially reasonable rates, reimbursing the Beneficiary in respect of what the net cost of such insurance to the Beneficiary would have been at commercially reasonable rates.

  - As and when reasonably requested to do so by the Beneficiary the Contractor shall produce for inspection reasonable documentary evidence (including if required by the Beneficiary, the originals of the relevant insurance documents) that its professional indemnity insurance is being maintained.

  - The above obligations in respect of professional indemnity insurance shall continue notwithstanding termination of this Deed for any reason whatsoever, including (without limitation) breach by the Beneficiary.

- [step in rights]

  - The Contractor covenants with the Beneficiary that it will not exercise nor seek to exercise any right of termination of its employment under the Building Contract or to discontinue the Contract Works for any reason whatsoever (including any breach on the part of the Employer) without giving not less than 21 days written notice of its intention to do so to the Beneficiary and specifying the grounds for the proposed termination or discontinuance.

  - Any period stipulated in the Building Contract for the exercise of a right of termination by the Contractor of its employment under the Building Contract or to discontinue the Contract Works shall, nevertheless, be extended as may be necessary to take account of the period of notice required under Clause 4.1.

  - The right of the Contractor to terminate its employment under the Building Contract or to discontinue the Contract Works shall cease within the period of 21 days referred to in Clause 4.1 if the Beneficiary shall give notice to the Contractor:-

    - requiring the Contractor to continue its obligations under the Building Contract with the Beneficiary or its nominee; and

    - acknowledging that the Beneficiary or its nominee will assume all the obligations of the Employer under the Building Contract; and

    - undertaking that the Beneficiary or its nominee will discharge all payments which may subsequently become due to the Contractor under the terms of the Building Contract and will pay to the Contractor any sums which have been due and payable to him under the Building Contract but which remain unpaid.

  - Upon service by the Beneficiary or its nominee of a notice complying with the requirements of Clause 4.3 the Building Contract will continue in full force and effect as if the same had been entered into between the Contractor and the Beneficiary to the exclusion of the Employer.

  - Compliance by the Contractor with the provisions of this Clause 4 will not be treated as a waiver of any breach on the part of the Employer giving rise to the right of termination nor otherwise prevent the Contractor from exercising its rights after the expiration of the notice issued pursuant to Clause 4.1 unless the rights of termination have ceased under the provisions of Clause 4.3.

  - If the employment of the Contractor under the Building Contract is terminated before service of any notice under clause 4.3, then if required to do so by notice served by the Beneficiary not later than 12 weeks after the date of such termination, the Contractor shall enter into a new building contract with the Beneficiary or its Appointee on the same terms as the Building Contract but with such revisions as the Beneficiary shall reasonably require to reflect altered circumstances. Forthwith upon the execution of such new building contract, the Beneficiary shall pay to the Contractor an amount equal to the sum which, immediately before termination of the Contractor’s employment, was owing to the Contractor by the Employer under the Building Contract for work done and materials delivered and which remains unpaid.

  - This Clause 4 shall cease to have effect upon the prior exercise by any third person of any similar rights of substitution contained in any other agreement concerning the Development and entered into between the Contractor and such person.]

- [beneficiary’s rights in relation to the building contract]

  - Notwithstanding that as between the Employer and the Contractor the Contractor's right of termination of its employment under the Building Contract may not have arisen the provisions of Clause 4.4 shall also apply if the Beneficiary gives notice to the Employer and to the Contractor to the effect that the Beneficiary wishes the provisions of Clause 4.4 to apply and the Beneficiary or its nominee complies with the requirements of Clause 4.3.

  - The Contractor shall not be concerned, or required to enquire whether, and shall be bound to assume that as between the Employer and the Beneficiary the circumstances have arisen permitting the Beneficiary to give notice under Clause 5.1.

  - This Clause 5 shall cease to have effect upon the prior exercise by any third person of any similar rights of substitution contained in any other agreement concerning the Development and entered into between the Contractor and such person.]

- [contractor’s position]

By acting in accordance with Clauses 4 and 5 the Contractor shall not incur any liability to the Employer.]

- Assignment

  - The Beneficiary may assign all of its rights under this Deed:

    - by way of security or by way of re-assignment on redemption; and

    - by absolute assignment to any Group Company of the Beneficiary; and

    - by absolute assignment on two other occasions only.

  - In this Deed references to the Beneficiary include where the context admits its permitted assignees.

  - The Contractor shall not be entitled to contend that any person to whom this Deed is assigned in accordance with clause 7.1 is precluded from recovering under this Deed any loss incurred by such assignee resulting from any breach of this Deed, (whenever happening) by reason that such person is an assignee and not a named promisee under this Deed.

- Copyright

  - The Contractor as beneficial owner hereby grants to the Beneficiary without further charge and notwithstanding the completion or abandonment of the Contract Works or determination or alleged determination of the Building Contract an irrevocable, non-exclusive, royalty-free licence to use and reproduce any of the drawings, details, plans, specifications, CAD materials, calculations, correspondence, meeting minutes and other information which have been or are prepared by or on behalf of the Contractor relating to the Contract Works and the designs contained in them (‘Documents’) for the construction of the Contract Works and the advertisement, sale, letting, maintenance, repair, reinstatement, reconstruction and extension of it, and to grant sub-licences in the terms of this licence but copyright in the Documents shall remain vested in the Contractor. The Contractor will not be liable for any use of the Documents by the Beneficiary or its nominees for any purposes other than those for which the same are or were prepared. The Beneficiary shall on written request and upon paying a reasonable copying charge, be entitled to be supplied by the Contractor with copies of the Documents.

  - The Contractor warrants to the Beneficiary that the use of the Documents for the purposes of the Development will not infringe the rights of any third person.

  - All royalties or other sums payable in respect of the supply and use of any patented articles, processes or inventions required in connection with the Building Contract shall be paid by the Contractor and the Contractor shall indemnify the Beneficiary from and against all claims, proceedings, damages, costs and expenses suffered or incurred by the Beneficiary by reason of the Contractor infringing or being held to infringe any intellectual property rights in the course of or in connection with the Building Contract.

  - The Contractor hereby waives any right to be identified as author of the Documents in accordance with section 77, Copyright Designs and Patents Act 1988 (‘the Copyright Act’) and any right not to have the Documents subjected to derogatory treatment in accordance with section 80 of the Copyright Act as against the Beneficiary or any licensee or assignee of the Beneficiary.

- Extraneous rights

  - This Deed shall not negate nor diminish any duty or liability otherwise owed by the Contractor to the Beneficiary.

  - No approval or inspection of the Contract Works or of any designs or specifications nor any testing of any work or materials by or on behalf of the Beneficiary and no omission to inspect or test shall negate nor diminish any duty or liability of the Contractor arising under this Deed.

  - This Deed may be executed in any number of counterparts all of which when taken together shall constitute one and the same instrument.

- Contracts (Rights of Third Parties) Act 1999

This Deed is not intended to confer any benefit on any third party pursuant to the Contracts (Rights of Third Parties) Act 1999 except that a person who is the successor to or the permitted assignee of the rights of the Beneficiary is deemed to be a party to this Deed.

- Expiry of warranty

No proceedings shall be commenced against the Contractor under this Deed more than 12 years after the Practical Completion of the Contract Works under the Building Contract (or, if earlier, more than 12 years after the employment of the Contractor under the Building Contract is terminated).

- Service of notice

Any notice to be served under this Deed must be in writing and must be served by hand or by registered post or recorded delivery, and in the case of a corporation must be served at its registered office for the time being. In any other case notice may be served at any address for the time being of the person to be served. Service shall take effect, if given by hand, on the date of delivery. If given by post, it shall take effect two days after posting, excluding Saturdays, Sundays and statutory holidays.

- Governing law and interpretation

  - The law of this Deed is English law and the English courts shall have jurisdiction with regard to all matters arising under it.

  - The definitions given in the recitals apply to this Deed.

  - In this Deed:

    - [‘Appointee’ means a person, partnership, company or other legal entity nominated by the Beneficiary to exercise the step-in rights contained in Clauses 4 and 5;]

    - ‘Contract Works’ means the works to be performed by the Contractor under the Building Contract;

    - ‘Group Company’ means any subsidiary company or holding company of the Beneficiary, or another subsidiary or holding company of such company, as ‘subsidiary’ and ‘holding company’ are defined in the Companies Act 2006 (as amended);

    - ‘Practical Completion’ means the date of practical completion of the Development as defined in accordance with the Building Contract;

    - ‘person’ includes a firm and any entity having legal capacity;

    - any term importing gender shall include any gender;

    - any term importing the singular includes the plural and vice versa;

    - any reference to any clause or schedule is a reference to such clause or schedule of or to this Deed.

  - Clause headings do not form part of nor affect the interpretation of this Deed.

EXECUTED AND DELIVERED as a deed:

| EXECUTED (but not delivered until the date hereof) AS A DEED by [ ] acting by:- | ) ) ) ) ) Director Director/Secretary |
| --- | --- |
| EXECUTED (but not delivered until the date hereof) AS A DEED by [ ] acting by:- | ) ) ) ) ) Director Director/Secretary |

| [ EXECUTED (but not delivered until the date hereof) AS A DEED by [ ] acting by:- | ) ) ) ) ) Director Director/Secretary] |
| --- | --- |

Part 2 – Design Consultant Collateral Warranty

[Contractor appointed and novated Consultants]

DATED						20[     ]

[CONSULTANT]

and

[BENEFICIARY]

and

[CONTRACTOR]

Draft [   ]: [Date]

[			] [PURCHASER/FUNDER/TENANT]

COLLATERAL WARRANTY

[description]

CONTENTS

1.	Duty Of Care	54

2.	Prohibited Materials	55

3.	Professional Indemnity Insurance	55

4.	[Step In Rights]	56

5.	[Beneficiary’s Rights In Relation To The Appointment]	57

6.	[Consultant's Position]	57

7.	Assignment	57

8.	Copyright	57

9.	Extraneous Rights	58

10.	Contracts (Rights Of Third Parties) Act 1999	58

11.	Expiry Of Warranty	58

12.	Service Of Notice	58

13.	Governing Law And Interpretation	59

THIS DEED is made 	20[     ]

BETWEEN:

(1)	[			] (CRN [			]) whose registered office is at [address] (‘Consultant’); and

(2)	[			] (CRN [			]) whose registered office is at [		] (‘Beneficiary’) [; and]

[(3)	[			] (CRN [			]) whose registered office is at [		] (‘Contractor’)]

WHEREAS:

(A)	The Consultant is [a partnership between the individuals named in schedule 1] in practice as consulting [architects or civil and structural engineers or mechanical and electrical engineers or [specify as appropriate]].

(B)	By Agreement in writing dated [date] (‘Building Contract’) [		] (CRN [		]) whose registered office is at [				] (“the Employer”) employed the Contractor to design and construct [give details] upon land at [address] (‘Development’ which expression means the said land and the works constructed or to be constructed on it or either of them as the case shall require).

(C)	By Agreement in writing between the [Employer/Contractor] and the Consultant dated [date] (‘Appointment’), the Consultant agreed to provide consulting [architectural or civil and structural engineering or mechanical and electrical engineering or [specify as appropriate]] services (‘the Services’) in connection with the Development.

(D)	[The Beneficiary is a funder of the Development.

or

The Beneficiary is the purchaser of [the premises known as [give details] (‘Premises’) forming part of] the Development.

or

The Beneficiary has taken or agreed to take a lease of [the premises known as [give details] (‘Premises’) forming part of] the Development.]

[(E)	The Appointment was novated by the Employer to the Contractor by a deed of novation dated [			].]

NOW THIS DEED WITNESSES in consideration of the sum of £1.00 paid by the Beneficiary, receipt of which the Consultant acknowledges, as follows:

- Duty of care

  - The Consultant undertakes with and warrants to the Beneficiary that he has carried out and will carry out the Services and obligations on his part to be performed under and in connection with the Appointment and that in performing the same he has used and shall use all the reasonable skill, care and diligence to be expected of a properly qualified and competent member of its profession experienced in carrying out work such as its duties under the Appointment in relation to developments of a similar nature, value, complexity and timescale to the Development.

  - The Consultant shall have no liability under Clause 1.1 of this Deed that is greater or of longer duration than it would have had and shall be entitled in any action or proceedings by the Beneficiary to raise equivalent rights in defence of liability (except for set-off or counterclaim) if in lieu of this Deed the Beneficiary had been a party to the Appointment as joint employer.

- Prohibited materials

The Consultant warrants that it will not specify or approve the specification for use by others of any products or materials not in conformity with (save where they exceed) relevant British or European standards or codes of practice or which are generally know in the construction industry at the time of use to be deleterious to health and safety or to the durability of buildings and/or other structures and/or finishes and/or plant and machinery in the particular circumstances in which they are specified.

- Professional indemnity insurance

  - The Consultant shall maintain professional indemnity insurance covering (inter alia) all liability hereunder upon customary and usual terms and conditions prevailing for the time being in the insurance market, and with reputable insurers lawfully carrying on such insurance business in the United Kingdom, in an amount of not less than £[                    ] ([                    ] million pounds) for any one occurrence or series of occurrences arising out of any one event for a period beginning now and ending 12 years after the date of Practical Completion of the Development, provided always that such insurance is available at commercially reasonable rates.  The said terms and conditions shall not include any term or condition to the effect that the Consultant must discharge any liability before being entitled to recover from the insurers, or any other term or condition which might adversely affect the rights of any person to recover from the insurers pursuant to the Third Parties (Rights Against Insurers) Act 1930, or any amendment or re-enactment thereof.  The Consultant shall not, without the prior approval in writing of the Beneficiary, settle or compromise with the insurers any claim which the Consultant may have against the insurers and which relates to a claim by the Beneficiary against the Consultant, or by any act or omission lose or prejudice the Consultant's right to make or proceed with such a claim against the insurers.

  - Any increased or additional premium required by insurers by reason of the Consultant's own claims record or other acts, omissions, matters or things particular to the Consultant shall be deemed to be within commercially reasonable rates.

  - The Consultant shall immediately inform the Beneficiary if such insurance ceases to be available at commercially reasonable rates in order that the Consultant and the Beneficiary can discuss means of best protecting the respective positions of the Beneficiary and the Consultant in respect of the Development in the absence of such insurance.

  - The Consultant shall fully co-operate with any measures reasonably required by the Beneficiary, including (without limitation) completing any proposals for insurance and associated documents, maintaining such insurance at rates above commercially reasonable rates if the Beneficiary undertakes in writing to reimburse the Consultant in respect of the net cost of such insurance to the Consultant above commercially reasonable rates or, if the Beneficiary effects such insurance at rates at or above commercially reasonable rates, reimbursing the Beneficiary in respect of what the net cost of such insurance to the Beneficiary would have been at commercially reasonable rates.

  - As and when reasonably requested to do so by the Beneficiary the Consultant shall produce for inspection documentary evidence (including, if required by the Beneficiary, the original of the relevant insurance documents) that his professional indemnity insurance is being maintained.

  - The above obligations in respect of professional indemnity insurance shall continue notwithstanding termination of this Deed for any reason whatsoever, including (without limitation) breach by the Beneficiary.

- [step in rights

  - The Consultant covenants with the Beneficiary that it will not exercise nor seek to exercise any right of termination of the Appointment or to discontinue the performance of any of its duties or obligations thereunder for any reason whatsoever (including any breach on the part of the Contractor) without giving not less than 21 days written notice of his intention to do so to the Beneficiary and specifying the grounds for the proposed termination or discontinuance.

  - Any period stipulated in the Appointment for the exercise by the Consultant of a right of termination or to discontinue the performance of any of its duties or obligations shall, nevertheless be extended as may be necessary, to take account of the period of notice required under Clause 4.1

  - The right of the Consultant to terminate the Appointment or to discontinue the performance of any of its duties or obligations thereunder shall cease within the period of 21 days referred to in Clause 4.1 if the Beneficiary shall give notice to the Consultant:-

    - requiring the Consultant to continue its duties and obligations under the Appointment with the Beneficiary or its nominee; and

    - acknowledging that the Beneficiary or its nominee will assume all the obligations of the Contractor under the Appointment; and

    - undertaking that the Beneficiary or its nominee will discharge all payments which may subsequently become due to the Consultant under the terms of the Appointment and will pay to the Consultant any sums which have been due and payable to it thereunder but which remain unpaid.

  - Upon compliance by the Beneficiary or its nominee with the requirements of Clause 4.3 the Appointment will continue in full force and effect as if the Appointment had been entered into between the Consultant and the Beneficiary or its nominee to the exclusion of the Contractor.

  - Compliance by the Consultant with the provisions of this Clause 4 will not be treated as a waiver of any breach on the part of the Contractor giving rise to the right of termination nor otherwise prevent the Consultant from exercising his rights after the expiration of the notice issued pursuant to Clause 4.1 unless the rights of termination have ceased under the provisions of Clause 4.3.

  - If the employment of the Consultant under the Appointment is terminated before service of any notice under clause 4.3, then if required to do so by notice served by the Beneficiary not later than 12 weeks after the date of such termination, the Consultant shall enter into a new agreement with the Beneficiary or its Appointee on the same terms as the Appointment but with such revisions as the Beneficiary shall reasonably require to reflect altered circumstances. Forthwith upon the execution of such new agreement, the Beneficiary shall pay to the Consultant an amount equal to the fees and disbursements (excluding cancellation fees) then owing to the Consultant under the Appointment.

  - This Clause 4 shall cease to have effect upon the prior exercise by any third person of any similar rights of substitution contained in any other agreement concerning the Development and entered into between the Consultant and such person.]

- [Beneficiary’s Rights in Relation to the Appointment

  - Notwithstanding that as between the Contractor and the Consultant the Consultant's right of termination of the Appointment may not have arisen the provisions of Clause 4.4 shall also apply if the Beneficiary gives notice to the Consultant and to the Contractor to the effect that the Beneficiary wishes the provisions of Clause 4.4 to apply and the Beneficiary or its nominee complies with the requirements of Clause 4.3.

  - The Consultant shall not be concerned, or required to enquire whether, and shall be bound to assume that as between the Contractor and the Beneficiary the circumstances have occurred permitting the Beneficiary to give such notice under Clause 5.

  - This Clause 5 shall cease to have effect upon the prior exercise by any third person of any similar rights of substitution contained in any other agreement concerning the Development and entered into between the Consultant and such person.]

- [Consultant's Position

By acting in accordance with Clauses 4 and 5 the Consultant shall not incur any liability to the Contractor.]

- Assignment

  - The Beneficiary may assign all of its rights under this Deed:

    - by way of security or by way of re-assignment on redemption; and

    - by absolute assignment to any Group Company of the Beneficiary; and

    - by absolute assignment on two other occasions only.

  - In this Deed references to the Beneficiary include where the context admits its permitted assignees.

  - The Consultant shall not be entitled to contend that any person to whom this Deed is assigned in accordance with clause 7.1 is precluded from recovering under this Deed any loss incurred by such assignee resulting from any breach of this Deed (whenever happening), by reason that such person is an assignee and not a named promisee under this Deed.

- Copyright

  - The copyright in all designs, drawings, models, plans, specifications, design details, photographs, brochures, reports, notes of meetings CAD Materials and any other materials provided by the Consultant in connection with the Development (whether in existence or to be made and hereinafter referred to as “Designs”) and all amendments and additions to them and any works, designs or inventions of the Consultant incorporated or referred to in them shall remain vested in the Consultant but the Consultant hereby grants to the Beneficiary an irrevocable royalty-free, non-exclusive licence to use and reproduce the same for all purposes relating to the Development including (without limitation) the construction, completion, reconstruction, modification, extension, repair, reinstatement, refurbishment, redevelopment, maintenance, use, letting, promotion and advertisement of the Development such licence carrying the right to grant sub-licences and to be transferable without the prior consent of the Consultant provided always that the Consultant shall have no liability for use by the Beneficiary or its nominees of the Designs for any purpose other than that for which they were originally prepared.

  - The Consultant agrees on request at any time to give the Beneficiary or any persons authorised by the Beneficiary access to material referred to in Clause 8.1 and to provide copies of it at the Client’s expense.

  - All royalties or other sums payable in respect of the supply and use of any patented articles, processes or inventions required in connection with the performance of the Services shall be paid by the Consultant and the Consultant shall indemnify the Beneficiary from and against all claims, proceedings, damages, costs and expenses suffered or incurred by the Beneficiary by reason of the Consultant infringing or being held to infringe any intellectual property rights in the performance of the Services.

  - The Consultant hereby waives any right to be identified as author of the Documents in accordance with section 77, Copyright Designs and Patents Act 1988 (‘the Copyright Act’) and any right not to have the Documents subjected to derogatory treatment in accordance with section 80 of the Copyright Act as against the Beneficiary or any licensee or assignee of the Beneficiary.

- Extraneous rights

  - This Deed shall not negate nor diminish any duty or liability otherwise owed by the Consultant to the Beneficiary or to the Contractor.

  - No approval or inspection of the Development or of any designs or specifications nor any testing of any work or materials by or on behalf of the Beneficiary and no omission to inspect or test shall negate nor diminish any duty or liability of the Consultant arising under this Deed.

  - This Deed may be executed in any number of counterparts all of which when taken together shall constitute one and the same instrument.

- Contracts (Rights of Third Parties) Act 1999

This Deed is not intended to confer any benefit on any third party pursuant to the Contracts (Rights of Third Parties) Act 1999 except that a person who is the successor to or the permitted assignee of the rights of the Beneficiary is deemed to be a party to this Deed.

- Expiry of warranty

No proceedings shall be commenced against the Consultant under this Deed more than 12 years after the Practical Completion of the Development under the Building Contract (or, if earlier, more than 12 years after the employment of the Consultant under the Appointment is terminated).

- Service of notice

Any notice to be served under this Deed must be in writing and must be served by hand or by registered post or recorded delivery, and in the case of a corporation must be served at its registered office for the time being. In any other case notice may be served at any address for the time being of the person to be served. Service shall take effect, if given by hand, on the date of delivery. If given by post, it shall take effect two days after posting, excluding Saturdays, Sundays and statutory holidays.

- Governing law and interpretation

  - The law of this deed is English law and the English courts shall have jurisdiction with regard to all matters arising under it.

The definitions given in the recitals apply to this Deed.

In this Deed:

    - ‘Appointee’ means a person, partnership, company or other legal entity nominated by the Beneficiary to exercise the step-in rights contained in Clause 4;

    - ‘Group Company’ means any subsidiary company or holding company of the Beneficiary, or another subsidiary or holding company of such company, as ‘subsidiary’ and ‘holding company’ are defined in the Companies Act 2006 (as amended);

    - ‘Practical Completion’ means the date of practical completion of the Development in accordance with the Building Contract;

    - ‘person’ includes a firm and any entity having legal capacity;

    - any term importing gender shall include any gender;

    - any term importing the singular includes the plural and vice versa; and

    - any reference to any clause or schedule or appendix is a reference to such clause or schedule or appendix of or to this Deed.

  - For the purposes of clause 1, references to the Appointment include any previous appointment (whether or not in writing) of the Consultant by the Beneficiary to provide in connection with the Development services of the kind mentioned in recital C to this Deed.

  - Clause headings do not form part of nor affect the interpretation of this Deed.

EXECUTED AND DELIVERED as a deed:

| EXECUTED (but not delivered until the date hereof) AS A DEED by [ ] acting by:- | ) ) ) ) ) Director Director/Secretary |
| --- | --- |
| EXECUTED (but not delivered until the date hereof) AS A DEED by [ ] acting by:- | ) ) ) ) ) Director Director/Secretary |
| EXECUTED (but not delivered until the date hereof) AS A DEED by [ ] acting by:- | ) ) ) ) ) Director Director/Secretary |

SCHEDULE 1

Partners of the Consultant

(Recital A)

[Full names of all the partners of the consultant]

Part 3 – Sub-Contractor Collateral Warranty to Employer

DATED				20[     ]

[SUB-CONTRACTOR]

and

[BENEFICIARY]

and

[CONTRACTOR]

Draft [       ]: [Date]

SUB-CONTRACTOR’S EMPLOYER COLLATERAL WARRANTY

[description]

CONTENTS

1.	Duty Of Care	64

2.	Prohibited Materials	64

3.	Indemnity Insurance	65

4.	Obligations Prior To Termination Of The Sub-Contract By The Sub-Contractor	65

5.	Beneficiary’s Rights In Relation To The Sub-Contract	66

6.	Sub-Contractor's Position	67

7.	Assignment	67

8.	Copyright	67

9.	Extraneous Rights	68

10.	Contracts (Rights Of Third Parties) Act 1999	68

11.	Expiry Of Warranty	68

12.	Service Of Notice	68

13.	Governing Law And Interpretation	69

THIS DEED is made 	 20[   ]

BETWEEN:

(1)	[			] (CRN [		]) whose registered office is at [		] (‘Sub-Contractor’);

(2)	[			] (CRN [		]) whose registered office is at [		]  (‘Beneficiary’); and

(3)	[			] (CRN [		]) whose registered office is at [		] (‘Contractor’).

WHEREAS:

(A)	By an agreement in writing dated [date] (‘Building Contract’) between the Beneficiary and Contractor the Contractor agreed to design and construct [give details] upon land at [address] (‘the Development’ which expression means the said land and the works constructed or to be constructed on it or either of them as the case shall require).

(B)	By agreement in writing dated [date] (‘Sub-Contract’) between the Contractor and the Sub-Contractor the Contractor appointed the Sub-Contractor to [complete the] design [of] and to supply [and erect or install] [give details] (‘Sub-Contract Works’) for or into the Development.

NOW THIS DEED WITNESSES in consideration of the sum of £1.00 paid by the Beneficiary, receipt of which the Sub-Contractor acknowledges:

- Duty of care

  - The Sub-Contractor undertakes with and warrants to the Beneficiary that the Sub-Contractor has carried out and will carry out and complete the Sub-Contract Works in accordance with and subject to the terms of the Sub-Contract and has observed and performed and will observe and perform all of its duties and obligations expressed in or arising out of the Sub-Contract and (without qualification to or derogation from the foregoing) has exercised and will exercise all reasonable skill and care and diligence in and about the execution of the Sub-Contract Works to be expected from a sub-contractor experienced in constructing works of a similar nature, value, complexity and timescale to the Development.

  - The Sub-Contractor shall have no liability under Clause 1.1 of this Deed that is greater or of longer duration than it would have had, and shall be entitled in any action or proceedings by the Beneficiary to raise equivalent rights in defence of liability (except for set off or counterclaim) as it would have against the Contractor under the Sub-Contract, and shall have no liability under this Deed that is of greater or of longer duration than it would have had if the Beneficiary had been a party to the Sub-Contract as joint employer.

  - Without derogation from Clause 1.1 and to the extent that under the Sub-Contract the Sub-Contractor takes responsibility for the design of the Sub-Contract Works or the selection of goods, materials, plant and equipment for incorporation in the Sub-Contract Works, the Sub-Contractor warrants that the same have been and will be designed and selected with all reasonable skill and care set out in Clause 1.1.

- Prohibited materials

- The Sub-Contractor warrants that it will not specify or use or approve the specification for use by others of any products or materials not in conformity with (save where they exceed) relevant British or European standards or codes of practice or which are generally known in the construction industry at the time of use to be deleterious to health and safety or to the durability of buildings and/or other structures and/or finishes and/or plant and machinery in the particular circumstances in which they are specified to be used.

- Indemnity Insurance

  - The Sub-Contractor shall maintain professional indemnity insurance covering (inter alia) all its design liabilities hereunder upon customary and usual terms and conditions prevailing for the time being in the insurance market, and with reputable insurers lawfully carrying on such insurance business in the United Kingdom, in an amount of not less than £[                    ] ([                    ] million pounds) for any one occurrence or series of occurrences arising out of any one event for a period beginning now and ending 12 years after the date of Practical Completion of the Development, provided always that such insurance is available at commercially reasonable rates.  The said terms and conditions shall not include any term or condition to the effect that the Sub-Contractor must discharge any liability before being entitled to recover from the insurers, or any other term or condition which might adversely affect the rights of any person to recover from the insurers pursuant to the Third Parties (Rights Against Insurers) Act 1930, or any amendment or re-enactment thereof.  The Sub-Contractor shall not, without the prior approval in writing of the Beneficiary, settle or compromise with the insurers any claim which the Sub-Contractor may have against the insurers and which relates to a claim by the Beneficiary against the Sub-Contractor, or by any act or omission lose or prejudice the Sub-Contractor's right to make or proceed with such a claim against the insurers.

  - Any increased or additional premium required by insurers by reason of the Sub-Contractor's own claims record or other acts, omissions, matters or things particular to the Sub-Contractor shall be deemed to be within commercially reasonable rates.

  - The Sub-Contractor shall immediately inform the Beneficiary if such insurance ceases to be available at commercially reasonable rates in order that the Sub-Contractor and the Beneficiary can discuss means of best protecting the respective positions of the Beneficiary and the Sub-Contractor in respect of the Development in the absence of such insurance.

  - The Sub-Contractor shall fully co-operate with any measures reasonably required by the Beneficiary, including (without limitation) completing any proposals for insurance and associated documents, maintaining such insurance at rates above commercially reasonable rates if the Beneficiary undertakes in writing to reimburse the Sub-Contractor in respect of the net cost of such insurance to the Sub-Contractor above commercially reasonable rates or, if the Beneficiary effects such insurance at rates at or above commercially reasonable rates, reimbursing the Beneficiary in respect of what the net cost of such insurance to the Beneficiary would have been at commercially reasonable rates.

  - As and when reasonably requested to do so by the Beneficiary the Sub-Contractor shall produce for inspection reasonable documentary evidence (including if required by the Beneficiary, the originals of the relevant insurance documents) that its professional indemnity insurance is being maintained.

  - The above obligations in respect of professional indemnity insurance shall continue notwithstanding termination of this Deed for any reason whatsoever, including (without limitation) breach by the Beneficiary.

- Obligations Prior to Termination of the Sub-Contract by the Sub-Contractor

  - The Sub-Contractor covenants with the Beneficiary that it will not exercise nor seek to exercise any right of termination of its employment under the Sub-Contract or to discontinue the performance of any of the Sub-Contract Works for any reason whatsoever (including any breach on the part of the Contractor) without giving not less than 21 days written notice of his intention to do so to the Beneficiary and specifying the grounds for the proposed termination or discontinuance.

  - Any period stipulated in the Sub-Contract for the exercise of a right of termination by the Sub-Contractor of its employment under the Sub-Contract or to discontinue the performance of any of its obligations thereunder shall, nevertheless, be extended as may be necessary to take account of the period of notice required under Clause 4.

  - The right of the Sub-Contractor to terminate its employment under the Sub-Contract or to discontinue to discharge its obligations thereunder shall cease within the period of 21 days referred to in Clause 4 if the Beneficiary shall give notice to the Sub-Contractor:-

    - requiring the Sub-Contractor to continue its obligations under the Sub-Contract with the Beneficiary or its nominee; and

    - acknowledging that the Beneficiary or its nominee will assume all the obligations of the Contractor under the Sub-Contract; and

    - undertaking that the Beneficiary or its nominee will discharge all payments which may subsequently become due to the Sub-Contractor under the terms of the Sub-Contract and will pay to the Sub-Contractor any sums which have been due and payable to it under the Sub-Contract but which remain unpaid.

  - Upon service by the Beneficiary or its nominee of a notice complying with the requirements of Clause 4.3 the Sub-Contract will continue in full force and effect as if the same had been entered into between the Sub-Contractor and the Beneficiary to the exclusion of the Contractor.

  - Compliance by the Sub-Contractor with the provisions of this Clause 4 will not be treated as a waiver of any breach on the part of the Contractor giving rise to the right of termination nor otherwise prevent the Sub-Contractor from exercising its rights after the expiration of the notice issued pursuant to Clause 4 unless the rights of termination have ceased under the provisions of Clause 4.3.

  - If the employment of the Sub-Contractor under the Sub-Contract is terminated before service of any notice under Clause 4.3, then the Beneficiary may within 28 days thereafter give notice requiring the Sub-Contractor to enter into a new contract in writing (‘New Contract’) with the Beneficiary or its Appointee (save any Appointee to whom the Sub-Contractor shall promptly make reasonable objection in writing) on the same terms as the Sub-Contract, but with such revisions as the Beneficiary may reasonably require to reflect altered circumstances, for the continuation and completion of the Sub-Contract Works and the Sub-Contractor shall comply with such notice and the cost of preparing the New Contract shall be met by the Beneficiary.

  - This Clause 3 shall cease to have effect upon the prior exercise by any third person of any similar rights of substitution contained in any other agreement concerning the Development and entered into between the Sub-Contractor and such person.

- Beneficiary’s Rights in Relation to the Sub-Contract

  - Notwithstanding that as between the Contractor and the Sub-Contractor the Sub-Contractor's right of termination of its employment under the Sub-Contract may not have arisen the provisions of Clause 4.4 shall also apply if the Beneficiary gives notice to the Sub-Contractor and to the Contractor to the effect that the Beneficiary wishes the provisions of Clause 4.4 to apply and the Beneficiary or its nominee complies with the requirements of Clause 4.3.

  - The Sub-Contractor shall not be concerned, or required to enquire whether, and shall be bound to assume that as between the Contractor and the Beneficiary the circumstances have arisen permitting the Beneficiary to give notice under Clause 5.1.

  - This Clause 5 shall cease to have effect upon the prior exercise by any third person of any similar rights of substitution contained in any other agreement concerning the Development and entered into between the Sub-Contractor and such person.

- Sub-Contractor's Position

- By acting in accordance with Clauses 4 and 5 the Sub-Contractor shall not incur any liability to the Contractor.

- Assignment

  - The Beneficiary may assign all of its rights under this Deed:

    - by way of security or by way of re-assignment on redemption; and

    - by absolute assignment to any Group Company of the Beneficiary; and

    - by absolute assignment on two other occasions only.

  - In this Deed references to the Beneficiary include where the context admits its permitted assignees.

  - The Sub-Contractor shall not be entitled to contend that any person to whom this Deed is assigned in accordance with clause 7.1 is precluded from recovering under this Deed any loss incurred by such assignee resulting from any breach of this Deed (whenever happening) by reason that such person is an assignee and not a named promisee under this Deed.

- Copyright

  - The Sub-Contractor as beneficial owner hereby grants to the Beneficiary without further charge and notwithstanding the completion or abandonment of the Sub-Contract Works or the determination or alleged determination of the Building Contract or the Sub-Contract an irrevocable, non-exclusive, royalty-free licence to use and reproduce any of the designs, drawings, specifications, CAD materials, calculations, details, correspondence, minutes of meetings and other information and documents (‘Documents’) which have been or are to be prepared by or on behalf of the Sub-Contractor relating to the Development for the construction of the Development and the maintenance, repair, reinstatement, reconstruction and extension of it and to grant sub-licences in the terms of this licence, but copyright in the Documents shall remain vested in the Sub-Contractor. The Sub-Contractor shall not be liable for any use of the Documents by the Beneficiary or its nominees for any purpose other than those for which the same are or were prepared.  The Beneficiary shall be entitled on written request and upon paying a reasonable copying charge to be supplied by the Sub-Contractor with copies of the Documents.

  - The Sub-Contractor warrants that the use of the Documents for the purposes of the Development will not infringe the rights of any third party.

  - All royalties or other sums payable in respect of the supply and use of any patented articles, processes or inventions required in connection with the Sub-Contract Works shall be paid by the Sub-Contractor and the Sub-Contractor shall indemnify the Beneficiary from and against all claims, proceedings, damages, costs and expenses suffered or incurred by the Beneficiary by reason of the Sub-Contractor infringing or being held to infringe any intellectual property rights in the course of or in connection with the Sub-Contract Works.

  - The Sub-Contractor hereby waives any right to be identified as author of the Documents in accordance with section 77, Copyright Designs and Patents Act 1988 (‘the Copyright Act’) and any right not to have the Documents subjected to derogatory treatment in accordance with section 80 of the Copyright Act against the Beneficiary or any licence or assignee of the Beneficiary.

  - The Sub-Contractor shall provide upon request from the Beneficiary a copy of the Sub-Contract.

- Extraneous rights

  - This Deed shall not negate or diminish any duty or liability otherwise owed by the Sub-Contractor to the Beneficiary.

  - No approval or inspection of the Development or of any designs or specifications nor the testing of any work or materials by or on behalf of the Beneficiary nor any omission to inspect or test shall negate or diminish any duty or liability of the Sub-Contractor arising under this Deed.

  - This Deed may be executed in any number of counterparts all of which when taken together shall constitute one and the same instrument.

- Contracts (Rights of Third Parties) Act 1999

- This Deed is not intended to confer any benefit on any third person pursuant to the Contracts (Rights of Third Parties) Act 1999 except that a person who is the successor to or the permitted assignee of the rights of the Beneficiary is deemed to be a party to this Deed.

- Expiry of warranty

- No proceedings shall be commenced against the Sub-Contractor under this Deed more than 12 years after the Practical Completion of the Development under the Building Contract (or, if earlier, more than 12 years after the employment of the Sub-Contractor under the Sub-Contract is terminated).

- Service of notice

- Any notice to be served under this Deed must be in writing and must be served by hand or by registered post or recorded delivery, and in the case of a corporation must be served at its registered office for the time being. In any other case notice may be served at any address for the time being of the person to be served. Service shall take effect, if given by hand, on the date of delivery. If given by post, it shall take effect two days after posting, excluding Saturdays, Sundays and statutory holidays.

- Governing law and interpretation

  - The law of this Deed is English law and the English courts shall have jurisdiction with regard to all matters arising from it.

  - The definitions given in the recitals to this Deed apply to this Deed.

  - In this Deed:

    - ‘Appointee’ means a person, partnership, company or other legal entity nominated by the Beneficiary to exercise the substitution rights contained in Clauses 3 and 5;

    - ‘Group Company’ means any subsidiary company or holding company of the Beneficiary, or another subsidiary or holding company of such company, as ‘subsidiary’ and ‘holding company’ are defined in the Companies Act 2006 (as amended);

    - ‘Practical Completion’ means the date of practical completion of the Development as defined in accordance with the Building Contract;

    - ‘person’ includes any firm and any entity having legal capacity;

    - any term importing gender shall include any gender;

    - any term importing the singular includes the plural and vice versa;

    - any reference to any clause or schedule is a reference to such clause or schedule of or to this Deed.

  - Clause headings do not form part of nor affect the interpretation of this Deed.

EXECUTED AND DELIVERED as a deed:

| EXECUTED (but not delivered until the date hereof) AS A DEED by [ ] acting by:- | ) ) ) ) ) Director Director/Secretary |
| --- | --- |
| EXECUTED (but not delivered until the date hereof) AS A DEED by [ ] acting by:- | ) ) ) ) ) Director Director/Secretary |
| EXECUTED (but not delivered until the date hereof) AS A DEED by [ ] acting by:- | ) ) ) ) ) Director Director/Secretary |

Part 4 – Sub-Contractor Collateral Warranty to Third Party

DATED				20[    ]

[SUB-CONTRACTOR]

and

[BENEFICIARY]

and

[CONTRACTOR]

Draft [   ]: [Date]

SUB-CONTRACTOR’S [PURCHASER/FUNDER/TENANT]

COLLATERAL WARRANTY

[description]

CONTENTS

1.	Duty Of Care	2

2.	Prohibited Materials	3

3.	Indemnity Insurance	65

4.	[Obligations Prior To Termination Of The Sub-Contract By The Sub-Contractor]	4

5.	[Beneficiary’s Rights In Relation To The Sub-Contract]	5

6.	[Sub-Contractor's Position]	5

7.	Assignment	5

8.	Copyright	6

9.	Extraneous Rights	6

10.	Contracts (Rights Of Third Parties) Act 1999	7

11.	Expiry Of Warranty	7

12.	Service Of Notice	7

13.	Governing Law And Interpretation	7

THIS DEED is made 	 20[   ]

BETWEEN:

(1)	[			] (CRN [		]) whose registered office is at [		] (‘Sub-Contractor’);

(2)	[			] (CRN [		]) whose registered office is at [		] (‘Beneficiary’); [and]

[(3)	[			] (CRN [		]) whose registered office is at [		] (‘Contractor’).]

WHEREAS:

(A)	By an agreement in writing dated [date] (‘Building Contract’) between [			] (CRN [			]) whose registered office is at [					] (the “Employer”) and the Contractor the Contractor agreed to design and construct [give details] upon land at [address] (‘the Development’ which expression means the said land and the works constructed or to be constructed on it or either of them as the case shall require).

(B)	By agreement in writing dated [date] (‘Sub-Contract’) between the Contractor and the Sub-Contractor the Contractor appointed the Sub-Contractor to [complete the] design [of] and to supply [and erect or install] [give details] (‘Sub-Contract Works’) for or into the Development.

(D)	[The Beneficiary is a funder of the Development.

or

The Beneficiary is the purchaser of [the premises known as [give details] (‘Premises’) forming part of] the Development.

or

The Beneficiary has taken or agreed to take a lease of [the premises known as [give details] (‘Premises’) forming part of] the Development.]

NOW THIS DEED WITNESSES in consideration of the sum of £1.00 paid by the Beneficiary, receipt of which the Sub-Contractor acknowledges:

- Duty of care

  - The Sub-Contractor undertakes with and warrants to the Beneficiary that the Sub-Contractor has carried out and will carry out and complete the Sub-Contract Works in accordance with and subject to the terms of the Sub-Contract and has observed and performed and will observe and perform all of its duties and obligations expressed in or arising out of the Sub-Contract and (without qualification to or derogation from the foregoing) has exercised and will exercise all reasonable skill and care and diligence in and about the execution of the Sub-Contract Works to be expected from a sub-contractor experienced in constructing works of a similar nature, value, complexity and timescale to the Development.

  - The Sub-Contractor shall have no liability under Clause 1.1 of this Deed that is greater or of longer duration than it would have had, and shall be entitled in any action or proceedings by the Beneficiary to raise equivalent rights in defence of liability (except for set off or counterclaim) as it would have against the Contractor under the Sub-Contract, and shall have no liability under this Deed that is of greater or of longer duration than it would have had if the Beneficiary had been a party to the Sub-Contract as joint employer.

  - Without derogation from Clause 1.1 and to the extent that under the Sub-Contract the Sub-Contractor takes responsibility for the design of the Sub-Contract Works or the selection of goods, materials, plant and equipment for incorporation in the Sub-Contract Works, the Sub-Contractor warrants that the same have been and will be designed and selected with all reasonable skill and care set out in Clause 1.1.

- Prohibited materials

- The Sub-Contractor warrants that it will not specify or use or approve the specification for use by others of any products or materials not in conformity with (save where they exceed) relevant British or European standards or codes of practice or which are generally known in the construction industry at the time of use to be deleterious to health and safety or to the durability of buildings and/or other structures and/or finishes and/or plant and machinery in the particular circumstances in which they are specified to be used.

- Indemnity Insurance

  - The Sub-Contractor shall maintain professional indemnity insurance covering (inter alia) all its design liabilities hereunder upon customary and usual terms and conditions prevailing for the time being in the insurance market, and with reputable insurers lawfully carrying on such insurance business in the United Kingdom, in an amount of not less than £[                    ] ([                    ] million pounds) for any one occurrence or series of occurrences arising out of any one event for a period beginning now and ending 12 years after the date of Practical Completion of the Development, provided always that such insurance is available at commercially reasonable rates.  The said terms and conditions shall not include any term or condition to the effect that the Sub-Contractor must discharge any liability before being entitled to recover from the insurers, or any other term or condition which might adversely affect the rights of any person to recover from the insurers pursuant to the Third Parties (Rights Against Insurers) Act 1930, or any amendment or re-enactment thereof.  The Sub-Contractor shall not, without the prior approval in writing of the Beneficiary, settle or compromise with the insurers any claim which the Sub-Contractor may have against the insurers and which relates to a claim by the Beneficiary against the Sub-Contractor, or by any act or omission lose or prejudice the Sub-Contractor's right to make or proceed with such a claim against the insurers.

  - Any increased or additional premium required by insurers by reason of the Sub-Contractor's own claims record or other acts, omissions, matters or things particular to the Sub-Contractor shall be deemed to be within commercially reasonable rates.

  - The Sub-Contractor shall immediately inform the Beneficiary if such insurance ceases to be available at commercially reasonable rates in order that the Sub-Contractor and the Beneficiary can discuss means of best protecting the respective positions of the Beneficiary and the Sub-Contractor in respect of the Development in the absence of such insurance.

  - The Sub-Contractor shall fully co-operate with any measures reasonably required by the Beneficiary, including (without limitation) completing any proposals for insurance and associated documents, maintaining such insurance at rates above commercially reasonable rates if the Beneficiary undertakes in writing to reimburse the Sub-Contractor in respect of the net cost of such insurance to the Sub-Contractor above commercially reasonable rates or, if the Beneficiary effects such insurance at rates at or above commercially reasonable rates, reimbursing the Beneficiary in respect of what the net cost of such insurance to the Beneficiary would have been at commercially reasonable rates.

  - As and when reasonably requested to do so by the Beneficiary the Sub-Contractor shall produce for inspection reasonable documentary evidence (including if required by the Beneficiary, the originals of the relevant insurance documents) that its professional indemnity insurance is being maintained.

  - The above obligations in respect of professional indemnity insurance shall continue notwithstanding termination of this Deed for any reason whatsoever, including (without limitation) breach by the Beneficiary.

- [Obligations Prior to Termination of the Sub-Contract by the Sub-Contractor]

  - The Sub-Contractor covenants with the Beneficiary that it will not exercise nor seek to exercise any right of termination of its employment under the Sub-Contract or to discontinue the performance of any of the Sub-Contract Works for any reason whatsoever (including any breach on the part of the Contractor) without giving not less than 21 days written notice of his intention to do so to the Beneficiary and specifying the grounds for the proposed termination or discontinuance.

  - Any period stipulated in the Sub-Contract for the exercise of a right of termination by the Sub-Contractor of its employment under the Sub-Contract or to discontinue the performance of any of its obligations thereunder shall, nevertheless, be extended as may be necessary to take account of the period of notice required under Clause 4.

  - The right of the Sub-Contractor to terminate its employment under the Sub-Contract or to discontinue to discharge its obligations thereunder shall cease within the period of 21 days referred to in Clause 4 if the Beneficiary shall give notice to the Sub-Contractor:-

    - requiring the Sub-Contractor to continue its obligations under the Sub-Contract with the Beneficiary or its nominee; and

    - acknowledging that the Beneficiary or its nominee will assume all the obligations of the Contractor under the Sub-Contract; and

    - undertaking that the Beneficiary or its nominee will discharge all payments which may subsequently become due to the Sub-Contractor under the terms of the Sub-Contract and will pay to the Sub-Contractor any sums which have been due and payable to it under the Sub-Contract but which remain unpaid.

  - Upon service by the Beneficiary or its nominee of a notice complying with the requirements of Clause 4.3 the Sub-Contract will continue in full force and effect as if the same had been entered into between the Sub-Contractor and the Beneficiary to the exclusion of the Contractor.

  - Compliance by the Sub-Contractor with the provisions of this Clause 4 will not be treated as a waiver of any breach on the part of the Contractor giving rise to the right of termination nor otherwise prevent the Sub-Contractor from exercising its rights after the expiration of the notice issued pursuant to Clause 4 unless the rights of termination have ceased under the provisions of Clause 4.3.

  - If the employment of the Sub-Contractor under the Sub-Contract is terminated before service of any notice under Clause 4.3 then the Beneficiary may within 28 days thereafter give notice requiring the Sub-Contractor to enter into a new contract in writing (‘New Contract’) with the Beneficiary or its Appointee (save any Appointee to whom the Sub-Contractor shall promptly make reasonable objection in writing) on the same terms as the Sub-Contract, but with such revisions as the Beneficiary may reasonably require to reflect altered circumstances, for the continuation and completion of the Sub-Contract Works and the Sub-Contractor shall comply with such notice and the cost of preparing the New Contract shall be met by the Beneficiary.

  - This Clause 4 shall cease to have effect upon the prior exercise by any third person of any similar rights of substitution contained in any other agreement concerning the Development and entered into between the Sub-Contractor and such person.]

- [Beneficiary’s Rights in Relation to the Sub-Contract

  - Notwithstanding that as between the Contractor and the Sub-Contractor the Sub-Contractor's right of termination of its employment under the Sub-Contract may not have arisen the provisions of Clause 4.4 shall also apply if the Beneficiary gives notice to the Sub-Contractor and to the Contractor to the effect that the Beneficiary wishes the provisions of Clause 4.4 to apply and the Beneficiary or its nominee complies with the requirements of Clause 4.3.

  - The Sub-Contractor shall not be concerned, or required to enquire whether, and shall be bound to assume that as between the Contractor and the Beneficiary the circumstances have arisen permitting the Beneficiary to give notice under Clause 5.1.

  - This Clause 5 shall cease to have effect upon the prior exercise by any third person of any similar rights of substitution contained in any other agreement concerning the Development and entered into between the Sub-Contractor and such person.]

- [Sub-Contractor's Position

- By acting in accordance with Clauses 4 and 5 the Sub-Contractor shall not incur any liability to the Contractor.]

- Assignment

  - The Beneficiary may assign all of its rights under this Deed:

    - by way of security or by way of re-assignment on redemption; and

    - by absolute assignment to any Group Company of the Beneficiary; and

    - by absolute assignment on two other occasions only.

  - In this Deed references to the Beneficiary include where the context admits its permitted assignees.

  - The Sub-Contractor shall not be entitled to contend that any person to whom this Deed is assigned in accordance with clause 7.1 is precluded from recovering under this Deed any loss incurred by such assignee resulting from any breach of this Deed (whenever happening) by reason that such person is an assignee and not a named promisee under this Deed.

- Copyright

  - The Sub-Contractor as beneficial owner hereby grants to the Beneficiary without further charge and notwithstanding the completion or abandonment of the Sub-Contract Works or the determination or alleged determination of the Building Contract or the Sub-Contract an irrevocable, non-exclusive, royalty-free licence to use and reproduce any of the designs, drawings, specifications, CAD materials, calculations, details, correspondence, minutes of meetings and other information and documents (‘Documents’) which have been or are to be prepared by or on behalf of the Sub-Contractor relating to the Development for the construction of the Development and the maintenance, repair, reinstatement, reconstruction and extension of it and to grant sub-licences in the terms of this licence, but copyright in the Documents shall remain vested in the Sub-Contractor. The Sub-Contractor shall not be liable for any use of the Documents by the Beneficiary or its nominees for any purpose other than those for which the same are or were prepared.  The Beneficiary shall be entitled on written request and upon paying a reasonable copying charge to be supplied by the Sub-Contractor with copies of the Documents.

  - The Sub-Contractor warrants that the use of the Documents for the purposes of the Development will not infringe the rights of any third party.

  - All royalties or other sums payable in respect of the supply and use of any patented articles, processes or inventions required in connection with the Sub-Contract Works shall be paid by the Sub-Contractor and the Sub-Contractor shall indemnify the Beneficiary from and against all claims, proceedings, damages, costs and expenses suffered or incurred by the Beneficiary by reason of the Sub-Contractor infringing or being held to infringe any intellectual property rights in the course of or in connection with the Sub-Contract Works.

  - The Sub-Contractor hereby waives any right to be identified as author of the Documents in accordance with section 77, Copyright Designs and Patents Act 1988 (‘the Copyright Act’) and any right not to have the Documents subjected to derogatory treatment in accordance with section 80 of the Copyright Act against the Beneficiary or any licence or assignee of the Beneficiary.

  - The Sub-Contractor shall provide upon request from the Beneficiary a copy of the Sub-Contract.

- Extraneous rights

  - This Deed shall not negate or diminish any duty or liability otherwise owed by the Sub-Contractor to the Beneficiary.

  - No approval or inspection of the Development or of any designs or specifications nor the testing of any work or materials by or on behalf of the Beneficiary nor any omission to inspect or test shall negate or diminish any duty or liability of the Sub-Contractor arising under this Deed.

  - This Deed may be executed in any number of counterparts all of which when taken together shall constitute one and the same instrument.

- Contracts (Rights of Third Parties) Act 1999

- This Deed is not intended to confer any benefit on any third person pursuant to the Contracts (Rights of Third Parties) Act 1999 except that a person who is the successor to or the permitted assignee of the rights of the Beneficiary is deemed to be a party to this Deed.

- Expiry of warranty

- No proceedings shall be commenced against the Sub-Contractor under this Deed more than 12 years after the Practical Completion of the Development under the Building Contract (or, if earlier, more than 12 years after the employment of the Sub-Contractor under the Sub-Contract is terminated).

- Service of notice

- Any notice to be served under this Deed must be in writing and must be served by hand or by registered post or recorded delivery, and in the case of a corporation must be served at its registered office for the time being. In any other case notice may be served at any address for the time being of the person to be served. Service shall take effect, if given by hand, on the date of delivery. If given by post, it shall take effect two days after posting, excluding Saturdays, Sundays and statutory holidays.

- Governing law and interpretation

  - The law of this Deed is English law and the English courts shall have jurisdiction with regard to all matters arising from it.

  - The definitions given in the recitals to this Deed apply to this Deed.

  - In this Deed:

    - [‘Appointee’ means a person, partnership, company or other legal entity nominated by the Beneficiary to exercise the substitution rights contained in Clauses 3 and 5;]

    - ‘Group Company’ means any subsidiary company or holding company of the Beneficiary, or another subsidiary or holding company of such company, as ‘subsidiary’ and ‘holding company’ are defined in the Companies Act 2006 (as amended);

    - ‘Practical Completion’ means the date of practical completion of the Development as defined in accordance with the Building Contract;

    - ‘person’ includes any firm and any entity having legal capacity;

    - any term importing gender shall include any gender;

    - any term importing the singular includes the plural and vice versa;

    - any reference to any clause or schedule is a reference to such clause or schedule of or to this Deed.

  - Clause headings do not form part of nor affect the interpretation of this Deed.

EXECUTED AND DELIVERED as a deed:

| EXECUTED (but not delivered until the date hereof) AS A DEED by [ ] acting by:- | ) ) ) ) ) Director Director/Secretary |
| --- | --- |
| EXECUTED (but not delivered until the date hereof) AS A DEED by [ ] acting by:- | ) ) ) ) ) Director Director/Secretary |
| [EXECUTED (but not delivered until the date hereof) AS A DEED by [ ] acting by:- | ) ) ) ) ) Director Director/Secretary] |

Part 5 – Parent Company Guarantee

DATED				20[	]

[			]

and

[			]

Draft [		]

PARENT COMPANY GUARANTEE

THIS AGREEMENT dated 						20[        ] is made BETWEEN:-

(1)	[					] whose registered office is at [

] (“the Guarantor”); and

(2)	[					] of [ 					]

] (“the Employer”).

BACKGROUND

(A)	The Employer [has entered/is about to enter] into a Contract [				     ] (‘the Contract’) (which expression shall include all plans, specifications, bills of quantities and other documents incorporated therein) with [						  ] whose registered office is at [					        ] (‘the Contractor’) in relation to the carrying out, construction and completion of certain works by the Contractor as more particularly described in the Contract (hereinafter called ‘the Works’).

(B)	The Contractor is a wholly owned subsidiary company of the Guarantor under the Companies Act 2006.

(C)	The Guarantor has agreed to guarantee the performance of all of the Contractor’s obligations under the Contract in the manner appearing below.

IT IS AGREED as follows:-

# GUARANTEE

- The Guarantor HEREBY irrevocably COVENANTS AND GUARANTEES to the Employer and its successors and assigns, the full, faithful and punctual performance, observance and compliance respectively by the Contractor of each and every of the terms, provisions, conditions, obligations, undertakings and agreements on the part of the Contractor to be performed, observed or carried out by the Contractor as contained or referred to in the Contract as such Contract may, from time to time, be amended (hereinafter called ‘the Obligations’).

# PERFORMANCE OBLIGATIONS

- If, at any time, any default is made by the Contractor in the performance of any of the Obligations, the Guarantor will well and truly perform or cause to be so performed each and every one of the Obligations and/or will pay any sum or sums that may be payable in consequence of any default made by the Contractor in the performance of any of the Obligations.

# LIABILITY

  - 3.1	As between the Guarantor and the Employer (but without affecting the Obligations), the Guarantor shall remain liable under this Guarantee as if it were the sole principal obligor and not merely a guarantor.

  - 3.2	Subject to the provisions of clause 5, the Guarantor shall not be discharged nor shall its liability be affected by anything which would not discharge it or affect its liability if it were the sole principal obligor including, but not limited to:

    - 3.2.1	any amendment, modification, waiver, consent or variation, express or implied, to the scope of the Works or to the Contract or any related documentation;

    - 3.2.2	the granting of any extensions of time or forbearance, forgiveness or indulgences in relation to time to the Contractor;

    - 3.2.3	the enforcement, absence of enforcement or release of the Contract or of any security, right of action or other guarantee or indemnity;

    - 3.2.4	the dissolution, amalgamation, reconstruction, reorganisation of the Contractor;

    - 3.2.5	any defect in any provision of the Contract or any of the Obligations;

    - 3.2.6	any indulgence or additional or advanced payment, forbearance, payment or concession to the Contractor;

    - 3.2.7	any compromise of any dispute with the Contractor;

    - 3.2.8	any failure of supervision to detect or prevent any fault of the Contractor; or

    - 3.2.9	any assignment of the benefit of the Contract.

# ASSIGNMENT

  - 4.1	This Guarantee and the benefit conferred by it may be assigned by the Employer to any party to whom it assigns or novates its interest under the Contract, at any time and references to the Employer shall include its assigns.

  - 4.2	Save for the provision of Clause 4.1 above, this Guarantee and the benefit conferred by it may not be assigned by either party.

# LIMIT OF LIABILITY

    - The Guarantor shall have no greater liability to the Employer under this Guarantee than it would have had had it been named as Contractor under the Contract.

# THIRD PARTY RIGHTS

No term of this Deed is enforceable under the Contracts (Rights of Third Parties) Act 1999 by a person who is not party to this Deed. This clause does not affect any right or remedy of any person which exists or is available otherwise than pursuant to that Act.

# NOTICES

All notices under this Deed shall be in writing and all certificates, notices or written instructions to be given under the terms of this Agreement shall be served by sending the same by first class post, facsimile or by hand, or leaving the same at:-

- Guarantor

Name		[insert name]

Address		[insert address]

Fax Number	[insert fax number]

- Employer

Name		[insert name]

Address		[insert address]

Fax Number	[insert fax number]

# GOVERNING LAW

- The construction, validity and performance of this Guarantee is subject to English law and the courts of England and Wales shall have jurisdiction over any dispute or difference arising out of or in connection herewith.

DELIVERED as a Deed on the date at the head of this document.

EXECUTED as a Deed by

Director

Director/Secretary

EXECUTED as a Deed by

Director

Director/Secretary

Schedule 6	Site plan

[Insert plan of the Site]

Schedule 7	Deed of Novation

DATED				20[     ]

[EMPLOYER]

and

[CONTRACTOR]

and

[CONSULTANT]

Draft [     ]: [Date]

DEED OF NOVATION

[description]

THIS AGREEMENT dated									20[     ]

BETWEEN:-

(1)	[			] (CRN [		]) whose registered office is at [												] (“the Employer”);

(2)	[			] (CRN [		]) whose registered office is at [												] (“the Contractor”); and

(3)	[			] (CRN [		]) whose registered office is at [												] (“the Consultant”).

WHEREAS:-

(A)	The Employer has appointed the Consultant to provide [			] services (“the Services”) by an agreement dated [				] (“the Appointment”) in connection with the development of [			] at [				] (“the Development”).

(B)	The Employer has appointed the Contractor under a contract (“the Building Contract”) to design and construct certain works as therein described (“the Works”).

(C)	The Employer, Consultant and Contractor have agreed that from the date of this Agreement the Contractor shall assume the obligations of the Employer and that the Consultant shall perform its obligations under the Appointment in favour of the Contractor and that the Employer and the Consultant shall each release the other from any obligations owed by the other to them under the Appointment.

NOW IT IS HEREBY AGREED as follows:-

- NOVATION

The Employer hereby releases and discharges the Consultant from any and all obligations and liabilities owed to the Employer under the Appointment.

The Consultant undertakes to perform the Appointment and to be bound by its terms in every way as if the Contractor were, and had been from the inception, a party to the Appointment in lieu of the Employer.

The Consultant hereby releases and discharges the Employer from any and all obligations and liabilities owed to the Consultant under the Appointment and accepts the liability of the Contractor under the Appointment in lieu of the liability of the Employer.

For the avoidance of doubt the Consultant undertakes with and warrants to the Contractor that it has carried out and will carry out the duties and obligations on its part to be performed under the Appointment, and that in performing the same the Consultant has exercised and will continue to exercise all the reasonable skill, care and attention to be expected of competent and fully qualified member of the Consultant's profession experienced in carrying out services the like of those undertaken by the Consultant under the Appointment for works of a similar nature, value, complexity and timescale to the Development.

Without prejudice to Clause 1.2, the Consultant warrants to the Contractor that it shall be liable for any loss or damage suffered or incurred by the Contractor arising out of any negligent act, default or breach by the Consultant in the performance of its obligations under the Appointment prior to the date of this Agreement.  Subject to any limitation of liability in the Appointment, the Consultant shall be liable for such loss or damage notwithstanding that such loss or damage would not have been suffered or incurred by the Employer (or suffered or incurred to the same extent by the Employer).

The Consultant acknowledges that all fees and expenses properly due to the Consultant under the Appointment up to the date of this Agreement have been paid in full by the Employer.

All rights of action and remedies vested in the Employer against the Consultant under the Appointment shall from the date of this Deed vest in the Contractor.

All rights of action and remedies vested in the Consultant against the Employer under and in respect of the Appointment shall from the date of this Deed lie against the Contractor.

The Contractor undertakes to perform the Appointment and to be bound by its terms in every way as if the Contractor were, and had been from the inception, a party to the Appointment in lieu of the Employer.

Nothing in this Deed shall affect or derogate from any collateral warranty given or to be given by the Consultant to the Employer respecting the Development.

PROPER LAW AND JURISDICTION

- This Agreement and the rights and obligations of the parties hereto shall be governed and construed according to English Law.  Any dispute shall be subject to the jurisdiction of the English Courts.

CONTRACTS (RIGHTS OF THIRD PARTIES) ACT 1999

Notwithstanding any other provision in this Agreement, nothing in this Agreement is intended to confer on any person any right to enforce any of the provisions of this Agreement which such person would not have had, but for the Contracts (Rights of Third Parties) Act 1999.

IN WITNESS whereof the parties hereto have executed this Agreement as a Deed the day and year first before written.

| EXECUTED (but not delivered until the date hereof) AS A DEED by [ ] acting by:- | ) ) ) ) ) Director Director/Secretary |
| --- | --- |
| EXECUTED (but not delivered until the date hereof) AS A DEED by [ ] acting by:- | ) ) ) ) ) Director Director/Secretary |
| EXECUTED (but not delivered until the date hereof) AS A DEED by [ ] acting by:- | ) ) ) ) ) Director Director/Secretary |

Delete as appropriate.

State nature of work in the Contractor’s Designed Portion.  The Contractor’s Designed Portion must not include any element of the Works or their design which is to be carried out by a Named Sub-Contractor

State the identifying numbers of the Contract Drawings or identify the schedule of drawings or other document listing them, which should be annexed to this Contract, and make the appropriate deletions.  The drawings themselves should be signed or initialled by or on behalf of each Party.

Delete as appropriate.

Delete if no items specifying a Named Sub-Contractor are included in the documents.  See also footnote 2 above and the Intermediate Building Contract Guide.

Delete these lines if a priced Activity Schedule is not provided.  In the Activity Schedule, each activity should be priced, so that the sum of those prices equals the Contract Sum excluding Provisional Sums,  and the value of work for which Approximate Quantities are included in the priced Bills of Quantities.

Where the Employer has accepted a divergence from his requirements, in the proposals submitted by the Contractor, the divergence should be removed by amending the Employer's Requirements before the Contract is executed.

Delete the Eleventh Recital if the Works are not divided into Sections.

The Technical Adviser will be the Architect/Contract Administrator

The Technical Adviser will be the Quantity Surveyor

The Contractor will undertake the role of principal designer unless expressly requested otherwise by the Authority.

Employer to confirm is any other third parties with an interest in the land should be included here

Sub-contract disciplines listed for illustration purposes only.  Contractor to confirm which elements of the Works they propose to sub-let for each school and Article 10.1 to be completed to reflect sub-contract works packages at each school prior to completion of the Contract.

Employer to confirm if any other third parties with an interest in the land should be included here

TA to agree levels of sub-contractor PII cover

Use where novation of consultants is required

Use where novation of consultants is required

Employer to confirm if any other third parties with an interest in the land should be included here

This is expected to be the ultimate parent company but can be the parent company that was identified at ITT stage

If the relevant document or set of documents takes the form of an Annex to this Contract, it is sufficient to refer to that Annex.

Continue on further sheets if necessary, which should be signed or initialled by or on behalf of each Party and then be annexed to this Contract.

Continue on further sheets if necessary which should be signed or initialled by or on behalf of each Party and then be annexed to this Contract.

The first date should not be more than one month after the Date of Possession.  Where it is intended that interim payments should become due on the last day of each month, the entry may be completed/amended to read "the last day of (insert month) and thereafter the last day in each month or the nearest Business Day in that month."  After practical completion, clause 4.7.1.3 allows for intervals of two months (or such other period as the Parties agree) between interim payments.

An insertion is needed here only if the default position is not to apply.  If no retention is required, insert "100" in the entries for clause 4.8.1.

An insertion is needed here only if the default position is not to apply.  If no retention is required, insert "100" in the entries for clause 4.8.1.

If the indemnity is to be for an aggregate amount and not for nay once occurrence or series of occurrences the entry should be amended to make this clear.

Delete all but one.

Obtaining Terrorism Cover, which is necessary in order to comply with the requirements of Insurance Option A, B or C will involve an additional premium and may in certain situations be difficult to effect.  Where a difficulty arises discussion should take place between the Parties and their insurance advisers.  See the Intermediate Building Contract Guide.

Where Insurance Option A applies these entries are made on information supplied by the Contractor.

Where Insurance Option A applies these entries are made on information supplied by the Contractor.

The Parties should either name the Adjudicator and select the nominating body or, alternatively, select only the nominating body.  The Adjudication Agreement (Adj) and the Adjudication Agreement (Named Adjudicator) (Adj/N) have been prepared by JCT for use when appointing an Adjudicator.

Clauses 4, 5 and 6 are only applicable to purchaser and funder warranties

Clauses 4, 5 and 6  are only applicable to funder and purchaser warranties

Clauses 4, 5 and 6 are only applicable to funder and purchaser warranties