| Contract Management Guidance – Template #10 CHANGE CONTROL FORM- Extensions – v. 5 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Contract Name: | Provision of Consultancy for Defence Academy Funding Model & Organisational Strategy (L1) |  |  | Contract Ref. No. |  | CCS Reference: CCCC16A94 MoD Contract Reference: CCCC16A94 (Variation Ref: CCCC16A94-01) |
|  |  |  | CLIENT CHANGE NOTICE (CCN) |  |  |  |
| CCN 1 REDACTED TEXT CCN Reference: Initiated by: 26th June 2017 Date CCN Raised by relevant party: Source of change: Ministry of Defence : |  |  |  |  |  |  |
| STAGE 1 – CLIENT |  |  |  |  |  |  |
| Summary of proposals/ requirements : |  | This is a variation to the Contract between the Crown Commercial Service, acting as Managing Agent on behalf of the Ministry of Defence and Deloitte LLP. The Terms and Conditions of the Contract apply but with the following amendments: - Variation to the Contract End Date - The original Contract period was 21st January 2017 until 7th April 2017. The intention of the Authority is to vary the Contract end date by three months, to 28th July 2017. - Uplift in Value of an additional £44,272.00 (Exc. VAT), increasing total Contract value from £88,832.00 (Exc. VAT) to £133,104.00 (Exc. VAT). - Inclusion of additional deliverables – Please refer to Annex 1 for revised deliverables. |  |  |  |  |
| Proposed payment: | In line with the existing terms and conditions of Contract and the proposed increased Contract value of £133,104 (exc. VAT). |  |  |  |  |  |
| Required delivery date, with rationale: | In line with the existing terms and conditions of Contract and the new proposed end date of 28th July 2017. |  |  |  |  |  |
| Date Print Name & Position Signature REDACTED TEXT REDACTED TEXT Change authorised to proceed to Stage 2 (Customer organisation representative): REDACTED TEXT REDACTED TEXT Change authorised to proceed to Stage 2 (CCS representative) Signature Print Name & Position Date |  |  |  |  |  |  |
| STAGE 2 – SUPPLIER |  |  |  |  |  |  |
| Comments/ caveats on requested change: |  |  |  |  |  |  |
| ABORTIVE COSTS : |  |  |  |  |  |  |
| Anticipated period from CCN being authorised by client to start of related provision |  |  |  |  |  |  |
| Deloitte LLP confirms that the costs identified above are the agreed figures that will be payable on CCN implementation |  |  |  |  |  |  |
| REDACTED TEXT Signed (Supplier Representative): REDACTED TEXT Print Name & Position: Date: |  |  |  |  |  |  |
| STAGE 3 – CLARIFICATIONS |  |  |  |  |  |  |
| Clarification/ queries to supplier regarding Date: their proposals: Supplier response Date: |  |  |  |  |  |  |
| STAGE 4 - CUSTOMER CCN SIGN-OFF TO PROCEED TO IMPLEMENTATION |  |  |  |  |  |  |
| Variation Withdrawn |  |  |  |  |  |  |
| By signing below, unless CCN is withdrawn, the Ministry of Defence agrees to pay Deloitte LLP the costs detailed in Stage 1, by deadlines agreed with the supplier, or as defined in the contract. |  |  |  |  |  |  |
| REDACTED TEXT Signed (Customer Representative): REDACTED TEXT Date Print Name & Position Signature Change authorised to proceed to implementation (CCS): REDACTED TEXT REDACTED TEXT Date Print Name & Position Signature |  |  |  |  |  |  |
| STAGE 5 - CCN COMPLETION SIGN-OFF |  |  |  |  |  |  |
| I confirm that the provision required under the CCN commenced in accordance with the customer requirements and supplier proposals in this CCN. |  |  |  |  |  |  |
| Date provision required under the CCN commenced: Date Signed by Customer: REDACTED TEXT REDACTED TEXT Signed (Customer representative): REDACTED TEXT REDACTED TEXT Print Name & Position |  |  |  |  |  |  |