# Annex A

| Title of project: | Sentinel 1 backscatter data provision service |
| --- | --- |
| Date and time for return of tenders: | 12th July 2017 @16:00 hours |
| Contract Reference No: | C17-0295-1142 |
| Address for tender submission: | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND TENDERS DIRECTLY TO PAUL ROBINSON, DORA IANTOSCA OR GORDON GREEN VIA THEIR PERSONAL EMAIL ADDRESSES, AS THIS WILL INVALIDATE YOUR TENDER Tender responses must be less than 10 MB in size. On receipt of your tender, you will receive an automated e-mail to confirm receipt by JNCC Support Co. If you do not receive this automated email, please contact, in the following order: Sue Wenlock (00 44 1733 866880) Chris Downes (00 44 1733 866877) |
| Contacts for technical information relating to this project specification: | Paul Robinson Joint Nature Conservation Committee Email: Paul.Robinson@jncc.gov.uk Tel: 01733 866867 OR Gwawr Jones Joint Nature Conservation Committee Email: Gwawr.Jones@jncc.gov.uk Tel: 01733 866822 |
| Contact for any queries regarding the tendering procedure: | Dora Iantosca or Gordon Green Finance Team Joint Nature Conservation Committee Email: Dora.Iantosca@jncc.gov.uk or Gordon.green@jncc.gov.uk Tel: 01733 866894 or 01733 866806 |
| Proposed start-date: | 17th July 2017 |
| Proposed end-date: | 30th March 2018 |

Title of Project

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Aims	3

3.	Project Background	4

4.	Project Objectives	4

5.	Outputs	6

6.	Dissemination	6

7.	Timescale	7

8.	Health and safety	7

9.	Project management	7

10.	Instructions for tender submission	7

11.	Evaluation Criteria	9

12.	Payment	10

13.	Additional Contractor requirements	10

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation. Its work contributes to maintaining and enriching biological diversity, conserving geological features and sustaining natural systems.

Our role is to provide evidence, information and advice so that decisions are made that protect natural resources and systems. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally:

advising Government  on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminate knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on the JNCC intranet:

http://cms/JNCCIntranet63/defalut.aspx?page=1569

## Project Aims

This project will investigate several technical issues regarding the production of standardised backscatter data derived from Sentinel 1 data.  It will then provide a service to generate and deliver backscatter data from Sentinel 1 imagery.  In order to address the different aspects of the work that are required, the following specification is broken down into a number of modules.  Each will need to be planned and costed separately so that decisions can be taken regarding priorities for the work within available resources.  The modules are:

- To carry out a short test by processing one or two Sentinel 1 scenes using 4 different combinations of settings.  The outputs of this test will be presented to stakeholders so that a decision can be taken as to how to modify the processing chain described in Annex B.

- To provide a service to generate and deliver imagery from the Sentinel 1 satellite processed into a backscatter product for the UK to the modified specification decided upon following the initial test phase.  This will enable multiple uses of that data and prevent the duplication of that processing.  Once created, that data will be made available for JNCC to ingest via an API into the Defra Collaboration Platform within a fully automated process.  All Sentinel 1A and 1B imagery over the UK from 1st January 2017 to 31st March 2018 will be included in the contract.  This module will also provide a troubleshooting element to ensure that support is available should anything go wrong with technical aspects of the data delivery.

- To carry out a detailed technical comparison between the modified version of the processing chain described in Annex B and other proposed standards such as from the CEOS Analysis Ready Data for Land (CARD4L) and the Satellite Applications Catapult.  This will assess the differences between the proposed standards and the likely implications of those differences for users.

- To provide a service to generate and deliver imagery from the Sentinel 1 satellite processed into a backscatter product for South Georgia and the South Sandwich Islands.  This will utilise the same approach as the UK service, but will need refining in order to address issues such as data mode, positional accuracy and coordinate systems to use.

- To carry out an assessment of the size of the task and the likely technical difficulties that would be faced in producing Sentinel 1 backscatter for the UK Overseas Territories.  Production of data for these areas is not part of this contract, but the assessment will advise on the best method, to include specifications of projections to be used and to estimate the costs of producing that data.

## Project Background

The Defra Earth Observation Centre of Excellence (EOCoE), through its EODIP (EO Data Integration Pilot) Programme is carrying out research into several applications of SAR data from the Sentinel 1 satellite.  In order to maximise efficiency in completing these applications, JNCC is looking to routinely generate analysis ready forms of Sentinel 1 data and make that data available so that it can be used for a range of applications.  This is intended to prevent duplication as much as possible and so keep costs to a minimum.  Data has already been produced for the time period 1st January 2015 to 30th March 2017.

## Project Objectives

To meet the overall aim of this project relating to modules 1 and 2 (Section 2), the objectives are to:

- The supplier will carry out a short test by processing one or two Sentinel 1 scenes using 4 different combinations of settings.  The two aspects that will vary are the elevation data and the image resampling method used within the terrain correction step.  Each of these has two different options:

  - SRTM 3 second or APGB 5m elevation data

  - Bilinear Interpolation or Nearest Neighbour

- Results of the test will be produced as a series of datasets and summarised in a form that can be presented to stakeholders.  The summaries will include recommendations of which settings to use in the subsequent production phase.

- Outputs from the 4 different tested options will each be tested for positional accuracy by comparison against Ordnance Survey data.  Recommendations made in point 2 above will include assessment of any impacts on positional accuracy of using the different settings for processing.

- Once a decision has been taken regarding how best to modify the processing chain given in Annex B, then the supplier will establish a production service to generate backscatter data according to the modified processing chain.  This processing will be carried out within their own systems.

- The scenes to include are all Sentinel 1 scenes from the numbered orbits listed in Annex C that overlap with any UK landmass.

- All Sentinel scenes over the UK from the 1st January 2017 will be processed and made available.  This system, once operating automatically will continue to provide processed data up to and including 31st March 2018.

- Once created, the pre-processed Sentinel 1 data will be made available for JNCC to ingest via an API from the supplier’s infrastructure into the Defra Collaboration Platform.  This step needs to operate on a fully automated process so that it does not require routine input from JNCC staff.

- Once the system is fully operational the data will be available for ingestion into the Defra Collaboration Node within 2 days of the imagery being made available by ESA through the SciHub.  Once generated the data will be held to be available for ingestion to the Collaboration Platform for a period of 4 weeks.

To meet the overall aim of this project relating to module 3 (Section 2), the objectives are to:

Determine the technical differences between the processing standard being used in this contract and two other standards being proposed for the generation of backscatter data.  Those two standards have been proposed by CEOS under its Analysis Ready Data for Land (CARD4L) work and by the Satellite Applications Catapult.  Findings will be presented as a comparison between the three schemes and an analysis of what the likely implications of those differences are for users.

To meet the overall aim of this project relating to module 4 (Section 2), the objectives are to:

- Meet with CEFAS staff at their offices in Lowestoft for a day to assess requirement and plan test.

- Analyse factors to be considered in drawing up a specification for the data.  This will include issue of projections to be used, data formats, whether data was collected by Sentinel 1 in multiple modes and any other technical considerations such as positional accuracy.

- Generate data for an area around South Georgia and the South Sandwich Islands, shown as SGSSI Maritime Zone and BAT AOI in Figure 1.  That data will be made available through the same API as the UK data.

Figure 1: Areas of interest around South Georgia and the South Sandwich Islands.

To meet the overall aim of this project relating to module 5 (Section 2), the objectives are to:

- Meet with CEFAS staff at their offices in Lowestoft for a day to assess requirement and plan test.

- Carry out and assessment of the size of the task of producing Sentinel 1 backscatter for specific UK Overseas Territories (Caribbean and South Atlantic) and the difficulties likely to be faced.

- Analyse factors to be considered in drawing up a specification for the data.  This will include issue of projections to be used, data formats, whether data was collected by Sentinel 1 in multiple modes and any other technical considerations such as positional accuracy and coordinate systems to use.

- Produce an analysis of the likely costs of producing that data.

## Outputs

- Four datasets from the initial test and a summary including descriptions of significant differences between the outputs and recommendations.  The format of the summary will be agreed with the Project Officer but could be a series of slides or a short report.

- A short report to include:

  - advice for utilising existing data to meet CEFAS requirement or proposal of how to produce data that would meet that requirement.

  - An assessment of the size of the task of producing Sentinel 1 backscatter for specific UK Overseas Territories (Caribbean and South Atlantic)

  - A short description of the data processing carried out, any changes made to the processing chain and the reasons for them, any difficulties faced and the solutions to them and any recommendations made for future provision of this data.

- Full UK Gemini compliant metadata for all data outputs.

- A service running from as early as possible in the contract through to the end of March 2018 that supplies fully pre-processed Sentinel 1 imagery for the UK following the modified processing chain, with metadata, via an automated process to the Defra Collaboration Platform.  Northern Ireland data will also be supplied separately in an appropriate projection (Irish Grid TM75 – EPSG 29903).

- A series of backscatter layers for South Georgia and the South Sandwich Islands.

- Technical support and troubleshooting to help fix any technical problems that arise.

## Dissemination

The report produced under this contract will be a JNCC product and shall not be published or disseminated without the written permission of JNCC. It may at some point be published on the JNCC website and all material supplied as part of this contract shall remain copyright of JNCC.

## Timescale

Provisional dates for delivery of the contact outputs are set out below. Exact dates are to be agreed at start-up meeting based on Contractor and JNCC staff availability.

| Milestones | Provisional dates |
| --- | --- |
| Start-up meeting (UK) | 18th July 2017 |
| Regular checkpoint meetings via teleconference | Fortnightly |
| Project completion | 30th March 2018 |

## Health and safety

The Contractor is expected to follow appropriate Health & Safety procedures and undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by JNCC H&S advisor)

Any incidents occurring within the contract should be immediately reported to JNCC.

## Project management

The Contractor shall nominate a project manager, who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Paul Robinson

Email: Paul.Robinson@jncc.gov.uk

Tel: +44 (0)1733 866867

Gwawr Jones

Email:  Gwawr.Jones@jncc.gov.uk

Tel: +44 (0)1733 866822

## Instructions for tender submission

The tender submission should include the following:

A brief summary of the potential Contractor’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract (and delivering the detailed tasks identified within each objective). This should be sufficiently detailed allow assessment against the evaluation criteria (Section 14);

A detailed project plan (including Gantt chart), including the proposed work programme and an estimate of time required to achieve each objective;

A draft Table of Contents for the final report;

Details of Quality Control procedures to be followed (note for author if research project/contract. For the See Evidence Quality Guidance Note #1 (Bias, Conflicting Evidence and uncertainty) and Evidence Quality Guidance Note #3 (Quality Assurance of Expert Knowledge and Opinion).

Details of the Contractor’s own internal Quality Management System;

Details of the Project Team, including their roles and experience, an estimate of their time input into each task, and CVs of all personnel involved in the contract;

Availability of the Project Team for a start-up meeting in Peterborough on…

Overall quote for the contract, to include:

  - Daily rates for all members of the Project Team;

  - Rates for attending start-up, interim and final meetings in Peterborough or Aberdeen (costs for travel and accommodation are attached and should be used. These rates are analogous to the civil service rates);

  - Costs and time allocation should be clearly allocated to specific tasks within this contract; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and to provide their company’s VAT registration number.

The following documentation:

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates; and

  - Copies of any appropriate risk assessments.

  - Copies of any environmental policies should you have them

In addition, note that the tender submission should provide sufficient information to allow assessment against the criteria outlined in Section 14.

## Evaluation Criteria

JNCC are not bound to accept the lowest priced or any tender.  Having the technical expertise and experience to complete the work to a high standard, and being able to complete it within the timescale, are of the essence for this contract.

Tenders will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Max Score | Score |
| --- | --- | --- | --- |
| 1. Quality of proposal, (50% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal (particularly work plan and deliverables) | 10 |  |
|  | Understanding of, and relevance to, the requirements | 10 |  |
|  | Soundness and logicality of methods | 7 |  |
|  | Realism and measurability of milestones | 6 |  |
|  | Identification and proposed solutions to potential problems/risks | 6 |  |
|  | Serious weaknesses which threaten success | 6 |  |
|  | Probability of success | 5 |  |
|  | Sub Totals | 50 |  |
| 2. Details of Contractor (25 % of the three assessment categories) |  |  |  |
|  | Expertise, experience and balance of team | 18 |  |
|  | Risks if important team members drop out | 7 |  |
|  | Sub Totals | 25 |  |
| 3. Cost (25% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation | 6 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 6 |  |
|  | Appropriateness of ratio of senior to junior staff time | 6 |  |
|  | Clarity of each team member’s contribution and value added | 7 |  |
|  | Sub Totals | 25 |  |
| Total score |  | 100 |  |

## Payment

Payment will be made on completion of the objectives, following the submission of an invoice(s); and based on satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Contractor requirements

All tenderers are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key milestones.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates and fees given.

The Contractor is expected to supply all necessary equipment, software, licences etc. to carry out the obligations required under the contract.