Provision of Item Writing Services – Skills Test Numeracy Call-Off Contract

Item Writing Framework Agreement – STA 0128

Call-Off Contract No: STA-0128 07

Title: Provision of Item Writing Services for Skills Test Numeracy

Supplier: NFER

Pursuant to the terms of the Item Writing Test Framework Agreement (STA 0128):

| Service Commencement Date: | 22/02/2017 |
| --- | --- |
| Call-Off Contract End Date: | 24th July 2017 |
| Call-Off Contract Value: | £36,346 |
| Relationship Manager for Department for Education: |  |
| Contract Manager for the Department for Education: |  |
| Relationship Manager for the Supplier: |  |

- Background

This call-off contract is for the provision of item writing services for Skills Test Numeracy (Work Package 1), including the drafting of potential items and their mark schemes, ready for formal trialling.

- Functional Requirements

| Functional Requirements |  |
| --- | --- |
| Assessment type | Professional Skills Tests for prospective teachers |
| Item development and design | The number of marks stated for each work package outlined below is the total number of marks which must be provided at final handover. Suppliers will need to ensure sufficient items are created to allow for any losses during the process, for example following the interim review meeting. Audio files are NOT required for any items. STA will produce audio files once items have been accepted for further use. |
| Item writing requirements for numeracy | 4.5.1 Numeracy The items are intended to cover the range of topic areas and question types detailed within the test specification, to ensure an even distribution of coverage across the given syllabus areas. Test format for live test Two sections: - Mental arithmetic (12 questions, each worth 1 mark with an additional unscored practice question). - Written questions, comprising written data and written arithmetic (7 data questions and 9 arithmetic questions each worth 1 mark). An onscreen four-function calculator is available for the written section. Candidates additionally have a whiteboard, which they may use for jottings/working out answers to all questions in the test. Please refer to the test specification (Annex A) for more detail on test format and composition. Work package requirements In each of work packages 1 and 2, STA requires 84 marks of questions. Section; Number of questions; Marks per question; Total marks. Mental arithmetic; 36; 1; 36. Written arithmetic; 27; 1; 27. Written data; 21; 1; 21. All questions to be based on the following item types: - Drag and drop – for example, ordering or completing a table - Fill in the blank – to enter a value. An item may comprise of single, or multiple, boxes. - Multiple choice – with either single or multiple correct values - Hot spot – for example, clicking on points on a graph. The number of items required for each item type is as follows: Section; Item types; Number. Mental arithmetic; Fill in the blank; 36. Written data; Fill in the blank Multiple choice* Drag and drop Hot spot*; 12 - 17 16 - 22 7 - 12 3 - 8. Written arithmetic. *Please note that multiple choice and hot spot questions include both those with a single correct answer option and those where multiple options are correct, there should be a roughly equal number of each type. For written questions only, the question stem can be used for up to three items. However, there must not be any ‘follow through’ from one item to another, i.e. the answer to one item should not be required to answer any subsequent items. No more than 25% of the total number of written questions should have stimulus in common with other items. Please additionally note that where items have a common question stem the primary syllabus reference must be different for each of the associated items, with no more than two items referenced to the same test section (i.e. written data or written arithmetic). Each work package should contain questions which address the syllabus groupings in the following quantities: Mental Arithmetic Mental Arithmetic; No, of ques; Comments. Number. 1r; 4 - 6. 1f, 1g, 1h; 4 - 6; 1g, 1h - under-represented in previous cycles.. 1c, 1d, 1e; 2 - 4. 1l, 1m, 1n, 1o, 1p, 1q; 3 - 5; 1m, 1n - under-represented in previous cycles. Measures. 1a; 3 - 5. 1b; 6 - 9. 1i, 1j, 1k, 1s; 7 - 10. Written Data Written Data; No, of ques; Comments. 2a; 3 – 6; Reduce number bar charts with a 2a reference. Aim to include more line graphs, but avoid currency conversion as a context. Okay to use unfamiliar / technical charts and graphs, but be mindful of the complexity of associated questions.. 2b; 6 – 9. 2c; 9. Written Arithmetic Syllabus grouping; No, of ques; Comments. Number. 3u.1, 3u.2; 2 - 4. 3h, 3i, 3g, 3l, 3m.1, 3m.2, 3m.3; 3 - 6. 3c, 3d, 3e, 3f; 2 - 4. Measures. 3a; 4 - 6. 3b; 4 - 6. 3j, 3k, 3v, 3w, 3x, 3n; 2 - 4; 3j, 3k – under-represented in previous cycles.. Statistics. 3o, 3p, 3q, 3r, 3y; 2 - 4. Algebra. 3t; 2 – 3; Essential to make sure that the formulas used in these questions have an educational context, as expert review panels have been critical of this in the past. Please don’t use any Fahrenheit to Celsius conversions.. Further information can be found in the item writing guidance document. |
| Marking guidance | Marking guidance must be provided for all items. This should be included in the completed template for each question. The marking guidance must include details of all correct answer(s). In the case of fill in the blank items for the numeracy test this must include all likely, acceptable equivalent values, eg: £6 and £6.00 but not £6.0. Only a single value, not a range of values, is allowed for each fill in the blank. Please refer to the item writing guidance document (Annex B) for more details |
| Item design | All items and their associated marking guidance must be submitted in Microsoft Word 2010 (or compatible subject to prior agreement) at Final Handover using the question templates provided. Please refer to the item writing guidance documents (Annex B) for further details on how items should be presented within the item writing templates. For each test section, a single word file should be provided which combines all items being submitted for that test section. These files should be provided both at interim handover and final handover. |
| Graphics, texts and other external materials | Written test item texts, artwork or data Where tables, graphics or other images are required for the inclusion with the question, the final version will be created by the e-assessment agency. The Item Writing Agency must provide a clear indication of how the final version should be presented, along with guidance notes for the programmer to support the accurate reproduction of the table, graphic or other image. Such guidance includes coordinates of all key points on graphs and the angle for segments in pie charts. This guidance should be included within the relevant section of the item writing template, rather than being provided in a separate document. Please note that all images must be presented in an editable format, either editable within the Word document itself or within a separate file, which is cross referenced within the Word version of the item. All such graphics that are fundamental to the questions (e.g. tables and diagrams) must be provided at both Interim and Final Handover. Where texts, artwork or data have been commissioned, please include the original material, contact details for the creator of the material, and a statement confirming assignment of the intellectual property rights (‘IPR’) in the material from the creator to DfE. The formal assignment of the relevant IPR in the commissioned work must be completed by the Final Handover Date. The documents in Annexes E (Copyright Permission Template) and F (Commissioning Materials to be written template) may be used for this purpose. The document in Annex G (Transfer of IPR to DfE Template) must be used when handing over texts, artwork or data that has been commissioned. Where there is a third party owner of any materials, it should be referenced as described below. Referencing source materials and artwork Any materials using externally sourced texts or data need to be fully referenced; including title, name of copyright owner, name of the author/editor/creator, details of the edition, publisher and page/location of the material within the source. If sourced from the web, a print out of the original website, showing the relevant artwork or data must also be included. |
| Item classification | The Supplier must classify all items according to the fields on the item classification spreadsheet, and present the item information on the spreadsheet template supplied. The spreadsheet is provided in Annex B. This spreadsheet should be included with the materials presented at Interim and Final Handovers. For numeracy, the IWA item audit template provided in Annex B should also be completed. Further guidance on classification of numeracy items is included within the numeracy item writing guidance document. |
| Interim Handover | Interim Handover must occur no later than 10 May 2017. The following materials must be sent to STA: - 100% of items to be provided in Microsoft Word 2010 (or compatible subject to prior agreement), using the item templates, which will be provided at the start up meeting. - All attribute fields on the template must be completed for each item, including curriculum reference and marking key. - Item classification spreadsheet in Microsoft Excel 2010 (or compatible). - Completed IWA item audit sheet (numeracy only) included within Annex B - For each test section, a single pdf file should be provided which combines all items being submitted for that test section. STA and the contracted agencies will review the supplied materials at the Interim Review meeting (24 to 26 April 2017). The Supplier will then make any revisions or amendments as necessary as a result of the discussions at that meeting. |
| Final Handover | Final Handover must occur on or before 3 July 2017. If the Final Handover Meeting is taking place the handover is as follows: Part 1, then Final Handover Meeting, then Part 2. If the Final Handover Meeting is not required, the handover is as follows: Part 2 only. Should STA decide that a final handover meeting is not needed, they may request at the interim handover meeting that parts 1 and 2 of the final handover process be combined to require electronic and hardcopy handover be provided to the part 1 dates. Part 1 – Electronic Handover of files prior to Final Handover Meeting. Final Handover Meeting – the purpose of the Final Handover meeting (if required) is to discuss the items and the rationale for all amends made. The meeting will be chaired by STA and either take place in STA offices in London or by telephone (to be decided by STA). A Final Handover Meeting will only be needed if 50% or more of items presented at Interim Handover are identified as needing significant amendments. Following the Handover Meeting the agreed changes must to be made prior to handover Part 2. Part 2 – Updated Electronic Handover of files and final Hardcopy Handover following changes discussed and agreed in the Final Handover Meeting. Electronic handover (parts 1 and 2) - 100% of items to be provided in Microsoft Word 2010 (or compatible subject to prior agreement), using the item templates included within Annex B. - A reference document that details the source of any data and text used in the test items. - All artwork/images used in the test items as unflattened files with all layers intact within the image file where applicable. Please ask for clarification on specific file types which are acceptable. - The updated item classification spreadsheet(s), - Completed item audit sheet included within Annex B. For each test section, a single pdf file should be provided which combines all items being submitted for that test section. Assignments and/or licences of IPR in the commissioned works to be completed by the Final Handover Date – as stated in this ITQ and the Contract, and all documentation relating to IPR. Electronic handover will take place either via the STA portal (preferred) or by encrypted memory stick (provided by STA); approach to be agreed at the Start-up Meeting. Hardcopy Handover – Supplier to hand over hardcopies of the numeracy items, including marking guidance and item classification spreadsheet. Up to 20 hard copies of all items, to be collated into 20 separate packs. Exact number to be agreed at the Interim Handover Meeting. |
| Acceptance of Final Handover | Following Final Handover, STA will check the provided materials. If any errors are found, all materials will be returned to the Supplier for a full check and for amendments to be carried out. An error free set of materials should be returned to STA no later than one week after the Final Handover date. |

- Required Service Elements

The Project deliverables/outputs are provided in the table below, and individual deliverables or outputs are indicated as Critical Steps where appropriate. All deliverables and outputs are categorised as mandatory and it is essential that you confirm that you can meet them, in full, and by the milestone date set. Failure to provide confirmation in your proposal documents may result in your proposal being rejected.

The specific date for all Requirements 1 – 6 must be included within the project plan in the response to the Technical Evaluation.

| No | Deliverables/Outputs | Acceptance Criteria | Due Date |
| --- | --- | --- | --- |
| 1 | Start-Up Meetings Provide: - Detailed plan for item development and scoring key production for review and joint sign-off; - Detailed project risk and issue log (Risk Log) for review and joint sign-off. | Project Director / Project Manager (or equivalent) attend the Start-Up Meeting and provision of listed documents by agreed date. | 13 February to 6 March 2017 |
| 2 | Checkpoint Meetings and Management Information To attend two Checkpoint meetings. These meetings may be held as telephone conference calls, and may also be combined with other meetings if appropriate. Checkpoint reports to be submitted to STA one working day in advance of each Checkpoint meeting. Attendance at Resolution meeting (maximum two days) following Expert Review 1 is also required. | Project Manager (or equivalent) attends each Checkpoint Meeting on agreed date and submission of Checkpoint report one working day in advance of each Checkpoint Meeting. | Weeks beginning 20 March 2017 and 29 May 2017 |
| 3 | Interim Handover – Critical Step Provide electronic copies of all draft item, marking guidance, draft item classification spreadsheet(s), a completed item audit template and details of copyright details for all items where this is relevant. The Contractor must handover 100% of the items in Microsoft Word format at the interim handover stage, with all items to be recorded on the item classification spreadsheet and the IWA item audit template. The Contractor must also handover a single pdf file of all items for each subject area (i.e. three pdf files in total, one for mental arithmetic, one for written data and one for written arithmetic). Templates for item writing, the item classification spreadsheet and the IWA item audit template are provided in Annex B. Please use the templates provided; guidance on how to use the item writing templates can be found in the item writing guidance document also provided in Annex B. N.B. Should STA decide that a final handover meeting is not needed, they may request at the interim handover meeting that parts 1 and 2 of the final handover process be combined to require electronic and hardcopy handover be provided to the part 1 dates. | 100% of drafts of all materials required for completion of work package(s) received electronically, including completed handover form, by agreed date and to criteria specified in section 4.5. | No later than 24 April 2017 |
| 4 | Interim Review Meeting Meeting with STA and item writers to review materials. Should more than 50% of items be identified as requiring significant amendment during interim review, a meeting with STA will be required to review the materials as part of Final Handover. | Project Manager / Lead Item Writer attend Interim Review Meeting on agreed date. | 8 to 10 May 2017 |
| 5 | Final Handover Part 1 – Electronic Handover of files prior to Final Handover Meeting. Final Handover Meeting – meeting to discuss amends to items. Part 2 – Updated Electronic Handover of files and final Hardcopy Handover following changes discussed and agreed in the Final Handover Meeting. Electronic handover – Supplier to hand over a Word file for each item (to include editable versions of all tables, charts, graphs and images either within the Word file or a separate Excel spreadsheet) with all sections populated as detailed in the item writing guidance document. Also to be provided: - a single word file of all items for each subject area (i.e. three word files in total, one for mental arithmetic, one for written data and one for written arithmetic). source references for all items (where applicable), - details of the copyright statement for the source materials (where applicable) - completed IWA item audit template - completed item classification spreadsheet. - signed copy of assignment/licences of IPR for DfE’s benefit. The preferred method of electronic handover is via the STA secure portal. The Contractor must also handover a single pdf file of all items for each subject area. Hardcopy Handover – Supplier to hand over hard copies of the numeracy items. | 100% of specified materials received at STA by agreed date, including completed handover form, and materials are of appropriate quality as listed under Performance Requirements. | Part 1 – 3 July 2017 Final Handover Meeting – 10 July to 12 June 2017 Part 2 – 17 July 2017 Hardcopy – 17 July 2017 |
| 6 | Acceptance of Final Handover materials – Critical Step If any errors are found following Final Handover or the materials are not compliant with this specification, all materials will be returned to the supplier for full checking and correction. Final payment will be withheld until this is completed. Fully checked and corrected materials should be returned no later than one week after the Final Handover date. | 100% of specified of materials with STA no later than one week after Final Handover Date, including completed handover form, . All materials to be error free. | No later than one week after Final Handover Date |

- Key Payment Milestones and Key Payment Milestones Dates

Payment will follow the completion of the Key Milestones listed at section 4.  Key Payment Milestones are:

[Redacted]

- Contract Management Arrangements

The Supplier shall be fully engaged on an on-going basis in regular Contract Management Reviews relating to this Call-Off Contract and the overarching Framework Agreement. These reviews provide an opportunity for the Department and the Supplier to discuss the end-to-end delivery of the Services which shall include but not be limited to: planning; progress; risk management; issue management; continuous improvement; proposed changes; lessons learnt; exit management. Reviews will be carried out with Senior Management on a six month basis where the Department and the Supplier will meet to discuss Supplier performance, lessons learnt, continuous improvement, value for money, exit management and any other issues considered relevant by the Department.

- Supporting documentation

The Skills Test Numeracy ITQ document sets out the full specification of requirements including the project deliverables, functional requirements and performance requirements. The original Skills Test Numeracy ITQ and the supplier’s response are appended to this contract document. [Supplier response redacted]

In witness whereof this Call-Off Contract has been duly executed.

Signed for and on behalf of the Department for Education:

Name and Title:

Date:

Signed for and on behalf of the Supplier:

Name and Title:

Date: