## Tender Clarifications
Tender Questions and Answers Tracker dated: |  | 2024-04-29
Client: | Croydon College
Project Name: | T421 - Internal Refurbishment Works
Clarification No. | Date Query Issued | Query | Response | Answered by | Date Answer Issued | Query Status (Open / Closed)
1 | 2024-04-18 | Please can you confirm if there is an ITT document available as this was not included in the tender zip folder? All documents were downloaded from Contracts Finder, please advise if the College has its own procurement portal where clarifications/additional documents are communicated. | ITT document included in the tender zip folder. 'Section 1 - Employer's Requirements' All documents, addendums, clarifications etc relating to this tender will be uploaded to the contracts finder page. | Fusion | 2024-04-18 | Closed
2 | 2024-04-18 | Please confirm if there are further drawings and specifications to be released? I have listed some items below ; - • Internal elevations of the classrooms • Further drawings for the refectory area – Currently only a plan and concept proposal | A tender addendum will be issued to include PCI information in due course. A further tender addendum will be issued on 29/04 to include a detailed design/specification for the Refectory section of works. A Catering Consultant is providing a quotation for the Refectory refurbishment and will be included in the tender addendum. Tenderer's are welcome to include this quotation in their tender return, but are not obliged to do so and are welcome to seek alternative quotes. Internal elevation drawings of the classrooms will not be issued. | Fusion | 2024-04-18 | Closed
3 | 2024-04-19 | The tender return date is the 20th (tomorrow / Saturday). Is there any scope for any extra time on the return of this tender? Also, how do register interest/ become approved to receive tenders as they are issued from Croydon council? | The tender deadline is 20th May 2024 with no availibility for an extension beyond that date. This is purely an open tender in the interest of a fair tender process, any interested suppliers will need to look at the contracts finder page for any opportunities. Please note this opportunity is for Croydon College, not Croydon Council. | Fusion | 2024-04-19 | Closed
4 | 2024-04-25 | Please confirm if the existing Design Team will be novated for this project? If so, can a schedule of services also be provided. | No designers are to be novated for these works. | Fusion | 2024-04-29 | Closed
5 | 2024-04-25 | We assume all tender information is fully compliant with RIBA Plan of Works 2020 Stage 4. | The information provided is not a full RIBA Stage 4 pack of information. No further design information will be provided (with the exception of the refectory information) and the successful tenderer will be expected to complete the design. | Fusion | 2024-04-29 | Closed
6 | 2024-04-25 | Please provide full contact details for incumbent BMS subcontractor. |  |  |  | Open
7 | 2024-04-25 | Please provide full contact details for incumbent Security/Intruder/Door Access subcontractor. |  |  |  | Open
8 | 2024-04-25 | Please provide doorset schedule confirming finishes and Ironmongery requirements. | To match existing recently refurbished areas in the College. | Fusion | 2024-04-29 | Closed
9 | 2024-04-25 | We assume all FFE including Teaching Walls are excluded from our works and are clients Group 3 items. | Correct | Fusion | 2024-04-29 | Closed
10 | 2024-04-25 | Dwg 14300 & 14302: We note on these drawings the full extent of the work areas are not indicated. Please provide plan drawings confirming these areas and enabling us to produce quantities for costing. | The drawings show the extent of finishes required as per the colour key on each drawing. | Fusion | 2024-04-29 | Closed
11
12
13
14
15
16
17
18