## Contract Schedule 10
Contract Schedule 9 - Key Performance Indicators
See notes below table.
No. | Category | KPI Name | Definition | Monitoring Method/Metrics | Suggested Monitoring Period | Units | How to Calculate | Governance Forum | RAG - Green Criteria | RAG - Amber Criteria | RAG - Red Criteria | Fee Impact
1 | Time | Delivery to Task Order programme milestones | Delivery of Task Order programme milestones by the milestone dates proposed by the Consultant to be measured within this KPI in the Task Order programme and agreed by the Employer, including where these dates are amended via a Compensation Event. | The Task Order programme will be used to monitor this KPI. The key measurement will be the timely delivery or otherwise of the programme milestones, in accordance with the accepted Task Order programme. | Monthly | Number | Number of Task Order programme milestones on schedule, forecast to miss, complete, and forecast early completion by comparing Task Order programme milestone dates against forecast dates for completion. | Monthly performance meeting | All Task Order programme milestones completed on time or forecast to completed on time. | Unless the impact of the delay can be mitigated to the reasonable satisfaction of the Employer, all Task Order programme milestones completed or forecast to be completed on time or within 4 working days late. | Unless the impact of the delay can be mitigated to the reasonable satisfaction of the Employer, completion of any Task Order programme milestone 5 working days late or more. | n/a
2 | Time | Delivery to Programme - Consultants Services | Completion of specified conditions by key dates. | The key criteria for measurement includes: * Were the stated conditions met by the key dates? * Were any Early Warnings / Compensation Events addressed, including any appropriate risk reduction measures? | Monthly | Number | Numbers of days late from key date without mitigating circumstances. | Monthly performance meeting | Completion on time. | Over 1 day working day late on any key conditions (provided the Red Criteria are not met). | Over 1 working day late on more than one key condition or 2 working days late or more on one key condition. | n/a
3 | Cost | Delivery to Price - Project Turn Out | Delivery of the Construction Project at a price consistent (or lower) with any pre-agreed construction budget (which will be inclusive of contingiency funding). This may be informed by the cost management strategy and recorded in a Project Initiation Document or Project Brief. This construction budget may be varied by Employer Instruction which materially effects the design / specification being delivered, or where the budget is articifically low due to consultant ommission. | Prior to commencing monitoring, agree and record the Construction Budget as the baseline (inclusive of contingiency funding), the out-turn is, at the relevant RIBA stage, either the reassessment of construction budget post design, the accepted tender cost of the construction contractors, or the actual constructed value. | Monthly | % and value | % difference and direct value difference between agreed construction budget vs actual cost | Monthly performance meeting | Construction saving | Nil construction overspend | Any construction overspend | n/a
4 | Quality | Delivery of the Consultants Services to Specification and Required Standards and Quality | Provision of the services in accordance with the Scope agreed with the Employer, the Specification and applicable Standards/Regulations. | Various monitoring methods to be used: a) the number of written complaints made by the Employer regarding the standard of performance being delivered. Complaints may be made for the delivery of a poor quality PMFDT service with defects/rework over and above what should be expected by 'third party comments', provision of a non-responsive service, or the lack of adequate contract management including the provision of proportionate Early Warnings and Compensation Events. b) The average score on a quarterly satisfaction survey to key stakeholders. The questions and scoring mechanism to be included in the survey will be developed with the Consultant in the life of the Call Off Contract. | Monthly | Number | Number of customer complaints and average survey score. | Monthly performance meeting | No complaints and good average survey score. | 1-2 complaints on service quality and/or mid-range average survey score (provided the Red Criteria are not met). | More than 2 complaints on service quality and/or poor average survey score | n/a
5 | Quality | Provision of accurate management information | Provision of right first time cost and management data (to be defined in the Employer's Statement of Requirements and Scope). | Measured by the delivery of quality cost and management information delivered on time and as described in the Employer's Statement of Requirements and Scope. | Monthly | Number | Number of data quality issues (where data is late, inaccurate or incomplete) | Monthly performance meeting | No issues | Between 1 and 2 issues | More than 2 issues | n/a
6 | Quality | Sub-contractor prompt payment | Demonstrate that the Consultant has complied with the Government policies, subject to any specific payment terms agreed with Supply Chain Partners. | Measured as the number of payments made by the Consultant outside of the 30 days stated within the Government fair payment charter. | Monthly | Number | Number of instances where sub-contractors' invoices have not been paid within 30 days. | Monthly performance meeting | No instances | Between 1 and 2 instances | More than 2 instances | n/a
7 | Quality | Consultants Resources and Staff Continuity | Provision of resources, with appropriate experience and skill level, and continuity of allocated staff. | The key criteria for measurement is the number of events where key persons are proposed and not accepted by the Employer, or where a key person is not proposed by the consultant within 3 weeks of being removed from providing the services Acceptance of key persons may include the following considerations: * Were resources for key roles with appropriate experience and skill allocated to the task ? * Was access to, and appropriate use of, Supply Chain partners evident? | Monthly | Number | Number of events where key persons are not proposed within 3 weeks by Consultant and accepted by the Employer. | Monthly performance meeting | All key personnel proposed accepted | 1-2 instances of rejection of key personnel | More than 2 instances of rejection of key personnel | n/a
The performance of the Consultant in the preceding month is classified as ‘Good’ if KPIs 1 to 5 are marked as Green, and KPIs 6 and 7 are marked as either Green or Amber. The performance of the Consultant in the preceding month is classified as ‘Poor’ if two or more of the KPIs are marked as Red. The performance of the Consultant in the preceding month is classified as ‘Requiring Improvement’ if the Key Performance Indicators are neither classified as ‘Good’ or ‘Poor.’