## COVER PAGE
SCHEDULES OF WORK
-in respect of-
COMPOST AREA ALTERATION WORKS
OPTIONS A, B & C
-at-
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
-for-
THE HORNIMAN PUBLIC MUSEUM &
PUBLIC PARK TRUST
Chartered Quantity Surveyors
Unit 83, Capital Business Centre
22 Carlton Road
South Croydon
January 2025 |  | Surrey, CR2 0BS

## CONTENTS
Schedules of Work
-in respect of-
Compost Area Alteration Works
Options A, B & C
-at-
100 London Road, Forest Hill, London, SE23 3PQ
-for-
The Horniman Public Museum &
Public Park Trust
- comprising -
Part 1 | - | Option A: Phase 1 works only
Part 2 | - | Option B: Phase 1 & 2 works (run concurrently)
Part 3 | - | Option C: Phase 1 & 2 works (run sequentially)
Summary
Appendix A | - | Detailed terms of the Conditions of Contract
Appendix B | - | Detailed terms of the Preliminaries

## 1 - OPTION A
Phase 1
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
COMPOST AREA ALTERATION WORKS
| PART 1 |  | = Contractor to insert pricing
OPTION A: PHASE 1 WORKS ONLY
£ p
GENERALLY
| 1.0.1 | In pricing the items that follow, the Contractor shall be deemed to have thoroughly inspected the tender documents and have acquainted himself with the site and the full extent / character of the items. The items have been split into the following priceable areas of work: | 0 | 0 | 0 | 0
1.1 - Preliminaries
1.2 - Temporary works
1.3 - Demolitions / Works on site
1.4 - Piling works
1.5 - Groundworks
1.6 - Steelwork
1.7 - Fencing work
| 1.0.2 | In pricing the Phase 1 works that follow the Contractor is to work on the assumption that only the works shown on drawing 210881-CON-XX-XX-DR-S-1000 are progressed | 0 | 0 | 0 | 0
0
|  | 1.1 - PRELIMINARIES |  |  |  | 0
0
|  | Following review of Appendix "A" and Appendix "B" the Contractor is to insert below his proposed costs in respect of the "Conditions of Contract" and "Preliminaries". In the event that no specific allowance is stated below the Contractor will be deemed to have covered elsewhere within the body of the pricing for the cost of fully complying with the terms detailed in Appendix "A" and "B". |  |  |  | 0
0
| 1.1.1 |  | 1 | Item |  | 0
0
| 1.1.2 |  | 1 | Item |  | 0
0
| 1.1.3 |  | 1 | Item |  | 0
0
| 1.1.4 |  | 1 | Item |  | 0
0
| 1.1.5 |  | 1 | Item |  | 0
0
| 1.1.6 |  | 1 | Item |  | 0
0
| 1.1.7 |  | 1 | Item |  | 0
0
| 1.1.8 |  | 1 | Item |  | 0
0
| 1.1.9 |  | 1 | Item |  | 0
0
| 1.1.10 |  | 1 | Item |  | 0
0
| 1.1.11 |  | 1 | Item |  | 0
0
| 1.1.12 |  | 1 | Item |  | 0
0
| 1.1.13 |  | 1 | Item |  | 0
0
| 1.1.14 |  | 1 | Item |  | 0
0
| 1.1.15 |  | 1 | Item |  | 0
0
0
0
0
|  | 1.2 - TEMPORARY WORKS |  |  |  | 0
0
|  | Temporary access |  |  |  | 0
0
| 1.2.1 | Notwithstanding the requirements stipulated in the preliminaries the Contractor is requested to price against this item for all necessary scaffolding / temporary access in undertaking the items of work so described in this document. | 1 | Item |  | 0
0
0
|  | Temporary works |  |  |  | 0
0
| 1.2.2 | Notwithstanding the requirements stipulated in the preliminaries the Contractor is requested to price against this item for all necessary temporary works including shoring / propping etc., in undertaking the items of work so described in this document. | 1 | Item |  | 0
0
0
0
0
|  | 1.3 - DEMOLITIONS / WORKS ON SITE |  |  |  | 0
0
|  | Work to existing Northern fence / gate line |  |  |  | 0
| 1.3.1 | Not applicable - No works specified | 0 | 0 | 0 | 0
0
0
|  | Work to existing Eastern retaining wall |  |  |  | 0
0
| 1.3.2 | Allow for carefully removing all existing timber sleepers; set aside for re-use | 1 | Item |  | 0
0
0
|  | Work to existing Southern retaining wall |  |  |  | 0
0
| 1.3.3 | Allow for carefully removing all existing timber sleepers; set aside for re-use | 1 | Item |  | 0
0
0
|  | Work to existing Western retaining wall |  |  |  | 0
0
| 1.3.4 | Allow for carefully removing all existing timber sleepers; set aside for re-use | 1 | Item |  | 0
0
| 1.3.5 | Remove existing metal columns down to ground level; dispose off site | 1 | Item |  | 0
0
0
0
0
|  | 1.4 - PILING WORKS |  |  |  | 0
0
| 1.4.1 | Contractor Designed Portion: Allow for designing, supplying and installing the following new isolated concrete piled foundations based on the information contained on drawing 210881-CON-XX-XX-DR-S-1000; the scope of works is to embrace the following: |  |  |  | 0
|  | • PHASE 1 - 5No piles to the Western retaining wall |  |  |  | 0
|  | • PHASE 1 - 3No piles to the South of the compost area in forming the new bay dividers | 0 | 0 | 0 | 0
0
0
|  | Borehole investigation works |  |  |  | 0
0
| 1.4.2 | Allow for undertaking a borehole investigation of the existing soil structure to enable the design of the piling works to be progressed | 1 | Item |  | 0
0
0
|  | Piling mat |  |  |  | 0
0
| 1.4.3 | Allow for providing a suitable piling mat | 1 | Item |  | 0
0
| 1.4.4 | extra for disposing of any surplus materials from the piling mat upon completion of the works | 1 | Item |  | 0
0
0
|  | Method statement |  |  |  | 0
0
| 1.4.5 | Allow for providing a detailed method statement | 1 | Item |  | 0
0
0
|  | Mobilisation |  |  |  | 0
0
| 1.4.6 | Mobilise plant, labour and equipment to site for the piling installation and clear away on completion | 1 | Item |  | 0
0
0
|  | Setting out |  |  |  | 0
0
| 1.4.7 | Allow for setting out the pile positions | 8 | No |  | 0
0
| 1.4.8 | Set up rig at each pile position; locations as indicated on drawing 210881-CON-XX-XX-DR-S-1000 | 8 | No |  | 0
0
0
|  | Piling |  |  |  | 0
0
|  | Allow for the design and installation of isolated concrete piled foundations; piles to be designed for 180kN unfactored lateral load on the pile head; as indicated on drawing 210881-CON-XX-XX-DR-S-1000 |  |  |  | 0
0
| 1.4.9 | in forming the 8No new piled foundations | 1 | Item |  | 0
0
| 1.4.10 | length of piles allowed for in forming the above = |  | m | 0 | 0
0
0
|  | Provisional piling items |  |  |  | 0
0
| 1.4.11 | Credit for reduction in the total piling meterage |  | m | 0 | 0
0
| 1.4.12 | Cost for increase in the total piling meterage |  | m | 0 | 0
0
| 1.4.13 | Rig standing time arising out of reasons beyond the contractor's control |  | hr | 0 | 0
0
0
|  | Integrity testing |  |  |  | 0
0
| 1.4.14 | Integrity test and report on the installed piles | 1 | Item |  | 0
0
0
|  | Concrete cube testing |  |  |  | 0
0
| 1.4.15 | Allow for providing concrete cube tests (PROVISIONAL) | 2 | No |  | 0
0
0
0
0
|  | 1.5 - GROUNDWORKS |  |  |  | 0
0
|  | Piling attendance works (ALL APPROXIMATE) |  |  |  | 0
0
|  | The following piling attendance works have been measured approximate and as such will be subject to remeasurement upon completion. To achieve this the Contractor will be required to provide a detailed site diary of the operations undertaken, relevant dates and the operatives names involved. |  |  |  | 0
0
| 1.5.1 | Delivery of plant to site / removal upon completion | 1 | Item |  | 0
0
| 1.5.2 | Labour and plant attendance; excavator with driver (APPROXIMATE) | 2 | Days |  | 0
0
| 1.5.3 | Labour and plant attendance; dumper with driver (APPROXIMATE) | 2 | Days |  | 0
0
| 1.5.4 | Labour and plant attendance; general operative (APPROXIMATE) | 2 | Days |  | 0
0
| 1.5.5 | Disposal of pile arisings; off site; clean inert (APPROXIMATE) | 100 | m3 |  | 0 | 0 | 79 | m3
0
| 1.5.6 | Cutting pile to level | 8 | No |  | 0
0
0
|  | Repair work to existing concrete slab (ALL APPROXIMATE) |  |  |  | 0
0
|  | Allow for the following works in resolving damaged areas of the existing concrete ground slab; the following quantities are all approximate and as such will be subject to remeasurement upon completion. To achieve this the Contractor will be required to provide a marked up drawing indicating the scope of the works undertaken. |  |  |  | 0
0
| 1.5.7 | Saw cut slab to straight line | 40 | m |  | 0
0
| 1.5.8 | Break out existing concrete and dispose off site; thickness not exceeding 150mm | 10 | m2 |  | 0
0
| 1.5.9 | Excavation of sub-base in removing soft spots; maximum depth not exceeding 0.25m | 3 | m3 |  | 0
0
| 1.5.10 | Filling to make up levels; DOT Type 1; average thickness not exceeding 0.25m | 3 | m3 |  | 0
0
| 1.5.11 | Dowel bar reinforcment between existing / new areas of concrete; H10 dowel drilled into edge of exposed slab and secured with Hilti HIT-HY 200-A adhesive; length not exeeding 500mm | 100 | No |  | 0
0
| 1.5.12 | In situ concrete; grade C28/35; in infilling slab to match adjacent levels | 3 | m3 |  | 0
0
0
|  | Provisional sums |  |  |  | 0
0
| 1.5.13 | Provide the Provisional Sum of £1,500.00 for remedial work to the existing hard / soft landscaping outside the compost area | 1 | Item | 1500 | 1500
0
0
0
0
|  | 1.6 - STEELWORK |  |  |  | 0
0
| 1.6.1 | Note: All steelwork connections not shown on Conisbee's drawings represent a Contractor Designed Portion of the works | 0 | 0 | 0 | 0
0
| 1.6.2 | Allow for forming all new steel framing for the Phase 1 compost area works; include for: all new steel columns/PFC's/angles/plates etc., hot dipped galvanised, zinc coating, holding down bolts, steelwork fixings, welding etc.; all as indicated on drawing 210881-CON-XX-XX-DR-S-1000; scope of works to include: |  |  |  | 0
|  | [1] Columns; 254 x 254 x 89 UC; 8.00m long with 6.00m of the column embedded into new concrete pile - 8No |  |  |  | 0
|  | [2] PFC; 230 x 90 x 32mm; 2.00m long; welded to existing UC column in forming new bay dividers - 3No |  |  |  | 0
|  | [3] PFC; 230 x 90 x 32mm; 2.00m long; welded to new UC column in forming South West corner - 1No | 1 | Item |  | 0
0
0
0
0
|  | 1.7 - FENCING WORK |  |  |  | 0
0
|  | Concrete panelling |  |  |  | 0
0
|  | Supply and install new reinforced precast concrete panels at low level to the following retaining walls; each panel to be formed such that it has capacity to support 44 kN/m2 unfactored surcharge load from one or both sides; panels cut if necessary and fitted between the UC steel sections with hardwood packing / Sikaflex 292i high strength marine adhesive in ensuring a snug fit |  |  |  | 0
0
| 1.7.1 | as described to existing Eastern retaining wall; each panel to be sized 100 x 1000 x 2600mm (at maximum) - 4No | 1 | Item |  | 0
0
| 1.7.2 | as described to existing Southern retaining wall; each panel to be sized 100 x 1000 x 2600mm (at maximum) - 4No | 1 | Item |  | 0
0
| 1.7.3 | as described to the South of the compost area in forming the new bay dividers; each panel to be sized 100 x 1000 x 2600mm (at maximum) - 3No | 1 | Item |  | 0
0
| 1.7.4 | as described to new Western retaining wall; each panel to be sized 150 x 1000 x 2600mm (at maximum) - 5No | 1 | Item |  | 0
0
0
|  | Timber sleepers - reinstallation of existing |  |  |  | 0
0
| 1.7.5 | Take from store the existing timber sleepers and, if deemed to be in sound condition, allow for reinstalling between the new / existing steel columns; in the event that the sleeper is too thick for the "I-section" columns allow for forming a notch locally; include for hardwood packing / Sikaflex 292i high strength marine adhesive in ensuring a snug fit (APPROXIMATE) | 60 | No |  | 0
0
| 1.7.6 | extra over last for the additional material cost in providing new untreated harwood sleepers, in lieu of reusing the existing, if there is deemed to be an unsufficient quantity of existing sleepers available; new sleepers are to be sized 250 x 150 x 2600mm long (APPROXIMATE) | 20 | No |  | 0
0
0
| 1.7.7 | Allow for the disposal off site of redundant timber sleeper if deemed unsuitable for re-use (APPROXIMATE) | 40 | No |  | 0
0
0
0
0
0
PART 1 - OPTION A
[5 empty] | To Summary £ | 1500

## 2 - OPTION B
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
COMPOST AREA ALTERATION WORKS
PART 2 |  | = Contractor to insert pricing
OPTION B: PHASE 1 & 2 WORKS (RUN CONCURRENTLY)
£ p
GENERALLY
2.0.1 | In pricing the items that follow, the Contractor shall be deemed to have thoroughly inspected the tender documents and have acquainted himself with the site and the full extent / character of the items. The items have been split into the following priceable areas of work: | 0 | 0 | 0 | 0
2.1 - Preliminaries
2.2 - Temporary works
2.3 - Demolitions / Works on site
2.4 - Piling works
2.5 - Groundworks
2.6 - Steelwork
2.7 - Fencing work
2.02 | In pricing the OPTION B works that follow the Contractor is to work on the assumption that the Phase 1 and 2 works, as shown on drawings 210881-CON-XX-XX-DR-S-1000 and 210881-CON-XX-XX-DR-S-1001, are run concurrently. | 0 | 0 | 0 | 0
0
| 2.1 - PRELIMINARIES |  |  |  | 0
0
2.1.1 |  | 1 | Item |  | 0
0
2.1.2 |  | 1 | Item |  | 0
0
2.1.3 |  | 1 | Item |  | 0
0
2.1.4 |  | 1 | Item |  | 0
0
2.1.5 |  | 1 | Item |  | 0
0
2.1.6 |  | 1 | Item |  | 0
0
2.1.7 |  | 1 | Item |  | 0
0
2.1.8 |  | 1 | Item |  | 0
0
2.1.9 |  | 1 | Item |  | 0
0
2.1.10 |  | 1 | Item |  | 0
0
2.1.11 |  | 1 | Item |  | 0
0
2.1.12 |  | 1 | Item |  | 0
0
2.1.13 |  | 1 | Item |  | 0
0
2.1.14 |  | 1 | Item |  | 0
0
2.1.15 |  | 1 | Item |  | 0
0
0
| 2.2 - TEMPORARY WORKS |  |  |  | 0
0
| Temporary access |  |  |  | 0
0
2.2.1 | Notwithstanding the requirements stipulated in the preliminaries the Contractor is requested to price against this item for all necessary scaffolding / temporary access in undertaking the items of work so described in this document. | 1 | Item |  | 0
0
0
| Temporary works |  |  |  | 0
0
2.2.2 | Notwithstanding the requirements stipulated in the preliminaries the Contractor is requested to price against this item for all necessary temporary works including shoring / propping etc., in undertaking the items of work so described in this document. | 1 | Item |  | 0
0
0
0
| 2.3 - DEMOLITIONS / WORKS ON SITE |  |  |  | 0
0
0
| Phase 1 works |  |  |  | 0
0
| Allow for the following works described within Option A (Phase 1 works): |  |  |  | 0
2.3.1 | • Item 1.3.2 | 1 | Item |  | 0
2.3.2 | • Item 1.3.3 | 1 | Item |  | 0
2.3.3 | • Item 1.3.4 | 1 | Item |  | 0
2.3.4 | • Item 1.3.5 | 1 | Item |  | 0
0
0
| Phase 2 works |  |  |  | 0
0
2.3.5 | Allow for clearing the area of the Phase 2 works of all vegetation, fencing etc.; scope as shown on drawing 210881-CON-XX-XX-DR-S-1001 | 1 | Item |  | 0
0
2.3.6 | extra for removing the existing entry gate / supporting posts which were stated as being retained in the Phase 1 scheme | 1 | Item |  | 0
0
0
0
0
| 2.4 - PILING WORKS |  |  |  | 0
0
2.4.1 | Contractor Designed Portion: Allow for designing, supplying and installing the following new isolated concrete piled foundations based on the information contained on drawing 210881-CON-XX-XX-DR-S-1000; the scope of works is to embrace the following: |  |  |  | 0
| • PHASE 1 - 5No piles to the Western retaining wall |  |  |  | 0
| • PHASE 1 - 3No piles to the South of the compost area in forming the new bay dividers | 0 | 0 | 0 | 0
| • PHASE 2 - 16No piles to the perimeter of the Phase 2 area |  |  |  | 0
| • PHASE 2 - 4No piles in forming bay dividers within the Phase 2 area |  |  |  | 0
0
0
| Borehole investigation works |  |  |  | 0
0
2.4.2 | Allow for undertaking a borehole investigation of the existing soil structure to enable the design of the piling works to be progressed | 1 | Item |  | 0
| Piling mat |  |  |  | 0
0
2.4.3 | Allow for providing a suitable piling mat | 1 | Item |  | 0
0
2.4.4 | extra for disposing of any surplus materials from the piling mat upon completion of the works | 1 | Item |  | 0
0
0
| Method statement |  |  |  | 0
0
2.4.5 | Allow for providing a detailed method statement | 1 | Item |  | 0
0
0
| Mobilisation |  |  |  | 0
0
2.4.6 | Mobilise plant, labour and equipment to site for the piling installation and clear away on completion | 1 | Item |  | 0
0
0
| Setting out |  |  |  | 0
0
2.4.7 | Allow for setting out the pile positions | 28 | No |  | 0
0
2.4.8 | Set up rig at each pile position; locations as indicated on drawing 210881-CON-XX-XX-DR-S-1000 | 28 | No |  | 0
0
0
| Piling |  |  |  | 0
0
| Allow for the design and installation of isolated concrete piled foundations; piles to be designed for 180kN unfactored lateral load on the pile head; as indicated on drawing 210881-CON-XX-XX-DR-S-1000 |  |  |  | 0
0
2.4.9 | in forming the 28No new piled foundations | 1 | Item |  | 0
0
2.4.10 | length of piles allowed for in forming the above = |  | m | 0 | 0
0
0
| Provisional piling items |  |  |  | 0
0
2.4.11 | Credit for reduction in the total piling meterage |  | m | 0 | 0
0
2.4.12 | Cost for increase in the total piling meterage |  | m | 0 | 0
0
2.4.13 | Rig standing time arising out of reasons beyond the contractor's control |  | hr | 0 | 0
0
0
| Integrity testing |  |  |  | 0
0
2.4.14 | Integrity test and report on the installed piles | 1 | Item |  | 0
0
0
| Concrete cube testing |  |  |  | 0
0
2.4.15 | Allow for providing concrete cube tests (PROVISIONAL) | 7 | No |  | 0
0
0
0
0
| 2.5 - GROUNDWORKS |  |  |  | 0
0
| Piling attendance works (ALL APPROXIMATE) |  |  |  | 0
0
| The following piling attendance works have been measured approximate and as such will be subject to remeasurement upon completion. To achieve this the Contractor will be required to provide a detailed site diary of the operations undertaken, relevant dates and the operatives names involved. |  |  |  | 0
0
2.5.1 | Delivery of plant to site / removal upon completion | 1 | Item |  | 0
0
2.5.2 | Labour and plant attendance; excavator with driver (APPROXIMATE) | 7 | Days |  | 0
0
2.5.3 | Labour and plant attendance; dumper with driver (APPROXIMATE) | 7 | Days |  | 0
0
2.5.4 | Labour and plant attendance; general operative (APPROXIMATE) | 7 | Days |  | 0
0
2.5.5 | Disposal of pile arisings; off site; clean inert (APPROXIMATE) | 300 | m3 |  | 0 | 0 | 277 | m3
0
2.5.6 | Cutting pile to level | 28 | No |  | 0
0
0
| Phase 1 - Repair work to existing concrete slab (ALL APPROXIMATE) |  |  |  | 0
0
| Allow for the following works in resolving damaged areas of the existing concrete ground slab; the following quantities are all approximate and as such will be subject to remeasurement upon completion. To achieve this the Contractor will be required to provide a marked up drawing indicating the scope of the works undertaken. |  |  |  | 0
0
2.5.7 | Saw cut slab to straight line | 40 | m |  | 0
0
2.5.8 | Break out existing concrete and dispose off site; thickness not exceeding 150mm | 10 | m2 |  | 0
0
2.5.9 | Excavation of sub-base in removing soft spots; maximum depth not exceeding 0.25m | 3 | m3 |  | 0
0
2.5.10 | Filling to make up levels; DOT Type 1; average thickness not exceeding 0.25m | 3 | m3 |  | 0
0
2.5.11 | Dowel bar reinforcment between existing / new areas of concrete; H10 dowel drilled into edge of exposed slab and secured with Hilti HIT-HY 200-A adhesive; length not exeeding 500mm | 100 | No |  | 0
0
2.5.12 | In situ concrete; grade C28/35; in infilling slab to match adjacent levels | 3 | m3 |  | 0
0
0
| Phase 2 - New concrete ground slab |  |  |  | 0
0
| Allow for the following works in forming the new reinforced concrete ground slab to the Phase 2 area; as indicated on drawing 210881-CON-XX-XX-DR-S-1001: |  |  |  | 0
0
2.5.13 | Excavate and level the ground over the area of the new pavings | 1 | Item |  | 0
0
2.5.14 | Dispoal off site of surplus excavated materials | 1 | Item |  | 0
0
2.5.15 | Construct the new reinforced concrete ground slab; include for: surface treatment, compacting existing ground; "210mm capping layer 6F1, 6F2, 6F4 OR 6F5 to clause 600 table 6/1 of SHW"; "150mm highways agency Type 1 sub-base to clause 803 of SHW" and "175mm thick reinforced concrete slab Grade C28/35 with A393 mesh at top and bottom with 50mm cover" | 1 | Item |  | 0
0
0
| Provisional sums |  |  |  | 0
0
2.5.16 | Provide the Provisional Sum of £1,500.00 for remedial work to the existing hard / soft landscaping outside the compost area | 1 | Item | 1500 | 1500
0
0
0
0
| 2.6 - STEELWORK |  |  |  | 0
0
2.6.1 | Note: All steelwork connections not shown on Conisbee's drawings represent a Contractor Designed Portion of the works | 0 | 0 | 0 | 0
| Phase 1 works |  |  |  | 0
0
| Allow for the following works described within Option A (Phase 1 works): |  |  |  | 0
2.6.2 | • Item 1.6.2 | 1 | Item |  | 0
0
0
| Phase 2 works |  |  |  | 0
0
2.6.3 | Allow for forming all new steel framing for the Phase 2 compost area works; include for: all new steel columns/PFC's/angles/plates etc., hot dipped galvanised, zinc coating, holding down bolts, steelwork fixings, welding etc.; all as indicated on drawing 210881-CON-XX-XX-DR-S-1001; scope of works to include: |  |  |  | 0
| [1] Columns; 254 x 254 x 89 UC; 8.00m long with 6.00m of the column embedded into new concrete pile; in forming the perimeter king post retaining walls - 16No |  |  |  | 0
| [2] Columns; 254 x 254 x 89 UC; 8.00m long with 6.00m of the column embedded into new concrete pile; in forming the bay dividers - 4No |  |  |  | 0
| [3] PFC; 230 x 90 x 32mm; 2.00m long; welded to new UC column in forming the bay dividers - 4No | 1 | Item |  | 0
0
0
0
0
| 2.7 - FENCING WORK |  |  |  | 0
0
| Phase 1 works |  |  |  | 0
0
| Allow for the following works described within Option A (Phase 1 works): |  |  |  | 0
2.7.1 | • Item 1.7.1 | 1 | Item |  | 0
2.7.2 | • Item 1.7.2 | 1 | Item |  | 0
2.7.3 | • Item 1.7.3 | 1 | Item |  | 0
2.7.4 | • Item 1.7.4 | 1 | Item |  | 0
2.7.5 | • Item 1.7.5 | 60 | No |  | 0
2.7.6 | • Item 1.7.6 | 20 | No |  | 0
2.7.7 | • Item 1.7.7 | 40 | No |  | 0
0
0
| Phase 2 - Concrete panelling |  |  |  | 0
0
| Supply and install new reinforced precast concrete panels at low level to the following retaining walls; each panel to be formed such that it has capacity to support 44 kN/m2 unfactored surcharge load from one or both sides; panels cut if necessary and fitted between the UC steel sections with hardwood packing / Sikaflex 292i high strength marine adhesive in ensuring a snug fit |  |  |  | 0
0
2.7.8 | as described in forming the perimeter walls to the Phase 2 area; each panel to be sized 150 x 1000 x 2600mm (at maximum) - 15No | 1 | Item |  | 0
0
2.7.9 | as described in forming the new bay dividers; each panel to be sized 100 x 1000 x 2600mm (at maximum) - 4No | 1 | Item |  | 0
0
0
| Phase 2 - New timber sleepers |  |  |  | 0
0
2.7.10 | Note: In the event that enough existing timber sleepers are available to enable and new units do not need to be provided the rates provided in Part 1 (see items 1.7.5 & 1.7.6) are to be reused in agreeing the Final Account. | 0 | 0 | 0 | 0
0
2.7.11 | Allow for providing new untreated harwood sleepers and for installing between the new / existing steel columns; in the event that the sleepers are too thick for the "I-section" columns allow for forming a notch locally; include for hardwood packing / Sikaflex 292i high strength marine adhesive in ensuring a snug fit (APPROXIMATE) | 60 | No |  | 0
0
0
| Phase 2 - New gate |  |  |  | 0
0
2.7.12 | Contractor Designed Portion: Allow for designing and installing a new self supporting, single leaf, steel framed gate and post with timber infill panelling; gate to be set within 4032mm opening between 2No new UC columns; height of gate to match the adjacent new king post retaining wall; steelwork to be black powder coated; hinge / post arrangement to be such that the gate can swing open 180 degrees to prevent the gate blocking the adjacent pedestrian footpath; design to be such that a 25 year service life guarantee is provided; all as indicated on drawing 210881-CON-XX-XX-DR-S-1001 | 1 | Item |  | 0
0
0
0
0
0
PART 2 - OPTION B
|  |  |  | To Summary £ | 1500

## 3 - OPTION C
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
COMPOST AREA ALTERATION WORKS
PART 3 |  | = Contractor to insert pricing
OPTION C: PHASE 1 & 2 WORKS (RUN SEQUENTIALLY WITH A BREAK)
£ p
GENERALLY
3.0.1 | The OPTION C works are to embrace the full scope / specification of the Phase 1 and 2 works that are shown on drawings 210881-CON-XX-XX-DR-S-1000 and 210881-CON-XX-XX-DR-S-1001 and is detailed within Part 2 (OPTION B). The nett difference between the two options is that in Option C the two Phases of work are to run sequentially with a break between them. The length of this break is still to be dertermined but the Contractor is price the below on the basis that this period will not exceed 12 months. To achieve this it is confirrmed Sectional Completion will be incorporated into the formal contract, with the addition of a break clause to enable the works to be terminated, if deemed necessary, after the first Section of works (i.e. Phase 1). | 0 | 0 | 0 | 0
| PART 2 TOTAL (OPTION B) |  |  |  | 1500
0
| ADDITIONAL COSTS |  |  |  | 0
0
3.1.1 | The Contractor is invited to insert below any additonal costs that will be incurred arising out of a break being introduced between the execution of the Phase 1 and Phase 2 works. Particular issues that the Contractor may want to consider include the following: |  |  |  | 0
| • Additional Preliminary costs |  |  |  | 0
| • Additional costs associated with demobilising / remobilising to site |  |  |  | 0
| • Additional sub-contractor costs |  |  |  | 0
| • Inflation |  |  |  | 0
| Note: The above is not intended to be an exhaustive list and as such the Contractor is to consider and set down below the costed ramifications of a delay being introduced. | 0 | 0 | 0 | 0
0
0
0
3.1.2 |  | 1 | Item |  | 0
0
3.1.3 |  | 1 | Item |  | 0
0
3.1.4 |  | 1 | Item |  | 0
0
3.1.5 |  | 1 | Item |  | 0
0
3.1.6 |  | 1 | Item |  | 0
0
3.1.7 |  | 1 | Item |  | 0
0
3.1.8 |  | 1 | Item |  | 0
0
3.1.9 |  | 1 | Item |  | 0
0
3.1.10 |  | 1 | Item |  | 0
0
3.1.11 |  | 1 | Item |  | 0
0
3.1.12 |  | 1 | Item |  | 0
0
3.1.14 |  | 1 | Item |  | 0
0
3.1.15 |  | 1 | Item |  | 0
0
3.1.16 |  | 1 | Item |  | 0
0
3.1.17 |  | 1 | Item |  | 0
0
3.1.18 |  | 1 | Item |  | 0
0
3.1.19 |  | 1 | Item |  | 0
0
3.1.20 |  | 1 | Item |  | 0
0
0
0
0
0
0
PART 1 - OPTION B
|  |  |  | To Summary £ | 1500

## SUMMARY
.
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
COMPOST AREA ALTERATION WORKS
SUMMARY
| OPTION A |  |  |  | £ p
| Part 1 | - | Option A: Phase 1 works only |  | 1500
| Part 2 | - | Option B: Phase 1 & 2 works run concurrently - EXCLUDED |  | 0
| Part 3 | - | Option C: Phase 1 & 2 works run sequentially - EXCLUDED |  | 0
|  |  |  | Sub-total £ | 1500
| - |  | Provide the Provisional sum of £7,500.00 for contingencies |  | 7500
|  |  |  | OPTION A - TOTAL £ | 9000 | #
OPTION B
| Part 1 | - | Option A: Phase 1 works only - Excluded |  | 0
| Part 2 | - | Option B: Phase 1 & 2 works run concurrently |  | 1500
| Part 3 | - | Option C: Phase 1 & 2 works run sequentially - EXCLUDED |  | 0
|  |  |  | Sub-total £ | 1500
| - |  | Provide the Provisional sum of £15,000.00 for contingencies |  | 15000
|  |  |  | OPTION B - TOTAL £ | 16500 | #
OPTION C
| Part 1 | - | Option A: Phase 1 works only - Excluded |  | 0
| Part 2 | - | Option B: Phase 1 & 2 works run concurrently - EXCLUDED |  | 0
| Part 3 | - | Option C: Phase 1 & 2 works run sequentially |  | 1500
|  |  |  | Sub-total £ | 1500
| - |  | Provide the Provisional sum of £15,000.00 for contingencies |  | 15000
|  |  |  | OPTION B - TOTAL £ | 16500 | #
Name of Contractor:
Address:
Date: