RMSPS PENSION ADMINISTRATION SERVICES AGREEMENT

# SCHEDULE 6.1

TRANSITION PLAN

Transition Plan

## INTRODUCTION

### This Schedule:

#### defines the process for the preparation and implementation of the Outline Transition Plan and Detailed Transition Plan; and

#### identifies the Transition Milestones (and associated Deliverables) including the Transition Milestones which trigger payment to the Supplier of the applicable Milestone Payments following the issue of the applicable Milestone Achievement Certificate.

## OUTLINE TRANSITION PLAN

### The Outline Transition Plan is set out in Annex 1.

### All changes to the Outline Transition Plan shall be subject to the Change Control Procedure provided that the Supplier shall not attempt to postpone any of the Transition Milestones using the Change Control Procedure or otherwise (except in accordance with Clause 31 (Authority Cause)).

## APPROVAL OF THE DETAILED TRANSITION PLAN

### The Supplier shall submit a draft of the Detailed Transition Plan to the Authority for approval by the 'Deliverable Approved Date' for the Detailed Transition Plan as set out in the Outline Transition Plan or where no 'Deliverable Approved Date' is specified within forty (40) Working Days of the Effective Date.

### The Supplier shall ensure that the draft Detailed Transition Plan:

#### incorporates all of the Transition Milestones and Milestone Dates set out in the Outline Transition Plan;

#### incorporates Milestones for the delivery of key components of the Supplier Solution, including:

      - configuring the Supplier System (including the core administration Database), and the data migration and reconciliation;

      - implementation of Calculation Engines and Scheme Calculations;

      - implementation of electronic document management (including back scanning of existing electronic documents), and reconciliation;

      - implementation of all system outputs (performance reporting, calculation outputs, Member letters, etc.);

      - all processes (including agreed payroll, technical and organisational (including the Joint Member Data Interface(s)) and organisational interfaces between the Supplier System and those systems used by the RMPP Administrator(s) and other key Stakeholders); and

      - workflow management technology;

#### outlines all the Deliverables, resourcing requirements and governance for each stage of the Transition Services, including details of any contingency that has been allowed for in planning the Transition Services;

#### includes (as a minimum) the Supplier's proposed timescales in respect of the following for each of the Transition Milestones:

      - the completion of each design document;

      - the completion of the build/configuration phase;

      - the completion of any Testing and assurance to be undertaken in accordance with Schedule 6.2 (Transition Testing Assurance Procedures and Project Testing Procedures); and

      - training and roll-out activities;

#### clearly outlines:

      - roles and responsibilities of each Party (including the Supplier, Sub-contractors, the Authority, Incumbent Provider);

      - profiles of the Supplier Personnel resources to be deployed by the Supplier to undertake the Transition;

      - the discovery work to be undertaken by the Supplier; and

      - the degree of automation targeted including the 95% calculation automation target set out in the Business Systems Requirements in Schedule 2.1 (Services Descriptions), how this will be agreed with the Authority, and the process for managing non-automated components;

#### clearly outlines all the steps required to implement the Transition Milestones to be Achieved in the next eighteen (18) months, together with a high level plan for the rest of the programme, in conformity with the Authority Requirements;

#### clearly outlines the required roles and responsibilities of both Parties and the Incumbent Provider, including staffing requirements; and

#### is produced using a software tool as specified, or agreed by the Authority.

### Prior to the submission of the draft Detailed Transition Plan to the Authority in accordance with Paragraph 3.1, the Authority shall have the right:

#### to review any documentation produced by the Supplier in relation to the development of the Detailed Transition Plan, including:

##### details of the Supplier's intended approach to the Detailed Transition Plan and its development;

##### copies of any drafts of the Detailed Transition Plan produced by the Supplier; and

##### any other work in progress in relation to the Detailed Transition Plan; and

#### to require the Supplier to include any reasonable changes or provisions in the Detailed Transition Plan.

### Following receipt of the draft Detailed Transition Plan from the Supplier, the Authority shall:

#### review and comment on the draft Detailed Transition Plan as soon as reasonably practicable; and

#### notify the Supplier in writing that it approves or rejects the draft Detailed Transition Plan no later than the date agreed by the Parties in accordance with the Review Plan or in the absence of such a date forty (40) Working Days after the date on which the draft Detailed Transition Plan is first delivered to the Authority.

### If the Authority rejects the draft Detailed Transition Plan:

#### the Authority shall inform the Supplier in writing of its reasons for its rejection; and

#### the Supplier shall then revise the draft Detailed Transition Plan (taking reasonable account of the Authority's comments) and shall re-submit a revised draft Detailed Transition Plan to the Authority for the Authority's approval within the time period agreed by the Parties in accordance with the Review Plan or in the absence of such a date twenty (20) Working Days of the date of the Authority's notice of rejection. The provisions of Paragraph 3.4 and this Paragraph 3.5 shall apply again to any resubmitted draft Detailed Transition Plan, provided that either Party may refer any disputed matters for resolution by the Dispute Resolution Procedure at any time.

### If the Authority approves the draft Detailed Transition Plan, it shall replace the Outline Transition Plan from the date of the Authority’s notice of approval.

## UPDATES TO AND MAINTENANCE OF THE DETAILED TRANSITION PLAN

### Following the approval of the Detailed Transition Plan by the Authority:

#### the Supplier shall submit a revised Detailed Transition Plan to the Authority every three (3) months starting three (3) months from the Deliverable Approved Date for the Detailed Transition Plan as set out in the Outline Transition Plan;

#### without prejudice to Paragraph 4.1(a), the Authority shall be entitled to request a revised Detailed Transition Plan at any time by giving written notice to the Supplier and the Supplier shall submit a draft revised Detailed Transition Plan to the Authority within ten (10) Working Days of receiving such a request from the Authority (or such longer period as the Parties may agree provided that any failure to agree such longer period shall be referred to the Dispute Resolution Procedure);

#### any revised Detailed Transition Plan shall (subject to Paragraph 4.2) be submitted by the Supplier for approval in accordance with the procedure set out in Paragraph 3; and

#### the Supplier’s performance against the Transition Plan shall be monitored at meetings of the Project Group for Transition Services to be established and governed in accordance with the governance structure set out in Schedule 8.1 (Governance). In preparation for such meetings, the current Detailed Transition Plan shall be provided by the Supplier to the Authority not less than five (5) Working Days in advance of each meeting of the Project Group for Transition Services.

### Save for any amendments which are of a type identified and notified by the Authority (at the Authority's discretion) to the Supplier in writing as not requiring approval, any material amendments to the Detailed Transition Plan shall be subject to review and agreement through the Change Control Procedure provided that:

#### any amendments to elements of the Detailed Transition Plan which are based on the contents of the Outline Transition Plan shall be deemed to be material amendments; and

#### in no circumstances shall the Supplier be entitled to alter or request an alteration to any Milestone Date except in accordance with Clause 31 (Authority Cause).

### Any proposed amendments to the Detailed Transition Plan shall not come into force until they have been approved in writing by the Authority.

## GOVERNMENT REVIEWS

The Supplier acknowledges that the Services may be subject to Government review at key stages of the project. The Supplier shall cooperate with any bodies undertaking such review and shall allow for such reasonable assistance as may be required for this purpose within the Charges.

# ANNEX 1: OUTLINE TRANSITION PLAN

[Redacted under FOIA s43, Commercial interests]