| Contract Management CHANGE CONTROL FORM- General – v. 4 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Contract Name: | Specialist Support for the Defence Support Network (Transformation) |  | Contract Ref. No. | CCS Reference: RM3793 Contract Number: CCCC16ABT (Variation Ref: CCCC16ABT - 01) |
| CUSTOMER CHANGE NOTICE (CCN) |  |  |  |  |
| REDACTED Ministry of Defence CCCC16ABT - 01 Initiated by: CCN Reference: Date CCN Raised by relevant party: 2nd May 2017 Customer Source of change: : STAGE 1 - CUSTOMER This is a variation to the Contract between the Crown Commercial Service Acting as Managing agent for the Ministry of Defence and Deloitte LLP. The Terms and Conditions of the Contract apply but with the following amendments: - Variation to the Contract end date – The original Contract term was 14th June 2016 to 14th March 2017, with an option to extend for a further three (3) months. The Authority now wishes to exercise the extension option. The proposed Contract end date will therefore be 13th June 2017. - Uplift in Contract Value – The original Contract value is £1,862,000 (Exc.VAT) It is proposed by the Authority to uplift the value by an additional £784, 000 (Exc. VAT) therefore bringing the overall total Contract value to £2,646, 000 (Exc. VAT). - Additional Deliverables – the Authority wishes to include the additional deliverables that are intrinsically linked to the scope of the original Contract, please refer to Annex 1 of this CCN for full details. Summary of proposals / requirements Proposed payment: In line with the existing terms and conditions of Contract and the proposed increased contract value of £2,646, 000.00 (excluding VAT). Required delivery date, with rationale: In line with the existing terms and conditions of Contract and the new proposed end date of 14th June 2017. Change authorised to proceed to Stage 2 (Customer organisation representative) ): 23/05/2017 REDACTED REDACTED Date Print Name & Position Signature 29th June 2017 Change authorised to proceed to Stage 2 (CCS representative): REDACTED REDACTED Date Print Name & Position Signature |  |  |  |  |
| STAGE 2 – SUPPLIER |  |  |  |  |
| Comments/ Caveats on requested change |  |  |  |  |
| 15th March 2017 Anticipated period from CCN being authorised by customer to start of related provision 15th March 2017 to 13th June 2017 Anticipated implementation period, if any Signed (Supplier Representative): REDACTED REDACTED Print Name & Position: 3rd July 2017 Date: Change authorised to proceed to Stage 4 (CCS): 4th July 2017 REDACTED REDACTED Signature Date Print Name & Position |  |  |  |  |
| STAGE 3 - CLARIFICATIONS |  |  |  |  |
| N/A Clarifications/ queries to supplier regarding Date: their proposals: Supplier Response Date: |  |  |  |  |
| STAGE 4 - CUSTOMER CCN SIGN-OFF TO PROCEED TO IMPLEMENTATION |  |  |  |  |
| No CCN Withdrawn: |  |  |  |  |
| By signing below, unless CCN is withdrawn, the Ministry of Defence agrees to pay Deloitte LLP the costs detailed in Stage 1, by deadlines agreed with the supplier, or as defined in the contract. |  |  |  |  |
| REDACTED REDACTED Signed (Customer Representative)): Print Name & Position 5 July 2017 Date: REDACTED Change authorised to proceed to implementation (CCS): REDACTED People Operations Lead - CCL Signature Print Name & Position 4th July 2017 Date: |  |  |  |  |
| STAGE 5 - CCN COMPLETION SIGN-OFF I confirm that the provision required under the CCN commenced in accordance with the customer requirements and supplier proposals in this CCN. Date provision required under the CCN commenced: Date Signed by Customer: In line with CCN 4th July 2017 REDACTED People Operations Lead - CCL Signed (Customer representative): REDACTED Print Name & Position |  |  |  |  |