## Sheet1
Highways England Confirmation of Task Order |  |  |  |  | Redacted under Section 40 and Section 43 of the FOI Act (2000)
Confidential and Commercially Sensitive Information which shall not be disclosed to third parties
Supplier: | Atkins
Project Title: | Arena Essex (Northlake) Development Proposal April 2019 – Task Order 3
Contract Ref. | 2589 | CPA No.: | 4094486 |  | BPA No.: | 4094933
PIN Description: | Development Planning 19-20 | Sub Pin: | 3 |  | PIN No.: | 564869
HE Reference: | SE 4 19/20ATK | HE Ordering Officer: |  |  | Redacted
Consultant Ref: | 5165058.511 | Consultant Contact: |  |  | Redacted
Start & End Date: | 05/04/2019 - 30/08/2019 | CTO Authorisation No.
Task Overview
Introduction and History: Atkins were tasked in the summer of 2018 to provide support to the Arena Essex Development Proposal. This was agreed as CTO SE 27 18_19ATK. Atkins (Redacted) continued to co-ordinate the task including completing a review of the SEARM and VISSIM model files provided by Arup with regular communication and progress calls/emails maintained with HE (Redacted) and Arup (Redacted). This was as per agreed scope in CTO SE 73 18_19ATK. HE stated the following to the applicant (ref: email from Redacted dated 18th March 2019): “The roundabouts at the A13/A126 junction are part of the SRN and the A13 is a route of near motorway standard. Therefore your proposed access on to the roundabout is contrary to the policy in Circular 02/2013 unless the strategic growth test is met. Whilst ‘strategic planned growth’ is not defined in the Circular we regard it as a development of the scale of a Garden Town or greater, so approximately 10,000 homes. Even if the strategic growth test is met you will need to demonstrate that there is no way that the development can take place without the proposed access. Your options identification and assessment exercise should include at least one option without a direct access to the SRN. We would be pleased to discuss the scope and objectives of the options identification and assessment exercise with you and Thurrock.” Methodology: Following a meeting in Thurrock on 28th March 2019, Atkins advised HE that the end of the agreed budget under the existing CTO was approaching, we will need to agree a further CTO to cover ongoing work, in particular further review of the modelling aspects and of the Options Assessment Report which is currently being prepared by Arup (review of which by Atkins was not covered under the existing CTO). In order to conclude the review of the VISSIM modelling undertaken by Arup, the following actions will be required: • Further liaison with Arup, to include participation in 2no. further telcons and 1no. technical face-to-face meeting. This further liaison is required to establish the following: o Confirm that suitable growth factors have been applied and the model is converged and stable from which inferences could be drawn; o Confirm that sensitivity tests have been undertaken to show that the model is gridlocked not due to lack of capacity in the network, and future mitigations have been considered; o Once the above is confirmed as being undertaken, be satisfied that the model would then be a suitable platform to infer any impact from the development. • Further review of updates to the VISSIM model; • Completion of TN summarising the reviews undertaken of the VISSIM model, including queries raised and responses provided by Arup. In order to conclude the review of the SEARM modelling undertaken by Arup, the following actions will be required: • Further liaison with Arup, to include participation in 2no. further telcons and 1no. technical face-to-face meeting. This further liaison is required to establish whether Arup’s revisions to the following elements of the SEARM model (as requested by Atkins) have remedied the problems identified: o VDM/Realism Tests o Journey Times o IP Trips o Comparison of Link Flows and Delays • Further review of updates to the SEARM model; • Completion of TN summarising the reviews undertaken of the SEARM model, including queries raised and responses provided by Arup. Atkins to review the Options Assessment Report currently being prepared by Arup, which should be prepared in accordance with Step 8 of Stage 1 of the HE Project Control Framework, and should address the following requirements: • Present a sound body of analysis to provide evidence of the problems and challenges and need for intervention; • Document the process of option generation, sifting and assessment. Decisions made on discarded options should be recorded, along with supporting evidence. The initial supporting evidence for feasible options should be summarised; • Identify the better-performing options to be taken forward for further, more detailed appraisal; cont under task objectives and milestones...
Task Objectives and Milestones
...cont Atkins will be required to determine the following from the review process: • Review of Arup’s justification in capacity terms for why a direct access onto the SRN at the A13/A126 southern roundabout is required; • Review whether Arup have presented a robust assessment of at least one option which provides access to the proposed development from the south (i.e. from A1306 Arterial Road West) only; • Review whether Arup have demonstrated why the proposals are considered to represent strategic development; • If this above has not been demonstrated, obtain confirmation from Arup that ‘special circumstances’ have been demonstrated (i.e. why the proposed development is unique) in order to obtain a departure from policy from DfT. The Atkins Task Lead (Redactedt) will also be required to: • Lead the task over a further 5-month period, with the task ending on 30th August 2019; • Participate in 2no. further telcons and 1no. face-to-face meeting with HE/Arup. Task Objectives: • Further review of the modelling aspects and of the Options Assessment Report which is currently being prepared by Arup. As per the previous task orders, the following will be expected: • To be familiar with the HE Licence and planning guidance in respect of new connections/links to the SRN. • Become familiar with the locality of the proposed Arena Essex proposals and of the general area and other development pressures. • Understand how Lakeside Shopping Centre expansion proposals impact the area. • Understand the demands of other developments on M25 J30. • Understand principles of ITS project (Atkins currently working with HE on this) on the locality. • Understand and track the Thurrock Council MRN (Major Road Network) submission for east facing slips at the dumbbell roundabout on the A13. • Arrange to meet with HE Spatial Planning Manager to discuss proposals as required. • Attend meetings/telcons as necessary with developers and/ or HE. Milestone • 30th August 2019
Task Outcomes
• To receive and comment on submissions from Arup and provide a response in the form of a note for HE use. • To have a good knowledge of the proposals. • To attend meetings/telcons to support HE officers or without HE attendance where the discussion is purely technical. • To react to and provide comment to HE on any phone conversations/meetings/submissions relating to the Arena Essex development proposal. • To monitor progress on the Arena Essex proposals and other development/spatial planning issues in the locality.
Project Risk and Management
Risks • The risks are around HE’s possible failure to engage with the developers appropriately and the consequence of that could be that the developer is not able to meet development timescales or financial risk profiles. • There is a risk to the HE strategic road network if the proposals for a new connection to the network are not assessed correctly. • There is a reputational risk to HE if the local planning authority cannot determine this application in accordance with their agreed PPA with the developer and HE are seen as holding back economic growth in the South Essex corridor. • Additional tasks and/or meetings will require additional budget, could affect programme and will be subject to agreement of an additional CE. Management • Contract management – Redacted • Contract co-ordinator – Redacted • Technical Lead – Redacted • Technical Reviewers – Redactedy/Redacted/RedactedRedacted/Redacted
Project Title: | Arena Essex (Northlake) Development Proposal April 2019 – Task Order 3 |  |  |  | HE Reference: | SE 4 19/20ATK
HE Project Sponsor | Sign: |  | Print Name: |  |  | Date:
Management Approver: | Sign: |  | Print Name: |  |  | Date:
Contractual Approval: |  |  | Print Name: |  |  | Date:
Fee Type: | Time Online
Notification of Non Conflict: | Redacted has signed the notification of non conflict or management of conflict for this task
Task History Record | Fee Estimate for the Task set out in this CTO | Invoiced Amount/Estimate this Financial Year |  | Date CTO Confirmed | Fee Amount Requested | HE Sponsor
SE 4 19/20ATK | 28709.8 | 0 |  |  | 28709.8 | Redacted
Fee Estimate / Fee Requested for the scope on this CTO |  |  |  |  | 28709.8
Carry over Amount from previous financial year |  |  |  |  | 0
Previously Invoiced Amount |  |  |  |  | 0
Cumulative Project Fee Estimate (this financial year) |  |  |  |  | 28709.8
Total Project Fee Estimate |  |  |  |  | 28709.8
Name | Grade | Hours |  | Hourly Rate | (£)
Redacted (Atkins Office) | Director | 4 | @ | Redacted | Redacted
Redacted (Atkins Office) | Principal Planner / Engineer | 8 | @ | Redacted | Redacted
Redacted (Atkins Office) | Senior Planner/Engineer | 124 | @ | Redacted | Redacted
Redacted (Atkins Office) | Principal Planner / Engineer | 52 | @ | Redacted | Redacted
Redacted (Atkins Office) | Assistant Planner/ Engineer | 32 | @ | Redacted | Redacted
Redacted (Atkins Office) | Principal Planner / Engineer | 16 | @ | Redacted | Redacted
Redacted (Atkins Office) | Director | 76 | @ | Redacted | Redacted
Redacted (Atkins Office) | Associate Director | 52 | @ | Redacted | Redacted
Redacted (Atkins Office) | Senior Planner/Engineer | 20 | @ | Redacted | Redacted
Redacted (Atkins Office) | Assistant Planner/ Engineer | 52 | @ | Redacted | Redacted
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
Date Produced: | 2019-04-04 |  | Works Total |  | 28709.8
Confidential and commercially sensitive information which shall not be disclosed to third parties
|  |  | Sub Total |  | 28709.8
|  |  | Expenses |  | 200
COMMERCIAL RESTRICTED / FINANCE FILE ONLY |  |  | Total |  | 28909.8