[image: image1.jpg]L
-
-
L
®
-
-
-




[image: image2.jpg]westwaddy ADP ‘





[image: image4.emf]


westwaddyADP



westwaddyADP



westwaddyADP











Schedule of Works 

For the Non-Conformist Chapel at

Fairmile Cemetery, Lower Assendon, Nr Henley on Thames, Oxon, RG9 6AA
For
Henley Town Council, Market Place, Henley on Thames RG9 2AQ

Description of the Works

The Non-Conformist Chapel at Fairmile Cemetery is a grade II Listed Building which has recently undergone extensive external repairs. The project is to carry out minor repairs to the interior and make-good internal decorations leading to installation of 408 timber niches to form a Columbarium. The works will include new electrical services for new lighting, security and fire alarms, new background electrical heating. 
The Chapel has no existing electrical, telephone and water services so new connections are to be made into the existing Cemetery mains.
Form of Contract

JCT Intermediate Building Contract with Contractor’s Design 2016
Contract Particulars

4th: Tender documents: Schedule of Works and drawings 685-C06, C07, C08, C09, C10, & C11. 
10th: CDM: The project is notifiable
1.1 Date for Completion of the Works: 12 weeks from the start date.

2.23.2: Date for Possession of Site: By agreement

2.23.2; Liquidated Damages: £500 per week

2.30 Rectification Period: 12 months

2.34.3 Contractor’s Design Portion: Heating and Electrical systems.

6.4.1 Contractor’s Public Liability Insurance: £10m for any single event.

6.7 Insurance: Option C Joint Names insurance by the Employer of Existing Structures.

Schedule of Works

External Works: 
Supply and install new telephone, electricity and water supply to the Chapel as shown on drawings 685-L01.

Internal refurbishments: 
Allow a provisional sum of £2,000 for plasterwork repairs. 
Allow a provisional sum of £3,000 for quarry floor tile repairs and replacements.

Supply and install new electrical installation as drawings.

Supply and install new electric heating as drawings.

Supply and install new lighting as drawings.

Supply and install new security system consisting 3 No. wireless PIRs, 2 No. door contacts, control unit, and internal siren linked to Redcare (by client) including door control system as described on the drawing.
Supply and install new water supply. 

Supply and install new telephone line as drawings.

Supply and install a sample timber niche for approval.

Supply and install Columbarium joinery for 408 niches as drawings.
Supply and install 2 No. 9Ltr dry powder fire extinguishers and 1.2x1.2m fire blanket.

Allow provisional sum of £2,500 for new bench and other fitments.

Please contact:
Liz Jones at Henley Town Council on 01491 576982 to arrange a site visit. 

l.jones@henleytowncouncil.gov.uk

[image: image3.emf]


westwaddyADP



westwaddyADP



westwaddyADP










West Waddy ADP LLP


The Malthouse • 60 East St Helen Street • Abingdon • Oxfordshire • OX14 5EB
01235 523139 • enquiries@westwaddy-adp.co.uk • www.westwaddy-adp.co.uk

