|  |  |  |  |
| --- | --- | --- | --- |
| **CHANGE CONTROL NOTICE (CCN)** | | | |
| **Contract Title:** | Contract for the Provision of **Spend Analysis on MCF3** (The Contract) | | |
| **Contract Reference:** | CCSO22A17 | **Contract Change Number:** | **1** |
| **Date CCN issued:** | 6 February 2023 | **Date Change Effective from:** | 7th of February 2023 |
| **Between**: The **Crown Commercial Services** (The Customer) and **Investigo Limited (**The Supplier)   1. The Contract is varied as follows:   1.1. This is a 143-day time extension, from the 7th of February 2023 to the 30th of June 2023. The Time extension is necessary because the supplier was not provided with all relevant information necessary to carry out their assigned tasks. By the time the information was made available there was insufficient time for the task to be completed to a satisfactory degree. It was therefore agreed to grant the supplier more time (extension) to carry out the assigned task.   1. Words and expressions in this Change Control Notice shall have the meanings given to them in the Contract. 2. The Contract, including any previous Contract changes, authorised in writing by both Parties, shall remain effective and unaltered except as amended by this Change Control Notice. | | | |
| **REDACTED TEXT under FOIA Section 40, Personal Information**  **REDACTED TEXT under FOIA Section 40, Personal Information**  Change authorised to proceed by: (Customer’s representative):  29/03/2023    Signature Print Name and Job Title Date | | | |
| **REDACTED TEXT under FOIA Section 40, Personal Information**  **REDACTED TEXT under FOIA Section 40, Personal Information**  5/4/23  Authorised for and on behalf of the Supplier:    Signature Print Name and Job Title Date | | | |
| **REDACTED TEXT under FOIA Section 40, Personal Information**  **REDACTED TEXT under FOIA Section 40, Personal Information**  29/03/2023  Authorised for and on behalf of the Customer:  Signature Print Name and Job Title Date | | | |