## Sheet1
Highways Agency Confirmation of Task Order
Supplier: | AECOM | Fee Request for this CTO |  | Redacted
Project Title: | A120 Millennium Way Slip Roads – Engineering Feasibility - Stage 1 – DX040.011 Inception & Data Collection
Contract Ref. | 114/2/1391/1 | CPA No.: | Redacted | BPA No.: | Redacted
PIN Description: | Redacted | Sub Pin: | Redacted | PIN No.: | Redacted
HA Reference: | EE 48 15/16AECOM | Start and End Date : |  | 21/09/2015 - 08/04/2016
Task Overview and Expected Outcomes
The A120 trunk road around Braintree experiences congestion in the AM, PM and Saturday peak periods. To alleviate the congestion Highways England, Essex County Council and Braintree District Council have identified a potential improvement scheme comprising the introduction of direct slip roads between the A120 and B1018 Millennium Way to the South East of the town. AECOM has been requested to assist in developing a preliminary Strategic Outline Business Case (pSOBC) for making the case for investment to the Department for Transport for making infrastructure improvements to this section of the Strategic Road Network to relieve existing and future capacity issues. Specific Tasks: This proposal is for an engineering feasibility study into possible east facing slip road connections between the A120 and Millennium Way at Braintree in Essex. AECOM will undertake this task in conjunction with other associated tasks concerning the Millennium Way slip roads. Emphasis will be on spatial fit of the connections to Millennium Way on either side of the existing A120 overbridge. Minimal impacts on the retail store and the electricity grid station will be sought. Some topographical survey work will be undertaken by AECOM to confirm available space in those areas. AECOM will obtain scheme cost information through Highways England's cost consultants Benchmark. Reporting will be provided on alternative layout options for the slip roads and preferred layout will be recommended based on the specialist and costing advice. Geotechnical scope of works Deliverables would be to inform whether a retaining wall solution for the slip roads would be possible given the likely ground conditions in the vicinity of the slip roads. Provide high-level advice to structures team on likely ground conditions in vicinity of bridges. This advice will be based on a desktop study of information that we can obtain from HE’s database or geological maps. Will need to get Project Sponsor to allow staff Access to HEs database (HAGDMS) although some borehole logs are available from BGS. Structures Team Scope of Works Assess the existing Millennium Way Bridge to see if we can move the proposed junctions away from shopping centre and substation i.e. to understand whether the slip roads junctions could be located on bridge structure and if not how close we can come to bridge structure. Assess the existing Railway bridge to the west of Millennium Way to see if it is feasible to move the existing retaining walls back closer to the abutments. The deliverables for this stage will be: BD101 forms for Millennium Way Bridge – this will include review and recording of previous assessment/design information to determine if Millennium Way Bridge will accept revised loading conditions. BD101 forms for the Railway bridge to reflect the proposed method of construction and suitability of the bridge abutments for movement of the retaining walls. This work assumes that HE are able to provide the As-built drawings and design info for these existing bridges. The work will be undertaken in four discrete stages as follows: Stage Description Output 1 Inception & Data Collection • Inception meeting with Client and Stakeholders • Review constraints and topographical survey information • Carry out site visit • Obtain utility services C2 information. We will use Atkins to undertake C2 • Procure topographical survey for critical spatial fit areas in conjunction with OS Mastermapping and LidAR information already held. • Progress Report
Task Objectives and Milestones
At this stage of the process the production of evidence can be used to produce information that can be documented for the development of an outline Business Case for option development.
Expected Project Outcomes
AECOM’s technical assistance will assist Highways England and partners Essex County Council and Braintree District Council to make a case for investment to the Department for Transport for making improvements to this section of the Strategic Road Network
Project Risk and Management
This fee proposal relates to Engineering inputs into developing the pSOBC Multi-disciplinary team inputs are required to complete the task. Project risks and exclusions are detailed below: 1. Only options taken forward from previous work completed by AECOM will be considered. Further options which may represent a better or worse solution, subsequently developed or put forward by others, are not included in this fee estimate. 2. Ground investigations and C3 Statutory Undertaker estimates are excluded from the proposal. 3. We will agree the cost of the topographical survey and Atkins C2 searches with Highways England before commissioning them. 4. Detailed Departures from Standards applications excluded 5. Pavement and Safety barrier design has also been excluded 6. Environmental surveys and assessment; traffic modelling and traffic signal junction modelling; cost benefit assessment are all excluded at this stage 7. Option costs will be developed by Highways England’s Commercial team. This input is critical to the completion of the task, if HE input is delayed or not provided this will impact upon the time and cost required to complete the task. 8. The outputs to be provided are based upon a reasonably limited level of detail and precision applicable to this stage of the appraisal process, with due consideration given to time, budget and information available. 9. We have also assumed that information relevant to the study will also be provided to assist with the study. 10. Programme is dependent in part upon the timely provision of information from third parties. AECOM cannot be held responsible for the timely provision of information that is outside of AECOM control.
HA Project Sponsor | Sign: |  | Print Name: |  | Date:
Management Approver: | Sign: |  | Print Name: |  | Date:
Contractual Approval: | Sign: |  | Print Name: |  | Date: