## Plan for Event & Office Spaces
ITEM | w/c 20 Feb |  |  |  |  | w/c 27 Feb |  |  |  |  | w/c 06 Mar |  |  |  |  | w/c 13 Mar |  |  |  |  | w/c 20 Mar |  |  |  |  | w/c 27 Mar |  |  |  |  | w/c 03 Apr |  |  |  |  | w/c 10 Apr |  |  |  |  | w/c 17 Apr |  |  |  |  | w/c 24 Apr |  |  |  |  | w/c 01 May |  |  |  |  | w/c 08 May |  |  |  |  | w/c 15 May |  |  |  |  | w/c 22 May |  |  |  |  | w/c 29 May
| M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
EOI notice issued | w/c 20 Feb T: 22
EOI submission period | w/c 20 Feb T: 22; w/c 27 Feb W: 1
EOI close date | bar: w/c 27 Feb W
EOIs scored against qualifying criteria | w/c 27 Feb T: 2; w/c 27 Feb F: 3
Tender notice issued to qualifying applicants | w/c 06 Mar M: 6
Tender submission period | w/c 06 Mar M: 6; w/c 20 Mar F: 24
Supplier questions accepted | w/c 06 Mar M: 6; w/c 13 Mar W: 15
Supplier site visits (on request) | w/c 13 Mar W: 15
Tender close date | w/c 20 Mar F: 24
Bids scored against awarding criteria | w/c 27 Mar M: 27; w/c 03 Apr T: 4
Supplier presentations (if required) | w/c 03 Apr M: 3
Contract awarded | w/c 03 Apr W: 5
Contract delivery period | w/c 03 Apr T: 6
Contract completion date | w/c 29 May W: 31