# Annex A

| Title of Project | Reduction of mammal predation on seabirds - assessing options and priorities |
| --- | --- |
| Date and Time for Return of Bids | 30th September 2024 @09:00 hours GMT |
| Contract Reference Number | C24-0619-1942 |
| Address for Bid Submission | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND BIDS DIRECTLY TO (name of project officers) OR A MEMBER OF THE JNCC PROCUREMENT TEAM VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the number below; (00 44 1733 866 988) |
| Contacts for Technical Information relating to this Project Specification | Unique Onyewueke Joint Nature Conservation Committee Email: unique.onyewueke@jncc.gov.uk Telephone: +441224 083515 |
| Contact for Queries Regarding the Procurement Procedure | Unique Onyewueke Joint Nature Conservation Committee Email: unique.onyewueke@jncc.gov.uk Telephone: +441224 083515 |
| Proposed Start Date | 21st October 2024 |
| Proposed End Date | 28th March 2025 |

Reduction of mammal predation on seabirds - assessing options and priorities

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Aims	3

3.	Project Background	3

4.	Project Objectives	3

5.	Project Objectives: Detailed Tasks	3

6.	Potential Follow-On Work	3

7.	Outputs	4

8.	Dissemination	4

9.	Timescale	4

10.	Health and Safety	4

11.	Product Specification	4

12.	Project Management	5

13.	Instructions for Bid Submission	5

14.	Evaluation Criteria	6

15.	Payment	7

16.	Additional Requirements	7

17.	References	7

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation

Our role is to provide scientific evidence, information, and advice to inform decisions to  protect the natural environment. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally, by:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/

## Project Aims

- Provide a suite of predator reduction options and opportunities for compensation to support delivery of OW in the UK and meet net zero and biodiversity targets.

- Provide a resource that can help to inform decision making by highlighting the risks of not undertaking biosecurity and the benefits of eradication.

- Contribute to the UK’s efforts in achieving Good Environmental Status for one of the UK indicators, B4: Invasive mammal presence on island seabird colonies.

## Project Background

The Collaboration in Offshore Wind Strategic Compensation (COWSC) initiative brings together industry, environmental NGOs, SNCBs, the UK Government and Devolved administrations to identify strategic compensation measures. Expert Group 2 was formed to identify potential compensation measures around predation reduction. Three potential measures were identified: predator eradication on islands, predator control and exclusion and biosecurity.

There are currently a number of seabird island SPAs that have non-native invasive mammals present as well as many other non-SPA seabird sites. Predator eradication involves a significant investment of resources and time to remove all target invasive mammals from an island until the island can be declared predator free. This is usually done using poison but for larger mammals can also include trapping and shooting. Once an island is predator-free biosecurity measures can be employed to maintain the predator-free status of the site. Significant strides have been made on biosecurity through the RSPB-led Biosecurity for Life project which has seen islands undertaking sufficient biosecurity measures increase from 20% to >90% (https://biosecurityforlife.org.uk/).

Predator control and exclusion is used to target impacts at colonies/sites where eradication is not possible, such as inshore islands which mammals can easily access by swimming and mainland colonies. Measures can include fences to prevent mammals accessing sensitive areas and reducing the density of predators using control such as trapping.

## Project Objectives

To meet the overall aims of this project (Section 2), the objectives are:

- Review of potential sites for management UK

- Prioritisation of species and locations

- Development of success criteria

- Adaptive management options

## Project Objectives: Detailed Tasks

The overarching objective of this project is to deliver a comprehensive list of locations in the UK for potential predator reduction/control, both islands and mainland. The work undertaken here should build on previous work in this area (Ratcliffe et al. 2009; Stanbury et al. 2017) and also be informed by the priorities identified by the Statutory Nature Conservation Bodies (SNCBs) and Government agencies (e.g. English Seabird Conservation and Recovery Pathway (ESCaRP)).

Stage 1 Review of potential sites for management UK

The first stage of the project will be to identify the seabird species to be considered for current and future compensation action, before a review of possible locations is explored based on the species list. The review should be based upon compensation needs: the seabird species affected, the number of birds that could be compensated for and should consider a wide-ranging geographic scope reflecting the potential for current and future OW development to ensure this work is relevant and useful in the future.

Based on the outcomes of the review and species identified, a review of the possible locations for management measures for each seabird species requiring compensation should be conducted. This can be based on the previous work done by Ratcliffe et al. (2009) and Stanbury et al. (2017) and should include a review of new evidence to reflect any eradications, incursions, changes to the conservation status of seabird species, changes to biosecurity plans or incursion response measures that have been put in place and any updated information on risk factors (such as new estimates of mammal predator swimming distances).  This review should expand on the previous work also include an assessment of mainland and inshore island sites where predation also occurs and where eradication is not an option, but predation reduction measures would be applicable and beneficial. A priority list of species to be considered will be provided to the contractor.

The review should also include site information that could contribute evidence on potential additionality for each location. This should include existing or planned management, site status (protected or not e.g. SPA/SSSI) and any other compensation/management actions being undertaken from a terrestrial standpoint.

Stage 2 Prioritisation of species and locations

A prioritisation stage should follow to provide a ranked list of options for management based on species and numbers of birds management measures have the potential to provide. Again this could be based on the work done by Ratcliffe et al.  and Stanbury et al. but does not necessarily have to follow the exact criteria and can be explored by the contractor with support from the steering group.  Although this project can be informed by previous work the priority species for this project may be different, e.g. razorbill and guillemot, and therefore it is essential that the focus is on identifying locations and quantifying the benefit for those key species.

As part of the prioritisation analysis should be carried out to assess the potential benefit of management for a particular site and for the species of interest to illustrate the potential gains and scale of impact. This should make use of the recent Seabirds Count and work done following HPAI outbreaks (https://base-prod.rspb-prod.magnolia-platform.com/dam/jcr:7983cad1-03f7-4ab4-b22e-c56c9f02243b/RSPB%20HPAI%20seabird%20counts%20report_Feb24.pdf) compared with previous census results to make estimates of the potential population size at UK colonies (islands and mainland) with and without mammal predators. This analysis should help prioritisation by developing an index of magnitude of impacts per species (similar to the work by Stanbury et al. 2017 which quantified conservation value) and per location which will indicate value for money and potential benefit for each scenario.

The contractor can run different scenarios of prioritisation, which scenario or combination of actions/management gives the best success, using different definitions e.g. habitat creation, cost, feasibility of success etc. to identify which is the best strategy.

As part of this criteria the location of the site should be included as a factor as creating habitat in certain regions/areas of the UK is likely to have greater benefits for species affected by climate change by improving population resilience. Proximity to offshore wind farms could also be considered to mitigate the possible impact of developments on new or increasing populations. To date the influence of climate change and warming have not been uniform and the impacts on seabirds are complex therefore this is not a straightforward issue but there are some areas of the UK that are likely to be able to support increased populations (e.g. Irish Sea). In addition creating more habitat in locations where populations are doing well, and where prey availability doesn’t seem to be a significant issue, should be prioritised and could be informed by specific colony trends. Consideration should also be given to sites where management or eradication may allow a species to occupy a former part of it’s distribution or extend it’s current distribution.

The resilience of the UK population network for each focal species should also be included in the prioritisation process. Some of the priority species have a significant proportion of their worldwide distribution within the UK and/or are restricted to a small number of SPAs. Increasing the number of potential sites or reducing the predation risk for these species in particular has the potential to have a considerable impact on population resilience.

The potential for unexpected consequences of compensation actions should be considered with respect to potential impacts on other species from increases in target species. For example, an increase in competition for prey.

Stage 3 Success Criteria

The contractor will then develop generalised success criteria to determine the conditions under which success is considered to have been achieved. There are two types of success criteria that should be considered here, the success of the management in reducing predation and the compensatory response (whether the species requiring compensation recovers sufficiently). There are several potential options that have been identified but as with the prioritisation criteria these could be changed or tailored.

- On offshore islands, achieve predator free status within 2-3 years of management starting.

- On offshore islands, maintain predator free status on islands through continued biosecurity measures and incursion response.

- On inshore islands (e.g. in Lochs), remove both native and non-native predators (e.g. mink) sufficiently each year to enable successful seabird breeding.

- On mainland breeding sites (e.g. on beaches), exclude native and non-native predators (e.g. fox, badger, cats) sufficiently each year to enable successful seabird breeding.

- On offshore islands where eradication has been achieved, the target seabird species has recolonised, expanded their existing distribution or achieved improved breeding success.

- On inshore islands and mainland breeding sites management allows seabird breeding success rates to increase.

Stage 4 Adaptive management for prioritised colonies

The final stage is to identify options for adaptive management should the management measures fail. This stage should be informed by the initial review of evidence and the methods used by others. This stage is not about finding alternative compensation options at a project level, this project is focussed on predation reduction but should look to identify alternative options in terms of individual site interventions. The management will depend on the success criteria developed and should ideally be novel, building on previous work for example, the Biosecurity for Life project which has already implemented biosecurity plans for the UK.

## Outputs

Any products or outputs submitted to JNCC [for publication] should adhere to JNCC’s house-style and should be produced in an accessible format (see product specification for more information).

## Product Specification

JNCC is committed to making its publicly available resources and documents accessible, in accordance with the Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.

Making material accessible means making sure it can be used by as many people as possible.  This includes those with:

- impaired vision

- motor difficulties

- cognitive impairments or learning disabilities

- deafness or impaired hearing

The outputs and material that JNCC publishes should be compliant with the Web Content Accessibility Guidelines version 2.1 AA standard.

To meet this standard, all reports and other documentation which are to be made publicly available must adhere to JNCC’s house-style (to be provided) and be produced using a JNCC template (to be provided), unless otherwise stated. (Project managers to note – there are two templates, please decide which is most appropriate, either the ‘standard’ template rather than the JNCC report template).  All reports (draft and final) should be provided electronically via email both as a Microsoft Word document and an Adobe PDF.

Copies of documentation associated with case studies should be provided in electronic format with an associated reference catalogue.

For any other outputs or products which are to be made publicly available through JNCC, evidence regarding how the accessibility standard will be reached should be included.

(Note for author if research project/contract: see EQA Policy Appendix 4 (Communicating Evidence Quality). Ensure that data management and storage requirements are stipulated taking into account relevant policy for data access. See https://jncc.gov.uk/about-jncc/corporate-information/evidence-quality-assurance/

## Dissemination (delete if non-applicable)

The products/outputs produced under this contract will be a JNCC product and shall not be published or disseminated without the written permission of JNCC. Outputs may at some point be published on the JNCC website and all material supplied as part of this contract shall remain copyright of JNCC. The findings from this contract will also be made available to staff within JNCC, the UK country nature conservation bodies (name them), Defra and (list other parties) (.

## Timescale

Provisional dates for delivery of the contact outputs are set out below. Exact dates are to be agreed at the start-up meeting based on Contractor and JNCC staff availability.

| Output | Provisional Date |
| --- | --- |
| Start-up meeting (UK) | w/c 21st October |
| - Review of potential sites for management UK | 21/10/2024 – 31/01/2025 |
| - Prioritised list of compensation options (incl. Assessment of additionality of compensation options) for UK | 21/10/2024 – 31/01/2025 |
| - Development of success criteria | 03/02/2025 – 28/03/2025 |
| - Adaptive management plan | 03/02/2025 – 28/03/2025 |

In agreeing exact dates please note that the potential for work under this contract to be funded into 2024/25 is subject to availability of funds.

## Health and Safety

The successful bidder is expected to follow appropriate Health & Safety procedures including adhering to JNCC’s policy on safeguarding. For further information  https://jncc.gov.uk/about-jncc/corporate-information/safeguarding/ and to be able to undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by the JNCC H&S Advisor).

Any incidents occurring within the contract period should be immediately reported to JNCC.

## Project Management

The successful Contractor shall nominate a project manager who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Name: Bryony Baker

Email: bryony.baker@jncc.gov.uk

Telephone: +441224 838640

Name: Ian Mitchell

Email:  ian.mitchell@jncc.gov.uk

Telephone: +441224 083512

## Instructions for Bid Submission

The bid submission should include the following:

A brief summary of the bidder’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract and delivering the detailed tasks identified within each objective. This should be sufficiently detailed to allow assessment against the evaluation criteria (Section 14);

A detailed project plan (including Gantt chart) with proposed work programme and an estimate of time required to achieve each objective;

A draft Table of Contents for the final report;

Details of Quality Control procedures to be followed (note for author if research project/contract: see EQA Policy Appendix 1 (Bias, Conflicting Evidence and Uncertainty) and EQU Policy Appendix 3 (Quality Assurance of Expert Knowledge and Opinion):

Details of the bidder’s own internal Quality Management System;

Details of the Project Team including their roles and experience, an estimate of their time input into each task and CVs of all personnel who will be involved in the contract/project; please ensure all CVs MUST be attached as a separate PDF documentation from the proposal, so that we can meet our JNCC GDPR retention policy requirements.

Availability of the Project Team for a start-up meeting in Peterborough or Aberdeen (Project Manager to complete. Please state whether  it will be a virtual meeting)

Overall quote for the contract to include:

  - Day rates for all members of the Project Team;

  - Rates for attending start-up, interim and final meetings in Peterborough or Aberdeen (costs for travel and accommodation are attached, and should be used. These rates are analogous to the civil service rates).

  - Costs and time allocation should be clearly allocated to specific tasks within this contract/project; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and if so, provide their VAT registration number.

The following documentation (to submit in a zip folder separate from the proposal):

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates;

  - Copies of any appropriate risk assessments;

  - Copies of your company's modern slavery and or safeguarding statement or policy and;

  - Copies of any environmental policies should you have them.

In addition, note that the bid submission should provide sufficient information to allow assessment against the evaluation criteria outlined in Section 14.

## Evaluation Criteria (Note to Project Managers evaluation table below is a guide and can be adapted to suit individual project requirements) delete brackets once Annex A finalised

JNCC is not bound to accept the lowest priced or any bid. Having the technical expertise and experience to complete the work to a high standard and being able to complete it within the timescale are of the essence for this contract.

The bid evaluation may be undertaken by a panel consisting of JNCC staff and staff members from Defra.  Unless otherwise stated in your bid submission, bids will be forwarded to these agencies for evaluation purposes only. (Project Manager to state who will undertake the evaluation, whether JNCC and/or other agencies)

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Maximum Score | Score |
| --- | --- | --- | --- |
| 1. Quality of Bid (55% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal particularly work programme and deliverables | 10 |  |
|  | Understanding of, and relevance to, the requirements in particular the adequacy of outputs and understanding of biosecurity, predator management in conservation, compensation for UK Offshore Wind developments | 10 |  |
|  | Proposed approach is scientifically sound and robust, and is based on excellent technical knowledge of sources of data, studies, analytical approaches and requirements | 10 |  |
|  | Realism and measurability of outputs | 5 |  |
|  | Evidence provided of how accessibility standards will be met | 5 |  |
|  | Identification and proposed solutions to potential risks/issues | 5 |  |
|  | Serious weaknesses which threaten success | 5 |  |
|  | Probability of success | 5 |  |
|  | Sub Total | 55 |  |
| 2. Details of Contractor (20% of the total for the three assessment categories) |  |  |  |
|  | Expertise, experience, and balance of team | 12 |  |
|  | Clarity and credibility of contingency plan to mitigating potential problem risks (e.g. if important team members drop out) | 8 |  |
|  | Sub Total | 20 |  |
| 3. Cost (25% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation | 10 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 7 |  |
|  | Clarity of each team member’s contribution, appropriateness of ratio of senior to junior staff time and value added | 8 |  |
|  | Sub Total | 25 |  |
| Total Score |  | 100 |  |

## Payment

Unless a payment schedule is stated in your submission and agreed by JNCC project manager. Payment will be made on completion of the objectives following the submission of invoice(s) and based on the satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key outputs.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates/fees given.

The bidder is expected to supply all necessary equipment, software, licences, etc. to carry out the obligations required under the contract.

## References

Stanbury, A., Thomas, S., Aegerter, J., Brown, A., Bullock, D., Eaton, M., Lock, L., Luxmoore, R., Roy, S., Whitaker, S. and Oppel, S., 2017. Prioritising islands in the United Kingdom and crown dependencies for the eradication of invasive alien vertebrates and rodent biosecurity. European Journal of Wildlife Research, 63, pp.1-13.

Ratcliffe, N., Mitchell, I.A.N., Varnham, K., Verboven, N. and Higson, P., 2009. How to prioritize rat management for the benefit of petrels: a case study of the UK, Channel Islands and Isle of Man. Ibis, 151(4), pp.699-708.

Where UK mentioned this also included Crown Dependencies.