## Timeline & Fee Drawdown
Britten Pears Arts
| SUSTAINABILITY CONSULTANT FEE PROPOSAL (CH2, HR1, HR2, HR3) | [16 empty] | Workstream key: |  |  | Concert Hall FOH and Heating & Renewables (CH2, CH3, HR1, HR2, HR3)
RESOURCE SUMMARY AND PRICING SCHEDULE
|  |  |  | 2021 |  |  |  |  | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | Total
|  |  |  | M | A | M | J | J | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
| Task |  | Duration
SINGLE CONTRACT TRADITIONAL PROCUREMENT
Stage 0 Strategic Definition and Stage 1 - Preparation and Brief
Stage 2 - Concept Design
Stage 3 - Developed Design
Stage 4 - Technical Design
Tender Period / Evaluation / Appointment
Stage 5 - Mobilisation
Stage 5 - Construction
Stage 6 - Handover and Closeout
Stage 7 - In Use (Rectification Period)
| AVERAGE DAYS PER MONTH |  |  | 2024 J: 2024; 2025 J: 2025; 2026 J: 2026; 2027 J: 2027; 2028 J: 2028 | Total
|  |  |  | M | A | M | J | J | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
| Name | Role
#REF! | A | X | [6 empty] | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [19 empty] | 41
| B | Y | [6 empty] | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [19 empty] | 42
#REF! | C | Z | [6 empty] | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [19 empty] | 43
0
| TOTAL DAYS PER MONTH |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126
FEE DRAWDOWN PER MONTH
|  |  |  | 2024 J: 2024; 2025 J: 2025; 2026 J: 2026; 2027 J: 2027; 2028 J: 2028 | Total
|  |  |  | M | A | M | J | J | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
| Resource | Year | Rate
| A | 2024 | 100 | M: 0; A: 0; M: 0; J: 0; J: 0; 2028 A: 0; 2028 M: 0; 2028 J: 0; 2028 J: 0; 2028 A: 0; 2028 S: 0; 2028 O: 0; 2028 N: 0; 2028 D: 0 | 0
|  | 2025 | 100 | 2024 J: 200; 2024 F: 100; 2024 M: 100; 2024 A: 100; 2024 M: 100; 2024 J: 100; 2024 J: 100; 2024 A: 100; 2024 S: 100; 2024 O: 100; 2024 N: 100; 2024 D: 0; 2028 A: #VALUE!; 2028 M: #VALUE!; 2028 J: #VALUE!; 2028 J: #VALUE!; 2028 A: #VALUE!; 2028 S: #VALUE!; 2028 O: #VALUE!; 2028 N: #VALUE!; 2028 D: #VALUE! | 1200
|  | 2026 | 100 | 2025 J: 100; 2025 F: 100; 2025 M: 100; 2025 A: 100; 2025 M: 100; 2025 J: 100; 2025 J: 100; 2025 A: 100; 2025 S: 100; 2025 O: 100; 2025 N: 100; 2025 D: 100 | 1200
|  | 2027 | 100 | 2026 J: 100; 2026 F: 100; 2026 M: 100; 2026 A: 100; 2026 M: 100; 2026 J: 100; 2026 J: 100; 2026 A: 100; 2026 S: 100; 2026 O: 100; 2026 N: 100; 2026 D: 100 | 1200
|  | 2028 | 100 | 2027 J: 100; 2027 F: 100; 2027 M: 100; 2027 A: 100; 2027 M: 100; 2027 J: 0; 2027 J: 0; 2027 A: 0; 2027 S: 0; 2027 O: 0; 2027 N: 0; 2027 D: 0; 2028 J: 0; 2028 F: 0; 2028 M: 0 | 500
| B | 2024 | 100 | M: 0; A: 0; M: 0; J: 0; J: 0; 2028 A: 0; 2028 M: 0; 2028 J: 0; 2028 J: 0; 2028 A: 0; 2028 S: 0; 2028 O: 0; 2028 N: 0; 2028 D: 0 | 0
|  | 2025 | 100 | M: 0; A: 0; M: 0; J: 0; J: 0; 2024 J: 300; 2024 F: 100; 2024 M: 100; 2024 A: 100; 2024 M: 100; 2024 J: 100; 2024 J: 100; 2024 A: 100; 2024 S: 100; 2024 O: 100; 2024 N: 100; 2024 D: 0; 2028 A: 0; 2028 M: 0; 2028 J: 0; 2028 J: 0; 2028 A: 0; 2028 S: 0; 2028 O: 0; 2028 N: 0; 2028 D: 0 | 1300
|  | 2026 | 100 | 2025 J: 100; 2025 F: 100; 2025 M: 100; 2025 A: 100; 2025 M: 100; 2025 J: 100; 2025 J: 100; 2025 A: 100; 2025 S: 100; 2025 O: 100; 2025 N: 100; 2025 D: 100 | 1200
|  | 2027 | 100 | 2026 J: 100; 2026 F: 100; 2026 M: 100; 2026 A: 100; 2026 M: 100; 2026 J: 100; 2026 J: 100; 2026 A: 100; 2026 S: 100; 2026 O: 100; 2026 N: 100; 2026 D: 100 | 1200
|  | 2028 | 100 | 2027 J: 100; 2027 F: 100; 2027 M: 100; 2027 A: 100; 2027 M: 100; 2027 J: 0; 2027 J: 0; 2027 A: 0; 2027 S: 0; 2027 O: 0; 2027 N: 0; 2027 D: 0; 2028 J: 0; 2028 F: 0; 2028 M: 0 | 500
| C | 2024 | 100 | M: 0; A: 0; M: 0; J: 0; J: 0; 2028 A: 0; 2028 M: 0; 2028 J: 0; 2028 J: 0; 2028 A: 0; 2028 S: 0; 2028 O: 0; 2028 N: 0; 2028 D: 0 | 0
|  | 2025 | 100 | M: 0; A: 0; M: 0; J: 0; J: 0; 2024 J: 400; 2024 F: 100; 2024 M: 100; 2024 A: 100; 2024 M: 100; 2024 J: 100; 2024 J: 100; 2024 A: 100; 2024 S: 100; 2024 O: 100; 2024 N: 100; 2024 D: 0; 2028 A: 0; 2028 M: 0; 2028 J: 0; 2028 J: 0; 2028 A: 0; 2028 S: 0; 2028 O: 0; 2028 N: 0; 2028 D: 0 | 1400
|  | 2026 | 100 | 2025 J: 100; 2025 F: 100; 2025 M: 100; 2025 A: 100; 2025 M: 100; 2025 J: 100; 2025 J: 100; 2025 A: 100; 2025 S: 100; 2025 O: 100; 2025 N: 100; 2025 D: 100 | 1200
|  | 2027 | 100 | 2026 J: 100; 2026 F: 100; 2026 M: 100; 2026 A: 100; 2026 M: 100; 2026 J: 100; 2026 J: 100; 2026 A: 100; 2026 S: 100; 2026 O: 100; 2026 N: 100; 2026 D: 100 | 1200
|  | 2028 | 100 | 2027 J: 100; 2027 F: 100; 2027 M: 100; 2027 A: 100; 2027 M: 100; 2027 J: 0; 2027 J: 0; 2027 A: 0; 2027 S: 0; 2027 O: 0; 2027 N: 0; 2027 D: 0; 2028 J: 0; 2028 F: 0; 2028 M: 0; 2028 A: 0; 2028 M: 0; 2028 J: 0; 2028 J: 0; 2028 A: 0; 2028 S: 0; 2028 O: 0; 2028 N: 0; 2028 D: 0 | 500
| Travel & Disbursements |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
|  |  | Fee £ | 0 | 0 | 0 | 0 | 0 | 900 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 0 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 12600
#REF!
32000000
#REF!

## Resource Summary
RESOURCE SCHEDULE
SUSTAINABILITY CONSULTANT FEE PROPOSAL (CH2, HR1, HR2, HR3)
Notes:
1. Please insert the number of days per RIBA stage and per workstream.
2. Please adapt rows for resources if required.
3. Please only adapt fields left in white.
Concert Hall FOH and Heating & Renewables (CH2, HR1, HR2, HR3)
Resource Level | Resource Name | Resource Dayrate | RIBA STAGE
|  |  | Preparation |  | Design | [5 empty] | Construction |  | Handover & Close out |  | Use |  | TOTAL
|  |  | 0-1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 1 - 6
|  |  | Days | Cost | Days | Cost | Days | Cost | Days | Cost | Days | Cost | Days | Cost | Days | Cost | Total Days Per Resource Head | % | Total Cost Per Resource Head | %
Director |  | 100 | 2 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 100% | 200 | #REF!
Associate |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | #REF!
Senior Professional |  | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | #REF!
Project Professional |  | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | #REF!
| Total No.of Days per RIBA stage |  | 2 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 100% | 200 | #REF!
[13 empty] | Total Days |  |  |  | 2
[13 empty] | Total Cost |  |  |  | 200
[13 empty] | Total Cost |  |  |  | #REF!

## Fee Summary
|  | Concert Hall FOH and Heating & Renewables (CH2, HR1, HR2,HR3) |  | TOTAL
| Construction Cost | 1930000 |  | 1930000
| Fee % | 0.01036% |  | 0.01036%
| Total | 200 |  | 200
Gateway | %
RIBA 0&1 | 100% |  | 200 | 200
RIBA 2 | 0% |  | 0 | 0
RIBA 3 | 0% |  | 0 | 0
RIBA 4 & Procurement | 0% |  | 0 | 0
RIBA 5 | 0% |  | 0 | 0
RIBA 6 | 0% |  | 0 | 0
RIBA 7 | 0% |  | 0 | 0
Totals | 100% |  | 200 | 200

## CM Single Stage Trad (hidden)
Winchester College - New Boarding Houses Project
COST MANAGEMENT FEE PROPOSAL
RESOURCE SUMMARY - AVERAGE DAYS PER MONTH
|  |  |  | 2021 | [9 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | Total
|  |  |  | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | N | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
| Task |  | Duration
SINGLE CONTRACT TRADITIONAL PROCUREMENT
| Stage 1 - Feasibility |  | 3 Months
| Stage 2 - Concept Design |  | 3 Months
| Stage 3 - Developed Design |  | 4 Months
| Planning Application |  | 3 Months
| Stage 4 - Technical Design |  | 8 Months
| Tender Preperation (incl BoQ) |  | 1 Month
| Tender Period |  | 3 Months
| Tender Report & Appointment |  | 6 Weeks
| Stage 5 - Mobilisation |  | 6 Weeks
| Stage 5 - Construction |  | 14 Months
| Stage 6 - Final Account |  | 2 Months
| Stage 7 - End of Rectification Period |  | 1 Month
| AVERAGE DAYS PER MONTH |  |  | 2021 A: 2021; 2024 J: 2022; 2025 J: 2023; 2026 J: 2024; 2027 J: 2025; 2028 J: 2026 | Total
|  |  |  | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
| Name | Role
#REF! | Nav Kang | Director |  | 2021 S: 4; 2021 O: 4; 2021 N: 4; 2021 D: 4; 2022 J: 4; 2022 F: 4; 2022 M: 4; 2022 A: 4; 2022 M: 4; 2022 J: 4; 2022 J: 4; 2022 A: 4; 2022 S: 4; 2022 O: 4; 2022 N: 4; 2022 D: 4; 2023 J: 4; 2023 F: 4; 2023 M: 2; 2023 A: 2; 2023 M: 2; 2023 J: 2; 2023 J: 2; 2023 A: 2; 2023 S: 2; 2023 O: 2; 2023 N: 2; 2023 D: 2; 2024 J: 2; 2024 F: 2; 2024 M: 2; 2024 A: 2; 2024 M: 2; 2024 J: 2; 2024 J: 2 | 106
| James Crampsie | Senior Cost Consultant |  | 2021 S: 4; 2021 O: 4; 2021 N: 6; 2021 D: 6; 2022 J: 6; 2022 F: 10; 2022 M: 8; 2022 A: 8; 2022 M: 8; 2022 J: 8; 2022 J: 8; 2022 A: 8; 2022 S: 8; 2022 O: 12; 2022 N: 2; 2022 D: 2; 2023 J: 8; 2023 F: 8; 2023 M: 2; 2023 A: 2; 2023 M: 2; 2023 J: 2; 2023 J: 2; 2023 A: 2; 2023 S: 2; 2023 O: 2; 2023 N: 2; 2023 D: 2; 2024 J: 2; 2024 F: 2; 2024 M: 2; 2024 A: 2; 2024 M: 2; 2024 J: 2; 2024 J: 2; 2025 A: 0.5 | 158.5
#REF! | Ben Crampsie | Cost Consultant |  | 2021 S: 4; 2021 O: 4; 2021 N: 4; 2021 D: 4; 2022 J: 4; 2022 F: 4; 2022 M: 4; 2022 A: 4; 2022 M: 4; 2022 J: 4; 2022 J: 4; 2022 A: 4; 2022 S: 8; 2022 O: 8; 2022 N: 4; 2022 D: 4; 2023 J: 6; 2023 F: 6; 2023 M: 4; 2023 A: 4; 2023 M: 4; 2023 J: 4; 2023 J: 4; 2023 A: 4; 2023 S: 4; 2023 O: 4; 2023 N: 4; 2023 D: 4; 2024 J: 4; 2024 F: 4; 2024 M: 4; 2024 A: 4; 2024 M: 4; 2024 J: 4; 2024 J: 4; 2025 A: 1 | 153
| Gokhan Hassan | Senior MEP Cost Consultant |  | 2021 N: 1; 2022 F: 2; 2022 J: 2; 2022 S: 2; 2022 O: 2; 2023 J: 2; 2023 F: 1; 2023 A: 0.5; 2023 M: 0.5; 2023 J: 0.5; 2023 J: 0.5; 2023 A: 0.5; 2023 S: 0.5; 2023 O: 0.5; 2023 N: 0.5; 2023 D: 0.5; 2024 J: 0.5; 2024 F: 0.5; 2024 M: 0.5; 2024 A: 0.5; 2024 M: 0.5; 2024 J: 0.5; 2024 J: 0.5; 2025 A: 1 | 21
| Senior Consultant(s) | BoQ Preperation |  | 2022 S: 10; 2022 O: 10 | 20
|  | Travel & Disbursements | [71 empty] | 36 | bar: 2021 S to 2024 J; 2025 A
| TOTAL DAYS PER MONTH |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 15 | 14 | 14 | 20 | 16 | 16 | 16 | 18 | 16 | 16 | 32 | 36 | 10 | 10 | 20 | 19 | 8 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 458.5
FEE DRAWDOWN PER MONTH
|  |  |  | 2021 A: 2021; 2022 J: 2022; 2023 J: 2023; 2024 J: 2024; 2025 J: 2025; 2026 J: 2026 | Total
|  |  |  | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Proposed fee drawdown
| Nav Kang | 2023 | 250 | M: 0; A: 0; M: 0; J: 0; J: 0; 2021 A: 0; 2021 S: 1000; 2021 O: 1000; 2021 N: 1000; 2021 D: 1000; 2026 A: 0; 2026 M: 0; 2026 J: 0; 2026 J: 0; 2026 A: 0; 2026 S: 0; 2026 O: 0; 2026 N: 0; 2026 D: 0 | 4000
|  | 2024 | 250 | 2022 J: 1000; 2022 F: 1000; 2022 M: 1000; 2022 A: 1000; 2022 M: 1000; 2022 J: 1000; 2022 J: 1000; 2022 A: 1000; 2022 S: 1000; 2022 O: 1000; 2022 N: 1000; 2022 D: 1000; 2026 A: #VALUE!; 2026 M: #VALUE!; 2026 J: #VALUE!; 2026 J: #VALUE!; 2026 A: #VALUE!; 2026 S: #VALUE!; 2026 O: #VALUE!; 2026 N: #VALUE!; 2026 D: #VALUE! | 12000
|  | 2025 | 262.5 | 2023 J: 1050; 2023 F: 1050; 2023 M: 525; 2023 A: 525; 2023 M: 525; 2023 J: 525; 2023 J: 525; 2023 A: 525; 2023 S: 525; 2023 O: 525; 2023 N: 525; 2023 D: 525 | 7350
|  | 2026 | 275.625 | 2024 J: 551.25; 2024 F: 551.25; 2024 M: 551.25; 2024 A: 551.25; 2024 M: 551.25; 2024 J: 551.25; 2024 J: 551.25; 2024 A: 0; 2024 S: 0; 2024 O: 0; 2024 N: 0; 2024 D: 0 | 3858.75
|  | 2027 | 289.4062 | 2025 J: 0; 2025 F: 0; 2025 M: 0; 2025 A: 0; 2025 M: 0; 2025 J: 0; 2025 J: 0; 2025 A: 0; 2025 S: 0; 2025 O: 0; 2025 N: 0; 2025 D: 0; 2026 J: 0; 2026 F: 0; 2026 M: 0 | 0
| James Crampsie | 2023 | 250 | M: 0; A: 0; M: 0; J: 0; J: 0; 2021 A: 0; 2021 S: 1000; 2021 O: 1000; 2021 N: 1500; 2021 D: 1500; 2026 A: 0; 2026 M: 0; 2026 J: 0; 2026 J: 0; 2026 A: 0; 2026 S: 0; 2026 O: 0; 2026 N: 0; 2026 D: 0 | 5000
|  | 2024 | 250 | M: 0; A: 0; M: 0; J: 0; J: 0; 2022 J: 1500; 2022 F: 2500; 2022 M: 2000; 2022 A: 2000; 2022 M: 2000; 2022 J: 2000; 2022 J: 2000; 2022 A: 2000; 2022 S: 2000; 2022 O: 3000; 2022 N: 500; 2022 D: 500; 2026 A: 0; 2026 M: 0; 2026 J: 0; 2026 J: 0; 2026 A: 0; 2026 S: 0; 2026 O: 0; 2026 N: 0; 2026 D: 0 | 22000
|  | 2025 | 262.5 | 2023 J: 2100; 2023 F: 2100; 2023 M: 525; 2023 A: 525; 2023 M: 525; 2023 J: 525; 2023 J: 525; 2023 A: 525; 2023 S: 525; 2023 O: 525; 2023 N: 525; 2023 D: 525 | 9450
|  | 2026 | 275.625 | 2024 J: 551.25; 2024 F: 551.25; 2024 M: 551.25; 2024 A: 551.25; 2024 M: 551.25; 2024 J: 551.25; 2024 J: 551.25; 2024 A: 0; 2024 S: 0; 2024 O: 0; 2024 N: 0; 2024 D: 0 | 3858.75
|  | 2027 | 289.4062 | 2025 J: 0; 2025 F: 0; 2025 M: 0; 2025 A: 144.7031; 2025 M: 0; 2025 J: 0; 2025 J: 0; 2025 A: 0; 2025 S: 0; 2025 O: 0; 2025 N: 0; 2025 D: 0; 2026 J: 0; 2026 F: 0; 2026 M: 0 | 144.7031
| Ben Crampsie | 2023 | 250 | M: 0; A: 0; M: 0; J: 0; J: 0; 2021 A: 0; 2021 S: 1000; 2021 O: 1000; 2021 N: 1000; 2021 D: 1000; 2026 A: 0; 2026 M: 0; 2026 J: 0; 2026 J: 0; 2026 A: 0; 2026 S: 0; 2026 O: 0; 2026 N: 0; 2026 D: 0 | 4000
|  | 2024 | 250 | M: 0; A: 0; M: 0; J: 0; J: 0; 2022 J: 1000; 2022 F: 1000; 2022 M: 1000; 2022 A: 1000; 2022 M: 1000; 2022 J: 1000; 2022 J: 1000; 2022 A: 1000; 2022 S: 2000; 2022 O: 2000; 2022 N: 1000; 2022 D: 1000; 2026 A: 0; 2026 M: 0; 2026 J: 0; 2026 J: 0; 2026 A: 0; 2026 S: 0; 2026 O: 0; 2026 N: 0; 2026 D: 0 | 14000
|  | 2025 | 262.5 | 2023 J: 1575; 2023 F: 1575; 2023 M: 1050; 2023 A: 1050; 2023 M: 1050; 2023 J: 1050; 2023 J: 1050; 2023 A: 1050; 2023 S: 1050; 2023 O: 1050; 2023 N: 1050; 2023 D: 1050 | 13650
|  | 2026 | 275.625 | 2024 J: 1102.5; 2024 F: 1102.5; 2024 M: 1102.5; 2024 A: 1102.5; 2024 M: 1102.5; 2024 J: 1102.5; 2024 J: 1102.5; 2024 A: 0; 2024 S: 0; 2024 O: 0; 2024 N: 0; 2024 D: 0 | 7717.5
|  | 2027 | 289.4062 | 2025 J: 0; 2025 F: 0; 2025 M: 0; 2025 A: 289.4062; 2025 M: 0; 2025 J: 0; 2025 J: 0; 2025 A: 0; 2025 S: 0; 2025 O: 0; 2025 N: 0; 2025 D: 0; 2026 J: 0; 2026 F: 0; 2026 M: 0 | 289.4062
| Gokhan Hassan | 2023 | 300 | M: 0; A: 0; M: 0; J: 0; J: 0; 2021 A: 0; 2021 S: 0; 2021 O: 0; 2021 N: 300; 2021 D: 0; 2026 A: 0; 2026 M: 0; 2026 J: 0; 2026 J: 0; 2026 A: 0; 2026 S: 0; 2026 O: 0; 2026 N: 0; 2026 D: 0 | 300
|  | 2024 | 300 | M: 0; A: 0; M: 0; J: 0; J: 0; 2022 J: 0; 2022 F: 600; 2022 M: 0; 2022 A: 0; 2022 M: 0; 2022 J: 600; 2022 J: 0; 2022 A: 0; 2022 S: 600; 2022 O: 600; 2022 N: 0; 2022 D: 0; 2026 A: 0; 2026 M: 0; 2026 J: 0; 2026 J: 0; 2026 A: 0; 2026 S: 0; 2026 O: 0; 2026 N: 0; 2026 D: 0 | 2400
|  | 2025 | 315 | 2023 J: 630; 2023 F: 315; 2023 M: 0; 2023 A: 157.5; 2023 M: 157.5; 2023 J: 157.5; 2023 J: 157.5; 2023 A: 157.5; 2023 S: 157.5; 2023 O: 157.5; 2023 N: 157.5; 2023 D: 157.5 | 2362.5
|  | 2026 | 330.75 | 2024 J: 165.375; 2024 F: 165.375; 2024 M: 165.375; 2024 A: 165.375; 2024 M: 165.375; 2024 J: 165.375; 2024 J: 165.375; 2024 A: 0; 2024 S: 0; 2024 O: 0; 2024 N: 0; 2024 D: 0 | 1157.625
|  | 2027 | 347.2875 | 2025 J: 0; 2025 F: 0; 2025 M: 0; 2025 A: 347.2875; 2025 M: 0; 2025 J: 0; 2025 J: 0; 2025 A: 0; 2025 S: 0; 2025 O: 0; 2025 N: 0; 2025 D: 0; 2026 J: 0; 2026 F: 0; 2026 M: 0 | 347.2875
| BQ Prep |  | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
| Travel & Disbursements |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
|  |  | Fee £ | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 3800 | 3500 | 3500 | 5100 | 4000 | 4000 | 4000 | 4600 | 4000 | 4000 | 10600 | 11600 | 2500 | 2500 | 5355 | 5040 | 2100 | 2257.5 | 2257.5 | 2257.5 | 2257.5 | 2257.5 | 2257.5 | 2257.5 | 2257.5 | 2257.5 | 2370.375 | 2370.375 | 2370.375 | 2370.375 | 2370.375 | 2370.375 | 2370.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 781.3969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 123886.5219 | 3021.6225
#REF!
32000000
#REF!
| RIBA Stage 1 |  | 9800 | 2021 A: 7.91%; 2021 S: 0.07%; 2021 O: 3266.6667; 2021 D: pm; 2026 D: Fixed Fee % | 0.8849%
| RIBA Stage 2 |  | 12100 | 2021 A: 9.767%; 2021 S: 0.08643%; 2021 O: 4033.3333; 2021 D: pm; 2026 D: Fixed Fee % | 0%
| RIBA Stage 3 |  | 16600 | 2021 A: 13.4%; 2021 S: 0.1186%; 2021 O: 4150; 2021 D: pm
| RIBA Stage 4 |  | 45595 | 2021 A: 36.8%; 2021 S: 0.3257%; 2021 O: 5699.375; 2021 D: pm
| RIBA Stage 5 |  | 34269.375 | 2021 A: 27.66%; 2021 S: 0.2448%; 2021 O: 2284.625; 2021 D: pm
| RIBA Stage 6 |  | 4740.75 | 2021 A: 3.827%; 2021 S: 0.03386%; 2021 O: 2370.375; 2021 D: pm
| RIBA Stage 7 |  | 781.3969 | 2021 A: 0.6307%; 2021 S: 0.005581%; 2021 O: 781.3969; 2021 D: pm
| TOTAL FEE (EXCL VAT) |  | 123886.5219 | 2021 A: 100%; 2021 S: 0.8849%
#REF!
#REF!
3.66

## CM Resource Schedule (hidden)
RESOURCE SCHEDULE
title of project
Notes:
1. Please insert the number of hours per RIBA stage
2. Please adapt rows for resources if required.
3. This table is to illustrate your indication of resources to be spent on the project only and the values have no bearing on your fee. Therefore this resource schedule cannot be used as a basis for any future additional fee claims under the contract.
4. Please insert your own formulae as none are contained in the cells below.
Resource Level | Resource Name | PROJECT STAGE
|  | Concept | Design | Pre-Construction | Construction | Handover & Close out | Use | All
|  | 2 | 3 | 4 | 5 | 6 | 7 | 2- 7
| Date (period / week / month): | - | 14.5 months | 11 months | 18 months | 2 months | 1 month | 45 months
|  | Days | Days | Days | Days | Days | Days | Total Days Per Resource Head | %
Director | Nav Kang | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Senior Cost Consultant | Ben Crampsie | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
MEP Senior Consultant | Gokhan Hassan | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Total number of hours per RIBA stage | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[6 empty] | Total Days |  | #REF!

## CM Resource Schedule Trad (hidden)
RESOURCE SCHEDULE
title of project
Notes:
1. Please insert the number of hours per RIBA stage
2. Please adapt rows for resources if required.
3. This table is to illustrate your indication of resources to be spent on the project only and the values have no bearing on your fee. Therefore this resource schedule cannot be used as a basis for any future additional fee claims under the contract.
4. Please insert your own formulae as none are contained in the cells below.
Resource Level | Resource Name | PROJECT STAGE
|  | Preparation |  | Design | Pre-Construction | Construction | Handover & Close out | Use | All
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 - 7
| Date (period / week / month): | 3 months | 3 months | 4 months | 8 months | 15 months | 2 months | 1 month | 36 months
|  | Days | Days | Days | Days | Days | Days | Days | Total Days Per Resource Head | %
Director | Nav Kang | 12 | 12 | 16 | 32 | 30 | 4 | 0 | 106 | 22.48%
Director | Adam Sukhon (Peer Review) | 1 | 1 | 1.5 | 4 | 5 | 0.5 | 0 | 13 | 2.757%
Senior Cost Consultant | James Crampsie | 14 | 22 | 32 | 56 | 30 | 4 | 0.5 | 158.5 | 33.62%
Cost Consultant | Ben Crampsie | 12 | 12 | 16 | 44 | 60 | 8 | 1 | 153 | 32.45%
MEP Senior Consultant | Gokhan Hassan | 1 | 2 | 2 | 7 | 7 | 1 | 1 | 21 | 4.454%
BoQ Preperation |  | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 20 | 4.242%
| Total No.of Days per RIBA stage | 40 | 49 | 67.5 | 163 | 132 | 17.5 | 2.5 | 471.5 | 100%
[7 empty] | Total Days |  | 471.5

## PM 2Stage Trad (hidden)
Oldham Performance Space
PM/CA FEE PROPOSAL
RESOURCE SUMMARY - AVERAGE DAYS PER MONTH
|  |  |  | 2023 | [8 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2025 | [15 empty] | 2025 | [11 empty] | 2026 | [11 empty] | Total
|  |  |  | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | J | J | A | S | O | N | N | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | O | A | S | O | N | D
| Task |  | Duration
TWO STAGE D&B PROCUREMENT
| Stage 2 - Concept Design |  | 5 Months
| Stage 3 - Developed Design |  | 4 Months
| Stage 4 - Technical Design & Procurement |  | 6 Months
| Procurement Singhe Stage Traditional |  | 4 Months
| Stage 5 - Construction |  | 18 Months
| Stage 6 - Handover |  | 2 Months
| Stage 7 - End of Rectification Period |  | 1 Month
| AVERAGE DAYS PER MONTH |  |  | 2023 A: 2023; 2024 J: 2024; 2025 J: 2025; 2025 J: 2025; 2025 J: 2025; 2026 J: 2026 | Total
|  |  |  | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | J | J | A | S | O | N | N | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | O | A | S | O | N | D
| Name | Role
#REF! | Amran Raja | Director |  | 2023 S: 2; 2023 O: 2; 2023 N: 2; 2023 D: 2; 2024 J: 2; 2024 F: 2; 2024 M: 1; 2024 A: 1; 2024 M: 1; 2024 J: 1; 2024 J: 1; 2024 A: 1; 2024 S: 1; 2024 O: 1; 2024 N: 1; 2024 D: 1; 2025 J: 1; 2025 F: 1; 2025 M: 1; 2025 A: 1; 2025 M: 1; 2025 J: 1; 2025 J: 1; 2025 A: 1; 2025 S: 1; 2025 O: 1; 2025 N: 1; 2025 D: 1; 2025 J: 1; 2025 F: 1 | 36
| Balazs Szabo | Cost Consultant |  | 2023 S: 4; 2023 O: 4; 2023 N: 4; 2023 D: 4; 2024 J: 4; 2024 F: 4; 2024 M: 4; 2024 A: 4; 2024 M: 4; 2024 J: 4; 2024 J: 4; 2024 A: 4; 2024 S: 4; 2024 O: 4; 2024 N: 4; 2024 D: 4; 2025 J: 4; 2025 F: 4; 2025 M: 4; 2025 A: 4; 2025 M: 4; 2025 J: 4; 2025 J: 4; 2025 A: 4; 2025 S: 4; 2025 O: 4; 2025 N: 4; 2025 D: 4; 2025 J: 4; 2025 F: 4; 2026 O: 2 | 122
| Akeem | Senior MEP Cost Consultant |  | 2023 S: 6; 2023 O: 6; 2023 N: 6; 2023 D: 6; 2024 J: 6; 2024 F: 6; 2024 M: 8; 2024 A: 8; 2024 M: 8; 2024 J: 8; 2024 J: 8; 2024 A: 8; 2024 S: 8; 2024 O: 8; 2024 N: 8; 2024 D: 8; 2025 J: 8; 2025 F: 8; 2025 M: 8; 2025 A: 8; 2025 M: 8; 2025 J: 8; 2025 J: 8; 2025 A: 8; 2025 S: 8; 2025 O: 8; 2025 N: 8; 2025 D: 8; 2025 J: 8; 2025 F: 8; 2026 O: 4 | 232
| tbc | Contract Administrator | [74 empty] | 0
|  | Travel & Disbursements | [74 empty] | 26 | bar: 2023 S; 2023 N; 2024 J; 2024 M; 2024 M; 2024 J to 2025 F; 2026 O
| TOTAL DAYS PER MONTH |  |  | 0 | 0 |  | 0 | 0 | 13 | 12 | 13 | 12 | 13 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 393
FEE DRAWDOWN PER MONTH
|  |  |  | 2023 A: 2023; 2024 J: 2024; 2025 J: 2025; 2025 J: 2025; 2025 J: 2025; 2026 J: 2026 | Total
|  |  |  | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | J | J | A | S | O | N | N | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | O | A | S | O | N | D
Proposed fee drawdown
| Amran Raja | 2023 | 950 | 2023 A: 0; 2023 M: 0; 2023 J: 0; 2023 J: 0; 2023 A: 0; 2023 S: 1900; 2023 O: 1900; 2023 N: 1900; 2023 D: 1900 | 7600
|  | 2024 | 997.5 | 2024 J: 1995; 2024 F: 1995; 2024 M: 997.5; 2024 A: 997.5; 2024 M: 997.5; 2024 J: 997.5; 2024 J: 997.5; 2024 A: 997.5; 2024 S: 997.5; 2024 O: 997.5; 2024 N: 997.5; 2024 D: 997.5 | 13965
|  | 2025 | 1047.375 | 2025 J: 1047.375; 2025 F: 1047.375; 2025 M: 1047.375; 2025 A: 1047.375; 2025 M: 1047.375; 2025 J: 1047.375; 2025 J: 1047.375; 2025 A: 1047.375; 2025 S: 1047.375; 2025 O: 1047.375; 2025 N: 1047.375; 2025 D: 1047.375 | 12568.5
|  | 2026 | 1099.7438 | 2025 J: 1099.7438; 2025 F: 1099.7438; 2025 M: 0; 2025 A: 0; 2025 M: 0; 2025 J: 0; 2025 J: 0; 2025 A: 0; 2025 S: 0; 2025 J: 0; 2025 J: 0; 2025 A: 0; 2025 S: 0; 2025 O: 0; 2025 N: 0; 2025 N: 0 | 2199.4875
|  | 2027 | 1154.7309 | 2025 J: 0; 2025 F: 0; 2025 M: 0; 2025 A: 0; 2025 M: 0; 2025 J: 0; 2025 J: 0; 2025 A: 0; 2025 S: 0; 2025 O: 0; 2025 N: 0; 2025 D: 0; 2026 J: 0; 2026 F: 0; 2026 M: 0; 2026 A: 0; 2026 M: 0; 2026 J: 0; 2026 O: 0; 2026 A: 0; 2026 S: 0; 2026 O: 0; 2026 N: 0; 2026 D: 0 | 0
| Balazs Szabo | 2023 | 550 | 2023 A: 0; 2023 M: 0; 2023 J: 0; 2023 J: 0; 2023 A: 0; 2023 S: 2200; 2023 O: 2200; 2023 N: 2200; 2023 D: 2200 | 8800
|  | 2024 | 577.5 | 2024 J: 2310; 2024 F: 2310; 2024 M: 2310; 2024 A: 2310; 2024 M: 2310; 2024 J: 2310; 2024 J: 2310; 2024 A: 2310; 2024 S: 2310; 2024 O: 2310; 2024 N: 2310; 2024 D: 2310 | 27720
|  | 2025 | 606.375 | 2025 J: 2425.5; 2025 F: 2425.5; 2025 M: 2425.5; 2025 A: 2425.5; 2025 M: 2425.5; 2025 J: 2425.5; 2025 J: 2425.5; 2025 A: 2425.5; 2025 S: 2425.5; 2025 O: 2425.5; 2025 N: 2425.5; 2025 D: 2425.5 | 29106
|  | 2026 | 636.6938 | 2025 J: 2546.775; 2025 F: 2546.775; 2025 M: 0; 2025 A: 0; 2025 M: 0; 2025 J: 0; 2025 J: 0; 2025 A: 0; 2025 S: 0; 2025 J: 0; 2025 J: 0; 2025 A: 0; 2025 S: 0; 2025 O: 0; 2025 N: 0; 2025 N: 0 | 5093.55
|  | 2027 | 668.5284 | 2025 J: 0; 2025 F: 0; 2025 M: 0; 2025 A: 0; 2025 M: 0; 2025 J: 0; 2025 J: 0; 2025 A: 0; 2025 S: 0; 2025 O: 0; 2025 N: 0; 2025 D: 0; 2026 J: 0; 2026 F: 0; 2026 M: 0; 2026 A: 0; 2026 M: 0; 2026 J: 0; 2026 O: 1337.0569; 2026 A: 0; 2026 S: 0; 2026 O: 0; 2026 N: 0; 2026 D: 0 | 1337.0569
| Akeem | 2023 | 410 | 2023 A: 0; 2023 M: 0; 2023 J: 0; 2023 J: 0; 2023 A: 0; 2023 S: 2460; 2023 O: 2460; 2023 N: 2460; 2023 D: 2460 | 9840
|  | 2024 | 430.5 | 2024 J: 2583; 2024 F: 2583; 2024 M: 3444; 2024 A: 3444; 2024 M: 3444; 2024 J: 3444; 2024 J: 3444; 2024 A: 3444; 2024 S: 3444; 2024 O: 3444; 2024 N: 3444; 2024 D: 3444 | 39606
|  | 2025 | 452.025 | 2025 J: 3616.2; 2025 F: 3616.2; 2025 M: 3616.2; 2025 A: 3616.2; 2025 M: 3616.2; 2025 J: 3616.2; 2025 J: 3616.2; 2025 A: 3616.2; 2025 S: 3616.2; 2025 O: 3616.2; 2025 N: 3616.2; 2025 D: 3616.2 | 43394.4
|  | 2026 | 474.6263 | 2025 J: 3797.01; 2025 F: 3797.01; 2025 M: 0; 2025 A: 0; 2025 M: 0; 2025 J: 0; 2025 J: 0; 2025 A: 0; 2025 S: 0; 2025 J: 0; 2025 J: 0; 2025 A: 0; 2025 S: 0; 2025 O: 0; 2025 N: 0; 2025 N: 0 | 7594.02
|  | 2027 | 498.3576 | 2025 J: 0; 2025 F: 0; 2025 M: 0; 2025 A: 0; 2025 M: 0; 2025 J: 0; 2025 J: 0; 2025 A: 0; 2025 S: 0; 2025 O: 0; 2025 N: 0; 2025 D: 0; 2026 J: 0; 2026 F: 0; 2026 M: 0; 2026 A: 0; 2026 M: 0; 2026 J: 0; 2026 O: 1993.4303; 2026 A: 0; 2026 S: 0; 2026 O: 0; 2026 N: 0; 2026 D: 0 | 1993.4303
| CSA Prep |  | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Travel & Disbursements |  | 250 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 250 | 0 | 250 | 0 | 250 | 0 | 250 | 0 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 6500
| Bloom fee |  | 5% | 0 | 0 | 0 | 0 | 0 | 340.5 | 328 | 340.5 | 328 | 356.9 | 344.4 | 350.075 | 337.575 | 350.075 | 337.575 | 350.075 | 350.075 | 350.075 | 350.075 | 350.075 | 350.075 | 366.9538 | 366.9538 | 366.9538 | 366.9538 | 366.9538 | 366.9538 | 366.9538 | 366.9538 | 366.9538 | 366.9538 | 366.9538 | 366.9538 | 384.6764 | 384.6764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179.0244 | 0 | 0 | 0 | 0 | 0 | 10865.8722
|  |  | Fee £ | 0 | 0 | 0 | 0 | 0 | 7150.5 | 6888 | 7150.5 | 6888 | 7494.9 | 7232.4 | 7351.575 | 7089.075 | 7351.575 | 7089.075 | 7351.575 | 7351.575 | 7351.575 | 7351.575 | 7351.575 | 7351.575 | 7706.0288 | 7706.0288 | 7706.0288 | 7706.0288 | 7706.0288 | 7706.0288 | 7706.0288 | 7706.0288 | 7706.0288 | 7706.0288 | 7706.0288 | 7706.0288 | 8078.2052 | 8078.2052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.5115 | 0 | 0 | 0 | 0 | 0 | 228183.3169 | 7130.7287
#REF!
32000000
#REF!
| RIBA 1-2 |  | 0 | 2023 A: 0%; 2023 M: 0%; 2023 J: 0; 2023 A: pm
| RIBA 3 |  | 0 | 2023 A: 0%; 2023 M: 0%; 2023 J: 0; 2023 A: pm; 2026 D: Fixed Fee % | 1.141%
| RIBA 4 |  | 42804.3 | 2023 A: 18.76%; 2023 M: 0.214%; 2023 J: 4280.43; 2023 A: pm
| RIBA 5 |  | 181619.5054 | 2023 A: 79.59%; 2023 M: 0.9081%; 2023 J: 7567.4794; 2023 A: pm
| RIBA 6 |  | 0 | 2023 A: 0%; 2023 M: 0%; 2023 J: 0; 2023 A: pm
| RIBA 7 |  | 3759.5115 | 2023 A: 1.648%; 2023 M: 0.0188%; 2023 J: 3759.5115; 2023 A: pm
| TOTAL FEE (EXCL VAT) |  | 228183.3169 | 2023 A: 100%; 2023 M: 1.141%
3.66

## 2Stage Trad CA (hidden)
University of Kent - The Docking Station
COST MANAGEMENT FEE PROPOSAL
RESOURCE SUMMARY - AVERAGE DAYS PER MONTH
|  |  |  | 2023 | [9 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2025 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | Total
|  |  |  | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | N | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
| Task |  | Duration
TWO STAGE D&B PROCUREMENT
| Stage 2 - Concept Design |  | 5 Months
| Stage 3 - Developed Design |  | 4 Months
| Stage 4 - Technical Design & Procurement |  | 8 Months
| First Stage Tender |  | 3.5 Months
| Negotiation & Selection |  | 6 Weeks
| PCSA |  | 10 Months
| ERs/ Tender Preperation |  | 1 Month
| Second Stage Tender Period |  | 4 Months
| Tender Report & Appointment |  | 2 Months
| Stage 5 - Construction |  | 12 Months
| Stage 6 - Final Account |  | 2 Months
| Stage 7 - End of Rectification Period |  | 1 Month
| AVERAGE DAYS PER MONTH |  |  | 2023 M: 2022; 2023 S: 2023; 2024 S: 2024; 2025 A: 2025; 2025 J: 2025; 2026 J: 2026; 2026 J: 2026 | Total
|  |  |  | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
| Name | Role
#REF! | Nav Kang | Director |  | 2024 J: 0.25; 2024 F: 0.25; 2024 M: 0.25; 2024 A: 0.25; 2024 M: 0.25; 2024 J: 0.25; 2024 J: 0.25; 2024 A: 0.25; 2024 S: 0.25; 2024 O: 0.25; 2024 N: 0.25; 2025 D: 0.25; 2025 J: 0.25; 2025 F: 0.25 | 3.5
| Ben Crampsie | Cost Consultant | [71 empty] | 0
| Gokhan Hassan | Senior MEP Cost Consultant | [71 empty] | 0
| tbc | Contract Administrator |  | 2024 J: 2; 2024 F: 2; 2024 M: 2; 2024 A: 2; 2024 M: 2; 2024 J: 2; 2024 J: 2; 2024 A: 2; 2024 S: 2; 2024 O: 2; 2024 N: 2; 2025 D: 2; 2025 J: 2; 2025 F: 2; 2026 J: 2 | 30
|  | Travel & Disbursements | [71 empty] | 15 | bar: 2024 J to 2025 F; 2026 J
| TOTAL DAYS PER MONTH |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 33.5
FEE DRAWDOWN PER MONTH
|  |  |  | 2022 J: 2022; 2023 J: 2023; 2024 J: 2024; 2025 D: 2025; 2025 M: 2025; 2026 J: 2026; 2026 J: 2026 | Total
|  |  |  | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Proposed fee drawdown
| Nav Kang | 2021 | 700 | 2022 J: 0; 2022 A: 0; 2022 S: 0; 2022 O: 0; 2022 N: 0; 2022 D: 0; 2023 J: 0; 2023 F: 0; 2023 M: 0; 2023 A: 0 | 0
|  | 2022 | 700 | 2023 M: 0; 2023 J: 0; 2023 J: 0; 2023 A: 0; 2023 S: 0; 2023 O: 0; 2023 N: 0; 2023 D: 0; 2024 J: 175; 2024 F: 175; 2024 M: 175; 2024 A: 175 | 700
|  | 2023 | 735 | 2024 M: 183.75; 2024 J: 183.75; 2024 J: 183.75; 2024 A: 183.75; 2024 S: 183.75; 2024 O: 183.75; 2024 N: 183.75; 2025 D: 183.75; 2025 J: 183.75; 2025 F: 183.75; 2025 M: 0; 2025 A: 0 | 1837.5
|  | 2024 | 771.75 | 2025 M: 0; 2025 J: 0; 2025 J: 0; 2025 A: 0; 2025 S: 0; 2025 O: 0; 2025 N: 0; 2025 D: 0; 2025 J: 0; 2025 F: 0; 2025 M: 0; 2025 A: 0 | 0
|  | 2025 | 930 | 2025 M: 0; 2025 J: 0; 2025 J: 0; 2025 A: 0; 2025 M: 0; 2025 J: 0; 2025 J: 0; 2025 A: 0; 2025 S: 0; 2025 O: 0; 2025 N: 0; 2025 D: 0; 2026 J: 0; 2026 F: 0; 2026 M: 0; 2026 A: 0; 2026 M: 0; 2026 J: 0; 2026 J: 0; 2026 A: 0; 2026 S: 0; 2026 O: 0; 2026 N: 0; 2026 D: 0 | 0
| Ben Crampsie | 2021 | 450 | 2022 J: 0; 2022 A: 0; 2022 S: 0; 2022 O: 0; 2022 N: 0; 2022 D: 0; 2023 J: 0; 2023 F: 0; 2023 M: 0; 2023 A: 0 | 0
|  | 2022 | 450 | 2023 M: 0; 2023 J: 0; 2023 J: 0; 2023 A: 0; 2023 S: 0; 2023 O: 0; 2023 N: 0; 2023 D: 0; 2024 J: 0; 2024 F: 0; 2024 M: 0; 2024 A: 0 | 0
|  | 2023 | 472.5 | 2024 M: 0; 2024 J: 0; 2024 J: 0; 2024 A: 0; 2024 S: 0; 2024 O: 0; 2024 N: 0; 2025 D: 0; 2025 J: 0; 2025 F: 0; 2025 M: 0; 2025 A: 0 | 0
|  | 2024 | 496.125 | 2025 M: 0; 2025 J: 0; 2025 J: 0; 2025 A: 0; 2025 S: 0; 2025 O: 0; 2025 N: 0; 2025 D: 0; 2025 J: 0; 2025 F: 0; 2025 M: 0; 2025 A: 0 | 0
|  | 2025 | 580 | 2025 M: 0; 2025 J: 0; 2025 J: 0; 2025 A: 0; 2025 M: 0; 2025 J: 0; 2025 J: 0; 2025 A: 0; 2025 S: 0; 2025 O: 0; 2025 N: 0; 2025 D: 0; 2026 J: 0; 2026 F: 0; 2026 M: 0; 2026 A: 0; 2026 M: 0; 2026 J: 0; 2026 J: 0; 2026 A: 0; 2026 S: 0; 2026 O: 0; 2026 N: 0; 2026 D: 0 | 0
| Gokhan Hassan | 2021 | 600 | 2022 J: 0; 2022 A: 0; 2022 S: 0; 2022 O: 0; 2022 N: 0; 2022 D: 0; 2023 J: 0; 2023 F: 0; 2023 M: 0; 2023 A: 0 | 0
|  | 2022 | 650 | 2022 J: 0; 2023 M: 0; 2023 J: 0; 2023 J: 0; 2023 A: 0; 2023 S: 0; 2023 O: 0; 2023 N: 0; 2023 D: 0; 2024 J: 0; 2024 F: 0; 2024 M: 0; 2024 A: 0 | 0
|  | 2023 | 682.5 | 2024 M: 0; 2024 J: 0; 2024 J: 0; 2024 A: 0; 2024 S: 0; 2024 O: 0; 2024 N: 0; 2025 D: 0; 2025 J: 0; 2025 F: 0; 2025 M: 0; 2025 A: 0 | 0
|  | 2024 | 775 | 2025 M: 0; 2025 J: 0; 2025 J: 0; 2025 A: 0; 2025 S: 0; 2025 O: 0; 2025 N: 0; 2025 D: 0; 2025 J: 0; 2025 F: 0; 2025 M: 0; 2025 A: 0 | 0
|  | 2025 | 820 | 2025 M: 0; 2025 J: 0; 2025 J: 0; 2025 A: 0; 2025 M: 0; 2025 J: 0; 2025 J: 0; 2025 A: 0; 2025 S: 0; 2025 O: 0; 2025 N: 0; 2025 D: 0; 2026 J: 0; 2026 F: 0; 2026 M: 0; 2026 A: 0; 2026 M: 0; 2026 J: 0; 2026 J: 0; 2026 A: 0; 2026 S: 0; 2026 O: 0; 2026 N: 0; 2026 D: 0 | 0
| CA |  | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 13800
| Travel & Disbursements |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Fee £ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075 | 1075 | 1075 | 1075 | 1083.75 | 1083.75 | 1083.75 | 1083.75 | 1083.75 | 1083.75 | 1083.75 | 1083.75 | 1083.75 | 1083.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 16337.5 | 510.5469
#REF!
32000000
#REF!
| RIBA 1-2 |  | 0 | 2022 J: 0%; 2022 A: 0%; 2022 S: 0; 2022 N: pm
| RIBA 3 |  | 0 | 2022 J: 0%; 2022 A: 0%; 2022 S: 0; 2022 N: pm; 2026 D: Fixed Fee % | 0.6535%
| RIBA 4 |  | 0 | 2022 J: 0%; 2022 A: 0%; 2022 S: 0; 2022 N: pm
| RIBA 5 |  | 15137.5 | 2022 J: 92.65%; 2022 A: 0.6055%; 2022 S: 840.9722; 2022 N: pm
| RIBA 6 |  | 0 | 2022 J: 0%; 2022 A: 0%; 2022 S: 0; 2022 N: pm
| RIBA 7 |  | 1200 | 2022 J: 7.345%; 2022 A: 0.048%; 2022 S: 1200; 2022 N: pm
| TOTAL FEE (EXCL VAT) |  | 16337.5 | 2022 J: 100%; 2022 A: 0.6535%
|  |  | 2019-04-01 | 2023 J: 2019-04-01
| Hertford CM Fee based on £8m-£9m (April 2019) |  | 154784 | 2023 J: 1.821%
| Hertford EA Fee based on £8m-£9m (April 2019) |  | 71276 | 2023 J: 0.8385%
|  |  | 2020-04-01 | 2023 J: 2020-04-01
| Hertford CM Fee based on £16.65m (April 2020) |  | 238440 | 2023 J: 1.432%
| Hertford EA Fee based on £16.65m (April 2020) |  | 112141.7 | 2023 J: 0.6735%
| Average CM Fee = £12.575m |  | 196612 | 2023 J: 1.564%
| Average EA Fee = £12.575m |  | 91708.85 | 2023 J: 0.7293%
#REF!
#REF!
3.66

## PM Resource Schedule (hidden)
RESOURCE SCHEDULE
title of project
Notes:
1. Please insert the number of hours per RIBA stage
2. Please adapt rows for resources if required.
3. This table is to illustrate your indication of resources to be spent on the project only and the values have no bearing on your fee. Therefore this resource schedule cannot be used as a basis for any future additional fee claims under the contract.
4. Please insert your own formulae as none are contained in the cells below.
Resource Level | Resource Name | PROJECT STAGE
|  | Concept | Design | Pre-Construction | Construction | Handover & Close out | Use | All
|  | 2 | 3 | 4 | 5 | 6 | 7 | 4-7
| Date (period / week / month): | - | 14.5 months | 10 months | 24 months | 2 months | 1 month | 37 months
|  | Days | Days | Days | Days | Days | Days | Total Days Per Resource Head | %
Director | Amran Raja |  |  | 12 | 24 | 0 | 0 | 36 | 9.231%
Senior PM/EA | Balazs Szabo |  |  | 24 | 96 | 0 | 2 | 122 | 31.28%
Assistant PM/EA | Akeem Champagnie |  |  | 36 | 192 | 0 | 4 | 232 | 59.49%
| Total number of hours per RIBA stage | 0 | 0 | 72 | 312 | 0 | 6 | 390 | 100%
[6 empty] | Total Days |  | 390