## Sheet1
Clarification Questions & Responses - Hall For Cornwall - Conservation Management Plan
Number | Date | Document | Section | Subject | Page | Clarification Question | Response | Date Responded | Provided To
1 | 2015-10-28 | ITT | 7 | Timescales | 10 | There have been a number of clarifications which we will be unable to respond to by the response to clarifications deadline. | Extension to the deadline by 1 week. Please see attached table (Revised timescales for HFC Conservation Management Plan.doc). TENDER RETURN DEADLINE NOW 13 NOVEMBER 2015. Apologies for any inconvenience this may cause. | 2015-10-28 | All
2 | 2015-10-26 | ITT | 2 | Interpretation and Education | 3 | Interpretation and education in the CMP: Will a specialist consultant will be engaged to carry out that part of the project? | As per the brief, the CMP will need to include an interpretation of the findings to aid understanding by all those for whom the CMP will be relevant. | 2015-11-06 | All
3 | 2015-10-26 | ITT | 2 | Training | 3 | Advice and guidance on the training required in the CMP: Similarly, will the same specialist consultant provide this section? | The CMP brief states that ‘Advice and guidance on the training required to enable better management and maintenance of the site’. Therefore this is required as part of the CMP for the consultant to advise on how to embed the CMP within the management and maintenance of the building | 2015-11-06 | All
4 | 2015-10-26 | ITT | 2 | Brief | 3 | Reference to the present 1996 layout of the Hall that will be removed: The brief states that the present ‘layout’ of the Hall for Cornwall is not part of the CMP? How so? Do you already have Planning Permission and Listed Building Consent for the removal of these interiors? Will they be removed? | The Auditorium will form part of the CMP and therefore needs to be included. | 2015-11-06 | All
5 | 2015-10-26 | ITT | 2 | Consultation | 3 | Stakeholder consultation: You specify two consultation stages when the key stakeholders need to be consulted; can you please confirm it is only these two days that will take place? Can you confirm there will be no other stakeholder consultation days required (i.e. with the public or local historic groups) please? | The brief states that ‘we ask the consultant to involve stakeholders during the preparation of the CMP, and manage a programme of involvement and consultation’ with a list of key stakeholders who will need to be involved in preparing the Plan. There are 2 consultation stages, not days, when the statements of significance and issues & vulnerability have to be produced and when the first full drafts of the CMP and HIA has been completed. It is for the consultant to say how they would manage the two consultation stages and how it can be done. | 2015-11-06 | All
6 | 2015-10-26 | ITT | 2 | Management Information | 4 | Management information: Aside from the planning and policy information you have specified in the brief, is there any other management information that you will require the consultant to read or reference i.e. existing in-house management information? If so, what is the information and size please? Is it possible to see a copy in advance? | Management information will be provided by HFC on appointment. | 2015-11-06 | All
7 | 2015-10-26 | ITT | 2 | Heritage Impact Assessment | 6 | The preparation of the Heritage Impact Assessment (HIA): The brief suggests that the HIA will be prepared by the appointed architect team (Burrell, Foley and Fischer) but with input from the CMP consultant. We understand this to mean that the CMP consultant will write paragraphs commenting on the final scheme and a mitigation strategy BUT the rest of the document will be prepared, illustrated and completed by the architect team? Please confirm. | The Heritage Impact Assessment will be produced by the Architect led Team but will need input from the CMP consultant. | 2015-11-06 | All
8 | 2015-10-26 | ITT | 4 | General | 9 | Completed summary sheet supplied by Historic England: You make reference to this as being required in the appendices – what is this please? | Please see separate attached document (Historic England Summary Sheet). This is also know as a Feature Sheet. | 2015-11-06 | All
9 | 2015-10-26 | ITT | 4 | Meeting | 9 | Attendance at meetings: The brief specifies that attendance is required at meetings as deemed appropriate by the client. In order to price efficiently and economically we would need to know the exact number of meetings the client would expect us to attend as each meeting will require a train journey to Truro. | Please price for attendance at 2x meetings in Truro. Attendance at any additional meetings, if necessary, will be reimbursed at cost. | 2015-11-06 | All
10 | 2015-10-26 | ITT | 6 | Budget | 9 | Budget of £8,000 to £10,000 (ex.VAT): The budget specified is very tight, is there any scope to expand that fee at all, please? | The budget identified will not change. | 2015-11-06 | All
11 | 2015-10-26 | ITT | - | General | - | Your project is entitled ‘Conservation Management Plan’ but I did not read any mention of the management and maintenance plan? Will this be prepared by the project architect with no direct input from the CMP consultant, as is normally the case? | The Management and Maintenance Plan will be prepared by the Architect and it is expected that the consultant will liaise directly with them. | 2015-11-06 | All