# REVIEW OF HUMAN RESOURCES SERVICES

# REF NLHF FINANCE 273

Organisation	National Lottery Heritage Fund

Department	Human Resources

Title of procurement	Review of Human Resources services

Brief description of supply

The National Lottery Heritage Fund (the Heritage Fund) is seeking a consultancy who can very quickly understand the Fund, our strategy, existing design, culture etc. and review our HR functional services to ensure we are maximising the value of that function.

Estimated value of tender	A sum not exceeding £30K (inclusive of VAT)

Estimated duration	Up to 20 working days

Name of Heritage Fund Contact	Colin Bailey

Executive Director (Business Services)

Timetable	Response deadline: 17th January 2020

Question & Answers Period End: 8th January 2020

Shortlist: 23rd January 2020

Presentations if needed: 27/28th January 2020

Decision: 30 January 2020

Confirmation of contract: 10th February 2020

Commencement of project: 12th February 2020

Completion of project: 12th March 2020

# 1.	Introduction

  - We are seeking organisations to make proposals to us for a review of our HR function and services.

  - We anticipate this work will focus on our function, services and processes with the goal of driving improved effectiveness and efficiency, so we better meet the future needs of our customers and supports the delivery of our future strategic goals.

- Background

  - The National Heritage Memorial Fund (NHMF) was set up in 1980 to help save heritage for the nation as a funder of last resort. Since then we have saved some magnificent and iconic heritage across the whole of the UK including:

  - Jane Austen manuscripts;

  - The Flying Scotsman;

  - The Mary Rose;

  - T E Lawrence’s robes and dagger and,

  - Many more items of exciting and memorable national heritage.

  - Nowadays, this aspect of our work is relatively modest, and you are more likely to know as the National Lottery Heritage Fund (the Heritage Fund) good cause money across the UK. We have been doing this for twenty-five years since the inception of the National Lottery.

  - We are a non-departmental public body. We are accountable to parliament via our sponsor department – the Department for Digital, Culture, Media and Sport.

  - Each year we distribute in excess of £300M in funding from the National Lottery across the UK. We have around 300 staff based in offices across all parts of the country and in our head office in London. It costs around £22M to run the organisation each year.

- The Commission

  - We are at an exciting moment in our history. We have started a new strategic funding cycle for our National Lottery work in April 2019. We are also mid-term through our new Corporate Strategy and have completed a major organisational design in April this year.

  - As a result, we are now at an opportune time to consider a short review of our HR function and services.

  - We are seeking a partner who can help us in this project. We are looking especially for a partner who can very quickly get to understand the Fund, our strategy, existing design, culture etc. and help us ensure the HR services and function provide the optimal delivery.

  - We also expect our partner to be cognisant of our goals and responsibilities to champion and support inclusion throughout our business, both internally and externally, ensuring that equality analysis is undertaken where relevant to minimise any direct/indirect disadvantage to any staff, customer or stakeholder groups.

- Our work as the National Lottery Heritage Fund.

  - Our work sees us fund projects from £3K to small community projects to over £10M for national heritage projects like the Cutty Sark and everything in between.

  - We have a portfolio of programmes that applicants can apply to us online. Some of these are wide, generic heritage projects (determined by grant size) and some are more targeted programmes that focus on particular areas of heritage like landscapes, parks, heritage skills etc.

  - Our range of applicants and grantees reflect the diversity of our heritage and funding programmes from small, local communities and charities to UK wide organisations such as the national museums in the UK and the evolved nations.

- Our governance, structure, skills etc.

  - We are managed by a Board of Trustees who oversee the organisation and also make decisions on grants at the highest level of awards.

  - The Board delegates day to day management to the Chief Executive (who is also Accounting Officer) and her Executive Team of Directors and her senior leadership team.

  - We have three departments who are Business Innovation and Insight, Business Delivery and Business Services. HR sits within Business Services.

  - Our Business Delivery teams are based in Scotland, Northern Ireland and Wales and the English teams and divided into three areas.

  - We have a diverse range of skills in areas like grant giving, policy development, communications, and so on but we also recognise there are some skills and competences we need to develop further and/or acquire.

  - The HR functional responsibilities include:

- Policy, Equality/Diversity and Inclusion, HR processing, HR operations, HR change management, reward and recognition, workforce development, learning and development, HR systems, organisational values, behavioural framework and performance management.

- The team has a series of Business Partners, Workforce Development Manager, Projects and Change Manager and a small administration support team.

- The team are distributed across the Fund’s UK offices.

- What we are looking for in our partners:

  - We are looking for a partner who has the following characteristics:

- The ability to quickly assimilate the processes, performance, culture and current design of the Fund;

- To gain early on the confidence of HR, staff and key players;

- To rapidly review the HR needs of the Fund and how it’s corporate strategy, operating environment etc. translate into HR needs going forward;

- To present well-constructed, cogent, risk and evidence-based views of the function and services;

- The ability to inherently work in genuine partnership and be a key trusted professional adviser;

- Ideally experience of working with grant giving and/or heritage organisations and,

- To complete this work within a period not exceeding 20 days.

# Outputs

  - The following outputs will be required:

- A draft final report in word along with a final report in word;

- A set of agreed, well evidenced, proposals/recommendations, supported by objective and demonstrable evidence.

# Contract management

  - We expect the project to begin on the 12th February and be completed by 12th March

  - The anticipated budget is not to exceed £30K to include all expenses and VAT. The contract will be let by the National Heritage Memorial Fund.

  - The payment schedule will be directly linked to final report delivery being satisfactorily completed and invoiced correctly.

  - The project will be managed on a day to day basis for the Fund by Richard Wilson, Director (Human Resources)

# Award Criteria

Quality Criteria

- A proposal for undertaking the work should include:

- A detailed methodology/approach for undertaking the project;

    - 25%

- Details of staff allocated to the project, the days allocated to each team member, together with your company’s (and staff members) in carrying out similar projects. The project manager / lead contact should be identified and their CV provided;

    - 25%

- Explanation of your core principles when managing an HR for a public sector organisation

    - 20%

- Detail factors that will determine key elements of the HR function and services

    - 20%

- A timescale for carrying out the project;

    - 10%

  - Your Quality element will be scored out of 100%.

60% of the total marks will be awarded to Quality

Each question below will be scored using the methodology in the table below. Ensure your Tender response sets out the 5 sections above, answering the criteria above so that we can easily score your response to the 5 questions below which align to the above criteria.:-

- To what extent is the method/ approach appropriate to the project?

- What is the extent of the consultant’s experience of similar projects, taking in to consideration staff CV’s and time allocate to each team member?

- To what extent does the tender response demonstrate an understanding of the core principles required to manage a public sector organisation?

- How well has the consultant’s identified the key elements of HR functions and services?

- How well has the tenderer structured their team in order to successfully manage the contract and timeframe to deliver the required work to the budget and timeline required by the Fund?

## Quality Questions scoring methodology

| Score | Word descriptor | Description |
| --- | --- | --- |
| 0 | Poor | No response or partial response and poor evidence provided in support of it. Does not give the Fund confidence in the ability of the Bidder to deliver the Contract. |
| 1 | Weak | Response is supported by a weak standard of evidence in several areas giving rise to concern about the ability of the Bidder to deliver the Contract. |
| 2 | Satisfactory | Response is supported by a satisfactory standard of evidence in most areas but a few areas lacking detail/evidence giving rise to some concerns about the ability of the Bidder to deliver the Contract. |
| 3 | Good | Response is comprehensive and supported by good standard of evidence. Gives the Fund confidence in the ability of the Bidder to deliver the contract. Meets the Fund’s requirements. |
| 4 | Very good | Response is comprehensive and supported by a high standard of evidence. Gives the Fund a high level of confidence in the ability of the Bidder to deliver the contract. May exceed the Fund’s requirements in some respects. |
| 5 | Excellent | Response is very comprehensive and supported by a very high standard of evidence. Gives the Fund a very high level of confidence the ability of the Bidder to deliver the contract. May exceed the Fund’s requirements in most respects. |

40% of total marks will be awarded for Price.

The evaluation of price will be carried out on the Schedule of charges you provide in response to Table A

## Price Criterion at 40%

- 40 marks will be awarded to the lowest priced bid and the remaining bidders will be allocated scores based on their deviation from this figure. Your fixed and total costs figure in your schedule of charges table will be used to score this question.

- For example, if the lowest price is £100 and the second lowest price is £108 then the lowest priced bidder gets 50% (full marks) for price and the second placed bidder gets 36.8% and so on. (8/100 x 40 = 3.2 marks; 40-3.2 = 36.8 marks)

- The scores for quality and price will be added together to obtain the overall score for each Bidder.

## Table A - Schedule of Charges

Please show in your tender submission, the number of staff and the amount of time that will be scheduled to work on the contract with the daily charging rate.

Please complete the table below providing a detailed breakdown of costs against each capitalised description, detailing a total and full ‘Firm Fixed Cost’ for each element of the service provision for the total contract period. Bidders may extend the tables to detail additional elements/costs if required.

VAT is chargeable on the services to be provided and this will be taken into account in the overall cost of this contract.

As part of our wider approach to corporate social responsibility the National Heritage Memorial Fund/Heritage Fund prefers our business partners to have similar values to our own. We pay all of our staff the living wage (in London and the rest of the UK) and we would like our suppliers and contractors to do likewise. Please highlight in you proposal/tender/bid whether you do pay your staff the living wage.

Bidders shall complete the schedule below, estimating the number of days, travel and subsistence costs associated with their tender submission.

TABLE A: (firm and fixed costs)

| Cost | Post 1 @cost per day (No of days) e.g. Project Manager/ Director @ £2 | Post 2 @cost per day (No of days) e.g. Senior Consultant/manager/researcher @£1.5 | Post 3 @cost per day (No of days) Junior Consultant/equivalent e.g. £1 | Total days | Total fees |
| --- | --- | --- | --- | --- | --- |
| Inception meeting to agree plans and finalise requirements with the Fund | Example 0.5 | 1 | 1.5 | 3 | £4 |
| [Add as necessary] |  |  |  |  |  |
| [Add as necessary] |  |  |  |  |  |
| [Add as necessary] |  |  |  |  |  |

| Cost Type | Value (£) |
| --- | --- |
| Sub - Total |  |
| VAT |  |
| Total* |  |

* (This must include all expenses as well as work costs; this figure will be used for the purposes of allocating your score for the price criterion and must cover the cost of meeting all our requirements set out in the ITT)

Notes: The Fund reserves the right to clarify quality and prices and to reject tenders that demonstrate an abnormally low quality response. The Fund also reserves the right to amend the timetable of work where required.

You should not submit additional assumptions with your pricing submission. If you submit assumptions you will be asked to withdraw them. Failure to withdraw them will lead to your exclusion from further participation in this competition.

# Procurement Process

  - The Fund reserves the right to reject abnormally low scoring tenders. The Fund reserves the right not to appoint and to achieve the outcomes of the research/evaluation through other methods.

  - The procurement timetable will be as required by the Framework:

- Response deadline:17th January 2020

- Question Period End: 20th December 2019

- Fund Answers Period End: 8th January 2020

- Shortlist: 23rd January 2020

- Presentations if needed: 27/28th January 2020

- Award decision: 30th January 2020

- Confirmation of contract: 10th February 2020

- Commencement of project: 12th February 2020

- Completion of project: 12th March 2020

- We reserve the right to carry out clarifications if necessary; these may be carried out via email or by inviting bidders to attend a clarification meeting.  In order to ensure that both the Fund’s and Bidder’s resources are used appropriately, we will only invite up to three (the ultimate number will depend on the closeness of the scores) highest scoring bidders to attend a clarification meeting.  Scores will be moderated based on any clarifications provided during this meeting.  You are responsible for all your expenses when attending such meetings.

  - Your tender proposals must be sent electronically via e-mail before the tender return deadline of 17th January 2020 at noon to the following contact:

Richard Wilson

Executive Director (Business Services)

National Heritage Memorial Fund

Mezzanine North

International House

1 St Katharine’s Way

London

E1W 1UN

Email: richard.wilson@heritagefund.org.uk

Telephone: 07796 444 272

www.heritagefund.org.uk

# Appendix: Accessibility and formatting guidance

The Fund is committed to providing a website that is accessible to the widest possible audience. Our site is annually tested by accessibility auditors and we must meet a AA compliance level. Our accessibility testing encompasses not just site functionality and design but all of our content, including downloadable documents.

Reports and other documents created for the Fund (including the tender submissions) need to be clear, straightforward to use and ready to circulate internally, externally and online, as well as suitable for use by screen reading software. Best practice in accessibility is summarised below:

## Readability

In the final report, and all other documents that may be published online including the tender application consultants should ensure that:

- The size of the font is at least 11pt;

- There is a strong contrast between the background colour and the colour of the text. Black text on a white background provides the best contrast. This also applies to any shading used in tables and/or diagrams;

- Italics are only used when quoting book titles for citations and items on the reference list should be arranged alphabetically by author

- Colour formatting and use of photos should be of a resolution size that is easily printable and does not compromise the printability of the document.

For further guidance on ensuring readability of printed materials, please refer to the RNIB Clear Print guidelines. These can be found on the RNIB website.

## Accessibility

Reports should adhere to the following guidelines:

## Formatting

Headings and content in your document should be clearly identified and consistently formatted to allow easy navigation for users. Heading Styles should be used to convey both the structure of the document and the relationship between sections and sub-sections of the content. Heading styles should follow on from each other i.e. Heading 1 then Heading 2.

## Spacing

Screen readers audibly represent spaces, tabs and paragraph breaks within copy, so it is best practice to avoid the repetitive use of manually inserted spaces. Instead, indenting and formatting should be used to create whitespace (e.g., use a page break to start a new page, as opposed to multiple paragraph breaks).

## Alternative text

Alt text is additional information for images and tables. This extra information is essential for both document accessibility (screen reading software reads the Alt text aloud) and for the web. Alt text should be concise and descriptive, and should not begin with ‘Image of’ or ‘Picture of’.

## Images

These should be formatted in-line with text, to support screen readers. Crediting pictures may be necessary, usually in response to a direct request from a third party.

## Tables

These should be for used for presenting data and not for layout or design. They should be simple and include a descriptive title. The header row should be identified and there shouldn’t be more than one title row in a table. There should be no merged or blank cells.

## Additional documents

Any additional information, separate to the report, for example proformas and transcripts which may be used as standalone documents must be fully referenced to the piece of work being submitting and therefore dated, formatted and numbered appropriately.

## Further resources

Please refer to the WCAG 2.0 article on PDF techniques for further information.

Submitting your report to THE FUND

Please check the accessibility of your document using the Word accessibility checker before submitting: File – Info – Check for Issues – Check Accessibility.

Please submit your document as a Word file.

The Fund retains the right to amend documents in order to create accessible versions for publishing.