## Risk Register
Risk Register
Project Name | Wondrous Place 2 |  | Liklihood Score |  |  |  | Impact Score |  |  | Personnel Key
Project Reference |  |  | 1 - Very Low | Less than 10% chance |  |  | 1 - Very Low | Insignificant impact [time / value / other thresholds to be agreed] |  | AC - Andrea Camponanes
Report date |  |  | 2 - Low | 10 - 30% chance |  |  | 2 - Low | Minor impact [time / value / other thresholds to be agreed] |  | CJ - Catherine Johnson
Issue number |  |  | 3 - Medium | 30 - 50% chance |  |  | 3 - Medium | Moderate impact [time / value / other thresholds to be agreed] |  | KJ - Kate Johnson
|  |  | 4 - High | 50 - 70% chance |  |  | 4 - High | Major impact [time / value / other thresholds to be agreed] |  | KOR - Karen O'Rourke
|  |  | 5 - Very High | More than 70% chance |  |  | 5 - Very High | Catastrophic impact [time / value / other thresholds to be agreed] |  | VS - Vivienne See
MD - Mannika Dhadwal
SN - Steve Newman
| Likelihood | 5 | 5 | 10 | 15 | 20 | 25 |  |  | AW - Andrew Winder
|  | 4 | 4 | 8 | 12 | 16 | 20 |  |  | ME - Matt Exley
|  | 3 | 3 | 6 | 9 | 12 | 15 |  |  | SG - Sadie Graham
|  | 2 | 2 | 4 | 6 | 8 | 10 |  |  | JD - Joseph Dixon
|  | 1 | 1 | 2 | 3 | 4 | 5 |  |  | AD - Andy Dougherty
|  |  | 1 | 2 | 3 | 4 | 5
Impact
No. | Risk Description E.g. As as result of … there is a risk that … which may result in … | Risk Owner (Initials) | Date Risk Identified | Last Review Date | Likelihood | Impact | Risk Rating | Controls / Mitigations | Current Status | Actions (including owner) | Target Action Date | Notes
[5 empty] | (1 - 5) | (1 - 5) | (L x I)
Finance
| Project budget inadequate resulting in project going over budget. | [5 empty] | 0 | Detailed cost plan drafted in line with exhibition design for submission and approval. Constantly review costs against allocations. Pre tender estimates agreed prior to tender issue. Development exploring additional funding opportunities and sponsorship. Substantial contingency included within overall budget. |  | Review costs, value engineer, be prepared to revise specification of works to ensure costs remain within budget. Use contingency. Explore alternative options to deliver the same visitor experience.
| Cost variations due to unforeseen costs during setworks/gallery prep (such as damage to gallery or other repairs works are revealed and required) & install of objects (such as damage to objects which result in repair works) | [5 empty] | 0 | Regular reviews between contractor and Design. Regular review at site and project team meetings.
Programme
| Delay in loan agreement sign off delays confirmation of confirmed object list. | [6 empty] | KOR to confirm final object list. SH to provide clear timeline for communication with lenders.
Inadequate time for review of Design & Digital strategy.
Design & Estates package deadlines don't align ahead of tender pakcages being drafted and going live.
| The Scheme Design and Design Brief documents for discussion and sign off are incomplete | [6 empty] | The quality of information required and the way that this information should be presented is agreed at the outset of the project. |  | Progress is reviewed at key stages and delays to the handover of information are discussed with Head of Design to ensure that any shortcomings are corrected.
| Delays during set works/gallery prep which directly impact the installation schedule | [6 empty] | Monitor progress againt programme. Contigency time built into schedule. |  | Reprogramme resources. Identify tasks that can take place concurrently.
| Programme slippage at key project milestone stages i.e. Design sign off. | [6 empty] | Close management of project objectives and programme schedule to ensure timely delivery. Regular and frequent communication with project team to ensure tasks and actions are realistic within set timeframe. |  | Review opening date.
Inadequate time for commissioning/handover periods with Software and Hardware packages.
Inadequate time for creative period for Digital production tender process
| Inadequate time for condition checks and installation of collections | [6 empty] | Confirm Liverpool on Wheels deinstall programme and establish install team plan and programme. |  | Agreed additional budget against Collections Care line to support Paper, Organics and Metal conservation with condition checking. Phased programme has been drafted to begin works early 2021 on the days the gallery is temp closed to public.
Statutory / legal risks
| Statutory & legal - GDPR, Licensing & copyright | [5 empty] | 0 | Key items are identified within the display, such as images, film footage, which require copyright or licensing. Budget is allocated to cover costs. |  | A log should be kept collating all licenses, copyright information to be referenced if any queries occur.
Performace risks
| Project team fail to meet deadlines. | [6 empty] | Regular meetings and reports to review programme.
| Contractors fail to meet deadlines. | [8 empty] | Appropriate selection through procurement route and proactive management of contractors with regular reviews and clear contract. |  | Review current conditions and constantly monitor
| Tender partners fail to meet deadlines. | [8 empty] | Appropriate selection through procurement route and proactive management of contractors with regular reviews and clear contract. |  | Carry out repair/conservation work if required.
Unable to secure key loans
Unable to cut back content/objects on display resulting in overcrowded cases/layout.
| Refreshed gallery is unsuitable for target audience and not prepresentitive/inclusive | [6 empty] | The target audience is clearly identified at the outset. Effective marketing and communications plan / campaign |  | Clearly identify objectives and target audience at the outset.
Unable to demonstrate outcomes from Co-curated community elements of display.
Display case assessment - access restricted until LoW deinstalled.
| AV Equipment maintenance & technical difficulties once gallery has reopened. | [6 empty] | Control measures discussed and agreed as part of hardware procurement and tender package in the event of an issue with the technical equipment. (IS Helpdesk)
Reputational risks
| Failure to maintain enviomental conditions | [6 empty] | Environmental monitoring in cases (prosorb & monitoring equip) Introduce remedial measures eg. de/humidifiers
| Major exhibits are damaged during transit and install period | [6 empty] | Establish Decant & Installation team to plan and programme object movement and handling, adhering to NML standards and guidelines. Selection of experienced contractors, supply of method statements etc.
| Failure to open on time | [5 empty] | 0 | Programme regularly reviewed, potential slippage identified as early as possible, additional staff resources brought in to support project team. |  | Controls are master programme, project procurement strategy, regular progress reviews.
| Staff/Stakeholders | [5 empty] | 0
| Difficulty in recruitment, loss of key project staff. Lack of appropriate skills and/or insufficient resourcing for project within NML. | [6 empty] | RTE's drafted in advance to prevent project delays. Training and opportunties to devleop appropriate skills. |  | Curatorial post has gone to the at risk group. Failing recruitment from this pool the post will be advertised externally. Likely to not be appointed earlier than Feb 2021. |  | Outsource.
| We lose key staff during the project | [8 empty] | Succession plan for key personnel.
| Staff have insufficient time to complete essential tasks | [8 empty] | A project programme is agreed at the outset and reviewed on a regular basis by the project team. Every attempt should be made by the team to correct any programme slippage. |  | All major variations to programme should be discussed with the Project Director and an appropriate cause of corrective action agreed.
Key partners fail to deliver and or there is a breakdown in communication.
| Community Interest groups i.e. OCOS involvement. fail to deliver and or there is a breakdown in communication. | [6 empty] | Programme to be drafted in agreement with Design to outline what these co-curated elements are and when the content will be recieved to meet set deadlines re Scheme designs & detailed design briefs
Stakeholders expectations are unaligned with project objectives.
| Health & Safety | [5 empty] | 0
| Covid 19 - Visitor focus | AD & JD |  |  |  |  | 0 | Latest guidence to be at the forefront of Design and Digital considerations. |  | Anticipation of government guidence changing. Regular reviews of display required to remain up to date with current practise.
| Covid 19 - Staff focus | JD | [5 empty] | During install ensure museum management aware if contractors on site. Site access form to be completed by all staff. |  | Anticipation of government guidence changing.
| Key members of the project team have to self isolate or fall ill so are unable to work on the project or installation. | [5 empty] | 0 | Where possible staff to continue to work from home. If during install periods, contingency plans in place for key personnel. Ensure all information is accessible via the Teams project folder.
| Restrictions mean that the building has to close during crucial milestones in the programme. | [5 empty] | 0 | Review programme for revised dates.
| Travel restrictions are in place | [5 empty] | 0 | Where possible staff to continue to work from home. If during install periods look to revise programme.
0
0
0
0
0
0
0
0
0
0
0
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35