Briefing Document for Specialist Consultancy Services to produce at least an initial Interpretation Plan for:

“Bridging the Tamar”:  a Learning Centre and STEAM Hub to explore Tamar’s two key bridges.

April 2017

| Contents |  |
| --- | --- |
| 1.0 | INTRODUCTION 1.1 This Brief 1.2 The Tamar Bridges and our project 1.3 Meeting HLF outcomes 1.4 Context |
| 2.0 | THE PROJECT 2.1 Project Timetable 2.2 Project Adjacencies 2.3 Target Audiences and current themes |
| 3.0 | INTERPRETATION PLAN CONTENT 3.1 Outputs 3.2 Development Phase details 3.3 Outline Delivery Phase requirements |
| 4.0 | BUDGET |
| 5.0 | TENDER PROCESS |

|  | 1.0 INTRODUCTION |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1.1 |  |  | This Brief |  |  |  |  |
|  | The Tamar Bridge and Torpoint Ferry seeks to employ consultants with relevant experience to produce our interpretation plan for our round 2 HLF application and, should we achieve success, to deliver the interpretation materials for our project. This brief provides the context, requirements and process for procuring such services. The Interpretation Plan consultant will be expected to communicate with the Activity, Design and Business consultants regularly throughout the process. |  |  |  |  |  |  |  |
|  | 1.2 |  |  |  | Bridging the Tamar: a Learning Centre and STEAM Hub to explore Tamar’s two key bridges |  |  |  |
|  | Our project will create a new learning centre focusing on the heritage of both the Tamar Bridge and Brunel’s Royal Albert Bridge. We will develop a STEAM (Science, Technology, Engineering, Art and Mathematics) hub on the site of redundant offices of the Tamar Bridge and Torpoint Ferry, and deliver a programme of events and learning activities through the creation of a new Community, Learning and Volunteering (CLV) post: this post will continue after the HLF funded project finishes. The HLF project will be organised around outcomes that will be of direct public benefit and in liaison with partners such as Plymouth History Centre, schools, universities and local community organisations. With a successful HLF application the learning centre will open in January 2019 and will attract approximately 35,000 visitors a year to the internal displays, and an additional 75,000 to the enhanced outdoor area, with a mixture of school groups, pre-booked coach groups and individual visitors. The learning centre is supported by key stakeholders including Plymouth City Council, Cornwall Council and Network Rail. The project will focus on the heritage of two world class bridges: the Tamar Bridge and Brunel’s Royal Albert Bridge. Although supported and encouraged by Network Rail, the project will be managed and then operated by the Tamar Bridge and Torpoint Ferry. The overall delivery of the project will cost £363, 600, with a proposed HLF grant of £272,700. All match funding is in place, and planning permission is already secured. |  |  |  |  |  |  |  |
|  | 1.3 |  |  | HLF Outcomes |  |  |  |  |
|  | Benefits to Heritage: • Better interpreted and explained through displays throughout the site, including external interpretation, the learning centre, activities and tours; • Identified and recorded through bringing the information for both bridges together on public display, and recording of reminiscences. Benefits to Individuals: people will • Learn about the social and economic history as well as the engineering significance of the two bridges; - Take part in lifelong learning programmes for primary/ secondary schools; colleges and universities; professional development; and informal adult education; • Develop skills through research, co-creation of interpretation and on-line media, and volunteer development; • Change their attitude towards the bridges and discover the potential fascination of engineering; • Have an enjoyable experience through participation and/or through visiting the centre; • Volunteer time through the delivery phase, or as centre learning assistants. Benefits for Communities/Society: • More people and a wider range of people will have engaged with heritage; - Permanent CLV post created; • The local area will have a new learning facility and destination, to make it a better place to live, work and visit; • Landscaping will make the site more attractive and welcoming, and provide outside learning spaces and picnic areas |  |  |  |  |  |  |  |
| 1.4 |  |  |  | Context |  |  |  |
| The Tamar Bridge is owned and operated jointly by Cornwall Council and Plymouth City Council. These Joint Authorities formed a special partnership in 1950 to lobby national government to fund a fixed crossing of the Tamar, but in the face of government inaction, decided in 1955 to go forward with the scheme themselves as a local enterprise financed from tolls. As a result, the bridge is an important source of local pride, and consultation has consistently showed enthusiasm for this project. Parliamentary powers were needed for compulsory purchase of land, construction of towers in navigable waters, closure of existing roads and then to subsequently charge tolls. The Tamar Bridge Act gained Royal Assent on 27th July 1957, provided these powers and also created the Tamar Bridge and Torpoint Ferry Joint Committee, which was charged with the subsequent operation, maintenance and improvement of both the planned Tamar Bridge and the existing chain ferry operation at Torpoint. The Bridge now carries over 16 million vehicles a year – over ten times that carried in the early years, and on a busy weekday over 50,000 vehicles use the crossing. The construction, operation, maintenance and improvement of the crossing have all been financed from toll income, and toll charges remain amongst the lowest for a major estuarial crossing in the UK. This HLF project will follow another major project, the completion of new offices for the organisation, which in turn will release old 1960s office buildings that will be converted into our proposed learning centre. This project focuses on the activities and learning enabled by the earlier capital works. |  |  |  |  |  |  |  |
| 2.0 |  |  |  | THE PROJECT |  |  |  |
| - Transforming refurbished office space into a learning centre and STEAM (Science, Technology, Engineering, Art and Mathematics) hub, to provide a display and exhibition room that can be screened off to provide a space for groups and schools, as well as a kitchenette and toilets. The learning centre will be physically linked to our office facilities with a lift to ensure DDA compliancy and integrated approach – the offices are being built with a viewing platform overlooking the bridges - Celebrate and interpret the engineering and social histories of two iconic structures: the Royal Albert Bridge and the Tamar Bridge - Deliver landscape work to improve the attractiveness of the site, including outdoor classroom, enhanced views of the bridges, picnic areas - Offer an attractive welcome, stopping point and new heritage destination for people on the Devon/Cornwall border - Provide external and internal learning spaces for (school) groups - Employ a Community, Learning and Volunteering Officer (CLV) to enable our ambitions to become realities - Incorporate a CLV role into the permanent staffing structure, reporting to the Customer Supervisor, to perpetuate the work beyond the life of the project - Work in partnership with local community or specialist organisations to mentor our volunteering and interpretation programmes Plymouth History Centre and Ashtorre Rock - Recruit, train and support 155 volunteers to assist with opening, educational visits and visitor welcome. Training will include general induction to the site and being a volunteer, history sessions, customer service, guiding techniques, working with children, running school sessions, evaluation techniques, research, co-creation of interpretation, and running family activities. - Use data and information from university research to inform displays, such as live bridge behaviour - Work with community groups and universities to co-create and evaluate displays, with a family focus group to test ideas - Install a permanent exhibition to include the making and design of the two bridges, Brunel’s genius, social history, why the bridges were built, and current maintenance – including live monitors - Bring together and make available material for the two bridges - Encourage work experience opportunities for local young people - Create temporary exhibitions to involve local people and attract repeat visits - Form a STEAM hub for Devon and Cornwall with primary, secondary and university level input encouraging understanding of engineering and related careers, and a place for teachers to meet - Produce a schools programme linking to the National Curriculum through a teachers’ focus group to attract schools from across Devon and Cornwall, linked with the schools programme at the Plymouth History Centre, focussing on Saltash and Plymouth schools and build up to 1,800 formal educational visits pa - Work with the Universities of Plymouth and Exeter to provide site visits for foundation year, undergraduate and postgraduate students - Develop activities with the scouting movement (Beavers, Cubs, Brownies, Guides, Scouts) to match learning outcomes against badges - Work with young people and other heritage sites in the Saltash area to explore the history and identity of the town, going behind the scenes to explore career opportunities within the heritage sector - Work with WEA to provide life-long learning courses covering engineering, history, art, poetry and literacy - Make the 1960s building more energy efficient - Enable a dropping off point for coaches, enabling 9,000 visitors in coach groups pa - Run pre-booked tours local user groups with access to the new viewing platform overlooking the two bridges - Hold an audience specific events programme to cover local people, families, young people, tourists, coach groups, engineering heritage specialists - Increase visitor numbers to 35,000 to the learning centre over three years, with another 75,000 pa having a light touch heritage experience through access to external interpretation - Continue our dialogue with Network Rail to improve intellectual access to their bridge - Supply light refreshments (drinks, snacks and sandwiches) to our visitors and contribute financially to the running of the learning centre and activities - Give local people a place to take pride in ‘their’ bridges |  |  |  |  |  |  |  |
|  | 2.1 |  |  | Project Timetable |  |  |  |
|  | Planning application approved; September 2015. HLF Round One submitted; August 2016. HLF Committee decision; December 2016. Work commences on new offices; March 2017. HLF Round Two; January 2016 – October 2017. HLF Committee decision Round Two; February 2018. Permission to start; March 2018. Advertising of CLV post; April 2018. Work starts on learning centre; April 2018. CLV Post Starts; June 2018. Volunteers recruited for initial delivery phase; June 2018. Volunteers recruited and trained for learning centre; Sep - Oct 2018. External Classroom etc; March 2018 – June 2018. M&E work to Learning Centre; March 2018 – June 2018. Fit-out with interpretation etc; September – November 2018. Learning Centre opens; January 2019. Activities and Learning programme start; January 2019. HLF funding ends; June 2022. Evaluation report; Spring-Summer 2022. |
|  | 2.2 |  |  | Project Adjacencies |  |  |  |
|  | During the development period, business and activities are being addressed alongside the interpretation design, all in the context of community and peer consultation. The physical work on creating our new offices is underway and the space for the interpretation and heritage activities will come out of this (non-HLF) project. |  |  |  |  |  |  |
|  | 2.3 Target Audiences & Themes |  |  |  |  |  |  |
|  | Following from the initial consultation work at Round One, we feel comfortable with the following segments as our target audiences: - Organisations working with young people - Schools - Universities and professional organisations - Leisure organisations - General public - Volunteers Interpretation themes identified at Round One include: • History of crossing the Tamar, the two bridges and their engineering significance • Brunel • Social and economic impact of the two bridges • Management and maintenance issues |  |  |  |  |  |  |
|  | 3 INTERPRETATION PLAN CONTENT |  |  |  |  |  |  |
|  | 3.1 |  |  | INTERPRETATION REQUIREMENTS - What we require Outputs This contract is for the creation of a developed and costed interpretation plan to accompany our round 2 Heritage Lottery Fund application; A break clause between round 2 submission and permission to start our project delivery; The delivery of the interpretation plan including the co-creation and methods of working as stated in the round 2 plan. |  |  |  |
|  | 3.2 |  |  | Detailed requirements for Development phase – March – August 2017 The Consultant will produce an Interpretation Plan following HLF guidance and to enhance our HLF project; The plan will be able to demonstrate that: - The themes and topics have come up through the consultation process (currently underway through the activity planning consultants); - The themes, topics resonate with the target audiences; - Design meets with the learning preferences of our target audiences; - Draft proposals have been tested at mid-point and by consultees and that feedback has been incorporated; - Proposals are in line with relevant delivery partners; - The proposals have been costed and are affordable within the capital project budgets and within the trust’s resources and sustainable maintenance planning; - The proposals are in line with the business and activity and planning to contribute to a joined-up project; |  |  |  |
|  | 3.3 |  |  | Outline proposals for Delivery phase – March 2018 – September 2020 - Delivery of round 2 interpretation plan according to the proposed methodologies, budgets and delivery programme; - Liaison with refit design team to ensure interpretation materials are aligned to proposed stowage and display space; - Participation in the evaluation process; |  |  |  |
|  | 4 |  |  | The current Interpretation budgets are: |  |  |  |
|  | Development Phase fee |  |  |  |  | 10,000 |  |  |  |
|  | External Signage on site Children's Trail Adult Trail Permanent displays Website/apps Temporary displays Projector/screen Guidebook Chairs, tables Refreshment/retail set up Consultant's fee Total |  |  |  | 15,000 10,000 2,500 2,500 85,000 5,000 2,000 1,000 6,000 1,000 3,000 17,000 150,000 |  |  |  |  |
| There is also consideration in the activity budgets towards co-creation and partnership work |  |  |  |  |  |  |  |  |

5.0     TENDER PROCESS AND NEXT STEPS

|  | Tender documentation issued to Interpretation Plan consultants |  |
| --- | --- | --- |
|  | Intention to bid submitted |  |
|  | Tender returns |  |
|  | Tender evaluation and engagement of consultant |  |
| October 2017 | Deadline for consultant’s Interpretation Plan |  |