# Annex A

| Title of Project | Ocean Country Partnership Programme: Sri Lanka Technical delivery of stakeholder led Protected Area Management Effectiveness assessments for four Marine Protected Areas across Sri Lanka (Hikkaduwa, Mirrissa, Vanakalai & Vidattaltivu) |
| --- | --- |
| Date and Time for Return of Bids | Tuesday 1 October 2024 @ 16:00 Hours (UK) |
| Contract Reference Number | C24-0604-1938 |
| Address for Bid Submission | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND BIDS DIRECTLY TO HANNAH LAWSON, HOLLY BAIGENT, OR A MEMBER OF THE JNCC PROCUREMENT TEAM VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the number below: (00 44 1733 866 988) |
| Contacts for Technical Information relating to this Project Specification | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: 01733 866987 |
| Contact for Queries Regarding the Procurement Procedure | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: 01733 866987 |
| Proposed Start Date | 14 October 2024 |
| Proposed End Date | 31 March 2025 |

Ocean Country Partnership Programme: Sri Lanka

Title: Technical delivery of stakeholder led Protected Area Management Effectiveness assessments for four Marine Protected Areas across Sri Lanka (Hikkaduwa, Mirrissa, Vanakalai & Vidattaltivu)

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Background	3

3.	Project Aims	4

4.	Project Objectives	5

5.	Contractor Requirements	6

6.	Potential Follow-On Work	7

7.	Product Specification	7

8.	Dissemination	7

9.	Timescale	8

10.	Health and Safety	8

11.	Project Management	9

12.	Instructions for Bid Submission	9

13.	Evaluation Criteria	10

14.	Payment	11

15.	Additional Requirements	11

16.	Procurement Timetable (which may be subject to change)	11

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation.

Our role is to provide scientific evidence, information, and advice to inform decisions to protect the natural environment. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally, by:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/

JNCC has a responsibility to protect the people we work with, and who work for us, and we will continuously strive to prevent bullying, harassment, exploitation and abuse and child abuse from happening.

JNCC takes a Gender Equality and Social Inclusion (GESI) approach across all elements of our work (under the OCPP) to address unequal power relations and inequalities, reduce disparities and ensure equal rights, responsibilities, opportunities and respect for all individuals. JNCC also takes all reasonable steps to safeguard the people we come into contact with (including staff and the communities in which programmes are delivered) from sexual exploitation, abuse and harassment (SEAH).  JNCC will work with the successful bidder to meet GESI and safeguarding expectations, including the collection of data to evaluate GESI under this project.

## Project Background

JNCC is a delivery partner for the Ocean Country Partnership Programme (OCPP), a UK government-led programme under the Blue Planet Programme. More information on the OCPP can be found here: https://www.gov.uk/government/publications/blue-planet-fund/ocean-country-partnership-programme-ocpp.

Through OCPP we aim to support countries to strengthen marine science expertise, develop science-based policy and management tools and create educational resources for coastal communities. There are three main objectives for the OCPP:

- Marine Pollution:- supporting countries to be equipped with the skills and expertise needed to tackle, reduce and mitigate marine pollution through the development of science led policy and improve our understanding of the impacts of pollution, as well as identifying and supporting effective responses, we will make sure that communities are better equipped to prevent and manage marine pollution. This will improve health and livelihoods.

- Sustainable Seafood:- supporting the development of the skills and expertise needed to adopt sustainable seafood practices to reduce risks such as the spread of zoonotic diseases from unsustainable or unsafe activities and support trade in safe seafood. Assisting countries to crack down on illegal, unreported and unregulated fishing by supporting the development of better management, monitoring and enforcement capabilities.

- Marine Biodiversity:- supporting countries to develop the skills and expertise needed to establish designated, well-managed and enforced marine protected areas to support healthy ecosystems with thriving biodiversity and fisheries that communities rely on for food and livelihoods. Achieving these objectives by strengthening marine science expertise, developing evidence-based policy and management tools, and creating educational resources for coastal communities.

JNCC on behalf of the OCPP is working in collaboration with the Sri Lanka Government providing technical assistance focused on MPAs and marine biodiversity.

This contract is being delivered on behalf of the Government of Sri Lanka, Department of Wildlife Conservation (DWC).

## Project Aims

Protected Area Management Effectiveness (PAME) assessments are a vital tool used by protected area managers to measure and understand the impact of their management actions on achieving the objectives of the protected area. They help to identify priorities to improve future management, enable effective resource allocation and highlight successes. Additionally, the results of PAME assessments are increasingly being used to inform national and international environmental reporting commitments.

The OCPP is supporting the Government of Sri Lanka's Department of Wildlife Conservation (DWC) to undertake PAME assessments for MPAs across Sri Lanka. To date, five PAME assessments have been completed under this partnership using the Management Effectiveness Tracking Tool, version 4 (METT-4).  The METT-4 is one of the most well-known and commonly used PAME methods globally and has been previously used in Sri Lanka to assess the management effectiveness of terrestrial protected areas.

This contract aims to deliver four METT-4 assessments for the DWC in financial year 2024/25. Assessments will focus on Mirissa Whale Sanctuary, Hikkaduwa Marine National Park, Vidattaltivu Nature Reserve and Vankalai Sanctuary, and will be completed with full stakeholder input through organised workshops.

The main outputs will be:

- Four stakeholder workshops (one for each MPA)

- Four completed METT-4 Assessments (one for each MPA)

- A Workshop Summary Report

JNCC, on behalf of OCPP, will support the technical delivery of these METT-4 assessments and workshops by:

- Supplying presentation materials and technical resources from previous METT-4 assessments and workshops.

- Supply monitoring, evaluation and learning (MEL) materials to capture required MEL reporting for OCPP.

- Providing training on undertaking METT-4 assessments, including example assessments, guidance on inputting information and valuing questions, and pulling out management actions from the workshop discussions and outputs.

- Providing formal QA of completed METT-4 assessments and any other outputs associated with the contract package.

## Project Objectives

The objectives of this contract include:

- Collate relevant information, from a range of sources, for each MPA.

  - These may include legal and policy documentation, management plans, monitoring and evaluation reports, maps and spatial data, and scientific research papers.

  - This information will then be fed into the METT-4 assessment and used to provide evidence throughout.

- Work alongside DWC and the OCPP team, to identify suitable stakeholders for each MPA workshop.

  - Workshops should include up to 30 stakeholders from a wide range of backgrounds who use and depend on each MPA, have an interest in the management of the MPA, whose activities affect the MPA or who will be impacted by management within the MPA.

  - Providing support to DWC when they send out invitations to attendees in advance of the workshops, and ensuring attendance is acknowledged.

- Organise one-day stakeholder workshops (x4) within the vicinity of each of the four MPAs (Mirissa Whale Sanctuary, Hikkaduwa Marine National Park, Vidattaltivu Nature Reserve and Vankalai Sanctuary).

  - Identify and book suitable workshop venues for each of the four MPAs. These venues need to be accessible, affordable, have access to the internet, projector facilities, and be of a suitable size to comfortably host up to 40 people (attendees and staff).

  - Organise lunch and refreshments for each workshop, from preferably a local organisation, for workshop attendees.

  - Provide any additional workshop tools and equipment e.g., projector, flip charts, pens, notebooks, and set up the workshops on the day.

  - Developing workshop materials to support discussions, including presentation slides introducing key information about each MPA, purpose of the workshop and breakout questions (OCPP can provide presentation materials and resources from previous METT-4 workshops). All materials to be in the appropriate local language.

  - Facilitate breakout groups within each workshop to gather relevant information to input into the METT-4 spreadsheet.

  - Capture stakeholder discussions and responses throughout the workshop.

- Coordinate a local travel, and subsistence payment for workshop attendees.

  - A small stipend is to be provided to cover the travel and subsistence of the stakeholders to travel locally to the workshop venue and any subsistence during their travel. For audit purposes, a collection of receipts or a signed declaration is required from each attendee when receiving the stipend.

  - If any stakeholders request additional support for travel and subsistence (for example, accommodation for a night or a larger reimbursement) this should be directed to JNCC to handle as soon as possible.

  - Attendees time to attend the workshop is not being covered.

- Support the translation (between Tamil, Sinhala and English) of presentations, questions, flipcharts and discussions throughout and after the workshops, to ensure all stakeholder opinions and statements are captured.

- Upon completion of the workshops, provide clean write ups of the flipcharts and information collected throughout each workshop in English, ideally as a brief workshop summary for each MPA.

- With support from the OCPP team, input information and complete the METT-4 assessments for each MPA.

- With support from the OCPP team, pull-out key management recommendations to feedback to DWC.

## Contractor Requirements

The successful contractor should:

- Have a broad understanding of PAME assessments and how they can be used to support management of protected areas.

- Have previous experience of planning and facilitating workshops in Sri Lanka that have included a range of stakeholders and varied in size, from small groups to over 30 participants.

- Have a good, overarching understanding of MPAs in Sri Lanka. Including a broad understanding of the marine habitats and species they protect, Sri Lanka’s legislation and current management of MPAs.

- Be familiar with existing information regarding Mirissa Whale Sanctuary, Hikkaduwa Marine National Park, Vidattaltivu Nature Reserve and Vankalai Sanctuary.

- Have a good understanding and ideally existing relationships with the local stakeholders at each of the four MPA locations.

- Be confident in translating between Tamil, Sinhala and English both verbally and through written text.

- Have experience of producing workshop reports that summarise the key findings from workshops.

## Potential Follow-On Work

Bidders should be aware that there is the potential for the successful bidder to be requested by JNCC to undertake additional work on this contract into the financial year 2025/26. This could include further stakeholder workshops.

Please note however that the potential for additional work to be undertaken is subject to a continuing need, availability of funds and satisfactory contractor performance. For the avoidance of doubt, no guarantee can be given that you will be asked to undertake the potential additional work outlined within this Annex A document. Bidders are not asked to provide detailed project plans for these follow-on aspects at this stage.

## Product Specification

All outputs will be shared with JNCC and DWC to support future management of these MPAs. Outputs may be made publicly available.

JNCC is committed to making its publicly available resources and documents accessible, in accordance with the Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.

All reports and other documentation which are to be made publicly available must be produced using an OCPP template (to be provided), unless otherwise stated. All reports (draft and final) should be provided electronically via email both as a Microsoft Word document and an Adobe PDF.

The outputs and material that JNCC publishes should be compliant with the Web Content Accessibility Guidelines version 2.1 AA standard.

Making material accessible means making sure it can be used by as many people as possible. This includes those with:

- impaired vision

- motor difficulties

- cognitive impairments or learning disabilities

- deafness or impaired hearing

## Dissemination

The products/outputs produced under this contract will be a JNCC product and shall not be published or disseminated without the written permission of JNCC. Outputs may at some point be published on the JNCC website and all material supplied as part of this contract shall remain copyright of JNCC. The findings from this contract will also be made available to OCPP partner governments.

## Timescale

Provisional dates for delivery of the contact outputs are set out below. Exact dates are to be agreed at the start-up meeting based on Contractor and JNCC staff availability.

| Output | Provisional Date |
| --- | --- |
| Start-up meeting (via video call) | 14th October 2024 |
| PAME training session 1 with JNCC (via video call) | Week commencing 21st October 2024 |
| Confirmed stakeholder lists for each workshop. | 28th October 2024 |
| Booking of venues for the four workshops. | 11th November 2024 |
| Finish collation of relevant documents and resources for each MPA. | 18th November 2024 |
| Successful delivery of four PAME workshops | 17th January 2025 |
| Translated summaries of answers to each question for the workshops including notes and flipcharts. | 27th January 2025 |
| PAME training session 2 with JNCC (in person) | 27th January - 14th February 2025 (1-2 days within this timeframe) |
| Assessments completed for each MPA. | 28th February 2025 |
| Assessment summary workshop reports written, management actions identified and prioritised. | 21st March 2025 |

In agreeing exact dates, please note that the potential for work under this contract to be funded into 2025/26 is subject to availability of funds.

## Health and Safety

The successful bidder is expected to follow appropriate Health and Safety Procedures including adhering to JNCC’ policy on safeguarding. For further information  https://jncc.gov.uk/about-jncc/corporate-information/safeguarding/ and to be able to undertake appropriate risk assessments, evidence of which should be supplied to JNCC.

(NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by the JNCC H&S Advisor)

Any incidents occurring within the contract period should be immediately reported to JNCC.

## Project Management

The successful Contractor shall nominate a project manager who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Name: Hannah Lawson

Email: Hannah.lawson@jncc.gov.uk

Telephone: (+44) 07503535710

Name: Holly Baigent

Email:  holly.baigent@jncc.gov.uk

Telephone: (+44) 01733 866986

## Instructions for Bid Submission

The bid submission should include the following:

A brief summary of the bidder’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract and delivering the detailed tasks identified within each objective. This should be sufficiently detailed to allow assessment against the evaluation criteria (Section 11);

A detailed project plan (including Gantt chart) with proposed work programme and an estimate of time required to achieve each objective;

Details of the Project Team including their roles and experience

Overall quote for the contract (in GBP) should include:

  - Attending virtual start-up, interim and final meetings with JNCC project team.

  - Costs and time allocation should be clearly allocated to specific tasks within this contract/project.

The following documentation:

  - If your company includes more than 5 employees, please provide copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates; Bidders should indicate the type of insurances they do hold and to submit copies of these insurance documents.

In addition, note that the bid submission should provide sufficient information to allow assessment against the evaluation criteria outlined in Section 11.

## Evaluation Criteria

JNCC is not bound to accept the lowest priced or any bid. Having the technical expertise and experience to complete the work to a high standard and being able to complete it within the timescale are of the essence for this contract.

The bid evaluation may be undertaken by JNCC staff.

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Maximum Score | Score |
| --- | --- | --- | --- |
| 1. Quality of Bid (30% of the total for the three assessment categories) |  |  |  |
| 1 | Clarity of proposal particularly work programme and deliverables | 10 |  |
| 2 | Understanding of the requirements and adequacy of outputs | 10 |  |
| 3 | Soundness and logicality of methods | 5 |  |
| 4 | Serious weaknesses which threaten success including identification and proposed solutions to potential risks/issue | 5 |  |
|  | Sub Total | 30 |  |
| 2. Details of Contractor (55% of the total for the three assessment categories) |  |  |  |
| 5 | Relevant expertise and experience organising and facilitating workshops in Sri Lanka with an environmental focus. | 15 |  |
| 6 | Relevant knowledge and experience of working with a range of stakeholders in Mirissa Whale Sanctuary, Hikkaduwa Marine National Park, Vidattaltivu Nature Reserve and Vankalai Sanctuary. | 10 |  |
| 7 | Familiarity with Sri Lanka’s MPAs and management, ideally with a focus on Mirissa Whale Sanctuary, Hikkaduwa Marine National Park, Vidattaltivu Nature Reserve and Vankalai Sanctuary. | 15 |  |
| 8 | Ability within suggested team to translate between English, Tamil, and Sinhala both verbally and written | 10 |  |
| 9 | Experience with PAME assessments and producing written summaries from workshops. | 5 |  |
|  | Sub Total | 55 |  |
| 3. Cost (15% of the total for the three assessment categories) |  |  |  |
| 10 | Transparency and correctness of presentation | 10 |  |
| 11 | Fairness/reasonableness for the level of work and expertise required | 5 |  |
|  | Sub Total | 15 |  |
| Total Score |  | 100 |  |

## Payment

PLEASE NOTE: All quotes and all payments must be based on British Pounds (£). If alternative currency payments are needed, please raise this at the earliest opportunity during the bid process so we can explore options.

Payment will be made on completion of the objectives following the submission of invoice(s) and based on the satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key outputs.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates/fees given.

The bidder is expected to supply all necessary equipment, software, licences, etc. to carry out the obligations required under the contract.

## Procurement Timetable (which may be subject to change)

| Activity | Date |
| --- | --- |
| Publication of Contract Notice | 5 September 2024 |
| Last date for receipt of clarification questions | 24 September 2024 |
| Final submission date for bids | 1 October 2024 |
| Evaluation of bids | w/e 4 October 2024 |
| Post-tender negotiation/clarification and or presentation if required | w/e 4 October 2024 |
| Successful Bidder Notified & Contract award | w/c 7 October 2024 |
| Unsuccessful bidders notified | w/e 11 October 2024 |
| Start of project | 14 October 2024 |