## Instructions
PMFDT KEY PERFORMANCE INDICATORS
1 | Introduction
1.1 | The management of this Call Off Contract is such that the Employer can decide prior to further competition that a level of Pain / Gain shall apply. The maximum deduction equates to the percentage of the Call Off Contract at risk; the maximum benefit equates to the percentage of the Call Off Contract identified as a bonus.
1.2 | Performance in the delivery of the Services is measured by the application of a number of Key Performance Indicators. Failure to perform against these service measures may result in payment deduction; performance excellence may result in additional payment.
1.3 | Individual Key Performance Indicators are weighted by the Employer which is done to reflect the priorities of the Key Performance Indicators against the Employers objectives; there is also the option for the Employer to determine bespoke Key Performance Indicators, thereby leading to maximum flexibility depending on the Employer-specific requirements and strategic objectives.
1.4 | A number of the Key Performance Indicators are negative only, this means that a payment deduction will be applied for poor performance but there will be no additional bonus payment for excellent performance. Therefore, dependent on the weightings applied, the maximum gain may be lower than the maximum gain percentage amount specified; the intent is that such indicators shall be used sparingly.
1.5 | This Key Performance Indicator template is designed to be suitable for use against all lots under the Project Management and Full Design Team Services framework, however certain Key Performance Indicators will not be suitable for all Lots. Employers shall, at their sole discretion, weight certain KPI's at zero weighting where they are inappropriate for use.
1.6 | This KPI document is intended to be a live document and the Key Performance Indicators will be modified over the lifecycle of the contract to incorporate Employer feedback, Supplier feedback, errors and omissions and new innovative Key Performance Indicators as appropriate. Key areas identified for further development are the incorporation of Key Performance Indicators aligned to encouraging the reduction of whole life cost of ownership for assets (TOTEX) and the reduction of carbon emissions over the lifecycle of the built asset.
1.7 | It is intended that upon placement of the Project Management Full Design Team Services Framework Agreements, the Authority shall review the Key Performance Indicator model with Employers and the Suppliers with a view to improvement prior to contract. For the avoidance of doubt, the Employer shall have ultimate discretion over the Key Performance Indicators utilised and the pain / gain percentage on offer.
2 | Sheets and Functionality
2.1 | This KPI document has a number of different sheets: 1. Instructions - this sheet informs on the model, its intended utilisation and gives guidance on how to use the model; 2. Call Off KPI's - this sheet is designed to be the record of KPI's to be used, inclusive of all variables and be used to calculate attainment; and 3. Look Up Tables - this is a datasheet that drives certain calculations within the "Call Off KPI's sheet", there is no other use for this sheet.
2.2 | The functions of the KPI model are: - To allow setting of the level of pain / gain which shall apply to the order, prior to any action for further completion, up to the maximum levels identified in the Framework Agreement; - To allow identification of the required KPI's, or creation of bespoke KPI's, by the Employer prior to any action for further competition, noting that some KPI's are negative only and shall reduce the maximum pain applicable; - To enable the Employer to allocate weightings of the KPI's based on their relative importance prior to further competition. Where a weighting is set at zero (0), the KPI shall not count towards calculation of the pain gain, but associated data shall still be recorded if practicable; and - To allow sense checking and failure testing of the KPI's, prior to utilising the model within a further competition. - To allow easy calculation of Consultant attainment and associated monetary pain / gain for utilisation in final valuation for payments.
3 | Call Off KPI's - Instructions for Use - Prior to Further Competition
3.1 | Prior to the call for further competition, the Employer must complete all boxes shaded in BLUE, these boxes are required information that may influence how Consultants bid for the opportunity to provide the services. The boxes to be completed in BLUE are:
3.2 | - Maximum Pain and Maximum Gain - the Employer can set the maximum pain and gain associated with the order within framework allowed by the Framework Agreement (±-10%). It should be noted that the pain / gain does not have to be equal, and can be set to 0 (zero) for pain, gain or both.
3.3 | - Insert Bespoke KPI's if required - should the Employer have any bespoke KPI's that they wish to apply to the order, they can insert them into the KPI table prior to the call for further competition, along with any instructions required to use the bespoke KPI's. Please note that care must be taken to retain the integrity of the KPI spreadsheet when making amendments; this includes both amendments to incorporate bespoke KPI's and unintentional formula amendments. Crown Commercial Services can support the introduction of new KPI's if required.
3.4 | - KPI weightings - all default weightings are available to be tailored by the Employer, it should be noted that care should be taken when amending weightings to ensure that the total of the weightings is equal to 100%, also care should be taken to ensure the impact of pain only KPI's are used as these reduce the maximum gain available to the Supplier.
4 | Call Off KPI's - Instructions for Use - Once Consultant has been selected
4.1 | Once the Consultant has been selected, the following information can be inserted into the model. These boxes are shared in GREEN
4.2 | Value of Services - this value will enable the calculation of the Consultant pain / gain.
4.3 | Baseline date for KPI 01 & KPI 02 - this will enable calculation of the attainment of project cost and services cost performance.
5 | Utilisation of the Call Off KPI model
5.1 | The model is designed to encourage understanding of it's workings, whilst cells are locked to ensure integrity of the model, an unlocked version is available on request from CCS to allow further interrogation of the model.
5.2 | Call Off KPI's are the only measures to impact on the Consultant fee, they can be amended at the time for further competition by the Employer. They are designed to be project specific and of interest to the delivery of individual projects and programmes.
5.3 | Any other indicators, such as Management Information or Mandatory Returns are not intended to impact this model. There may be some intended duplication of information provided as part of this model and Management Information.
5.4 | Each Key Performance Indicator has a data entry field, with an explanation of the units associated with that field.
5.5 | On a periodic basis (for trending purposes) the Consultant / Employer should enter agreed data into the ORANGE boxes.
5.6 | Particular care should be made to ensuring that any accepted compensation events, which amends the fee to deliver the Services or the expected price of the Construction project, are incorporated into the appropriate cells.
5.7 | At Completion, the final data should be entered into the ORANGE boxes, this shall be auditable data agreed between the parties.
5.8 | This model shall then calculate the final pain / gain through performance of the Consultant.
5.9 | This value returned by the KPI model shall be applied to the final application for payment, or repaid as a debt by the Consultant as appropriate.
6 | Disagreements shall be resolved using the dispute resolution process specified in the contract.

## Call Off KPI's
Call Off Key Performance Indicators
|  |  |  | Call Off Pain (at risk percentage) | 10% |  |  | Maximum Allowable Pain |  | 10%
|  |  |  | Call off Gain (bonus percentage) | 5% |  |  | Maximum Allowable Gain |  | 10%
Step 1. Insert information required prior to Call Off for Further Competition - pale blue cells (Cell I3, I4, and Column K14-K25), plus Employer bespoke KPI's using lines K27,K28,K29 if desired) |  |  |  | Gain Share Potential | 500000 |  |  |  |  | Step 3. Insert information based on actual performance (Cells N14-N25)
Step 2. Insert winning bid information in bright green cells once Consultant as been selected (or when otherwise availible) (Cell I9 and L15) |  |  |  | Pain Share Potential | 1000000 |  |  |  |  | Step 4. Retrieve total pain / gain from cell H31 and apply it to final valuation certificate
|  |  |  | Value of Services | 10000000
Service Element | KPI | Explanation |  | Monitoring Method/Metrics | Suggested Monitoring Period | Weighting | Baseline | Unit | Actual Value | Unit | Target Score | Supplier Attainment | (Unweighted) Fee Impact Explanation | Unweighted % Impact | Fee Impact
Cost | KPI 01 Delivery to Price - Project Turn Out | Delivery of the Construction Project at a price consistent (or lower) with any pre-agreed construction budget. This may be informed by the cost management strategy and recorded in a Project Initiation Document or Project Brief. This construction budget may be varied by Employer Instruction which materially effects the design / specification being delivered, or where the budget is articifically low due to consultant ommission. |  | Prior to commencing monitoring, agree and record the Construction Budget as the baseline, the out-turn is either the reassessment of construction budget post design, the accepted tender cost of the construction contractors, or the actual constructed value. | Key Milestone Stages as defined by the client. | 30% | 1 | Estimate Final Project Construction Price (£) |  | Final Project Construction Price (£) | <100% | 0% | >25% construction saving/overspend = 100% gain/pain 25%-16% construction saving/overspend = 80% gain/pain 15% - 7% construction saving/overspend = 40% gain/pain 6% - 5% construction saving/overspend = 20% gain/pain 4%-3% construction saving/overspend = 10% gain/pain 2%-1% construction saving/overspend = 5% gain/pain | 0% | 0
| KPI 02 Delivery to Price - Consultants Services. | Delivery of the Service(s) consistent with the Fee Structure agreed with the Customer at Call Off, as amended by the terms of a Direct Appointment or Mini Competition. |  | Prior to commencement of Monitoring, the Consultant and Customer shall agree the Fee Structure, procedures for reporting, payment and basis for any variations if different from that set out in the Framework Specifications. The key measure of performance will be the delivery of the Services, in line with the price agreed, prior to the letting of the Call Off order: | Quarterly | 25% | 10000000 | Initial Fee Structure (£) |  | PSPD (£) | <100% | 0% | >30% fees saving/overspend = 100% gain/pain 30%-21%fees saving/overspend = 80% gain/pain 20%- 16% fees saving/overspend = 40% gain/pain 15% - 11% fees saving/overspend = 20% gain/pain 10% - 6% fees saving/overspend = 10% gain / pain 5% - 1% fees saving/overspend = 5% gain / pain | 0% | 0
Time | KPI 03 Delivery to Programme - Project Turn Out | Delivery of the Construction project at a time consistent with the pre-agreed construction schedule. |  | Prior to monitoring, agree the programme for the Construction Project including key dates and Deliverables. The key measurement will be the timely delivery or otherwise of the Construction Project, in accordance with the accepted programme(s) and key dates. | Quarterly or as agreed on the project basis and programme | 15% | 0 | n/a |  | Days late of Completion and other customer defined milestones / deliverables (On time is defined as having a 1 day tolerance) | On time | 0 | Completion on time = no impact Completion 2 day early / late = 5% gain / pain Completion 1 week early / late = 10% gain / pain Completion 30 days early / late = 40% gain / pain Completion >60 days early / late = 100% gain / pain | 0% | 0
Time | KPI 04 Delivery to Programme - Consultants Services | Completion of the services, and the meeting of specified conditions by key dates. |  | The key criteria for measurement includes: * Were the services provided in line with the completion date? * Were the stated conditions met by the key dates? * Were any Early Warnings / Compensation Events addressed, including any appropriate risk reduction measures? | Quarterly or as agreed on the project basis and programme | 15% | 0 | n/a |  | Days late of Completion and other customer defined milestones / deliverables (On time is defined as having a 1 day tolerance) | On time | 0 | Completion on time = no impact Completion 2 day early / late = 5% gain / pain Completion 1 week early / late = 10% gain / pain Completion 30 days early / late = 40% gain / pain Completion >60 days early / late = 100% gain / pain | 0% | 0
Quality | KPI 05 Delivery of the Consultants Services to Specification and Required Standards and Quality | Provision of the services in accordance with the Scope agreed with the Employer, the Specification and applicable Standards/Regulations. |  | Monitoring method to be the number of written complaints made by the Employer regarding the standard of performance being delivered. Complaints may be made for the delivery of a poor quality PMFDT service with defects/rework over and above what should be expected by 'third party comments', provision of a non-responsive service, or the lack of adequate contract management including the provision of proportionate Early Warnings and Compensation Events. | Quarterly | 5% | 0 | n/a |  | Number of customer complaints | No complaints over service made | 0 | No complaints = 100% 1 compliant on service quality = 95% 2 complaints on service quality = 90% 3 complaints on service quality = 60% More than 3 complaints on service quality = 0% | 0% | 0
| KPI 06 Consultants Resources and Staff Continuity | Provision of resources, with appropriate experience and skill level, and continuity of allocated staff. |  | The key criteria for measurement is the number of events where key persons are proposed and not accepted by the Employer, or where a key person is not proposed by the consultant within 3 weeks of being removed from providing the services Acceptance of key persons may include the following considerations: * Were resources for key roles with appropriate experience and skill allocated to the task ? * Was access to, and appropriate use of, Supply Chain partners evident? | Quarterly | 2% | 0 | n/a |  | Number of events where key persons are not proposed within 3 weeks by Consultant and accepted by the Employer. | All Key Persons accepted | 0 | All key personnel proposed accepted = 100% 1 instance of rejection of key personnel = 95% 2 instances of rejection of key personnel = 90% 3 instances of rejection of key personnel = 60% More than 3 instances of rejection of key personnel = 0% | 0% | 0
0%
Sustainability | KPI 07 Cost and Management Information Reporting | Delivery of right first time cost and management data. |  | Measured by the delivery of quality Management Information delivered on time as described by the Framework Schedule 9 and Cost Information for the Employer, as descirbed in the Contractong Authority Scope. | Quarterly | 5% | 0% | n/a | 2 | Number of data quality issues - this being instances where Consultant provides late, incomplete or poor quality data | Zero data quality issues (instances of late or poor quality data submittals by the Consultant) | 200% | No data quality issues = 100% 1 data quality issue = 95% 2 data quality issues = 90% 3 data quality issues = 80% 4 data quality issues = 60% 5 data quality issues = 40% More than 5 data quality issues= 0% | -10% | -2500
| KPI 08 Fair Payment for Services, works and products to Supply Chain Partners | Demonstrate that the Consultant has complied with the Government policies, subject to any specific payment terms agreed with Supply Chain Partners. |  | Measured as the number of payments made by the Consultant outside of the 30 days stated within the Government fair payment charter. | Quarterly | 2% | 0 | n/a |  | Instances of breaching fair payment charter | No instances of breaching fair payment charter | 0 | 0 instances = 100% 1 instance = 80% 2 instances = 70% 3 instances = 60% 4 instances = 0% | 0% | 0
| KPI 09 Health & Safety - Compliance with CDM Regulations | Demonstrate Management of H&S and Compliance, with CDM Regulations, as applicable to the Call Off Appointment. |  | Measured as the number of RIDDOR recordable incidents by Consultant staff (including Contract Supplied Workers, Agency Supplied Workers and all sub-consultants) who are working on delivering the services. | Quarterly | 1% | 0 | n/a |  | RIDDOR recordable incidents | Zero reportable accidents | 0 | 0 instances = 100% 1 instance = 80% 2 instances = 70% 3 instances = 60% 4 instances = 0% | 0% | 0
Performance Indicators | KPI 10 Customer Satisfaction | This KPI is reserved for a user defined customer satisfaction KPI where required. |  |  |  | 0% | [5 empty] | 0
| KPI 11 Customer Bespoke | Left blank for Customer bespoke KPI |  |  |  | 0% | [5 empty] | 0
| KPI 12 Customer Bespoke | Left blank for Customer bespoke KPI |  |  |  | 0% | [5 empty] | 0
Checksums | [5 empty] | 100%
|  |  | Total Pain / Gain Amount to be applied to final valuation for payment | -2500
Note on N17: Use a negative number if delivered early
Note on K20: This is a negative only metric, therefore any weighting greater than 0 reduces the gain share potential
Note on K21: This is a negative only metric, therefore any weighting greater than 0 reduces the gain share potential
Note on K23: This is a negative only metric, therefore any weighting greater than 0 reduces the gain share potential
Note on K24: This is a negative only metric, therefore any weighting greater than 0 reduces the gain share potential
Note on K25: This is a negative only metric, therefore any weighting greater than 0 reduces the gain share potential

## Look Up Tables
KPI 01 |  | KPI 02 |  | KPI 03 |  | KPI 04 |  | KPI 05 |  | KPI 06 |  | KPI 07 |  | KPI 08 |  | KPI 09
Project Spend | Supplier Score | Service Spend | Supplier Score | Completion days late | Supplier Score | Completion days late | Supplier Score | Customer Complaints | Supplier Score | Key Persons Rejected | Supplier Score | Data | Supplier Score | Fair Payment | Supplier Score | Riddor Occurnces | Supplier Score
0% | 0% | 0% | 0% | -101 | 100% | -101 | 100% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
1% | 100% | 1% | 100% | -100 | 100% | -100 | 100% | 1 | -5% | 1 | -5% | 1 | -5% | 1 | -20% | 1 | -20%
2% | 100% | 2% | 100% | -99 | 100% | -99 | 100% | 2 | -10% | 2 | -10% | 2 | -10% | 2 | -30% | 2 | -30%
3% | 100% | 3% | 100% | -98 | 100% | -98 | 100% | 3 | -40% | 3 | -40% | 3 | -20% | 3 | -40% | 3 | -40%
4% | 100% | 4% | 100% | -97 | 100% | -97 | 100% | 4 | -100% | 4 | -100% | 4 | -40% | 4 | -100% | 4 | -100%
5% | 100% | 5% | 100% | -96 | 100% | -96 | 100% | 5 | -100% | 5 | -100% | 5 | -60% | 5 | -100% | 5 | -100%
6% | 100% | 6% | 100% | -95 | 100% | -95 | 100% | 6 | -100% | 6 | -100% | 6 | -100% | 6 | -100% | 6 | -100%
7% | 100% | 7% | 100% | -94 | 100% | -94 | 100% | 7 | -100% | 7 | -100% | 7 | -100% | 7 | -100% | 7 | -100%
8% | 100% | 8% | 100% | -93 | 100% | -93 | 100% | 8 | -100% | 8 | -100% | 8 | -100% | 8 | -100% | 8 | -100%
9% | 100% | 9% | 100% | -92 | 100% | -92 | 100% | 9 | -100% | 9 | -100% | 9 | -100% | 9 | -100% | 9 | -100%
10% | 100% | 10% | 100% | -91 | 100% | -91 | 100% | 10 | -100% | 10 | -100% | 10 | -100% | 10 | -100% | 10 | -100%
11% | 100% | 11% | 100% | -90 | 100% | -90 | 100% | 11 | -100% | 11 | -100% | 11 | -100% | 11 | -100% | 11 | -100%
12% | 100% | 12% | 100% | -89 | 100% | -89 | 100% | 12 | -100% | 12 | -100% | 12 | -100% | 12 | -100% | 12 | -100%
13% | 100% | 13% | 100% | -88 | 100% | -88 | 100% | 13 | -100% | 13 | -100% | 13 | -100% | 13 | -100% | 13 | -100%
14% | 100% | 14% | 100% | -87 | 100% | -87 | 100% | 14 | -100% | 14 | -100% | 14 | -100% | 14 | -100% | 14 | -100%
15% | 100% | 15% | 100% | -86 | 100% | -86 | 100% | 15 | -100% | 15 | -100% | 15 | -100% | 15 | -100% | 15 | -100%
16% | 100% | 16% | 100% | -85 | 100% | -85 | 100% | 16 | -100% | 16 | -100% | 16 | -100% | 16 | -100% | 16 | -100%
17% | 100% | 17% | 100% | -84 | 100% | -84 | 100% | 17 | -100% | 17 | -100% | 17 | -100% | 17 | -100% | 17 | -100%
18% | 100% | 18% | 100% | -83 | 100% | -83 | 100% | 18 | -100% | 18 | -100% | 18 | -100% | 18 | -100% | 18 | -100%
19% | 100% | 19% | 100% | -82 | 100% | -82 | 100% | 19 | -100% | 19 | -100% | 19 | -100% | 19 | -100% | 19 | -100%
20% | 100% | 20% | 100% | -81 | 100% | -81 | 100% | 20 | -100% | 20 | -100% | 20 | -100% | 20 | -100% | 20 | -100%
21% | 100% | 21% | 100% | -80 | 100% | -80 | 100% | 21 | -100% | 21 | -100% | 21 | -100% | 21 | -100% | 21 | -100%
22% | 100% | 22% | 100% | -79 | 100% | -79 | 100% | 22 | -100% | 22 | -100% | 22 | -100% | 22 | -100% | 22 | -100%
23% | 100% | 23% | 100% | -78 | 100% | -78 | 100% | 23 | -100% | 23 | -100% | 23 | -100% | 23 | -100% | 23 | -100%
24% | 100% | 24% | 100% | -77 | 100% | -77 | 100% | 24 | -100% | 24 | -100% | 24 | -100% | 24 | -100% | 24 | -100%
25% | 100% | 25% | 100% | -76 | 100% | -76 | 100% | 25 | -100% | 25 | -100% | 25 | -100% | 25 | -100% | 25 | -100%
26% | 100% | 26% | 100% | -75 | 100% | -75 | 100% | 26 | -100% | 26 | -100% | 26 | -100% | 26 | -100% | 26 | -100%
27% | 100% | 27% | 100% | -74 | 100% | -74 | 100% | 27 | -100% | 27 | -100% | 27 | -100% | 27 | -100% | 27 | -100%
28% | 100% | 28% | 100% | -73 | 100% | -73 | 100% | 28 | -100% | 28 | -100% | 28 | -100% | 28 | -100% | 28 | -100%
29% | 100% | 29% | 100% | -72 | 100% | -72 | 100% | 29 | -100% | 29 | -100% | 29 | -100% | 29 | -100% | 29 | -100%
30% | 100% | 30% | 100% | -71 | 100% | -71 | 100% | 30 | -100% | 30 | -100% | 30 | -100% | 30 | -100% | 30 | -100%
31% | 100% | 31% | 100% | -70 | 100% | -70 | 100% | 31 | -100% | 31 | -100% | 31 | -100% | 31 | -100% | 31 | -100%
32% | 100% | 32% | 100% | -69 | 100% | -69 | 100% | 32 | -100% | 32 | -100% | 32 | -100% | 32 | -100% | 32 | -100%
33% | 100% | 33% | 100% | -68 | 100% | -68 | 100% | 33 | -100% | 33 | -100% | 33 | -100% | 33 | -100% | 33 | -100%
34% | 100% | 34% | 100% | -67 | 100% | -67 | 100% | 34 | -100% | 34 | -100% | 34 | -100% | 34 | -100% | 34 | -100%
35% | 100% | 35% | 100% | -66 | 100% | -66 | 100% | 35 | -100% | 35 | -100% | 35 | -100% | 35 | -100% | 35 | -100%
36% | 100% | 36% | 100% | -65 | 100% | -65 | 100% | 36 | -100% | 36 | -100% | 36 | -100% | 36 | -100% | 36 | -100%
37% | 100% | 37% | 100% | -64 | 100% | -64 | 100% | 37 | -100% | 37 | -100% | 37 | -100% | 37 | -100% | 37 | -100%
38% | 100% | 38% | 100% | -63 | 100% | -63 | 100% | 38 | -100% | 38 | -100% | 38 | -100% | 38 | -100% | 38 | -100%
39% | 100% | 39% | 100% | -62 | 100% | -62 | 100% | 39 | -100% | 39 | -100% | 39 | -100% | 39 | -100% | 39 | -100%
40% | 100% | 40% | 100% | -61 | 100% | -61 | 100% | 40 | -100% | 40 | -100% | 40 | -100% | 40 | -100% | 40 | -100%
41% | 100% | 41% | 100% | -60 | 100% | -60 | 100% | 41 | -100% | 41 | -100% | 41 | -100% | 41 | -100% | 41 | -100%
42% | 100% | 42% | 100% | -59 | 40% | -59 | 40% | 42 | -100% | 42 | -100% | 42 | -100% | 42 | -100% | 42 | -100%
43% | 100% | 43% | 100% | -58 | 40% | -58 | 40% | 43 | -100% | 43 | -100% | 43 | -100% | 43 | -100% | 43 | -100%
44% | 100% | 44% | 100% | -57 | 40% | -57 | 40% | 44 | -100% | 44 | -100% | 44 | -100% | 44 | -100% | 44 | -100%
45% | 100% | 45% | 100% | -56 | 40% | -56 | 40% | 45 | -100% | 45 | -100% | 45 | -100% | 45 | -100% | 45 | -100%
46% | 100% | 46% | 100% | -55 | 40% | -55 | 40% | 46 | -100% | 46 | -100% | 46 | -100% | 46 | -100% | 46 | -100%
47% | 100% | 47% | 100% | -54 | 40% | -54 | 40% | 47 | -100% | 47 | -100% | 47 | -100% | 47 | -100% | 47 | -100%
48% | 100% | 48% | 100% | -53 | 40% | -53 | 40% | 48 | -100% | 48 | -100% | 48 | -100% | 48 | -100% | 48 | -100%
49% | 100% | 49% | 100% | -52 | 40% | -52 | 40% | 49 | -100% | 49 | -100% | 49 | -100% | 49 | -100% | 49 | -100%
50% | 100% | 50% | 100% | -51 | 40% | -51 | 40% | 50 | -100% | 50 | -100% | 50 | -100% | 50 | -100% | 50 | -100%
51% | 100% | 51% | 100% | -50 | 40% | -50 | 40% |  |  | 51 | -100% | 51 | -100% | 51 | -100% | 51 | -100%
52% | 100% | 52% | 100% | -49 | 40% | -49 | 40% |  |  | 52 | -100% | 52 | -100% | 52 | -100% | 52 | -100%
53% | 100% | 53% | 100% | -48 | 40% | -48 | 40% |  |  | 53 | -100% | 53 | -100% | 53 | -100% | 53 | -100%
54% | 100% | 54% | 100% | -47 | 40% | -47 | 40% |  |  | 54 | -100% | 54 | -100% | 54 | -100% | 54 | -100%
55% | 100% | 55% | 100% | -46 | 40% | -46 | 40% |  |  | 55 | -100% | 55 | -100% | 55 | -100% | 55 | -100%
56% | 100% | 56% | 100% | -45 | 40% | -45 | 40% |  |  | 56 | -100% | 56 | -100% | 56 | -100% | 56 | -100%
57% | 100% | 57% | 100% | -44 | 40% | -44 | 40% |  |  | 57 | -100% | 57 | -100% | 57 | -100% | 57 | -100%
58% | 100% | 58% | 100% | -43 | 40% | -43 | 40% |  |  | 58 | -100% | 58 | -100% | 58 | -100% | 58 | -100%
59% | 100% | 59% | 100% | -42 | 40% | -42 | 40% |  |  | 59 | -100% | 59 | -100% | 59 | -100% | 59 | -100%
60% | 100% | 60% | 100% | -41 | 40% | -41 | 40% |  |  | 60 | -100% | 60 | -100% | 60 | -100% | 60 | -100%
61% | 100% | 61% | 100% | -40 | 40% | -40 | 40% |  |  | 61 | -100% | 61 | -100% | 61 | -100% | 61 | -100%
62% | 100% | 62% | 100% | -39 | 40% | -39 | 40% |  |  | 62 | -100% | 62 | -100% | 62 | -100% | 62 | -100%
63% | 100% | 63% | 100% | -38 | 40% | -38 | 40% |  |  | 63 | -100% | 63 | -100% | 63 | -100% | 63 | -100%
64% | 100% | 64% | 100% | -37 | 40% | -37 | 40% |  |  | 64 | -100% | 64 | -100% | 64 | -100% | 64 | -100%
65% | 100% | 65% | 100% | -36 | 40% | -36 | 40% |  |  | 65 | -100% | 65 | -100% | 65 | -100% | 65 | -100%
66% | 100% | 66% | 100% | -35 | 40% | -35 | 40% |  |  | 66 | -100% | 66 | -100% | 66 | -100% | 66 | -100%
67% | 100% | 67% | 100% | -34 | 40% | -34 | 40% |  |  | 67 | -100% | 67 | -100% | 67 | -100% | 67 | -100%
68% | 100% | 68% | 100% | -33 | 40% | -33 | 40% |  |  | 68 | -100% | 68 | -100% | 68 | -100% | 68 | -100%
69% | 100% | 69% | 100% | -32 | 40% | -32 | 40% |  |  | 69 | -100% | 69 | -100% | 69 | -100% | 69 | -100%
70% | 100% | 70% | 80% | -31 | 40% | -31 | 40% |  |  | 70 | -100% | 70 | -100% | 70 | -100% | 70 | -100%
71% | 100% | 71% | 80% | -30 | 40% | -30 | 40% |  |  | 71 | -100% | 71 | -100% | 71 | -100% | 71 | -100%
72% | 100% | 72% | 80% | -29 | 10% | -29 | 10% |  |  | 72 | -100% | 72 | -100% | 72 | -100% | 72 | -100%
73% | 100% | 73% | 80% | -28 | 10% | -28 | 10% |  |  | 73 | -100% | 73 | -100% | 73 | -100% | 73 | -100%
74% | 100% | 74% | 80% | -27 | 10% | -27 | 10% |  |  | 74 | -100% | 74 | -100% | 74 | -100% | 74 | -100%
75% | 80% | 75% | 80% | -26 | 10% | -26 | 10% |  |  | 75 | -100% | 75 | -100% | 75 | -100% | 75 | -100%
76% | 80% | 76% | 80% | -25 | 10% | -25 | 10% |  |  | 76 | -100% | 76 | -100% | 76 | -100% | 76 | -100%
77% | 80% | 77% | 80% | -24 | 10% | -24 | 10% |  |  | 77 | -100% | 77 | -100% | 77 | -100% | 77 | -100%
78% | 80% | 78% | 80% | -23 | 10% | -23 | 10% |  |  | 78 | -100% | 78 | -100% | 78 | -100% | 78 | -100%
79% | 80% | 79% | 80% | -22 | 10% | -22 | 10% |  |  | 79 | -100% | 79 | -100% | 79 | -100% | 79 | -100%
80% | 80% | 80% | 40% | -21 | 10% | -21 | 10% |  |  | 80 | -100% | 80 | -100% | 80 | -100% | 80 | -100%
81% | 80% | 81% | 40% | -20 | 10% | -20 | 10% |  |  | 81 | -100% | 81 | -100% | 81 | -100% | 81 | -100%
82% | 80% | 82% | 40% | -19 | 10% | -19 | 10% |  |  | 82 | -100% | 82 | -100% | 82 | -100% | 82 | -100%
83% | 80% | 83% | 40% | -18 | 10% | -18 | 10% |  |  | 83 | -100% | 83 | -100% | 83 | -100% | 83 | -100%
84% | 80% | 84% | 40% | -17 | 10% | -17 | 10% |  |  | 84 | -100% | 84 | -100% | 84 | -100% | 84 | -100%
85% | 40% | 85% | 20% | -16 | 10% | -16 | 10% |  |  | 85 | -100% | 85 | -100% | 85 | -100% | 85 | -100%
86% | 40% | 86% | 20% | -15 | 10% | -15 | 10% |  |  | 86 | -100% | 86 | -100% | 86 | -100% | 86 | -100%
87% | 40% | 87% | 20% | -14 | 10% | -14 | 10% |  |  | 87 | -100% | 87 | -100% | 87 | -100% | 87 | -100%
88% | 40% | 88% | 20% | -13 | 10% | -13 | 10% |  |  | 88 | -100% | 88 | -100% | 88 | -100% | 88 | -100%
89% | 40% | 89% | 20% | -12 | 10% | -12 | 10% |  |  | 89 | -100% | 89 | -100% | 89 | -100% | 89 | -100%
90% | 40% | 90% | 10% | -11 | 10% | -11 | 10% |  |  | 90 | -100% | 90 | -100% | 90 | -100% | 90 | -100%
91% | 40% | 91% | 10% | -10 | 10% | -10 | 10% |  |  | 91 | -100% | 91 | -100% | 91 | -100% | 91 | -100%
92% | 40% | 92% | 10% | -9 | 10% | -9 | 10% |  |  | 92 | -100% | 92 | -100% | 92 | -100% | 92 | -100%
93% | 40% | 93% | 10% | -8 | 10% | -8 | 10% |  |  | 93 | -100% | 93 | -100% | 93 | -100% | 93 | -100%
94% | 20% | 94% | 10% | -7 | 5% | -7 | 5% |  |  | 94 | -100% | 94 | -100% | 94 | -100% | 94 | -100%
95% | 20% | 95% | 5% | -6 | 5% | -6 | 5% |  |  | 95 | -100% | 95 | -100% | 95 | -100% | 95 | -100%
96% | 10% | 96% | 5% | -5 | 5% | -5 | 5% |  |  | 96 | -100% | 96 | -100% | 96 | -100% | 96 | -100%
97% | 10% | 97% | 5% | -4 | 5% | -4 | 5% |  |  | 97 | -100% | 97 | -100% | 97 | -100% | 97 | -100%
98% | 5% | 98% | 5% | -3 | 5% | -3 | 5% |  |  | 98 | -100% | 98 | -100% | 98 | -100% | 98 | -100%
99% | 5% | 99% | 5% | -2 | 5% | -2 | 5% |  |  | 99 | -100% | 99 | -100% | 99 | -100% | 99 | -100%
100% | 0% | 100% | 0% | -1 | 0% | -1 | 0% |  |  | 100 | -100% | 100 | 100% | 100 | -100% | 100 | -100%
101% | -5% | 101% | -5% | 0 | 0% | 0 | 0%
102% | -5% | 102% | -5% | 1 | 0% | 1 | 0%
103% | -10% | 103% | -5% | 2 | -5% | 2 | -5%
104% | -10% | 104% | -5% | 3 | -5% | 3 | -5%
105% | -20% | 105% | -5% | 4 | -5% | 4 | -5%
106% | -20% | 106% | -10% | 5 | -5% | 5 | -5%
107% | -40% | 107% | -10% | 6 | -5% | 6 | -5%
108% | -40% | 108% | -10% | 7 | -5% | 7 | -5%
109% | -40% | 109% | -10% | 8 | -10% | 8 | -10%
110% | -40% | 110% | -10% | 9 | -10% | 9 | -10%
111% | -40% | 111% | -20% | 10 | -10% | 10 | -10%
112% | -40% | 112% | -20% | 11 | -10% | 11 | -10%
113% | -40% | 113% | -20% | 12 | -10% | 12 | -10%
114% | -40% | 114% | -20% | 13 | -10% | 13 | -10%
115% | -40% | 115% | -20% | 14 | -10% | 14 | -10%
116% | -80% | 116% | -40% | 15 | -10% | 15 | -10%
117% | -80% | 117% | -40% | 16 | -10% | 16 | -10%
118% | -80% | 118% | -40% | 17 | -10% | 17 | -10%
119% | -80% | 119% | -40% | 18 | -10% | 18 | -10%
120% | -80% | 120% | -40% | 19 | -10% | 19 | -10%
121% | -80% | 121% | -80% | 20 | -10% | 20 | -10%
122% | -80% | 122% | -80% | 21 | -10% | 21 | -10%
123% | -80% | 123% | -80% | 22 | -10% | 22 | -10%
124% | -80% | 124% | -80% | 23 | -10% | 23 | -10%
125% | -80% | 125% | -80% | 24 | -10% | 24 | -10%
126% | -100% | 126% | -80% | 25 | -10% | 25 | -10%
127% | -100% | 127% | -80% | 26 | -10% | 26 | -10%
128% | -100% | 128% | -80% | 27 | -10% | 27 | -10%
129% | -100% | 129% | -80% | 28 | -10% | 28 | -10%
130% | -100% | 130% | -80% | 29 | -10% | 29 | -10%
131% | -100% | 131% | -100% | 30 | -40% | 30 | -40%
132% | -100% | 132% | -100% | 31 | -40% | 31 | -40%
133% | -100% | 133% | -100% | 32 | -40% | 32 | -40%
134% | -100% | 134% | -100% | 33 | -40% | 33 | -40%
135% | -100% | 135% | -100% | 34 | -40% | 34 | -40%
136% | -100% | 136% | -100% | 35 | -40% | 35 | -40%
137% | -100% | 137% | -100% | 36 | -40% | 36 | -40%
138% | -100% | 138% | -100% | 37 | -40% | 37 | -40%
139% | -100% | 139% | -100% | 38 | -40% | 38 | -40%
140% | -100% | 140% | -100% | 39 | -40% | 39 | -40%
141% | -100% | 141% | -100% | 40 | -40% | 40 | -40%
142% | -100% | 142% | -100% | 41 | -40% | 41 | -40%
143% | -100% | 143% | -100% | 42 | -40% | 42 | -40%
144% | -100% | 144% | -100% | 43 | -40% | 43 | -40%
145% | -100% | 145% | -100% | 44 | -40% | 44 | -40%
146% | -100% | 146% | -100% | 45 | -40% | 45 | -40%
147% | -100% | 147% | -100% | 46 | -40% | 46 | -40%
148% | -100% | 148% | -100% | 47 | -40% | 47 | -40%
149% | -100% | 149% | -100% | 48 | -40% | 48 | -40%
150% | -100% | 150% | -100% | 49 | -40% | 49 | -40%
151% | -100% | 151% | -100% | 50 | -40% | 50 | -40%
152% | -100% | 152% | -100% | 51 | -40% | 51 | -40%
153% | -100% | 153% | -100% | 52 | -40% | 52 | -40%
154% | -100% | 154% | -100% | 53 | -40% | 53 | -40%
155% | -100% | 155% | -100% | 54 | -40% | 54 | -40%
156% | -100% | 156% | -100% | 55 | -40% | 55 | -40%
157% | -100% | 157% | -100% | 56 | -40% | 56 | -40%
158% | -100% | 158% | -100% | 57 | -40% | 57 | -40%
159% | -100% | 159% | -100% | 58 | -40% | 58 | -40%
160% | -100% | 160% | -100% | 59 | -40% | 59 | -40%
161% | -100% | 161% | -100% | 60 | -100% | 60 | -100%
162% | -100% | 162% | -100% | 61 | -100% | 61 | -100%
163% | -100% | 163% | -100% | 62 | -100% | 62 | -100%
164% | -100% | 164% | -100% | 63 | -100% | 63 | -100%
165% | -100% | 165% | -100% | 64 | -100% | 64 | -100%
166% | -100% | 166% | -100% | 65 | -100% | 65 | -100%
167% | -100% | 167% | -100% | 66 | -100% | 66 | -100%
168% | -100% | 168% | -100% | 67 | -100% | 67 | -100%
169% | -100% | 169% | -100% | 68 | -100% | 68 | -100%
170% | -100% | 170% | -100% | 69 | -100% | 69 | -100%
171% | -100% | 171% | -100% | 70 | -100% | 70 | -100%
172% | -100% | 172% | -100% | 71 | -100% | 71 | -100%
173% | -100% | 173% | -100% | 72 | -100% | 72 | -100%
174% | -100% | 174% | -100% | 73 | -100% | 73 | -100%
175% | -100% | 175% | -100% | 74 | -100% | 74 | -100%
176% | -100% | 176% | -100% | 75 | -100% | 75 | -100%
177% | -100% | 177% | -100% | 76 | -100% | 76 | -100%
178% | -100% | 178% | -100% | 77 | -100% | 77 | -100%
179% | -100% | 179% | -100% | 78 | -100% | 78 | -100%
180% | -100% | 180% | -100% | 79 | -100% | 79 | -100%
181% | -100% | 181% | -100% | 80 | -100% | 80 | -100%
182% | -100% | 182% | -100% | 81 | -100% | 81 | -100%
183% | -100% | 183% | -100% | 82 | -100% | 82 | -100%
184% | -100% | 184% | -100% | 83 | -100% | 83 | -100%
185% | -100% | 185% | -100% | 84 | -100% | 84 | -100%
186% | -100% | 186% | -100% | 85 | -100% | 85 | -100%
187% | -100% | 187% | -100% | 86 | -100% | 86 | -100%
188% | -100% | 188% | -100% | 87 | -100% | 87 | -100%
189% | -100% | 189% | -100% | 88 | -100% | 88 | -100%
190% | -100% | 190% | -100% | 89 | -100% | 89 | -100%
191% | -100% | 191% | -100% | 90 | -100% | 90 | -100%
192% | -100% | 192% | -100% | 91 | -100% | 91 | -100%
193% | -100% | 193% | -100% | 92 | -100% | 92 | -100%
194% | -100% | 194% | -100% | 93 | -100% | 93 | -100%
195% | -100% | 195% | -100% | 94 | -100% | 94 | -100%
196% | -100% | 196% | -100% | 95 | -100% | 95 | -100%
197% | -100% | 197% | -100% | 96 | -100% | 96 | -100%
198% | -100% | 198% | -100% | 97 | -100% | 97 | -100%
199% | -100% | 199% | -100% | 98 | -100% | 98 | -100%
200% | -100% | 200% | -100% | 99 | -100% | 99 | -100%
|  |  |  | 100 | -100% | 100 | -100%