## Cover Sheet
SCHEDULE 3C Passenger Transfer Boat Variant Tables 1 - 5 Table 1 - Summary of Build Requirements Table 2 - Passenger Tran Variant Table 2B - Contract Change Prices Table 3 - Firm Rates Table 4 - Planned Maintenance Table 5A - Capital Spares Table 5B - Initial Provisioning of Spares

## Table 1-Summary of Build
Schedule 3C (Passenger Transfer Boat Variant) - Table 1 - Summary of Build Requirements
Delivery Requirements
Workboat Variant | Firm Requirement |  |  |  | Firm / Option Requirement | Total | Statement of Technical Requirements Reference
| Contract Start Date to Mar 18 | FY 18/19 | FY 19/20 | FY 20/21 | FY 21/22
Standard Workboat |  | 1 x Apr-18 1 x Jun-18 1 x Sep-18 1 x Dec-18 1 x Mar-19 | 1 x Jun-19 1 x Sep-19 1 x Dec-19 | 1 x Dec-20 1 x Mar-21 | - | 10 | Section 2.1 and Annex 1
Survey Motor Launch |  | 1 x May-18 | - | - | - | 1 | Section 2.1, 2.2 and 2.2.1
Passenger Transfer Boat (for Prince of Wales) |  | 1 x Jun-18 1 x Jul-18 1 x Aug-18 | - | - | 1 x Nov-21 (option) 1 x Feb-22 (option) 1 x Mar-22 (option) | 3 - Firm 3 - Option | Section 2.1 and 2.3
Dive Support Boat | - |  | 1 x Apr-19 1 x Jul-19 1 x Oct-19 1 x Jan-20 | 1 x Apr-20 1 x Jun-20 1 x Sep-20 |  | 7 | Section 2.1 and 2.4
Officer Training | - | - | - | 1 x Mar-21 | 1 x May-21 1 x Jul-21 1 x Sep-21 1 x Nov-21 1 x Jan-22 1 x Feb-22 (option) 1 x Mar-22 (option) | 6 - Firm 2 - Option | Section 2.1 and 2.5
Survey Motor Boat (Medium) | - | - | - | 1 x Nov-20 1 x Jan-21 1 x Mar-21 |  | 3 | Section 2.1, 2.2 and 2.2.2
Survey Motor Boat (Small) | - | - | - |  | 1 x Jun-21 1 x Sep-21 1 x Dec-21 | 3 | Section 2.1 and 2.2 and Annex 1
Total | 0 | 9 | 7 | 9 | 13 | 38
A Financial Year run from April to March

## Table 2-Firm Prices
Schedule 3C (Passenger Transfer Boat Variant) - Table 2 - Firm Prices
Requirement for Delivery in FY 18/19
1 in number Passenger Transfer Boat Variant Statement of Technical Requirements (SoTR) Reference - Section 2.3 - Passenger Transfer Requirement
No | Firm Price per Boat (£) (ex VAT) (SoTR ref - Section 2.3 - Passenger Transfer) | Firm Price Training for (£) (ex VAT) (SoTR ref - Section 4.0 - Training (ID 133, 134 & 135)) | Firm Price for Documentation (£) (ex VAT) (SoTR ref - Section 3.0 - Documentation (ID 119, 120, 121, 123, 124, 125, 127, 128, 129 & 130)) | Firm Price for Initial Provisioning of Spares* (£) (ex VAT) (SoTR ref - Section 5.0 - Logisitics and In-Service Support (ID 140)) | Total Firm Price (£) (ex VAT) | Required Delivery Date (DD/MM/YYYY)
PTB-01 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | 2018-06-30
Requirement for Delivery in FY 18/19
2 in number Passenger Transfer Variant Statement of Technical Requirements (SoTR) Reference - Section 2.3 - Passenger Transfer Requirement
No | Firm Price per Boat (£) (ex VAT) (SoTR ref - Section 2.1 - Standard Workboat) | Firm Price Training for (£) (ex VAT) (SoTR ref - Section 4.0 - Training (ID 133, 134 & 135)) | Firm Price for Documentation (£) (ex VAT) (SoTR ref - Section 3.0 - Documentation (ID 127)) | Firm Price for Initial Provisioning of Spares* (£) (ex VAT) (SoTR ref - Section 5.0 - Logisitics and In-Service Support (ID 140)) | Total Firm Price (£) (ex VAT) | Required Delivery Date (DD/MM/YYYY)
PTB-02 | REDACTED | N/A | REDACTED | REDACTED | REDACTED | 2018-07-31
PTB-03 | REDACTED | N/A | REDACTED | REDACTED | REDACTED | 2018-08-31
Option Yr - for Delivery in FY 21/22
3 in number Passenger Transfer Variant Statement of Technical Requirements (SoTR) Reference - Section 2.3 - Passenger Transfer Requirement
No | Firm Price per Boat (£) (ex VAT) (SoTR ref - Section 2.1 - Standard Workboat) | Firm Price Training for (£) (ex VAT) (SoTR ref - Section 4.0 - Training (ID 133, 134 & 135)) | Firm Price for Documentation (£) (ex VAT) (SoTR ref - Section 3.0 - Documentation (ID 127)) | Firm Price for Initial Provisioning of Spares* (£) (ex VAT) (SoTR ref - Section 5.0 - Logisitics and In-Service Support (ID 140)) | Total Firm Price (£) (ex VAT) | Required Delivery Date (DD/MM/YYYY)
PTB-04 | REDACTED | N/A | REDACTED | REDACTED | REDACTED | 2021-11-30
PTB-05 | REDACTED | N/A | REDACTED | REDACTED | REDACTED | 2022-02-28
PTB-06 | REDACTED | N/A | REDACTED | REDACTED | REDACTED | 2022-03-31
Key
* = | This figure is automatically populated from Table 5b - Initial Provisioning of Spares

## Table 2a-CCP
Schedule 3C (Passenger Transfer Boat Variant) - Table 2A - Contract Change Prices
| FY 18/19 |  |  | FY 21/22
Boat No | PTB-01 | PTB-02 | PTB-03 | PTB-04 | PTB-05 | PTB-06
Original Boat Contract Value | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
CCP No
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
Revised Boat Contract Value | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED

## Table 3-Rates
Schedule 3C (Passenger Transfer Boat Variant) - Table 3 - Firm/Fixed Rates
ITEM No | ACTIVITY | YEAR 1 Contract Start Date-Mar 18 Firm Price (ex VAT) | YEAR 2 FY 18/19 Firm Price (ex VAT) | YEAR 3 FY 19/20 Firm Price (ex VAT) | YEAR 4 FY 20/21 Firm Price (ex VAT) | YEAR 5 FY 21/22 Firm Price (ex VAT) | YEAR 6 FY 22/23 Fixed Price (ex VAT) | YEAR 7 FY 23/24 Fixed Price (ex VAT)
1 | Weighted Average Hourly Rate (WAHR) -The WAHR rates below shall apply to all Contract Change Proposals, In Service tasking and Ad Hoc tasking authorised by the Authority and shall be either Firm rate, i.e. not subject to variation in any respect, or where stated a Fixed rate subject to variation in accordance with Clause 11 (Price). Rates shall be inclusive of all allowances, overtime, overheads and profit.
1.1 | Maintenance, upkeep and repair (for Planned & Unplanned work and Contract Change Proposals ) | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
1.2 | Design Office (for PDS and technical support work and Contract Change Proposals) | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
1.3 | Project Management (for PDS and technical support work and Contract Change Proposals) | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
1.4 | Administration (for PDS and technical support work and Contract Change Proposals) | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2 | Materiel/Spares and Sub-Contracts Handling Fee(s) - The percentage fees below shall apply to materiel/spares and sub-contract costs only and to all Contract Change Request Propsals and Ad Hoc tasking.
2.1 | Percentage uplift on Spares only | N/A | Year 1 to Year 2 | Year 2 to Year 3 | Year 3 to Year 4 | Year 4 to Year 5 | Year 5 to Year 6 | Year 6 to Year 7
|  |  | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.2 | Materiel/Spares Handling Fee (inclusive of profit) | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.3 | Sub-contract Fee (inclusive of profit) | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
3 | Travel and Subsistence Rates applicable to all Contractors personnel for work carried out away from the Contractor's Site (using the most economic method)
3.1 | Night Subsistence (per 24 hour period - inclusive of accommodation, meals and incidental expenses. | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
3.2 | Day Subsistence (5 to 10 hours away from the Contractor's site) | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
3.3 | Day Subsistence (more than 10 hours away from the Contractor's site) | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
3.4 | Car Hire - Rental (per day) | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
3.5 | Car Hire - Fuel (rate per mile) | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
3.6 | Private Car - Fuel (rate per mile) | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
3.7 | Public Transport | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
4 | Transport of Boats to and from the Authority's establishment to the Contractor's Site and/or Sub-contractor's premises (to include loading and unloading)
4.1 | Articulated lorry/low loader (rate per mile) | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
5 | Storage of Boats and/or Capital Spares (to include loading and unloading)
5.1 | Storage of Boats (per boat, per week) | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
5.2 | Storage of Capital Spare (per capital spare, per week) | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED

## Table 4-Planned Maintenance
Schedule 3C (Passenger Transfer Boat Variant) - Table 4 - Planned Maintenance
Tariff No. | Statement of Technical Requirement |  | YEAR 1 Contract Start Date-Mar 18 | YEAR 2 FY 18/19 | YEAR 3 FY 19/20 | YEAR 4 FY 20/21 | YEAR 5 FY 21/22 | YEAR 6 FY 22/23 | YEAR 7 FY 23/24
|  |  | Firm Price (ex VAT) | Firm Price (ex VAT) | Firm Price (ex VAT) | Firm Price (ex VAT) | Firm Price (ex VAT) | Fixed Price (ex VAT) | Fixed Price (ex VAT)
| Short Title | Description
1 | Contractors Annual Work package (At Contractors Premises) per boat in accordance with SoTR reference - Section 5.0 - Logistics and In-Service Support (ID 142)
PTB-1.1 | Contractors Annual Work package (At Contractors Premises) | The Contractor shall undertake firm priced annual maintenance package of calendar based inspection and maintenance when tasked through the Contract tasking process. The package is to include, but not limited to, tasks as follows: • Calendar based inspection and replacement activities (such as anodes, antifouling, skin fittings) • Calendar based inspection and certification of systems (such as fire fighting, lifting equipment, HP Air Systems) • Calendar based servicing and certification of equipment & systems (such as lifesaving appliances, lifting devices) • Replacement of Lifed items (hydraulic hoses etc) • MCA surveys and certification • Material state survey (for a further year of usage in application) • Production of survey report • Minor defect rectification (with limit of liability) | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | .
2 | Hours Based Maintenance (in accordance with Manufacturers Recommendations) per boat in accordance with SoTR reference - Section 5.0 - Logistics and In-Service Support (ID 143)
PTB-2.1 | Hours Based Maintenance (in accordance with Manufacturers Recommendations) - Main Engines | 2000 hours When tasked through the Contract tasking process, the Contractor shall undertake firm priced tariff items for the servicing and maintenance of systems & equipments in accordance with the manufacturers recommendations. The tariff items are to include, but not limited to, service tasks for: - Main Engines; | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
PTB-2.1.1 | Hours Based Maintenance (in accordance with Manufacturers Recommendations) - Main Engines | 250, 750, 1250 and 1750 hours | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
PTB-2.1.2 | Hours Based Maintenance (in accordance with Manufacturers Recommendations) - Main Engines | 500 and 1500 hours | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
PTB-2.1.3 | Hours Based Maintenance (in accordance with Manufacturers Recommendations) - Main Engines | 1000 hours | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
PTB-2.2 | Hours Based Maintenance (in accordance with Manufacturers Recommendations) - Generator | 2000 hours When tasked through the Contract tasking process, the Contractor shall undertake firm priced tariff items for the servicing and maintenance of systems & equipments in accordance with the manufacturers recommendations. The tariff items are to include, but not limited to, service tasks for: - Generator; | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
PTB-2.3 | Hours Based Maintenance (in accordance with Manufacturers Recommendations) - Gearbox | 2000 hours When tasked through the Contract tasking process, the Contractor shall undertake firm priced tariff items for the servicing and maintenance of systems & equipments in accordance with the manufacturers recommendations. The tariff items are to include, but not limited to, service tasks for: - Gearbox; | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
PTB-2.3.1 | Hours Based Maintenance (in accordance with Manufacturers Recommendations) - Gearbox | 250, 750, 1250 and 1750 hours | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
PTB-2.3.2 | Hours Based Maintenance (in accordance with Manufacturers Recommendations) - Gearbox | 500, 1000 and 1500 hours | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
PTB-2.4 | Hours Based Maintenance (in accordance with Manufacturers Recommendations) - Compressor | This is tariff item is not applicable for Passenger Transfer Boat Variant and is not to be priced
PTB-2.5 | Hours Based Maintenance (in accordance with Manufacturers Recommendations) - Propulsion System | 2000 hours When tasked through the Contract tasking process, the Contractor shall undertake firm priced tariff items for the servicing and maintenance of systems & equipments in accordance with the manufacturers recommendations. The tariff items are to include, but not limited to, service tasks for: - Propulsion System; | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
3 | Change of Outward Appearance per boat in accordance with SoTR reference - Section 5.0 - Logistics and In-Service Support (ID 144)
PTB-3.1 | Change of Outward Appearance | The Contractor shall undertake firm priced tariff item on the Replacement Workboat to change the outward appearance of the Hull and Superstructure through the application of a coloured coating. | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED

## Table 5a-Capital Spares
Schedule 3C (Passenger Transfer Boat Variant) - Table 5a- Capital Spares
Item No | IMC | NATO Stock Number |  | Description | D of Q | Delivery Timescale (Weeks) | YEAR 1 Contract Start Date-Mar 18 | YEAR 2 FY 18/19 | YEAR 3 FY 19/20 | YEAR 4 FY 20/21 | YEAR 5 FY 21/22 | YEAR 6 FY 22/23 | YEAR 7 FY 23/24
|  |  | Description & Part No |  |  |  | Firm Price (ex VAT) | Firm Price (ex VAT) | Firm Price (ex VAT) | Firm Price (ex VAT) | Firm Price (ex VAT) | Fixed Price (ex VAT) | Fixed Price (ex VAT)
1 | Capital Spares in accordance with SoTR reference - Section 5.0 - Logistics and In-Service Support (ID 141) | [5 empty] | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
1.1 |  |  |  | Engine - Yanmar 6LY440 | 1 | 14 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
1.2 |  |  |  | Generator - Not fitted | N/A | N/A | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
1.3 |  |  |  | Gearbox - Yanmar ZF280 | 1 | 12 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
1.4 |  |  |  | Compressor - Not fitted | N/A | N/A | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
1.5 |  |  |  | Waterjet - Hamilton HJ364 | 1 | 20 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED

## Table 5b-IPS
Schedule 3C (Passenger Transfer Boat Variant) - Table 5b - Initial Provisioning of Spares
Item No | IMC | NATO Stock Number |  | Description | D of Q | Delivery Timescale (Weeks) | YEAR 1 Contract Start Date-Mar 18 | YEAR 2 FY 18/19 | YEAR 3 FY 19/20 | YEAR 4 FY 20/21 | YEAR 5 FY 21/22 | YEAR 6 FY 22/23 | YEAR 7 FY 23/24
|  |  | Description & Part No |  |  |  | Firm Price (ex VAT) | Firm Price (ex VAT) | Firm Price (ex VAT) | Firm Price (ex VAT) | Firm Price (ex VAT) | Fixed Price (ex VAT) | Fixed Price (ex VAT)
2 | Initial Provisioning of Spares in accordance with SoTR reference - Section 5.0 - Logistics and In-Service Support (ID 140) | [5 empty] | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.11 |  |  |  | Year 1 - Engine Service Pack 250hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.12 |  |  |  | Year 1 - Engine Service Pack 500hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.13 |  |  |  | Year 1 - Engine Service Pack 750hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.14 |  |  |  | Year 1 - Engine Service Pack 1000hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.15 |  |  |  | Year 1 - Engine Service Pack 1250hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.16 |  |  |  | Year 1 - Engine Service Pack 1500hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.17 |  |  |  | Year 1 - Engine Service Pack 1750hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.18 |  |  |  | Year 1 - Engine Service Pack 2000hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.19 |  |  |  | Year 1 - Gearbox Service Pack 500hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.2 |  |  |  | Year 1 - Gearbox Service Pack 1000hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.21 |  |  |  | Year 1 - Gearbox Service Pack 1500hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.22 |  |  |  | Year 1 - Gearbox Service Pack 2000hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.23 |  |  |  | Year 1 - Propulsion Service Pack 1000hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.24 |  |  |  | Year 1 - Propulsion Service Pack 2000hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
[8 empty] | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.25 |  |  |  | Year 2 - Engine Service Pack 250hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.26 |  |  |  | Year 2 - Engine Service Pack 500hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.27 |  |  |  | Year 2 - Engine Service Pack 750hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.28 |  |  |  | Year 2 - Engine Service Pack 1000hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.29 |  |  |  | Year 2 - Engine Service Pack 1250hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.3 |  |  |  | Year 2 - Engine Service Pack 1500hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.31 |  |  |  | Year 2 - Engine Service Pack 1750hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.32 |  |  |  | Year 2 - Engine Service Pack 2000hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.33 |  |  |  | Year 2 - Gearbox Service Pack 500hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.34 |  |  |  | Year 2 - Gearbox Service Pack 1000hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.35 |  |  |  | Year 2 - Gearbox Service Pack 1500hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.36 |  |  |  | Year 2 - Gearbox Service Pack 2000hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.37 |  |  |  | Year 2 - Propulsion Service Pack 1000hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED
2.38 |  |  |  | Year 2 - Propulsion Service Pack 2000hrs | 2 | 4 | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED | REDACTED