- Viewpoint reference number: 888888_0000-MOJ-000-XX-T-J-0065

- PART 1 – FORM OF NOTICE TO PROCEED TO STAGE 2

THIS NOTICE TO PROCEED TO STAGE 2 is made on the	20[22]

BETWEEN:

(1)	THE SECRETARY OF STATE FOR JUSTICE of the Ministry of Justice, 102 Petty France, Westminster, London, SW1H 9AJ (the "Client", with such term including its successors in title and permitted assigns); and

(2)	GALLIFORD TRY CONSTRUCTION LIMITED (company number 02472080), whose registered office is at Blake House 3 Frayswater Place, Cowley, Uxbridge, Middlesex, United Kingdon, UB8 2AD (the "Contractor").

BACKGROUND:

(A)	This Notice to Proceed to Stage 2 has been issued pursuant to and in accordance with the contract between (1) the Client and (2) the Contractor dated [INSERT DATE] (in their capacity as the "Client" and the "Alliance Member" respectively) (the "FAC-1 Contract").

(B)	In accordance with the FAC-1 Contract and following the completion of the Works Package Procedure, the Client wishes to appoint the Contractor to undertake the design and construction of the Works Package known as [INSERT DESCRIPTION OF PROJECT] at [INSERT ADDRESS], as more particularly described in Contract Data: Part One and the Main Works Terms as the "works".

IT IS AGREED:

The Client will pay to the Contractor the amount due and carry out its duties in accordance with the Main Works Terms.

The Contractor will Provide the Works and comply with its other obligations in connection with the Works Package in accordance with the Main Works Terms (and for an amount to be determined in accordance with the Main Works Terms).

The Main Works Terms comprise:

this Notice to Proceed to Stage 2;

the "conditions of contract" of (and as such term is defined in) the standard form of NEC4 Engineering and Construction Contract (June 2017 Edition, amended January 2019 and October 2020) incorporating Option A – Priced contract with activity schedule (with such "conditions of contract" deemed to be incorporated into the Main Works Terms by reference);

the Main Works Amendments (which shall be deemed to be incorporated into the Main Works Terms by reference and shall be subject to any agreed modifications to the same as expressly stated in Contract Data: Part One only);

the Contract Terms (incorporating the Special Terms and subject always to clause 12.1);

Schedule 1: Contract Data (and the Main Works Amendments referred to therein);

Schedule 1 – Appendix 1: Scope;

Schedule 1 – Appendix 2: Site Information;

Schedule 1 – Appendix 3: Free Issue Schedule;

[Schedule 1 – Appendix 4: Materials Schedule;]

the Collateral Warranties & Third Party Rights Schedule;

[the Parent Company Guarantee;]

[the Performance Bond;]

the Vesting Agreement;

the Data Protection Schedule; and

any and all other documents annexed to and/or referred to in the Contract Data,

which, together with the Short Schedule of Cost Components, form the Main Works Terms and all references to the "contract" in the conditions of contract (as amended by the Main Works Amendments) shall be construed in accordance with clause 12.1.

If there is any error, mistake, inaccuracy, inadequacy, ambiguity, inconsistency, omission, discrepancy and/or conflict in or between the documents which are part of the Main Works Terms (or that are referred to herein and/or are incorporated into the Main Works Terms by reference), the priority of such documents is in accordance with the following sequence

this Notice to Proceed to Stage 2;

[(in the context of all matters relating to the security of and/or access to the Site only) the 4.20 Meeting Minutes;]

the "conditions of contract" (as modified by the Main Works Amendments and any further modifications to the same as expressly stated in Contract Data: Part One);

the Special Terms;

the Contract Terms (excluding the Special Terms);

Contract Data: Part One (forming part of the Contract Data referred to above);

Contract Data: Part Two (forming part of the Contract Data referred to above); and

all other documents annexed to or referred to in the above in the sequence stated.

If there is any error, mistake, inaccuracy, inadequacy, ambiguity, inconsistency, omission, discrepancy and/or conflict in or between:

the "conditions of contract" and the Main Works Amendments, the Main Works Amendments shall take precedence; and

the content of Contract Data: Part One (including any annexures to and/or documents referred to in the same) and the content of Contract Data: Part Two, Contract Data: Part One takes priority over the relevant part(s) of Contract Data: Part Two.

Where the Contractor has performed any Pre-Construction Services and/or any Pre-Construction Activities pursuant to and in accordance with the FAC-1 Contract for the Client in connection with the works before the Effective Date, such works and/or services shall be deemed to have been performed under the Main Works Terms [and any payments made to the Contractor in respect of the same shall be deemed to have been paid on account in respect of the relevant works of which they form a part], provided that the Contractor shall have no entitlement to notify the Client of and/or submit a claim in respect of a compensation event under the contract arising out of or in connection with any such Pre-Construction Services and/or any Pre-Construction Activities that it has so completed (or is yet to complete) prior to, on or after the Effective Date.

The Parties acknowledge and agree that this Notice to Proceed to Stage 2 may be executed:

in any number of counterparts and by the Parties to it on separate counterparts, each of which when so executed and delivered is an original, and all counterparts together constitute one and the same instrument; and

by electronic signature, which shall be considered as an original signature for all intents and purposes and shall have the same force and effect as an original signature (with "electronic signature" in this context including, without limitation, electronically scanned and transmitted versions of an original signature provided by a Party to the other Party).

Pursuant to and in accordance with the FAC-1 Contract, this Notice to Proceed to Stage 2 and the Main Works Terms shall be governed by and construed in accordance with the laws of England and Wales and the Parties hereby irrevocably submit to the non-exclusive jurisdiction of the English courts, provided that other jurisdictions may apply solely for the purpose of giving effect to this paragraph 7 and for the enforcement of any judgment, order or award given under English jurisdiction.

IN WITNESS WHEREOF THIS NOTICE TO PROCEED TO STAGE 2 HAS BEEN SIGNED BY THE PARTIES ON THE DATE FIRST WRITTEN ABOVE

| SIGNED by THE SECRETARY OF STATE FOR JUSTICE acting by affixing hereto its corporate seal and authenticated by: |  |
| --- | --- |
| Authenticated by (signature): | _______________________________________________ |
| Authenticated by (printed name): | _______________________________________________ |

[EXECUTION BLOCK FOR THE CONTRACTOR TO BE CONFIRMED.]

| SIGNED by GALLIFORD TRY CONSTRUCTION LIMITED acting by a director in the presence of a witness: |  |
| --- | --- |
| Director (signature): | _______________________________________________ |
| Director (printed name): | _______________________________________________ |
| Witness (signature): | _______________________________________________ |
| Witness (printed name): | _______________________________________________ |
| Witness address: | _______________________________________________ |
| Witness occupation: | _______________________________________________ |

- SCHEDULE 1

- CONTRACT DATA

- [TO BE INSERTED IN THE FINAL VERSION OF EACH NOTICE TO PROCEED TO STAGE 2, BASED UPON PART 2 OF THIS SCHEDULE IN THE FAC-1 CONTRACT, ALONG WITH ALL APPENDICES INCLUDED AS PART OF THE CONTRACT DATA DOCUMENT.]

- PART 2 – TEMPLATE MAIN WORKS CONTRACT DATA

CONTRACT DATA

PART ONE – DATA PROVIDED BY THE CLIENT

| 1 General |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | - The conditions of contract are the core clauses and the clauses for the following main Option, the Option for resolving and avoiding disputes and secondary Options of the NEC4 Engineering and Construction Contract (June 2017, amended January 2019 and October 2020). |  |  |  |  |
|  |  | - The main Option is Option A. |  |  |  |  |
|  |  | - The Option for resolving and avoiding disputes is Option W2. |  |  |  |  |
|  |  | - The Secondary Options are Options X2 (Changes in the law), [X4 (Ultimate holding company guarantee)], [X5 (Sectional Completion),] [X7 (Delay damages),] X8 (Undertakings to the Client or Others), X10 (Information modelling), X11 (Termination by the Client), [X13 (Performance bond),] X15 (The Contractor's design), X16 (Retention), X18 (Limitation of liability), X20 (Key performance indicators), Y(UK)1 (Project Bank Account), Y(UK)2 (The Housing Grants, Construction and Regeneration Act 1996), Y(UK)3 (The Contract's (Rights of Third Parties) Act 1999) and Z (Main Works Amendments). |  |  |  |  |
|  |  | - The works are [INSERT DESCRIPTION OF THE WORKS] (as more particularly described in the Scope). |  |  |  |  |
|  |  | - The Client is: Name: The Secretary of State for Justice, of the Ministry of Justice. Address for communications: FAO [INSERT NAME OR POSITION], The Secretary of State for Justice, of the Ministry of Justice, 102 Petty France, Westminster, London, SW1H 9AJ. Address for electronic communications: [INSERT EMAIL ADDRESS]. |  |  |  |  |
|  |  | - The Project Manager is: Name: [INSERT NAME]. Address for communications: [INSERT ADDRESS]. Address for electronic communications: [INSERT EMAIL ADDRESS]. |  |  |  |  |
|  |  | - The Supervisor is: Name: [INSERT NAME]. Address for communications: [INSERT ADDRESS]. Address for electronic communications: [INSERT EMAIL ADDRESS]. |  |  |  |  |
|  |  | - The Scope is in [Appendix 1] of the Contract Data. |  |  |  |  |
|  |  | - The Site (or "site") is [INSERT DETAILS]. |  |  |  |  |
|  |  | - The Site Information is in [Appendix 2] of the Contract Data. |  |  |  |  |
|  |  | - [The Site Surveys are set out at [INSERT LOCATION] of the Site Information.] |  |  |  |  |
|  |  | - The boundaries of the site are [INSERT DETAILS]. |  |  |  |  |
|  |  | - [The Contractor has provided (or is in the process of providing) Pre-Construction Services in connection with the works pursuant to an Order dated [INSERT DATE] in accordance with the FAC-1 Contract.] |  |  |  |  |
|  |  | - [The Contractor has provided (or is in the process of providing) Pre-Construction Activities in connection with the works pursuant to an Order dated [INSERT DATE] in accordance with the FAC-1 Contract.] |  |  |  |  |
|  |  | - The Consents Schedule is set out at [INSERT LOCATION] of the Scope. |  |  |  |  |
|  |  | - The Third Party Agreements as at the Effective Date are set out at [INSERT LOCATION] of the Scope. |  |  |  |  |
|  |  | - The Client's Policies are set out at [INSERT LOCATION] of the Scope. |  |  |  |  |
|  |  | - The language of the contract is English. |  |  |  |  |
|  |  | - The law of the contract is the law of England and Wales. |  |  |  |  |
|  |  | - The period for reply is [ten] ([10]) Working Days. |  |  |  |  |
|  |  | - The following matters will be included in the Early Warning Register: - [None OR INSERT DETAILS]. |  |  |  |  |
| 1A General – supplemental |  |  |  |  |  |  |
|  |  | - The Principal Contractor is [the Contractor]. |  |  |  |  |
|  |  | - The Principal Designer is [the Contractor]. |  |  |  |  |
|  |  | - Without prejudice to the generality of clause 12.1, the BIM Requirements are the requirements identified as such in the FAC-1 Agreement (unless otherwise specified in the Scope, in which case all references to "BIM Requirements" in this contract shall be construed by reference to such requirements). |  |  |  |  |
|  |  | - Without prejudice to the generality of clause 12.1, the Data Protection Schedule is the document identified as such in the FAC-1 Agreement (subject to the Project Manager providing an alternative form of such document to the Contractor for use exclusively in connection with the works). |  |  |  |  |
|  |  | - The Required Apprenticeship Number is five (5). For the purposes of clause 101.5, the reporting interval is monthly as from the Contract Date. |  |  |  |  |
| 1B General – supplemental provisions: existing premises |  |  |  |  |  |  |
|  |  | - The Operational Parties (which do not include any Programme Consultants) are [ ] (or such other party or parties as the Project Manager notifies to the Contractor in writing from time to time). |  |  |  |  |
|  |  | - A Decant Protocol [applies / does not apply] to this contract[.][; and - The Decant Protocol is set out at [INSERT LOCATION].] |  |  |  |  |
|  |  | - The 4.20 Meetings Minutes [apply / do not apply] to this contract[.][; and - the minutes of the meeting attended by (a) the governor of the Site at which the works and/or services comprising the works are to be undertaken and (b) the Contractor (and, as required, other interested parties), the purpose of which is to discuss and agree security and access issues and requirements in relation to the Site and the works; and - set out at [INSERT LOCATION], provided always that the 4.20 Meeting Minutes may be updated and/or replaced by the Client from time to time by way of a written notice from the Project Manager.] |  |  |  |  |
| 2 The Contractor's main responsibilities |  |  |  |  |  |  |
|  |  | - The key dates and conditions to be met are: condition to be met; key date. [INSERT DESCRIPTION]; [INSERT DATE]. [INSERT DESCRIPTION]; [INSERT DATE]. [INSERT DESCRIPTION]; [INSERT DATE]. |
| 3 Time |  |  |  |  |  |  |
|  |  | - The starting date is [INSERT DETAILS]. |  |  |  |  |
|  |  | - The access dates are: Part of the Site; Date. [INSERT DESCRIPTION]; [INSERT DATE]. [INSERT DESCRIPTION]; [INSERT DATE]. [INSERT DESCRIPTION]; [INSERT DATE]. |
|  |  | - The approved form of programme is set out at [INSERT LOCATION]. |  |  |  |  |
|  |  | - The Contractor submits revised programmes at intervals no longer than [twenty-eight] ([28]) days. |  |  |  |  |
|  |  | - The completion date for the whole of the works is [INSERT DATE] [(subject to Option X5)]. |  |  |  |  |
|  |  | - The Client is not willing to take over the works before the Completion Date. |  |  |  |  |
| 4 Quality management |  |  |  |  |  |  |
|  |  | - The Contractor provides a quality policy statement and quality plan for acceptance within [INSERT PERIOD] ([INSERT PERIOD]) days of the Effective Date. |  |  |  |  |
|  |  | - The requirements in respect of the quality management system are set out at [INSERT LOCATION] of the Scope. |  |  |  |  |
|  |  | - The defects date is [one hundred and four (104) weeks] after the earlier of the following dates to occur: - the Completion of the whole of the works; - the last date on which the Contractor completed an activity forming part of the works; or - the termination of the engagement of the Contractor under the contract. |  |  |  |  |
|  |  | - The defect correction period is: - twenty-eight (28) days for "Routine Defects"; and - forty-eight (48) hours for "Emergency Defects", with each such defect correction period commencing: - where the Contractor has notified the Project Manager of the Defect, on the date of the Project Manager's response to the Contractor's notification specifying whether the Defect is a Routine Defect or an Emergency Defect; and - where the Project Manager has notified the Contractor of the Defect, the date of the Project Manager's notice, in each case, subject to clause 13.2 and as notified in accordance with clause 42.3. |  |  |  |  |
| 5 Payment |  |  |  |  |  |  |
|  |  | - The currency of the contract is pound sterling (£). |  |  |  |  |
|  |  | - The assessment interval is monthly on the final Working Day of the month. |  |  |  |  |
|  |  | - The interest rate is as specified in the FAC-1 Agreement (as the "rate of interest"). |  |  |  |  |
|  |  | - For the purpose of Option Y(UK)2, the final date for payment is fourteen (14) days after the later of the following dates to occur: - the date on which payment becomes due; and - the date of receipt by the Client of a Valid Invoice for the sums due. |  |  |  |  |
|  |  | - For the purposes of clause 53 (Final assessment) and Option Y(UK)2 in respect of the final assessment, the date on which the final payment becomes due is: - if the Project Manager makes an assessment after the issue of the Defects Certificate, [five (5) weeks] after the issue of the Defects Certificate; - if the Project Manager does not make an assessment after the issue of a Defects Certificate, [one (1) week] after the Contractor issues its assessment; or - if the Project Manager has issued a termination certificate, [thirteen (13) weeks] after the issue of the termination certificate. |  |  |  |  |
|  |  | - The Purchase Order Number is [INSERT DETAILS] |  |  |  |  |
|  |  | - Without prejudice to the generality of clause 12.2, the template form of Valid Invoice is as specified in the FAC-1 Agreement (including a reference to the Purchase Order Number), provided that the Project Manager may (acting reasonably and with reasonable notice) vary the form of invoice from time to time by written notice to the Contractor, with any such amendments applying as from the next assessment date after the Project Manager notification. |  |  |  |  |
| 6 Compensation events |  |  |  |  |  |  |
| Weather |  | - [The place where weather is to be recorded is [INSERT LOCATION]. |  |  |  |  |
|  |  | - The weather measurements to be recorded for each calendar month are: - the cumulative rainfall (millimetres); - the number of days with rainfall more than five (5) millimetres; - the number of days with minimum air temperature less than zero (0) degrees Celsius; and - the number of days with snow lying at 09.00 hours (Greenwich Mean Time). |  |  |  |  |
|  |  | - The weather measurements are supplied by [INSERT DETAILS]. |  |  |  |  |
|  |  | - The weather data are the records of past weather measurements for each calendar month which were recorded at [INSERT LOCATION WHERE WEATHER IS TO BE RECORDED] and which are available from the Meteorological Office. |  |  |  |  |
|  |  | - Where no recorded data is available, the assumed values for the ten (10) year return weather data for each weather measurement for each calendar month are [INSERT DETAILS].] |  |  |  |  |
| Value engineering |  | - The value engineering percentage is [fifty] per cent ([50]%). |  |  |  |  |
| 7. Title |  |  |  |  |
|  |  | - The Free Issue Materials are set out in Schedule 1, Appendix 3. - The Free Issue Inspection Period is [INSERT PERIOD] ([INSERT PERIOD]) days. |  |  |
| 8 Liabilities and insurance |  |  |  |  |  |  |
| Client's liabilities |  | - There are no additional Client's liabilities. |  |  |  |  |
| Insurance |  | - In respect of the insurances that the Contractor is required to take out and maintain pursuant to and in accordance with the Main Works Terms, the minimum amount of cover / indemnity for these insurances is as follows: Insurance against; Minimum amount of cover or minimum level of indemnity. Loss of or damage to the works, Plant and Materials (including any Free Issue Materials).; The reinstatement cost of the works, Plant and Materials and Free Issue Materials from the Effective Date and up to and including the date of Completion of the whole of the works and, following Completion, up to (and including) the issue of the Defects Certificate.. Loss of or damage to Equipment.; The replacement cost of the relevant Equipment from the Effective Date and up to and including the date of Completion of the whole of the works and, following Completion, up to (and including) the issue of the Defects Certificate.. Loss of or damage to property (except the works, Plant and Materials and Equipment) and liability for bodily injury to or death of a person (that is not an employee of the Contractor) caused by activity in connection with the contract.; [REDACTED] REDACTED]) in respect of any one (1) occurrence, the number of occurrences being unlimited in any one (1) policy period, but in the aggregate in respect of product liability or pollution liability (to the extent insured under the policy) from the Effective Date and up to and including the date of Completion of the whole of the works and, following Completion, up to (and including) the issue of the Defects Certificate.. Death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with the contract.; The greater of the amount required by applicable law or [REDACTED] pounds (£[REDACTED in respect of any one (1) occurrence inclusive of costs, the number of occurrences being unlimited in any annual policy period from the Effective Date and up to and including the date of Completion of the whole of the works and, following Completion, up to (and including) the issue of the Defects Certificate.. New pollution and new contamination caused by the Contractor’s activity under the contract, including exacerbation of existing pollution and contamination at the Site.; [REDACTED] million pounds REDACTED in respect of any one (1) occurrence and [REDACTED] million REDACTED]) in the aggregate during any one (1) policy period (policy period not to exceed three years), as from the Effective Date and up to and for insurance on a claims made basis including the End of Liability Date.. Negligent acts, errors and/or omissions in the performance of the Contractor’s professional obligations under the contract (with such insurance being referred to in the contract as "professional indemnity insurance").; [REDACTED] pounds (£[REDACTED]) for each and every claim against the Contractor in relation to the works from the Effective Date for the duration of the contract renewable on an annual basis unless agreed otherwise by the Client and up to and including the End of Liability Date.. - The Client elects to "self-insure" the existing buildings and property at the Site and in doing so accepts all of the Client's associated risks arising out of or in relation to such "self-insurance". In accordance with the Client's decision to "self-insure", the Client does not require any additional premium / cost from the Contractor other than as set out above and/or referred to in the Insurance Table. |
| Resolving and avoiding disputes |  |  |  |  |  |  |
|  |  | - The tribunal is litigation in the courts of England. |  |  |  |  |
|  |  | - The Senior Representatives of the Client are: Name:; [INSERT NAME]. Address for communications:; [INSERT ADDRESS]. Address for electronic communications:; [INSERT EMAIL ADDRESS]. Name:; [INSERT NAME]. Address for communications:; [INSERT ADDRESS]. Address for electronic communications:; [INSERT EMAIL ADDRESS]. |
|  |  | - The Adjudicator is as nominated by the Adjudicator nominating body. |  |  |  |  |
|  |  | - The Adjudicator nominating body is The Technology and Construction Solicitors Association (TeCSA). |  |  |  |  |
| [X1: Price adjustment for inflation |  |  |  |  |  |  |
|  |  | - The Materials Schedule is set out in Schedule 1, Appendix 4.] |  |  |  |  |
| X2: Changes in law |  |  |  |  |  |  |
|  |  | - The Change in Law Base Date is [INSERT DATE OF THE CONTACTOR'S SUBMISSION IN CONNECTION WITH THE WORKS PACKAGE PROCEDURE]. |  |  |  |  |
| [X4: Ultimate parent company guarantee |  |  |  |  |  |  |
|  |  | - The form of Parent Company Guarantee is the document identified as such in the FAC-1 Agreement. |  |  |  |  |
|  |  | - The Contractor's Parent Company is the Contractor's ultimate holding company, being [INSERT NAME] (company number [INSERT NUMBER], whose registered office is at [INSERT ADDRESS]).] |  |  |  |  |
| [X5: Sections |  |  |  |  |  |  |  |
|  |  |  |  | - The works are divided into the following sections: Section 1:; [TO BE CONFIRMED]. Section 2:; [TO BE CONFIRMED]. - The completion date for each section of the works is: Section 1:; [TO BE CONFIRMED]. Section 2:; [TO BE CONFIRMED]]. |
| [X7: Delay damages (where used with Option X5) |  |  |  |  |  |  |  |
| - Delay damages for each section of the works are: Section 1:; [TO BE CONFIRMED]. Section 2:; [TO BE CONFIRMED]]. |  |  |  |
| [X7: Delay damages (where Option X5 is not used) |  |  |  |  |  |  |
|  |  | - Delay damages for Completion of the whole of the works are [one hundred thousand] (£[100,000]) pounds per week or part thereof.] |  |  |  |  |
| [X13: Performance bond |  |  |  |  |  |  |
|  |  | - The form of Performance bond is the document identified as such in the FAC-1 Agreement. |  |  |  |  |
|  |  | - The amount of the Performance Bond is [INSERT AMOUNT IN WORDS] (£[INSERT AMOUNT AS A NUMBER]).]. |  |  |  |  |
| X16: Retention |  |  |  |  |  |  |
|  |  | - The retention free amount is nil (£0). |  |  |  |  |
|  |  | - The retention percentage is three per cent (3%). |  |  |  |  |
| X18: Limitation on liability |  |  |  |  |  |  |
|  |  | - For the purposes of the Option X18, the Parties have agreed the following: - The Contractor's total aggregate liability to the Client for indirect or consequential loss is limited to the sum of [INSERT AMOUNT EQUAL TO THE PII SUB-CAP] per cent ([INSERT AMOUNT EQUAL TO THE PII SUB-CAP]%) of the tendered total of the Prices (as adjusted in accordance with the Main Works Terms) (Option X18.1). - For any one event, the Contractor's liability to the Client for loss of or damage to the Client's property is limited to a sum equal to one hundred per cent (100%) of the tendered total of the Prices (as adjusted in accordance with the Main Works Terms) (Option X18.2). - The Contractor's liability for Defects due to its design which are not listed on the Defects Certificate is limited to a sum equal to one hundred per cent (100%) of the tendered total of the Prices (as adjusted in accordance with the Main Works Terms) (Option X18.3). - The Contractor's total aggregate liability to the Client and any Beneficiary (or Beneficiaries) for all matters arising under or in connection with the contract (whether in contract, tort (including negligence) or any other basis of law) other than in respect of the excluded matters, is limited to a sum equal to one hundred per cent (100%) of the tendered total of the Prices (as adjusted in accordance with the Main Works Terms) (Option X18.4). |  |  |  |  |
|  |  | - The End of Liability Date is the date identified as such in the FAC-1 Agreement. |  |  |  |  |
| X20: Key performance indicators |  |  |  |  |  |  |
|  |  | - [The KPI Schedule is set out at [INSERT LOCATION]. |  |  |  |  |
|  |  | - The KPI Reporting Interval is every [INSERT PERIOD] ([INSERT PERIOD] days.] |  |  |  |  |
| Y(UK)1: Project Bank Account |  |  |  |  |  |  |
|  |  | - The project bank is [INSERT DETAILS]. |  |  |  |  |
|  |  | - The named suppliers are [INSERT DETAILS]. |  |  |  |  |
|  |  | - The account holder is [the Contractor / the Parties]. |  |  |  |  |
|  |  | - The Contractor [is / is not] to pay any charges made and to be paid any interest paid by the project bank |  |  |  |  |
| Z: Main Works Amendments |  |  |  |  |  |  |
|  |  | - The Main Works Amendments is the document identified as such in the FAC-1 Agreement and referred to in the Notice to Proceed to Stage 2 to which the Contract Data is annexed. |  |  |  |  |
|  |  | - [The Parties have agreed the following modifications to the conditions of contract and/or the Main Works Amendments referred to above, which will take priority over the relevant provisions of the conditions of contract and/or the Main Works Amendments (as the context requires): - [INSERT DETAILS].] |  |  |  |  |

PART TWO – DATA PROVIDED BY THE CONTRACTOR

| 1 General |  |
| --- | --- |
|  | - The Contractor is Name: [INSERT DETAILS]. Address: [INSERT DETAILS]. Address for communications: FAO [INSERT NAME OR POSITION], [INSERT ADDRESS]. Address for electronic communications: [INSERT EMAIL ADDRESS]. |
|  | - The fee percentage is [INSERT PERCENTAGE] per cent ([INSERT PERCENTAGE])%. |
|  | - The Working Areas (and "working areas") are the Site and [INSERT DETAILS]. |
|  | - The key people (each being a key person) are [as set out in the Key People Schedule and]: Name; [INSERT DETAILS]. Job; [INSERT DETAILS]. Responsibilities; [INSERT DETAILS]. Experience; [INSERT DETAILS]. Name; [INSERT DETAILS]. Job; [INSERT DETAILS]. Responsibilities; [INSERT DETAILS]. Experience; [INSERT DETAILS]. |
|  | - The following matters will be included in the Early Warning Register: - [None OR INSERT DETAILS]. |
| 5 Payment |  |
|  | - The activity schedule is in [INSERT LOCATION OF DOCUMENT]. |
|  | - The tendered total of the Prices is [INSERT NUMBER] pounds (£[INSERT NUMBER]). |
| Resolving and avoiding disputes |  |
|  | - The Senior Representatives of the Contractor are: Name:; [INSERT NAME]. Address for communications:; [INSERT ADDRESS]. Address for electronic communications:; [INSERT EMAIL ADDRESS]. Name:; [INSERT NAME]. Address for communications:; [INSERT ADDRESS]. Address for electronic communications:; [INSERT EMAIL ADDRESS]. |
| Data for the Short Schedule of Cost Components |  |
|  | - The people rates are: Category of person; Unit; Rate. [INSERT DETAILS]; [INSERT DETAILS]; [INSERT DETAILS]. [INSERT DETAILS]; [INSERT DETAILS]; [INSERT DETAILS]. [INSERT DETAILS]; [INSERT DETAILS]; [INSERT DETAILS]. |
|  | - The published list of Equipment is the edition current at the Effective Date of the list published by [INSERT DETAILS]. |
|  | - The rates for other Equipment are: Equipment; Rate. [INSERT DETAILS]; [INSERT DETAILS]. [INSERT DETAILS]; [INSERT DETAILS]. [INSERT DETAILS]; [INSERT DETAILS]. |
|  | - The rates for Defined Cost of manufacture and fabrication outside the Working Areas by the Contractor are: Category of person; Rate. [INSERT DETAILS]; [INSERT DETAILS]. [INSERT DETAILS]; [INSERT DETAILS]. [INSERT DETAILS]; [INSERT DETAILS]. |
|  | - The rates for Defined Cost of design outside the Working Areas are: Category of person; Rate. [INSERT DETAILS]; [INSERT DETAILS]. [INSERT DETAILS]; [INSERT DETAILS]. [INSERT DETAILS]; [INSERT DETAILS]. |
|  | - The categories of design people whose travelling expenses to and from the Working Areas are included in the Defined Cost are [INSERT DETAILS]. |

- APPENDIX 1

SCOPE

[TO BE INSERTED]

- APPENDIX 2

SITE INFORMATION

[TO BE INSERTED]

- APPENDIX 3

FREE ISSUE SCHEDULE

[TO BE INSERTED]

- [APPENDIX 4

MATERIALS SCHEDULE

| - Agreed Material(s) | - Agreed Materials Cost(s) - (as included in the Prices) | - Overhead and/or profit element (%) included in the Agreed Materials Costs | - Benchmark Market Price | - Agreed Materials Benchmark | - Maximum Increase Tolerance | - Maximum Reduction Tolerance | - Latest Order Date(s) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| - [TBC] | - [TBC] | - [TBC] | - [TBC] | - [TBC] | - +[TBC]% | - -[TBC]% | - [TBC] |

]

PART 3 – MAIN WORKS AMENDMENTS

|  | AMENDMENTS TO CLAUSE 1 – GENERAL |  |
| --- | --- | --- |
|  | At the end of clause 10.2, delete the full stop and insert the following: ", but without prejudice to the respective rights and obligations of the Parties". |  |
|  | Replace the definition of "Completion" at clause 11.2(2) in its entirety with the following: "Completion is when the Contractor has - done all the work (and provided any documentation) which the Scope states it is to do by the Completion Date, - delivered to the Client all of the Contractor Collateral Warranties, Subcontractor Collateral Warranties, Subsubcontractor Collateral Warranties and Subconsultant Collateral Warranties which the Contractor is obliged under the contract to provide and/or procure as at that date (provided that the Client has first notified the Contractor of the requirement for it to provide (or procure) the same within a period no shorter than the relevant period stated in Option X8 and - corrected notified Defects save for any minor items of incomplete work or minor defects, the existence, completion and/or rectification of which in the reasonable opinion of the Project Manager would not prevent or interfere with the use (or the fitting out for use) of the works by the Client or Others and are identified by the Project Manager as "snagging" items, with the Project Manager notifying the Contractor of the reasonable period following Completion within which such "snagging" items are to be rectified by the Contractor." If the work which the Contractor is to do by the Completion Date is not stated in the Scope, Completion is when the Contractor has done all the work necessary for the Client to use the works and for Others to do their work and there are no minor items of incomplete work or minor defects (whether notified to the Contractor or otherwise), the existence, completion and/or rectification of which in the reasonable opinion of the Project Manager would not prevent or interfere with the use (or the fitting out for use) of the works by the Client or Others and are identified by the Project Manager as "snagging" items, with the Project Manager notifying the Contractor of the reasonable period following Completion within which such "snagging" items are to be rectified by the Contractor." |  |
|  | Replace the definition of "Contract Date" at clause 11.2(4) with the following: "The Effective Date is the date of the Notice to Proceed to Stage 2." |  |
|  | Replace the definition of "Corrupt Act" at clause 11.2(5) with "Not used." |  |
|  | Replace the definition of "Defect" at clause 11.2(6) with the following: "A Defect is a part of the works (whether designed or treated as having been designed by the Contractor under the contract) which is not in accordance with - the Scope, - applicable law, - the Consents or - any other part of or requirement in the contract." |  |
|  | In the definition of "Parties" at clause 11.2(13): - after the word "Client" insert "(which expression includes its successors in title and assigns)"; and - insert "and the term "Party" means the Client or the Contractor, as the case may be" immediately before the full stop at the end of the clause. |  |
|  | In line 2 of the definition of "To Provide the Works" at clause 11.2(15): - insert ", applicable law and statutory requirements" after the first instance of the word "contract" in the clause; and - insert "and the expression "Providing the Works" shall be construed accordingly" immediately before the full stop at the end of the clause. |  |
|  | Replace the wording of clause 11.2(19) in its entirety with "Not used." |  |
|  | Insert new a clause 11.2(A) after clause 11.2 with the heading "Additional identified and defined terms" and accompanying new clauses (and associated numbering) as follows: |  |
|  |  | 4.20 Minutes are the minutes (if any) identified as such in Contract Data: Part One. |
|  |  | [Agreed Materials means the materials, products and/or equipment identified as such in the Materials Schedule. |
|  |  | Agreed Materials Costs means the total price for each class of Agreed Materials as set out in the Materials Schedule. |
|  |  | Agreed Materials Benchmark means the benchmarking basis identified in the Agreed Materials Schedule as applying to a class of Agreed Materials. |
|  |  | Agreed Materials Decrease has the meaning given to such term in Option X1.2. |
|  |  | Agreed Materials Increase has the meaning given to such term in Option X1.2.] |
|  |  | Adverse Site Condition means the presence of: - Asbestos[,][and/or] - Contamination[,][and/or - treasure, historic artefacts, antiquities and/or human remains that the Client and/or the Contractor is required by applicable law to report to a Statutory Authority or a third party with jurisdiction over the same under applicable law prior to its removal and/or - unexploded ordnances, unexploded bombs and/or explosive remnants of war,] at or within the perimeter of the Site. |
|  |  | Asbestos has the meaning given to it in the Control of Asbestos Regulations 2012 SI 2012/632. |
|  |  | [Benchmark Market Price has the meaning given to such term in Option X1.1. |
|  |  | BMP Difference has the meaning given to such term in the relevant section of Option X1.2 (as the context requires).] |
|  |  | A Class 1 Force Majeure Event is an event identified as such in the definition of Force Majeure Event. |
|  |  | A Class 2 Force Majeure Event is an event identified as such in the definition of Force Majeure Event. |
|  |  | Client Consent means a Consent (if any) identified in the Consents Schedule as being a "Client Consent". |
|  |  | Client's Policies are the policies detailed and identified as such in Contract Data: Part One (and as may be updated from time to time by written notice of the Project Manager to the Contractor). |
|  |  | Consents Schedule means the schedule (if any) identified as such in Contract Data: Part One. |
|  |  | Contamination means any pollutants or contaminants, including any chemical, industrial, radioactive, dangerous, medical / biomedical and sharps waste, toxic or hazardous substances, waste or residue (whether in solid, semi-solid or liquid form or a gas or vapour). |
|  |  | Contractor's Parent Company means the entity identified as such in Contract Data: Part One. |
|  |  | Contract Data: Part One means the document identified as such and forming part of the Contact Data. |
|  |  | Contract Data: Part Two means the document identified as such and forming part of the Contact Data. |
|  |  | COVID-19 means the strain of coronavirus known as coronavirus infectious disease 2019 (COVID-19) and/or the causative virus known as severe acute respiratory syndrome coronavirus 2 (SARS-CoV-2), including any mutations and/or strains of COVID-19 and/or SARS-CoV-2 recognised by the World Health Organization. |
|  |  | [Current Market Price has the meaning given to such term in the relevant section of Option X1.2 (as the context requires).] |
|  |  | [Data Protection Schedule means the schedule identified as such in the Contract Data.] |
|  |  | Decant Protocol is the document (if any) identified as such in Contract Data: Part One. |
|  |  | Emergency Defect is a Defect which - substantially adversely affects the performance and/or use of all or part of the works and/or the Site by the Client or any third party, including - any failure (whether intermittent or otherwise) of any central heating system and/or comfort cooling and/or air conditioning systems, - any impact on the constant availability of hot water at any time, - water leaks (if the water cannot or there is a danger that the water will not be contained) and/or if the water leak is causing or is likely to cause damage and/or penetration into any electrical fitting(s) and/or personal items, - any loss (whether intermittent or otherwise) of gas, electricity and/or the water supply, - gas leaks, - any loss of roof and/or ridge coverings which may result in water penetration and - blocked foul water drains causing flooding and/or overflowing internally and/or externally, - requires immediate rectification in order to ensure the continuous safe occupation and/or use of all or part of the works and/or any part(s) of the Site (including its immediate surroundings) and/or to protect the health and safety of those occupying, using or visiting the works and/or the Site (including its immediate surroundings) and/or - presents a security risk at the Site or is such that a failure to rectify it immediately would be materially detrimental to the security of any part(s) of the Site (including in relation to any Security Measures). |
|  |  | FAC-1 Contract has the meaning given to such term in the Notice to Proceed to Stage 2. |
|  |  | A Force Majeure Event means any of the following events (and any circumstance arising as a direct consequence of any of the following events, other than any circumstances which are excluded in the description of such event) which is not or does not result in the occurrence of a Client's liability - a "Class 1 Force Majeure Event", being any of the following events - war, civil war, rebellion, revolution, insurrection, military or usurped power, - ionising radiations or contamination by radioactivity from any nuclear fuel or from any nuclear waste from the combustion of nuclear fuel, radioactive toxic explosive or other hazardous properties of any explosive nuclear assumption or nuclear component thereof (unless caused or contributed towards by the acts and/or omissions of the Contractor), - pressure waves caused by aircraft or other aerial devices travelling at sonic or supersonic speeds and/or - any epidemic, pandemic or pestilence (as classified or advised by the World Health Organization or the United Kingdom government) other than COVID-19 and - a "Class 2 Force Majeure Event", being any of the following events - riot, civil commotion, public disorder, sabotage and/or acts of vandalism outside of the Working Areas (and not involving solely nor originating with the personnel or other employees of the Contractor or Subcontractors or lower tier subcontractors or the employees or subcontractors of any group company associated with the Contractor) and/or - strike, industrial action, lockout or trade dispute occurring nationwide and neither involving solely nor originating with the personnel or other employees of the Contractor or Subcontractors or lower tier subsubcontractors or the employees or subcontractors of any group company associated with the Contractor. |
|  |  | Free Issue Inspection Period means the period identified as such in a Contract Data Part One. |
|  |  | Free Issue Materials means any materials identified as such in the Contract Data, Part One. |
|  |  | Key Performance Indicator has the meaning given to such term in Option X20.1. |
|  |  | KPI Reporting Interval is the period identified as such in Contract Data: Part One. |
|  |  | KPI Schedule is the document identified as such in Contract Data: Part One. |
|  |  | [Latest Order Date has the meaning given to such term in Option X1.1. |
|  |  | Materials Order has the meaning given to such term in Option X1.2. |
|  |  | Materials Schedule means the schedule identified as such in Contract Data: Part One. |
|  |  | Materials Supplier means the supplier of any Agreed Materials. |
|  |  | Maximum Increase Tolerance has the meaning given to such term in Option X1.1. |
|  |  | Maximum Reduction Tolerance has the meaning given to such term in Option X1.1.] |
|  |  | Notice to Proceed to Stage 2 means the document entitled "Notice to Proceed to Stage 2" as executed by the Client and the Contractor in connection with the works pursuant to and in accordance with the Contract Terms. |
|  |  | Pre-Construction Services are (without prejudice to the generality of the same term as used in the FAC-1 Contract) the services identified as such in Contract Data: Part One. |
|  |  | Pre-Construction Activities are (without prejudice to the generality of the same term as used in the FAC-1 Contract) the works and/or services identified as such in Contract Data: Part One. |
|  |  | Principal Contractor is the party identified as such in Contract Data: Part One to fulfil such statutory role under and as defined in the CDM Regulations. |
|  |  | Principal Designer is the party identified as such in Contract Data: Part One to fulfil such statutory role under and as defined in the CDM Regulations. |
|  |  | Programme Consultants means the parties identified as such in the FAC-1 Agreement; |
|  |  | Project Focused is the principle applied in the consideration of any decision, outcome, solution or resolution in relation to the Project which facilitates or encourages objectively-assessable quality and performance outcomes and (as the Project is publicly funded) with the objective of achieving value for money, innovation and education, the exchange of information, and the integration, adaptation and standardisation of roles, expertise and responsibilities in connection with the works and/or the wider Project; |
|  |  | Purchase Order Number means the number identified as such in Contract Data: Part One. |
|  |  | Routine Defect is a Defect that is not determined by the Project Manager pursuant to clause 42.3 as being an Emergency Defect. |
|  |  | Site (and "site") means the site of the works as identified in Contract Data: Part One. |
|  |  | Site Conditions has the meaning given to such term in clause 28A.1. |
|  |  | Site Surveys means, if any, the surveys (and other information concerning the Site) identified as such in Contract Data: Part One. |
|  |  | Third Party has the meaning given to such term in clause 28C.1. |
|  |  | Third Party Agreement has the meaning given to such term in clause 28C.1. |
|  |  | Third Party Rights Schedule means the schedule identified as such in Contract Data: Part One. |
|  |  | Unforeseeable means, in respect of any potential Adverse Site Condition, whether it would not have been reasonably foreseeable to an experienced contractor as at the Effective Date, exercising the Standard of Care and having - regard to any condition(s) referred to in and/or reasonably inferable from any Site Survey(s), - regard to the Scope and the Site Information, - [regard to the same information concerning the Site as expressly identified and/or documented by the Contractor as part of the Pre-Construction Services (whether or not communicated by it to (or communicated to it by or on behalf of) the Client),] - [regard to the same information concerning the Site as expressly identified and/or documented by the Contractor as part of the Pre-Construction Activities (whether or not communicated by it to (or communicated to it by or on behalf of) the Client),] - undertaken a visual inspection of the Site and its surroundings and - regard to any relevant publicly available information in respect of the Site, provided always that if there is any inconsistency within the information and/or knowledge referred to in the bulleted items above, the Contractor shall be assumed to have taken into account the conditions at the Site less favourable to undertaking the construction of the works. |
|  | Replace the wording of clause 12.1 in its entirety with the following: "Subject to paragraph 4 of the Notice to Proceed to Stage 2, the Parties acknowledge and agree that - this contract forms part of the FAC-1 Contract and is supplemental to and shall be read in conjunction with the Contract Terms wherever the context requires and, subject to Contract Term 1A to Contract Term 1C (inclusive) of the Contract Terms, the Contract Terms (including, for the avoidance of doubt, Special Term 35) shall be deemed to be incorporated into the contract mutandis mutatis as between the Client and the Contractor and - save where defined in the Contract Terms, capitalised terms and/or italicised terms in the contract have the meaning given to them in clause 11.2 and clause 11.2(A) unless expressly defined elsewhere in the contract." |  |
|  | Insert the following after "governed by" in clause 12.2: "and shall be construed in accordance with". |  |
|  | Replace the wording of clause 12.4 in its entirety with the following: "Subject to paragraph 4 of the Notice to Proceed to Stage 2, the Client and the Contractor acknowledge and agree that - the Main Works Terms, together with the remainder of the FAC-1 Contract, represent the entire understanding and agreement between the Client and Contractor in relation to the obligation for the Contractor to Provide the Works and - without prejudice to either Party's liability for fraudulent misrepresentation under or connection with the FAC-1 Contract, each Party hereby acknowledges and agrees that, in executing the Notice to Proceed to Stage 2, it has placed no reliance upon any statement, representation or warranty made or given by the other Party during the course of negotiations which is not reflected in the Main Works Terms or any documents referred to herein." |  |
|  | Insert a new clause 13.9 as follows: "Any communication required under the contract from the Contractor to Others is copied simultaneously to the Client and the Project Manager." |  |
|  | Insert the following after "the work" on the second line of clause 14.1: "or any review or approval of or comment on such work". |  |
|  | Insert a new clause 14.5 with the following wording: "Without prejudice to the generality of clause 14.3, the Contractor acknowledges and agrees that the Project Manager may give an instruction to the Contractor which changes the Scope to remove or omit all or part of the works at any time and for any reason and the Client may instruct Others to carry out such omitted work, in which case - the tendered total of the Prices shall be reduced to reflect such removal or omission, calculated by reference to the Client's reasonable determination of the value attributable to such omitted part(s) or by such other sum as otherwise agreed between the Parties, - the Client shall have no liability whatsoever to the Contractor in respect of any such reduction or omission (whether in contract, tort (including negligence) or otherwise), and such reduction or omission shall not give rise to any entitlement for the Contractor to claim for abortive costs, actual or expected loss of payment or profit, loss of revenue, loss of goodwill, loss of opportunity or any direct, consequential or indirect losses of any type or for any other amount under the contract and - the Contractor shall not be entitled to any adjustment to the Completion Date arising out of or in connection with any instruction(s) issued by the Project Manager pursuant to this clause 14.5, provided always that nothing in this clause 14.5 shall affect, in respect of any works and/or services forming part of an activity that is subject to such an omission instruction, the Contractor's entitlement to payment (or reimbursement) in respect of - any works and/or services forming part of that activity that have been properly performed by the Contractor as at the effective date of the relevant omission instruction but which cannot, by reason of the omission, be completed, the value of which shall be determined by the Project Manager, acting reasonably, on a pro rata basis by reference to the value of the relevant works and/or services as against the total of the Prices for the relevant activity, - the Contractor's reasonably and properly incurred direct demobilisation costs (as disclosed to the Project Manager for review and approval on an open book basis) in relation to the omitted works and/or services only, - the cost of any Plant and Materials that the Contractor has itself manufactured in connection with the works and that are stored, as at the date of the omission, at a location other than at the site that and provided that the Contractor has used reasonable endeavours to mitigate such costs, either whole or in part (including by using such Plant and Materials as part of the wider delivery of the works) and - any direct costs that the Contractor is contractually committed to pay to any third party (including its Subcontractors) that relate to such omitted works and/or services only (such as cancellation costs and the cost of Plant and Materials that have been manufactured by a third party in connection with the works and that are stored, as at the date of the omission, at a location other than at the site) and to the extent that which the Contractor is unable, using reasonable endeavours and exercising the terms of the relevant contract with such third party (but without having to incur further costs to such third party in doing so) to mitigate such costs, either whole or in part (including by using any Plant and Materials, Equipment and/or other physical items that the Contractor is contractually committed to purchase as part of the wider delivery of the works). Where any sums are to be paid to the Contractor under the third and fourth bulleted items above in respect of Plant and Materials, Equipment and/or other physical items referred to in such bulleted items, it shall be a precondition to the Contractor's entitlement to payment in respect of the same under this clause 14.5 that - (save in relation to Plant and Materials and/or Equipment that is hired by the Contractor and/or its Subcontractors) ownership and title in such Plant and Materials, Equipment and/or other physical items transfers to the Client and - the Contractor delivers the same to a location to be agreed between the Parties in advance, no later than the date on which the Contractor receives payment from the Client in connection with the relevant Plant and Materials, Equipment and/or other physical items under this clause 14.5. " |  |
|  | Insert a new clause 14.6 as follows: "No communication from the Client, the Project Manager or the Supervisor given in accordance with the provisions of the contract, including but not limited to comments on the Contractor's design, drawings, specifications and method statements, instructions, notices or approvals removes, amends or varies any of the Contractor's obligations, responsibilities or liabilities under the contract, including (without limitation) its responsibility to Provide the Works and its liability for Defects and defective design." |  |
|  | In clause 15.1: - in the third bulleted item, replace "or" with ","; - in the fourth bulleted item, replace the full stop with "," and insert the following new bulleted items: "· affect the procuring and/or discharge of any Consents, · change the Accepted Programme, · affect the work of the Client, a Client's contractor, any Operational Parties or another consultant or adversely affect the Client (including, without limitation, by increasing the monies payable by the Client to Others), · constitute a Defect, · constitute a compensation event which has not been previously notified, · result in a breach of the contract or · cause a breach of any applicable law or statutory requirements."; and - at the end of the final paragraph of clause 15.1 insert the following: "In such notification, the Project Manager or the Contractor states whether the early warning must be dealt with immediately or can wait until the next scheduled early warning meeting." |  |
|  | In clause 15.2: - insert "(1)" after "one" and "(2)" after "two"; - delete "either" and replace "or Contractor instructs the other" in the first bulleted item of clause 15.2 with "instructs the Contractor"; - replace "or Contractor may instruct" in the penultimate paragraph of clause 15.2 with "may instruct"; and - replace "other" on the final line in the penultimate paragraph with "Contractor". |  |
|  | In clause 15.4, insert "(1)" after "one". |  |
|  | Insert a new clause 15.5 as follows: “The Parties acknowledge and agree that the issuing and/or revision of any Early Warning Register is not to be treated as an instruction changing the Scope and any failure of the Project Manager to issue an Early Warning Register (or any revisions thereto) does not constitute a compensation event. If the Contractor believes that the issue of any Early Warning Register or any other instruction from the Project Manager (not expressed to be a change to the Scope) should be treated as an instruction changing the Scope (or otherwise gives rise to a compensation event), the Contractor (save in circumstances of emergency), before acting on the revised Early Warning Register or instruction, notifies the Project Manager of the Contractor's belief that the Early Warning Register or instruction gives rise to a change in the Scope or other compensation event and allows the Project Manager time to consider the impact of the revised Early Warning Register or instruction in relation to the Contractor’s notice.” |  |
|  | Insert a new clause 15.6 as follows: "The risks identified in the Early Warning Register from time to time shall not affect the risk allocation between the Parties as set out in the conditions of contract. Unless otherwise stated in the conditions of contract, the Prices, the Completion Date and the Key Dates are not to be changed for any risks entered into the Early Warning Register or for any matter notified as an early warning. The Client has no liability to the Contractor for any risks entered into the Early Warning Register or for any matter notified as an early warning unless the risks are carried by the Client as stated in the conditions of contract." |  |
|  | In clause 16.2: - insert "(4)" after "four"; and - insert "(or such other longer period as may be agreed between the Contractor and the Project Manager, acting reasonably)," after "proposal" on the first line of clause 16.2. |  |
|  | Replace the wording of clause 17.1 in its entirety with the following: "The Project Manager or the Contractor notifies the other as soon as either becomes aware of any error, mistake, inaccuracy, inadequacy, ambiguity, inconsistency, omission, discrepancy and/or conflict in or between the documents which are part of the contract. Subject to paragraph 4 of the Notice to Proceed to Stage 2, the Project Manager gives an instruction resolving the error, mistake, inaccuracy, inadequacy, ambiguity, inconsistency, omission, discrepancy and/or conflict. Notwithstanding any other provision of the contract, any such error, mistake, inaccuracy, inadequacy, ambiguity, inconsistency, omission, discrepancy and/or conflict, or any instruction issued under this clause 17.1 in respect of the same, does not give rise to nor constitute a compensation event." |  |
|  | Replace the wording of clause 17.2 in its entirety with the following: "The Project Manager or the Contractor notifies the other as soon as either becomes aware that the Scope includes an illegal or impossible requirement. If the Scope does include an illegal or impossible requirement, the Project Manager gives an instruction to change the Scope appropriately. Notwithstanding any other provision of the contract (but subject to Option X2, where selected in Contract Data: Part One), any such illegality, impossibility and/or instruction is not a compensation event." |  |
|  | Insert a new clause 17.3 as follows: "Without prejudice to clause 21.1, the Contractor - is deemed to have examined, reviewed and verified the accuracy, adequacy and sufficiency of the Scope (including any designs contained in and/or referred to in the Scope) and the accuracy, adequacy and sufficiency of any design which has not been prepared by or on behalf of the Contractor, - accepts that the Client makes no representations and does not give any warranty, whether express or implied, as to the accuracy, adequacy, sufficiency, suitability or completeness of the Scope or any designs prepared by or on behalf of the Client (including any designs contained in and/or referred to in the Scope), - the Contractor accepts responsibility for any mistake, inaccuracy, inadequacy, discrepancy, ambiguity, inconsistency or omission in the Scope and any design of the works (whether the same has been prepared by or on behalf of the Client, the Contractor or otherwise) including any designs contained in and/or referred to in the Scope. If the Contractor identifies any error, mistake, inaccuracy, inadequacy, ambiguity, inconsistency, omission, discrepancy and/or conflict in - the Scope which does not relate to design, the Contractor notifies the Project Manager who gives an instruction resolving the same and any such instruction is not a compensation event and/or - any design of the works (including any designs contained in and/or referred to in the Scope), the Contractor submits its proposals for the correction of such mistake, inaccuracy, inadequacy, discrepancy, ambiguity, inconsistency or omission in the same way as it submits particulars of its design to the Project Manager for acceptance and any such correction or instruction of the Project Manager in relation to the same is not a compensation event." |  |
|  | Replace the wording of clause 19 with "Not used". |  |

|  | AMENDMENTS TO CLAUSE 2 – THE CONTRACTOR'S MAIN RESPONSIBILITIES |
| --- | --- |
|  | Replace the wording of clause 20.1 with the following: "20.1 The Contractor Provides the Works in accordance with the Scope, the applicable laws (and (to the extent that the Contractor can control the same) so that the product of the works complies with all applicable laws), the other parts of and requirements of the contract and in a good and workmanlike manner, in Providing the Works, uses only materials which are new (unless the contract states otherwise or as otherwise agreed with the Client in writing), and are sound and of good quality and which are consistent with the intended use of the works as stated in the contract or reasonably to be inferred given the nature of the works, (where identified as the Principal Designer in the Contract Data) fulfils the role of Principal Designer in connection with the works and (where identified as the Principal Contractor in the Contract Data) fulfils the role of Principal Designer in connection with the works." |
|  | Insert a new clause 20.2 with the following wording: "The works when completed by the Contractor shall comply with all appropriate requirements of any relevant local or other relevant authority and all relevant statutory requirements." |
|  | Insert a new clause 20.3 as follows: "The Contractor advises the Project Manager on the practical implications of the design of the works and on subcontracting arrangements." |
|  | Replace the wording of clause 21.1 in its entirety with the following: "Exercising the Standard of Care, the Contractor designs the parts of the works which the Scope states the Contractor is to design and designs such parts of the works in accordance with the requirements stated in the Scope and the other requirements of the contract. Whether the Contractor designs the whole or part of the works, the Contractor accepts the entire responsibility for the design of the whole of the works and adopts the same as its own (whether or not such design has been prepared by or on behalf of the Contractor) including any designs contained in and/or referred to in the Scope." |
|  | Delete the second sentence in clause 21.2 and replace with the following: "A reason for not accepting the Contractor’s design is that it does not comply with the contract or the applicable law." |
|  | Insert a new clause 21.4 as follows: "Without prejudice to the generality of Option X15, the Parties acknowledge and agree that nothing in the contract, whether express or implied, shall impose a fitness for purpose obligation on the Contractor in relation to the works." |
|  | Insert a new clause 21.5 as follows: "Without prejudice to the generality of clause 17.3, the Contractor checks the Scope provided by the Client and satisfies itself that its own design meets the Client's Scope with no discrepancy within and/or between the Scope and its own design or the Contractor's Scope. Where there is ambiguity, inconsistency or conflict between these documents, the provisions of clause 17.1 and clause 17.2 shall apply." |
|  | Delete clause 22 and replace with "Not Used". |
|  | In clause 24.2, insert "(1)" after "one". |
|  | Replace the wording of clause 25.3 in its entirety with the following: "If the Project Manager decides that the work does not meet the Condition stated for a Key Date by the date stated and, as a result, the Client incurs additional costs, losses and/or expenses either - in carrying out work or - by paying an additional amount to Others in carrying out work (including the costs of acceleration measures under other contracts), on the same project, the additional costs, losses and/or expenses which the Client has paid, incurred or will incur are paid by the Contractor or may be deducted from any sum due to the Contractor. The Project Manager assesses the additional costs, losses or expenses within four (4) weeks of the date when the Condition for the Key Date is met. These costs, losses and/or expenses have been excluded from the calculation and do not form any part of the delay damages for late Completion or the delay damages for failure to meet a Condition by the relevant Key Date, and the Client is entitled to recover them from the Contractor." |
|  | In clause 26.1: - after the word "work" in the first line insert the words "(including design)"; and - delete the full stop at the end of the clause and insert the following: "and the Contractor accordingly is and remains responsible for the acts and omissions (including tortious acts and omissions) of its Subcontractors and their employees and any acts or omissions by its Subcontractor and their employees shall be treated as if they were the acts or omissions of the Contractor." |
|  | In clause 26.2: - In the third line of clause 26.2, after the words "Provide the Works", insert: "and/or the Client has reasonable grounds for concern in relation to the Subcontractor's experience, performance on other projects, financial stability, insurance cover or status"; and - insert the following as a new paragraph at the end of the clause: "No sum due under a subcontract is eligible for treatment as the Price for Work Done to Date under the contract if and for so long as the requirements of this clause 26.2 are not satisfied in relation to that subcontract." |
|  | Replace the wording of clause 26.3 in its entirety with the following: "The Contractor submits the proposed conditions of contract for each subcontract to the Project Manager for acceptance. The Contractor does not appoint a Subcontractor on the proposed subcontract conditions submitted until the Project Manager has accepted them. A reason for not accepting them is that (save where one or more of the requirements below is waived in respect of a specific subcontract by way of advance written approval of the Project Manager only) - the Contractor has not complied with the requirements of clause 26.2, - the appointment of the proposed Subcontractor and/or the proposed conditions of contract will not allow the Contractor to Provide the Works, - there are compulsory grounds for excluding the Subcontractor under regulation 57 of the Public Contracts Regulations 2015, - the terms of the proposed conditions of contract do not, in the Project Manager's reasonable opinion, adequately reflect the terms of the contract or are inconsistent with the Main Works Terms, - the proposed conditions of contract do not include provisions requiring the Subcontractor to grant a licence in favour of the Client in relation to the materials produced by or on behalf of the Subcontractor equivalent to that granted by the Contractor to the Client pursuant to clause 11 of the Contract Terms, requiring the Subcontractor to provide any Subcontractor Collateral Warranty (or Subconsultant Collateral Warranty, as applicable) or procure in favour of any Beneficiary a Subsubcontractor Collateral Warranty and imposing equivalent obligations of confidentiality on the proposed Subcontractor to those required by the contract, - they do not include a statement that the parties to the subcontract shall act in a spirit of mutual trust and co-operation and/or - the period for payment of the amount due to the Subcontractor stated in the conditions is greater than twenty-one (21) days after the due date in the contract or the date on which the Subcontractor issues a valid VAT invoice to the Contractor in accordance with the terms of the subcontract, if later. The Contractor will have no entitlement to any sums under the contract that related to work that has been subcontracted and has been (or will be) undertaken by a Subcontractor as part of the Price for Work Done to Date under the contract if and for so long as the requirements of this clause 26.3 are not satisfied in relation to that subcontract." |
|  | Insert a new clause 26.4 to clause 26.6 (inclusive) as follows: "26.4 Without prejudice to the generality of clause 26.3, the Contractor, in relation to any subletting of any portion of the works (or the design of them) - procures that each subcontract contains such obligations as necessary to ensure that it is, in all respects, compatible with the terms of the contract and without limitation, replicates the obligation to use the degree of skill and care specified in clause 21.1 and requires collateral warranties to be provided in favour of any Beneficiary in the form of the Subcontractor Collateral Warranty and/or Subsubcontractor Collateral Warranty (as the context requires, in each case with any such amendments that the Client may agree, acting reasonably), - procures that all subcontracts are executed and delivered as deeds, - warrants each Subcontractor's compliance with any provisions referred to herein and/or the FAC-1 Contract that are expressed as applying to Subcontractors of the Contractor, - warrants that all Subcontractors are fully aware of their obligations under the CDM Regulations and are fully competent and are adequately resourced to meet those obligations, - provides to the Project Manager a certified copy of any subcontract, - ensures that the period for payment of any amount due to a Subcontractor under a subcontract is not greater than twenty-one (21) days after the payment due date under this contract, - does not appoint a Subcontractor or supplier if there are compulsory grounds for excluding the Subcontractor or supplier under regulation 57 of the Public Contracts Regulations 2015 and - notifies the Client of the name, contact details and legal representatives of each Subcontractor before appointing the Subcontractor." 26.5 The Contractor includes in any subcontract awarded by it provisions requiring that - invoices for payment submitted by the Subcontractor or supplier are considered and verified by the Contractor in a timely fashion, - undue delay in considering and verifying invoices is not sufficient justification for failing to regard an invoice as valid and undisputed and - any contract awarded by the Subcontractor or supplier for work included in the contract includes provisions to the same effect as these provisions (unless otherwise agreed by the Client, acting reasonably). 26.6 The Contractor does not vary the terms of any subcontract or terminate the engagement of any Subcontractor or supplier without the prior written consent of the Client (such consent not to be unreasonably withheld or delayed). Any such consent by or on behalf of the Client does not give rise to any liability (whether it contract, tort (including negligence) or under any other legal theory) on the part of the Client under, in connection with or pursuant to the contract or otherwise (save to the extent that such liability cannot be limited or excluded by law)." |
|  | In clause 27.1, replace "The Contractor" with "Without prejudice to the generality of clause 28B, the Contractor". |
|  | Insert a new clause 27.5 as follows: "The Contractor - at all times Provides the Works preventing public or private nuisance (including, without limitation, any such nuisance caused by noxious fumes, noisy working operations or the deposit of any material or debris on the public highway) or other interference with the rights of any adjoining or neighbouring landowner, tenant or occupier or any statutory undertaker and assists the Client in defending any action or proceedings which may be instituted in relation thereto and - the Contractor is responsible for and indemnifies the Client from and against any and all expenses, liabilities, losses, claims and proceedings whatsoever resulting from any such nuisance or interference, save only where such nuisance or interference is the consequence of an instruction of the Project Manager (which is not itself the result of any negligence, default or breach of contract by or on behalf of the Contractor or any Subcontractor) and could not have been avoided by the Contractor using all reasonable and practical means, provided always that the Project Manager may issue to the Contractor such instructions as the Project Manager considers necessary if any injunction is granted or Court order is made in consequence of any such nuisance or interference, but (save as aforesaid) no such instruction is a compensation event." |
|  | Insert a new clause 27.6 as follows: "The Contractor ensures that in Providing the Works there is no trespass on or over any adjoining or neighbouring property. If Providing the Works is likely to necessitate any interference (including, without limitation, the over-sailing of tower crane jibs) with the rights of adjoining or neighbouring owners or occupiers, then the Contractor, at no cost to the Client, obtains the prior written agreement of such owners or occupiers thereto, and such agreement is subject to the reasonable approval of the Client before execution (such approval not to be unreasonably withheld or delayed). The Contractor complies with any conditions contained in any such agreement." |
|  | Insert a new clause 27.7 as follows: "The Contractor Provides the Works in accordance with the Client's Policies. If the Contractor is unable to Provide the Works in accordance with the Client's Policies, the Contractor notifies the Project Manager and the Client stating the reason(s) for its inability to comply and the Parties discuss whether the Contractor should be obliged to so comply." |
|  | Replace the wording of clause 28.1 in its entirety with the following: "The Contractor does not assign, transfer, charge or otherwise deal with the contract (or any of its rights or obligations under it) nor grant, declare a trust of, create or dispose of any right or interest in it without the prior written consent of the Client." |
|  | Insert a new clause 28.2 as follows: "The Client may assign in whole or in part any benefit or right under the contract at any time to any person." |
|  | Insert a new clause 28A with the heading "Site Conditions" as follows: "28A Site Conditions 28A.1 For the purposes of the contract, "Site Conditions" means the physical conditions and other conditions of or affecting the Site and/or the sub-surface and/or sub-soil of the Site including (but not limited to) climatic, hydrological, hydro-geological, environmental, geotechnical, geological and archaeological conditions, adjacent properties, services and pipes below or over the surface of the Site and any structures or sub-structures on the Site. 28A.2 Subject to clause 28A.4, the Site Conditions are the sole responsibility of the Contractor and accordingly (but without prejudice to any other obligation of the Contractor under the contract) the Contractor is deemed to have - carried out a ground physical and geophysical investigation and to have inspected and examined the Site and its surroundings and (where applicable) any existing structures or works on, over or under the Site, - satisfied itself as to the nature of the Site Conditions, the ground and the subsoil, the form and nature of the Site, the load bearing and other relevant properties of the Site, the risk of injury or damage to property affecting the Site, the nature of the materials (whether natural or otherwise) to be excavated and the nature of the design, works and materials necessary for Providing the Works, - satisfied itself as to the adequacy of the means and rights of access to and through the Site and any accommodation it may require for the purposes of fulfilling its obligations under the contract (such as additional land or buildings outside the Site), - satisfied itself as to the possibility of interference by persons of any description whatsoever (other than the Client) with access to or use of, or rights in respect of, the Site with particular regard to the owners of any land adjacent to the Site and - satisfied itself as to the precautions, times and methods of working necessary to prevent any nuisance or interference, whether public or private, being caused to third parties, and the Contractor acknowledges that it has sufficient knowledge of the Site and its surroundings (including but not limited to the risks listed as bullet points above) and the Contractor acknowledges that should it encounter any of the foregoing (without limitation) in providing the works or in Providing the Works in accordance with the contract the Prices, the Completion Date and/or the Key Dates are not to be changed, the Contractor will not be entitled to have or make a claim for a compensation event nor entitled to have a claim against the Client in law or otherwise to deal with such matters under this clause 28A.2. No failure on the part of the Contractor to discover or foresee any such condition, risk, contingency or circumstance relating to the Site and its surroundings entitles the Contractor to a compensation event nor a change in the Prices, the Completion Date and the Key Dates, nor entitles the Contractor to have a claim against the Client in law or otherwise to deal with such matters under this clause 28A.2. 28A.3 The Contractor acknowledges and agrees - the Client makes no representation or gives any warranty as to the accuracy, adequacy, sufficiency, suitability or completeness of the Site Surveys and/or any other information provided by or on behalf of it to the Contractor in connection with the Site and - to the extent permitted by applicable law, the Client has no liability arising out of or in relation to such Site Surveys and/or other information provided by or on behalf of it to the Contractor or from any representation or statement, whether negligently or otherwise made in relation to the Site. 28A.4 Without prejudice to the generality of clause 28A.1 to clause 28A.3 (inclusive), if the Contractor encounters any Adverse Site Conditions at the Site that are Unforeseeable, this shall constitute a compensation event for the purposes of clause 60.1(12)." |
|  | Insert a new clause 28B with the heading "Planning and Consents" as follows: "28B Planning and Consents 28B.1 Save in respect of the Client Consents only, the Contractor shall - (save as stated in the third bulleted item of this clause 28B.1) obtain, enter into and maintain (as the context permits) and discharge the requirements of each and every Consent required by applicable law for it to design and construct and/or provide any works and/or services in connection with the works and/or to remedy any defects in the works and otherwise perform its obligations under the contract, - give all notices and submit all applications as may be required in order to discharge its obligations in the above-mentioned bulleted item and - pay (at its own cost) any and all costs, taxes, duties, fees and otherwise satisfy and/or discharge any financial and/or security requirements in connection with each Consent as may be required, save only where - the Consents Schedule expressly specifies that the Client is responsible for making specific types of payment to an identified third party in connection with a Consent (and identifies the nature, type and, where known, value of any such payment) and/or - due to the nature of the Consent, the counterparty to the Consent confirms in writing to the Contractor and the Client that certain sums payable under or in connection with the Consent can only be paid directly by the Client, in which case, to the extent that the Activity Schedule includes any sums in connection with such Consent on the assumption that the Contractor is responsible for paying it directly under this clause 28B.1, the Prices will be reduced following a written notice of the Project Manager to the Contractor, without constituting a compensation event, in an amount equal to the sums paid by the Client to such third party where it is identified that the Contractor is unable to make such payment directly, provided that where the amount to be paid to such third party is greater than the sum allowed for by the Contractor in the Activity Schedule, the surplus will be borne by the Client. 28B.2 The Contractor shall indemnify the Client against the Client's reasonably foreseeable and properly incurred and mitigated expenses, liabilities, losses, claims and proceedings whatsoever arising out of or in connection with a failure by the Contractor to comply with the requirements of this clause 28B, save only where such failure is the direct consequence of an instruction of the Project Manager (which is not itself the result of any negligence, default or breach of contract by or on behalf of the Contractor or any Subcontractor) and could not have been avoided by the Contractor using reasonable and practical means. 28B.3 The Contractor shall provide to the Client such - advice and information as may be reasonably required and - additional assistance (including providing confirmations to third parties and Statutory Authorities) as may be reasonably required, including the provision of information and of documents (including methodologies, specifications, plans and drawings), as and when reasonably requested by the Client and/or the Project Manager from time to time in connection with the works and/or the obtaining, maintenance and discharge by the Client of the Client Consents and/or any payments that are to be made by the Client in connection with a Consent pursuant to clause 28B.1 (and at such times, in such form and content and with such level of detail reasonably required or approved by the Client). 28B.4 If and insofar as discharge of any condition of any Consent is part of the works and/or services in connection with the works (or necessary to create and/or complete the same), the Contractor shall discharge the same in accordance with (and by the date(s), if any, required by) the Consent. 28B.5 The Contractor hereby agrees that it shall - ensure that the works comply with, and its performance of its obligations under the contract are in compliance with the Consents, - ensure that the works (as designed, constructed, commissioned and completed in accordance with the contract) are capable of operation in accordance with the applicable laws and Consents applicable to the works and/or to the Client and - as otherwise necessary or appropriate for the proper carrying out of the works, be responsible for the removal and/or re-routing of any temporary cables, utilities and/or pipelines which are present on the Site, provided that nothing in this clause 28B.5 shall - have the effect of preventing or limiting the operation of Option X2 and/or - impose upon the Contractor a higher standard of care in respect of the preparation of the design of such part(s) of the works as may be referred to in and/or specified by any Consents than the Standard of Care. 28B.6 The Contractor shall be responsible, at its own cost, for liaising with all appropriate Statutory Authorities to locate and connect water and electricity, where required in relation to the works, and for obtaining and installing all necessary apparatus for the metering and consumption of such consumables and will pay the cost for all electricity and water consumed at the Site(s) by or on behalf of the Contractor (including its Subcontractors) until the date of Completion. 28B.7 The Contractor shall carry out and complete the works and/or services it is required to perform for the works in accordance with all Statutory Agreements, which shall include paying all sums, fees and/or fines required pursuant to the Statutory Agreements in order to perform such works and/or services." |
|  | Insert a new clause 28C with the heading "Third Party Agreements" as follows: "28C Third Party Agreements 28C.1 The Contractor acknowledges that the Client has and will from time to time enter into agreements with third parties and be bound by decisions, consents and approvals of relevant authorities which may relate to the Contractor's obligations hereunder (each a "Third Party Agreement" and each counter-party to such Third Party Agreement being a "Third Party"). The details of any Third Party Agreement entered into by the Client before the Effective Date are referred to in Contract Data: Part One. 28C.2 The Contractor complies with and performs its obligations under and arising out of the contract so that no negligent act, omission or default on its part (or on the part of any Subcontractors engaged by it or other subcontractors of any tier engaged in connection with the works) - causes or contributes to any breach by the Client of any of its obligations, - gives rise to any liability of the Client and/or - leads to any diminution or loss of any rights, entitlements or other benefits of the Client, under any Third Party Agreement, save to the extent that the Contractor has not been provided with a copy of such Third Party Agreement. 28C.3 The Contractor shall indemnify the Client against the Client's reasonably foreseeable and properly incurred and mitigated expenses, liabilities, losses, claims and proceedings whatsoever arising out of or in connection with a failure by the Contractor to comply with the requirements of this clause 28C, save only where such failure is the direct consequence of an instruction of the Project Manager (which is not itself the result of any negligence, default or breach of contract by or on behalf of the Contractor or any Subcontractor) and could not have been avoided by the Contractor using reasonable and practical means. 28C.4 In the event the Client enters into any Third Party Agreement after the Effective Date that was not disclosed to the Contractor and/or referred to in Contract Data: Part One as at the Effective Date (including any amendment agreement to a Third Party Agreement entered into before the Effective Date) the same shall constitute a change to the Scope and be treated as a compensation event under clause 60.1(1). 28C.5 The Contractor provides the Project Manager with copies of all correspondence and communications between the Contractor and any Third Party in relation to any actual or potential Third Party Agreements." |
|  | Replace the wording of clause 29 in its entirety with "Not used." |

|  | AMENDMENTS TO CLAUSE 3 – TIME |
| --- | --- |
|  | Replace the wording of clause 30.1 in its entirety with the following: "Subject to any modification to the Completion Date and/or any Key Date in pursuant to and in accordance with clause 60 to clause 66 (inclusive), the Contractor starts work on the starting date and starts work on the Site on the first access date and proceeds with the work regularly and diligently in accordance with the Accepted Programme and the contract so that - (if identified in Contract Data: Part One) the Condition stated for each Key Date is met on or before the Key Date and - Completion is on or before the Completion Date." |
|  | In clause 30.2, replace "one week" with "two (2) weeks". |
|  | Delete clause 30.3 in its entirety. |
|  | In the final sentence of clause 31.2, replace "in the Scope" with "in Contract Data: Part One". |
|  | In clause 31.3: - insert "(2)" after "two"; and - insert "(1)" after "one". |
|  | In clause 32.1, insert a new bulleted item after the first bulleted item with the following wording: "the effects of implemented compensation events," |
|  | In clause 33.1: - replace the words "The Client allows access to and use of each part of the Site to the Contractor" with "The Client allows non-exclusive access to and use of each part of the Site to the Contractor" and - insert the following as a new sentence at the end of the clause: "The Contractor acknowledges and agrees that the Client and all persons authorised by the Client shall at all times have access to the Site and the non-exclusive access that it is entitled to under this clause 33.1 takes effect as a non-exclusive licence only for the purpose of Providing the Works and performing the Contractor's other obligations under the contract, and such non-exclusive licence shall not give rise to any other rights or entitlements in favour of the Contractor over or in connection with the Site and/or the Site's use. Any additional arrangements and/or requirements relating to this period of non-exclusive possession referred to in this clause 33.1 will be set out in the Scope and/or (if stated in Contract Data: Part One as applying to this contract) the Decant Protocol. [If the Contractor require access to any area within the Client’s control outside the agreed Site of the works, it shall notify the Client as soon as reasonably practicable and not access any such area(s) without the Client’s express written approval. The Contractor shall comply with any restrictions in relation to such areas that are referred to in this contract (including as part of the Scope and/or the 4.20 Meeting Minutes) which shall be deemed the equivalent requirements set out in this contract in relation to the Site and/or any other requirements that may be notified to the Contractor by the Project Manager.]” |
|  | Insert a new clause 33A with the following wording: “33A Decant Protocol 33A.1 The provisions of this clause 33A apply where it is specified in Contract Data: Part One that a Decant Protocol applies to this contract. 33A.2 The Parties acknowledge that the Contractor shall comply (and ensure that its Subcontractors comply) with the Decant Protocol (and if the works are to be constructed in sections, the Decant Protocol shall apply to each section on the basis set out therein). 33A.3 Without prejudice to the generality of clause 33A.2), the Contractor shall not commence any works and/or services in connection with the works at the Site other than in accordance with the Decant Protocol.” |
|  | Insert a new clause 33B with the following wording: “33B 4.20 Meeting Minutes 33B.1 The provisions of this clause 33B apply where it is specified in Contract Data: Part One that the 4.20 Meeting Minutes apply to this contract. 33A.2 The Contractor shall at all times comply (and ensure that its Subcontractors comply) with any requirements set out and/or referred to in the 4.20 Meeting Minutes.” |
|  | In the second bulleted item of clause 34.1, insert "pursuant to and in accordance with clause 14.5" after "remove the work from the Scope". |
|  | In clause 35.1, insert "(2)" after "two". |
|  | In clause 35.3, replace "one week" with "two (2) weeks". |
|  | In clause 36.1, insert "(3)" after both instances of "three". |

|  | AMENDMENTS TO CLAUSE 4 – TESTING AND DEFECTS |
| --- | --- |
|  | In clause 40.1, replace "in the Scope" with "in Contract Data: Part One". |
|  | In clause 41.3, insert at the end of the second sentence before the bulleted item: "and if the Contractor fails to so notify, the Contractor repeats (at its own cost) the test or inspection and gives notification as required in this clause". |
|  | In clause 43.1, insert "opening-up," before "uncovering" in the first bulleted item of the clause. |
|  | Insert a new clause 43.3 as follows: "If - the Contractor notifies the Project Manager of a Defect, the Project Manager will specify in a response to such notice, acting reasonably, whether the defect is an Emergency Defect or a Routine Defect and - the Project Manager notifies the Contractor of a Defect, the Project Manager will, as part of such written notification, acting reasonably, specify whether the Defect is an Emergency Defect or a Routine Defect. Following the notification of a Defect by the Contractor or the Project Manager to the other, the Contractor shall - make good any Defects that the Project Manager determines to be Emergency Defects and - make good all Routine Defects, within the relevant defect correction period applicable to such category of Defect as specified in Contract Data: Part One (referred to below as the "relevant period") following the date of the notification for that Defect being issued by the Project Manager or the Contractor (whichever is earlier and as the context requires). If, following such notification and no later than twenty-four (24) hours after the initial inspection of the Defect by the Contractor, the Contractor notifies the Project Manager that due to the - severity, extent and/or material nature of the Defect and/or - lack of immediate availability to the Contractor of the relevant Plant and Materials that are necessary for the Contractor to make good the Defect within the relevant period, the Contractor is unable to make good the Defect within the relevant period, the Project Manager may (acting reasonably and as soon as reasonably practicable upon receiving the Contractor's notification) authorise - an extension to the relevant period in respect of such Defect only and/or - the Contractor in writing to, in advance of making good the Defect as required in accordance with the contract, initially undertake such temporary works as may reasonably be necessary (as agreed by the Project Manager) in order to make safe and/or minimise the long-term impact and effect of the Defect, provided always that - any such authorisation of the Project Manager shall be in writing and shall not be implied in any circumstance and - the Contractor shall - make good such Defect in full no later than the date on which the relevant period expires (as such relevant period may have been extended pursuant to this clause 43.3), - (or its Subcontractor, acting on behalf of the Contractor, shall) provide guidance and/or make recommendations to the Client in writing in respect of potential preventative and/or mitigatory measures (that do not involve the undertaking of any physical works) that might be reasonable in the context of the use of the completed works as a custodial facility and may assist with mitigating on a temporary basis the cause and/or potential impact of that Defect (referred to below as "temporary measures"), provided always that - the Client may accordingly choose to implement (or not implement) any such temporary measures at its sole discretion, - the liability of the Contractor for any Defect under the contract shall not be reduced if the Client chooses to or chooses not to implement any such temporary measures and - the liability of the Contractor for a Defect shall only be reduced to the extent that the Client, at its sole discretion, attempts to implement its own mitigatory and/or temporary measures (other than any temporary measures of the Contractor or a Subcontractor under this bulleted item) that the Contractor is subsequently then able to demonstrate is the direct cause of any worsening of the Defect (or causes, by such act but not any omission, any manufacturer warranty and/or product guarantee to be invalidated), in which case the Contractor will remain liable for remedying the Defect but shall not be liable to the Client for any worsening of the Defect that can be demonstrated by the Contractor as having been a direct consequence of the Client's actions, - be liable to the Client for any costs that the Client reasonably and properly incurs arising out of or in connection with the hiring and/or purchase of any plant, materials and/or equipment (of any type) that may reasonably be required on a temporary basis to minimise the impact of the Defect on the completed works and the operation of the completed works throughout any period during which the Defect has not been made good and - keep the Project Manager fully informed as to the progress of such temporary and/or other works in relation to such Defects." |
|  | Replace the wording of clause 44.2 in its entirety with the following: "For a Defect notified - before Completion, the Contractor corrects the Defect before Completion and - on or after Completion, the Contractor corrects the Defect before the end of the defect correction period which begins when the Defect is notified." |
|  | In clause 44.3, replace "earlier of" with "the later of the following dates to occur". |
|  | Delete the second sentence of clause 44.4. |
|  | Insert a new clause 44.5 as follows: "The Project Manager arranges for the Client to give the Contractor the access to those parts of the Site which the Contractor needs to correct a Defect which it is required to correct under the contract, after the Client has taken over any part of the works. In this case the defect correction period begins when the necessary access has been provided." |
|  | Insert a new clause 44A as follows: “Without prejudice to the generality of clause 44, all Defects shall be rectiﬁed by the Contractor in accordance with any requirements as set out in (as the context requires) the 4.20 Meeting Meetings, the Decant Protocol and/or the Scope at no additional cost to the Client unless the Project Manager otherwise agrees in writing.” |
|  | Insert a new clause 46.3 as follows: "The provisions of clauses 43 to 45 (inclusive) are without prejudice to any other rights or remedies the Client may have whether in contract, by statute, in tort or otherwise at law (including negligence) and the Contractor remains liable for Defects after - the defects date and - the termination of the Contractor's obligation to Provide the Works for any reason, up to and including the End of Liability Date." |

|  | AMENDMENTS TO CLAUSE 5 – PAYMENT |
| --- | --- |
|  | Insert a new sentence at the end of clause 50.1: "The Contractor acknowledges and agrees that - it is a condition precedent to the commencement of the processes set out in clause 50 to clause 53 (inclusive) and Option Y(UK)2 in respect of an application for payment submitted by or on behalf of the Contractor that the application for payment is a Valid Invoice (provided always that the Project Manager must act reasonably and proportionately in making a determination as to whether an invoice is a Valid Invoice based upon the nature and type of the purported non-compliant part(s) of the invoice), - where an invoice submitted by the Contractor to the Project Manager pursuant to clause 50.2 is not a Valid Invoice, the Client shall notify the Contractor of this in writing and the Contractor shall be entitled to apply for payment for the items otherwise referred to in the non-compliant application for payment as part of the invoice that it issues to the Client at the next assessment date and no earlier and - clause 50 to clause 53 (inclusive) and Option Y(UK)2 shall be construed accordingly." |
|  | In clause 50.2, replace "stated in the Scope" with "of a Valid Invoice". |
|  | In clause 50.3: - replace "If the Contractor submits an application for payment before the assessment date, the" with "The"; and - in the second bulleted item of the clause, insert "(which includes any VAT that may be payable on the amount due)" after "paid to the Contractor". |
|  | Replace the wording of clause 50.4 in its entirety with "Not used." |
|  | Insert a new clause 50.7 as follows: "If there is subsequently any adjustment to the consideration due to the Contractor under the contract or the extent to which the Contractor Providing the Works is a supply on which VAT is chargeable under applicable law, then - if the adjustment is upward or the extent to which the supply is a supply on which the VAT that is chargeable increases, then - the Contractor shall issue a new Valid Invoice or an additional or revised Valid Invoice (as the case may be) to the Client, and - the Client will pay to the Contractor an amount which is equal to any VAT or additional VAT (as the case may be) arising on and from the date of the adjustment in respect of the supply for which the Contractor is liable to account, and - if the adjustment is downward or the extent to which the supply is a supply on which the VAT that is chargeable decreases, then - the Contractor shall issue a valid VAT credit note or a revised Valid Invoice to the Client, and - the Contractor will pay to the Client an amount which is equal to any reduction in the VAT arising in respect of the supply for which the Contractor is liable to account, or - the Parties may agree in writing to withhold from any further sums payable to the Contractor an amount which is equal to any reduction in the VAT arising in respect of the supply for which the Contractor is liable to account." |
|  | In clause 51.1, replace "one week" with "seven (7) days". |
|  | In clause 51.2: - replace "within three weeks" until the end of the clause with "by the final date for payment as referred to in Option Y2.2" and - insert the following as a new sentence at the end of the clause: "If the Client pays the Contractor any sums under or in connection with the contract prior to the submission of a Valid Invoice, such payment shall be deemed to have been paid to the Contractor on account and shall be deductible from the next payment to be made to the Contractor under the contract." |
|  | In clause 51.4 replace "compounded annually" with "simple interest". |
|  | Insert a new clause 51.6 as follows: "If the Client is a "contractor" for the purposes of the Construction Industry Scheme ("CIS") under the Finance Act 2004, or if at any time the Client becomes such a "contractor", the obligation of the Client to make any payment under the contract is subject to the provisions of the CIS." |
|  | Insert a new clause 51.7 as follows: "Notwithstanding clause 51.3, where a Party notifies the other Party that it has made an overpayment to that Party in connection with the contract, the payee shall repay such overpaid amount to the payer within twenty-eight (28) days of the date of the notification of the overpayment and the amount of such sum, if not so repaid, shall be recoverable on demand by the payer as a debt. The Parties agree that this clause 51.7 shall not apply in relation to any overpaid amounts that are, as at the time of the notification, the subject of any dispute which has been referred to an Adjudicator and/or a tribunal to be resolved. The Parties further acknowledge and agree that neither shall exercise the rights afforded under this clause 51.7 in a manner which is inconsistent with Part II of the Housing Grants Construction and Regeneration Act 1996 (as amended)." |
|  | Insert a new clause 51.8 as follows: "The Contractor shall make all payments due to the Client under or in connection with the contract without any deduction (whether by set-off, counterclaim, abatement or otherwise) unless the Contractor has a valid adjudication, judgment (or equivalent) or court order requiring an amount equal to such deduction to be paid to the Contractor." |
|  | In clause 53.1: - insert "(4)" after "four"; - insert "(13)" after "thirteen"; - insert "(2)" after "two"; and - replace the final sentence of clause 53.1 with the following: "Where an amount is due to the Client, the final payment is made within three (3) weeks after the end of the relevant period described in the bullet points above, as applicable. Where an amount is due to the Contractor, the final payment is made within three (3) weeks of the later of the following to occur: - the end of the relevant period described in the bullet points above, as applicable and - the date of receipt by the Client of a Valid Invoice from the Contractor in respect of the amount due." |
|  | Replace the final sentence of clause 53.2 with the following: "If the Client agrees with this assessment, then - where an amount is due to the Client, a final payment is made within three (3) weeks of the assessment, - where an amount is due to the Contractor, a final payment is made within three (3) weeks of the later of the following to occur - the assessment and - the date of receipt by the Client of a Valid Invoice from the Contractor in respect of the amount due." |
|  | In clause 53.3: - insert "(3)" after each instance of "three"; and - insert "(4)" after each instance of "four". |
|  | In clause 53.4, insert "(4)" after "four". |

|  | AMENDMENTS TO CLAUSE 6 – COMPENSATION EVENTS |
| --- | --- |
|  | Replace the first sentence of clause 60.1 with the following: "The following are compensation events, but only to the extent that they - are not due to any negligence, default, fault, unlawful act or omission or breach of or failure to comply with the contract by the Contractor or due to any acts and omissions (including tortious acts and omissions) of its Subcontractors and its employees, - are not attributable or related to any works and/or services undertaken (or to be undertaken) by or on behalf of the Contractor pursuant to any Order for the Pre-Construction Services and/or the Pre-Construction Activities issued pursuant to the Contract Terms as referred to in Contract Data: Part One, whether due to any negligence, default, fault, unlawful act or omission or breach of or failure to comply with the relevant contract (in each case, by act or omission) or due to any acts or omissions of its subcontractors and/or its employees in respect of the same and/or - do not otherwise arise as a consequence of (or are related to) the presence at the Site of the Contractor pursuant to and in accordance with any Order for Pre-Construction Activities issued pursuant to the Contract Terms as referred to in Contract Data: Part One." |
|  | In clause 60.1(1): - delete the words "for its design" in the second bulleted item of the clause; and - replace the "or" at the end of the first bulleted item with "," and the full stop at the end of the second bulleted item with "," and insert the following as new bulleted items: "· (subject to Option X2, where selected in Contract Data: Part One) a change made in order to deal with an illegal or impossible requirement in the Scope, · a change made to resolve a conflict, ambiguity, discrepancy or inconsistency in or between the documents which are part of the contract, · a change to deal with any mistake, inaccuracy, inadequacy, discrepancy, ambiguity, inconsistency or omission in the Scope (including in any designs contained in and/or referred to in the Scope, whether the same has been prepared by or on behalf of the Client, the Contractor or otherwise), or · a change required as a result of an event or matter which is the Contractor's liability or at the Contractor's risk or which is the Contractor's responsibility pursuant to the contract or which is expressly stated in the contract not to give rise to a compensation event." |
|  | At the beginning of clause 60.1(5), replace "The" with "Save in respect of any Consents and/or any works undertaken (or to be undertaken) by a Statutory Authority in its capacity as a statutory undertaker and/or utility provider, the". |
|  | Insert a new clause 60.1(5A) with the following wording: "A Statutory Authority or other third party fails to issue to, enter into or approve (as the context requires) a Consent by the date stated on the Accepted Programme in respect of the same, provided always that - where the Consent is not a Client Consent, the Contractor demonstrates to the Project Manager (acting reasonably) that the Contractor - has used reasonable endeavours to secure (or, as the context requires, facilitate) such issuance, entering into and/or approval in accordance with clause 28B by the date shown on the Accepted Programme and - (save where attributable to the acts or omissions of such Statutory Authority or third party) is not in breach of its obligations under clause 28B or - where the Consent is a Client Consent, such failure is not attributable to any failure by or on behalf of the Contractor to comply with the requirements of clause 28B." |
|  | Insert a new clause 60.1(5B) with the following wording: "A Statutory Authority, acting in the capacity of a statutory undertaker or utility provider and pursuant to a Consent fails to undertake the works and/or services that it is required to undertake and complete under that Consent within any period(s) identified in the Accepted Programme for such works and/or services, provided that where such works are to be undertaken pursuant to - a Consent other than a Client Consent, the Contractor - has first supplied such information required, placed any necessary orders and otherwise performed its obligations under the contract in respect of such work as soon as reasonably practicable after the Effective Date so as not to delay or disrupt such Statutory Authority in undertaking and completing such work and/or services and/or - (save where attributable to the acts or omissions of such Statutory Authority) is not in breach of its obligations under clause 28B and/or under the relevant Consent or - a Client Consent (and without prejudice to the generality of clause 28B), the Contractor - has first supplied to the Client such information required, assisting the Client with the placing of any necessary orders and otherwise performed its obligations under the contract in respect of such work as soon as reasonably practicable after the Effective Date so as not to cause the Client to delay or disrupt such Statutory Authority in relation to such work and - (save where attributable to the acts or omissions of such Statutory Authority) is not in breach of its obligations under clause 28B." |
|  | Replace the wording of clause 60.1(7) in its entirety with "Not used." |
|  | At clause 60.1(10), at the end of the clause after the words "obstructing a required test or inspection" but before the full stop, insert the words "or unless it was reasonable for the Project Manager to instruct the Contractor to search, having regard to previous instances of non-compliant work in Providing the Works". |
|  | Replace the wording of clause 60.1(12) in its entirety with: "The Contractor encounters Adverse Site Conditions that are Unforeseeable for the purposes of Clause 28A.5." |
|  | Replace the wording of clause 60.1(18) in its entirety with the following: "A breach of contract or other act of prevention by the Client which is not one of the other compensation events in the contract." |
|  | Replace the wording of clause 60.1(19) with the following: "The occurrence of a Force Majeure Event which - stops the Contractor completing the whole of the works or - stops the Contractor completing the whole of the works by the date for planned Completion shown on the Accepted Programme." |
|  | Replace the wording of clause 60.1(21) with "Not used." |
|  | Delete clause 60.2 and replace with "Not used." |
|  | Delete clause 60.3 and replace with "Not used." |
|  | In clause 61.3, insert "(8)" after "eight". |
|  | In clause 61.4: - replace "one week" in the first bulleted item of the clause with "the period for reply"; - insert "(acting reasonably)" after "has agreed" in the second bulleted item of the clause; - replace the words "arises from a fault of the Contractor" with "arises from any negligence, default, fault, unlawful act or omission or breach of or failure to comply with the contract by or on behalf of the Contractor or from any acts or omissions (including tortious acts and omissions) of its Subcontractors or suppliers or their respective employees, subcontractors or agents," in the first bulleted item of the second bulleted list; - insert "(2)" after "two"; and - in the final sentence, insert after "submit quotations" the following: "(provided always that the Contractor has first notified the Project Manager a further time in writing of its failure to reply and the Project Manager then fails to reply to the Contractor within a further five (5) Working Days of such notice)". |
|  | In clause 61.6, insert "the Project Manager decides that" before "the effects". |
|  | Insert a new clause 61.8 as follows: "Notwithstanding any other provision of the contract, where the compensation event notified by the Contractor to the Project Manager is a Force Majeure Event that is a Class 2 Force Majeure Event, the Contractor shall not be entitled to any adjustment to the Prices and shall, subject to the provisions of clause 61 to clause 65 (inclusive), be entitled to an adjustment to any Key Date(s) and the Completion Date only." |
|  | Delete clause 62.2 and replace with the following: "Quotations for compensation events comprise proposed changes to the Prices and any delay to the Completion Date and Key Dates assessed by the Contractor. The Contractor submits details of its assessment with each quotation. If the programme for remaining work is altered by the compensation event, the Contractor includes the alterations to the Accepted Programme in place on the date the Project Manager instructed or should have instructed the Contractor to submit quotations in its quotation." |
|  | In clause 62.3: - insert "(3)" after "three" and - insert "(2)" after "two". |
|  | At clause 62.4: - after the words "revised quotation" in the second sentence, insert "as soon as possible, and in any event"; and - insert "(3)" after "three". |
|  | In clause 62.6: - insert "(2)" after "two"; and - insert the following after "quotation" at the end of the clause: "(provided always that the Contractor has first notified the Project Manager a further time in writing of its failure to reply and the Project Manager then fails to reply to the Contractor within a further five (5) Working Days of such notice)". |
|  | Replace the wording of clause 63.5 in its entirety with the following: "A delay to the Completion Date is assessed as the length of time that, due to the compensation event, planned Completion is later than planned Completion as shown on the Accepted Programme in place on the date the Project Manager instructed or should have instructed the Contractor to submit quotations. A delay to a Key Date is assessed as the length of time that, due to the compensation event, the planned date when the Condition stated for a Key Date will be met is later than the date shown on the Accepted Programme in place on the date the Project Manager instructed or should have instructed the Contractor to submit quotations." |
|  | Replace the wording of clause 63.6 in its entirety with the following: "The rights of the Client and the Contractor to changes to the Prices, the Completion Date and the Key Dates are their only rights in respect of a compensation event. The Client has no other liability under the contract or in law to the Contractor for a compensation event." |
|  | Replace the wording clause 63.8 in its entirety with "Not used." |
|  | In clause 64.4: - insert "(2)" after "two"; and - insert the following after "the quotation " at the end of the clause: "(provided always that the Contractor has first notified the Project Manager a further time in writing of its failure and the Project Manager then fails to reply to the Contractor within a further five (5) Working Days of such notice)". |
|  | In clause 65.2: - insert "(3)" after "three"; and - insert the following after "quotation is not accepted " at the end of the clause: "(provided always that the Contractor has first notified the Project Manager a further time in writing of its failure to accept the quotation and the Project Manager then fails to reply to the Contractor within a further five (5) Working Days of such notice)". |

|  | AMENDMENTS TO CLAUSE 7 – TITLE |
| --- | --- |
|  | Replace the wording of clause 70.1 in its entirety with "Not used". |
|  | Replace the wording of clause 70.2 in its entirety with the following: "Each item of Plant and Materials becomes the property of the Client at whichever is the earlier of the following circumstances to occur - when it is brought within the Working Areas or - (whether or not the item has been brought within the Working Areas), the date when the Contractor receives payment from the Client for the item in question. Where, prior to delivery to the Working Areas, the title to Plant and Materials passes to the Client, the Contractor sets such item of Plant and Materials aside and marks it clearly and visibly as the Client's property and identifies its destination as the Working Areas. It is a precondition to payment for any Plant and Materials that the Contractor marks and stores such Plant and Materials in accordance with the contract (including the Scope) and, unless otherwise agreed in advance and in writing by the Project Manager, provides a properly executed Vesting Agreement in favour of the Client in respect of such Plant and Materials in the form referred to in the Contract Data (with such amendments as the Project Manager may approve in advance, acting reasonably) or in such alternative form as is acceptable to the Project Manager, acting reasonably). Upon request, the Contractor provides reasonable proof to the Client (in a form to be agreed in writing in advance with the Project Manager) that the relevant item of Plant and Materials has been so set aside and marked (including procuring access for the Client and/or the Supervisor and/or the Project Manager to inspect the item of Plant and Materials at the relevant place of storage). The Contractor does not remove the relevant item from its place of storage without the prior written consent of the Project Manager (unless it is delivered to the Site)." |
|  | After clause 70.2, insert a new clause 70.3 as follows: "Title to Plant and Materials that the Client has not paid for under this contract passes back to the Contractor if they are removed from the Working Areas. If the Plant and Materials have been paid for by the Client under this contract, the title in such Plant and Materials remains with the Client even if they are removed from the Working Areas and the Contractor complies with the requirements of clause 70.2 as to the marking and storage of such removed Plant and Materials. No Plant and Materials within the Working Areas may be removed from the Working Areas without the Project Manager's prior written permission." |
|  | At clause 73.1, at the end of the first sentence after "Site" but before the full stop insert the words: "and the Contractor acknowledges and agrees that title in any such object vests in the Client" |
|  | In clause 73.2, delete the word "Contractor" and replace with "Client". |
|  | Replace the wording of clause 74.1 in its entirety with "Not used." |
|  | Insert a new clause 75 with the heading “Free Issue Materials” as follows: “75 Free Issue Materials 75.1 Where the Contract Data, Part One specifies that the Client will provide Free Issue Materials to the Contractor in connection with the works - the Contractor agrees and acknowledges that it is familiar with the specification of the Free-Issue Materials and has no objection to the incorporation of such items in the works, - the Client supplies to the Contractor, free of charge, the Free Issue Materials in accordance with the Accepted Programme, so as not to prevent, hinder and/or delay the Contractor complying with its obligations under the contract, - unless otherwise agreed between the Client and the Contractor, such Free Issue Materials may be supplied in one of the following ways (at the sole discretion of the Client) - the Contractor may be required to collect the Free Issue Materials from a location specified in advance and in writing by the Client and/or the Project Manager or - the Client may deliver (or arrange the delivery of) the Free Issue Materials to the Site or an area within the prison estate at HMP Guys Marsh which may include a location under the control of the Contractor, - when attending a location specified by the Client and/or the Project Manager to collect the Free Issue Materials or taking receipt of the Free Issue Materials (as the context permits) - the Contractor shall inspect the Free Issue Materials within the Free Issue Inspection Period to determine their suitability for use in the works (as assessed by reference to the Contractor's own duties and obligations relating to the provision of goods and materials under or in connection with the contract) provided always that the Contractor cannot object to their suitability if such items are in accordance with the specification referred to in the Scope or otherwise made known to the Contractor in advance of delivery, - the Contractor shall give notice to the Client (or the party delivering the Free Issue Materials to the Contractor, if not the Client) of any shortage and/or defect in the Free Issue Materials identified by such inspection (and in the context of Free Issue Materials delivered by a party other than the Client, comply with any requirements of that party in relation to the inspection and notification of shortages and/or defects in the Free Issue Materials as may be specified in any accompanying delivery note or as notified to the Contractor as at the time of such delivery, including within a time period shorter than the Free Issue Inspection Period where so specified, with the Free Issue Inspection Period being deemed to be adjusted to reflect such time period), - the Client (acting reasonably) shall rectify any notified shortage and/or arrange for any defective Free Issue Materials to be replaced as soon as reasonably practicable upon being notified of the same and the provisions of the fourth main bullet point of this clause 75 shall apply mutatis mutandis to such replacement Free Issue Materials and - following the expiration of the Free Issue Inspection Period (or following the inspection of any shorter period specified by a party other than the Client where that party has delivered the Free Issue Materials), risk in the Free Issue Materials shall come under the care, custody and control of the Contractor and the Contractor procures that the Free Issue Materials are insured pursuant to the first entry of the Insurance Table (save in respect of any defective or missing Free Issue Materials that have been properly notified by the Contractor in accordance with this clause 75, in which case the defective and/or missing Free Issue Materials so notified shall come under the care, custody and control of the Contractor (and the Contractor is obliged to insure the same pursuant to the first entry of the Insurance Table) once replaced, inspected and free from any further shortage or defect in accordance with the fourth main bullet point of this clause 75).” |

|  | AMENDMENTS TO CLAUSE 8 – RISKS AND INSURANCE |
| --- | --- |
|  | In the first bulleted item of clause 80.1: - after the words "use or occupation of the Site by the works or for the purpose of the works which is the unavoidable result of the works" in its first sub-bulleted item insert "(save where the relevant claims, proceedings, compensation and/or costs arise from a risk and/or liability borne by the Contractor pursuant to this contract (including where the Contractor breaches clause 27.5 and/or clause 27.6)"; and - at the end of its second sub-bullet point, insert "and except any such negligence, breach of statutory duty or interference in respect of any design or any other documentation or information provided and/or prepared by or on behalf of the Client for which the Contractor is responsible pursuant to the terms of this contract." |
|  | At the end of the second bulleted item of clause 80.1, insert the following: "and except any fault in any design or any other documentation or information provided and/or prepared by or on behalf of the Client for which the Contractor is responsible pursuant to the terms of this contract." |
|  | Delete the third bulleted item of clause 80.1 in its entirety. |
|  | Delete the fifth bulleted item of clause 80.1 in its entirety. |
|  | In the sixth bulleted item of clause 80.1, delete the first sub-bulleted item (which starts with the words "a Defect"). |
|  | Delete the ninth bulleted item of clause 80.1 in its entirety. |
|  | Replace the wording of clause 81.1 in its entirety with the following: "From the stating date until the Defects Certificate has been issued, the risks which are not carried by the Client are carried by the Contractor." |
|  | At the beginning of clause 82.1, replace "Any cost" with "Without prejudice to the Contractor's indemnities in this contract and its other liabilities pursuant to the contract, any cost". |
|  | Replace the wording of clause 83.1 in its entirety with "Not used." |
|  | In clause 83.3 add the following two rows to the Insurance Table: Insurance against; Minimum amount of cover or minimum limit of indemnity. New pollution and new contamination caused by the Contractor’s activity under the contract, including exacerbation of existing pollution and contamination at the Site.; The amount stated in Contract Data: Part One.. Negligent acts, errors and/or omissions in the performance of the Contractor’s professional obligations under the contract (with such insurance being referred to in the contract as "professional indemnity insurance").; The amount stated in Contract Data: Part One.. |
|  | After clause 86, insert a new clause 86A with the heading "Joint Fire Code" as follows: "In Providing the Works and performing its other obligations pursuant to the contract, the Contractor complies with the Joint Code of Practice on the Protection from Fire of Construction Sites and Buildings Undergoing Renovation, published by Construction Industry Publications Ltd and the Fire Protection Association (as the same may be updated from time to time)." |

|  | AMENDMENTS TO CLAUSE 9 – TERMINATION |
| --- | --- |
|  | Replace the first row of the Termination Table in clause 90.2 (for "The Client") with the following: TERMINATING PARTY; REASON; PROCEDURE; AMOUNT DUE. The Client; R1 – R15 (including 5A); P1, P2, P3 and P5; A1 and A3. R17 or R20; P1, P4 and P5; A1 and A2. R21; P1, P3 and P5; A1 and A2. |
|  | In the "Procedure" column for each of the "P1 and P4" entries in the row for "The Contractor", insert "(and P5)". |
|  | Replace the wording of clause 91.1 in its entirety with the following: "Subject to clause 91.1A below - either Party may terminate the contract immediately if the other Party is subject to or has suffered an Insolvency Event or - where the Client (in its capacity as the "Client" under the FAC-1 Contract) terminates the Contractor's engagement (in its capacity as the "Alliance Member" under the FAC-1 Contract) under the FAC-1 Contract pursuant to Contract Term 14.3, the notice of such termination shall also constitute a valid notice of termination of the obligation of the Contractor to Provide the Works purposes of clause 90.1 if the notice states that it also applies to the same, (R1 to R10 (inclusive))." |
|  | Insert a new clause 91.1A as follows: "The Contractor's right to terminate under clause 91.1 where the Client is subject to or suffers an Insolvency Event will not arise where the Insolvency Event involves the Client - having a winding-up order made against it, - having a monitor appointed or any document is filed at court to obtain or apply for a moratorium or order is made for a moratorium to come into force, - having a provisional liquidator appointed to it, - passing a resolution for winding-up (other than in order to amalgamate or reconstruct), - having an administration order made against it or had an administrator appointed over it, - having an administrative receiver appointed over the whole or a substantial part of its underlying or assets, - making an arrangement, compromise or composition with its creditors, where a voluntary arrangement approved under Part 1 of the Insolvency Act 1986 takes effect in relation to the Client or after a court order is made under section 901C(1) of the Companies Act 2006 in relation to the Client, (in each case, a "relevant insolvency procedure") unless and to the extent that - in a case where the Client has entered administration, an administrative receiver of the company has been appointed (otherwise than in succession to another administrative receiver), gone into liquidation and/or a provisional liquidator of the Client is appointed (otherwise than in succession to another provisional liquidator), the office-holder consents to the termination, - in any other case, the Client consents to the termination, - the court is satisfied that the continuation would cause the Contractor hardship and grants permission for the termination or - the termination is otherwise permitted pursuant to Section 233B of the Insolvency Act 1986 (as amended and in force from time to time)." |
|  | In clause 91.2, insert "(4)" after "four". |
|  | In clause 91.3, insert "(4)" after "four". |
|  | In clause 91.4, insert "(13)" after "thirteen". |
|  | In clause 91.5, insert "applicable" before "law". |
|  | In clause 91.6: - insert "(13)" after "thirteen"; and - insert "(pursuant to clause 14.5 or otherwise)" after "from the Scope". |
|  | In clause 91.7: - insert "(13)" after "thirteen"; and - replace "Contract Date" with "Effective Date". |
|  | Replace the wording of clause 91.8 in its entirety with the following: "The Client may immediately terminate the Contractor's obligation to Provide the Works if the Client (in its capacity as the "Client" under the FAC-1 Contract) terminates or has the right to terminate the Contractor's engagement (in its capacity as the "Alliance Member" under the FAC-1 Contract) under the FAC-1 Contract pursuant to Contract Term 14.4 of the FAC-1 Contract (R22)." |
|  | Insert a new clause 91.9 as follows: "The Client may immediately terminate the engagement of the Contractor's obligation to Provide the Works by reference to the circumstances set out at regulation 73(1)(a) or regulation 73(1)(c) of the Public Contracts Regulations 2015, in which case the procedures and amounts due on termination are the same as if the Parties had been released under the law from further performance of the whole of the contract (R17)." |
|  | Insert a new clause 91.10 as follows: "The Contractor's termination rights under clauses 91.4, 91.5 and 91.6 may not be exercised while the Client is and remains subject to a relevant insolvency procedure unless such exercise is expressly permitted and/or is not prohibited by the provisions of Section 233B of the Insolvency Act 1986 (as amended and in force from time to time)." |
|  | In the "P4" entry of clause 92.2, replace “Working Areas” with “Site”. |
|  | After the "P4" entry of clause 92.2, insert the following as a new paragraph: "P5 The Contractor provides for such reasonable period as required by the Client following termination to answer any queries raised by the Client and supply any information required by the Client in connection with the works and co-operates with the Client. The Contractor, upon notification from the Client, delivers to the Client all Plant and Materials and other items of any kind whatsoever relating to the contract and/or in respect of the works which is in the Contractor's control, custody or possession, including those in the control, custody or possession of the Subcontractors. The Contractor transfers title in all Plant and Materials to the Client for which the Client has paid or discharged payment and delivers such Plant and Materials to the Site or such location as instructed by the Client." |
|  | In the "A4" entry of clause 93.2, replace "Contract Date" with "Effective Date". |

|  | ADDITIONAL CLAUSE 10 – ADDITIONAL PROVISIONS |
| --- | --- |
|  | Insert a new core clause 10 after core clause 9 (Termination) in the conditions of contract with the heading "Additional provisions" |
|  | Insert a new clause 101 as follows: "101 Apprenticeships 101.1 The Contractor takes all reasonable steps to employ apprentices, and reports to the Client the numbers of apprentices employed and the wider skills training provided, during the delivery of the works. 101.2 The Contractor takes all reasonable steps to ensure that no less than the Required Apprenticeship Number are on formal apprenticeship programmes or that a similar proportion of hours worked in Providing the Works, (which may include support staff and Subcontractors) are provided by people on formal apprenticeship programmes. 101.3 The Contractor makes available to its people and Subcontractors working on the contract, information about the United Kingdom government’s apprenticeship programme and wider skills opportunities. 101.4 The Contractor provides any further skills training opportunities that are appropriate for its people engaged in Providing the Works. 101.5 The Contractor provides a report detailing the following measures at the reporting interval specified in Contract Data: Part One and is prepared to discuss apprenticeships at its regular meetings with the Project Manager - the number of people during the reporting period employed on the contract, including support staff and Subcontractors, - the number of apprentices and number of new starts on apprenticeships directly initiated through this contract, - the percentage of all people taking part in an apprenticeship programme, - if applicable, an explanation from the Contractor as to why it is not managing to meet the specified number target, - actions being taken to improve the take up of apprenticeships and - other training/skills development being undertaken by people in relation to this contract, including: - work experience placements for fourteen (14) to sixteen (16) year olds, - work experience / work trial placements for other ages, - student sandwich / gap year placements, - graduate placements, - vocational training, - basic skills training and - on-site training provision / facilities.” |
|  | Insert a new clause 102 as follows: "102 Cooperation 102.1 The Contractor acknowledges and agrees that due to the operational (or to be operational) nature of the Site, each Operational Party has an interest in the on-going management and operation of the Site and the interfacing of the works and/or services comprising the Project with its own duties, obligations and responsibilities to the Client under separate contractual arrangements and shall cooperate and work with the Operational Parties on the basis set out in this contract generally and specifically pursuant to this clause 102. 102.2 The Contractor shall - cooperate with and interface in the performance of the works with the Operational Parties in connection with the Project as may be reasonably required and - establish an integrated collaborative team environment in order to encourage proactive, open and efficient sharing of knowledge and information between the Contractor and the Operational Parties, in each case so far as reasonably practicable on a Project Focused basis. 102.3 The Contractor shall work with the Operational Parties so far as is reasonably practicable, using the Standard of Care, to - to the extent reasonably within the Contractor's control, assist the Operational Parties in performing their obligations under their respective contractual arrangements with the Client in respect of which they are reliant upon information provided and/or developed by and/or input provided by the Contractor in connection with Project and - share best practice in connection with the Project, on a Project Focused basis. 102.4 The Contractor acknowledges and agrees, for the purposes referred to in this clause 102, to promptly supply or allow each Operational Party access to all information and documentation in its possession or control that is reasonably requested by them in connection with the Project, insofar as the same is - not subject to disclosure and/or confidentiality restrictions by applicable law and/or the contract, - reasonably required by the Contractor to properly perform its obligations under the contract and/or - reasonably required by an Operational Party to properly perform its obligations under its contractual arrangements with the Client. 102.5 The Contractor shall: - comply with and perform its obligations under this contract so as to avoid or (where avoidance is not practicable) mitigate causing each Operational Party to incur any additional cost, delay and/or disruption in connection with the performance of their duties and obligations under and in accordance with the Project and/or any separate contractual arrangement with the Client respectively and - (and shall procure that its Subcontractors) otherwise not - delay, impede, inhibit, disrupt and/or hinder any Operational Party in the carrying out of their duties and obligations in connection with the Project and - act in a manner that might reasonably be expected to cause any Operational Party to be in breach of its own obligations under any separate contractual arrangement with the Client and/or otherwise to suffer and/or incur any loss, delay, disruption, and/or inconvenience in performance of such obligations. 102.5 The Contractor shall, in complying with its obligations under this clause 102, consult with the Contractor, the Project Manager and the Client and attend such meetings as and when reasonably requested by the Client or the Project Manager to discuss any matters arising under the contract and/or in relation to the Project. 102.5 Nothing in this clause 102 shall require the Contractor to perform tasks and/or duties which are the responsibility of Operational Party under any its contractual arrangements with the Client ." |

|  | AMENDMENTS TO DISPUTE RESOLUTION OPTION W2 |
| --- | --- |
|  | In Option W2.1(2), insert "(1)" after "one". |
|  | In Option W2.1(3), insert "(3)" after "three". |
|  | In Option W2.2(5), insert "(4)" after "four". |
|  | In Option W2.3(1), insert "(3)" after both instances of "three". |
|  | In Option W2.3(2): - insert "(7)" after "seven"; and - insert "(14)" after "fourteen". |
|  | After Option W2.3(4), insert a new Option W2.3(4A) with the following wording: "The Adjudicator has the power to determine more than one dispute under the contract at the same time and, if requested to do so by either Party, determines any matter raised by such Party in the nature of set-off, abatement or counterclaim at the same time as the Adjudicator determines any other matter referred to him." |
|  | In Option W2.3(7), insert "(7)" after "seven". |
|  | In Option W2.3(8): - insert "(28)" after "twenty-eight"; and - insert "(14)" after "fourteen". |
|  | In Option W2.3(12), insert "(5)" after "five". |
|  | Replace the wording of Option W2.4(1) in its entirety with the following: "A Party may refer any dispute under or in connection with the contract to the tribunal." |
|  | In Option W2.4(2), insert "(4)" after "four". |

|  | AMENDMENTS TO SECONDARY OPTION CLAUSES |
| --- | --- |
|  | [Replace the wording of Option X1 in its entirety with the following: “X1 THE AGREED MATERIALS X1.1 As at the Contract Date - the Prices include, as fixed costs, the Agreed Materials Costs for the Agreed Materials that will form part of the works (and the Contractor has clearly identified, in relation to its Agreed Materials Costs, any profit and/or overhead elements forming part of the same in the Materials Schedule), - in addition to setting out the Agreed Materials Costs for the Agreed Materials, the Materials Schedule also identifies - the market price (excluding any profit and/or overheads of the relevant Materials Supplier and the Contractor) for each class of Agreed Materials as at the Contract Date, as determined by reference to the Agreed Materials Benchmark for such Agreed Materials (identified in the Materials Schedule as the “Benchmark Market Price”), - the latest date(s) by which the Contractor will place an order for each class of Agreed Materials (including full details of where multiple orders will be placed in relation to the same class of Agreed Materials at different dates and their respective latest order dates) with each Materials Supplier (the “Latest Order Date”), - what pricing fluctuation tolerance (expressed as a percentage), when considered against the relevant Benchmark Market Price, the Contractor has allowed for in its Agreed Materials Costs for each class of Agreed Materials to account for any - increases to the Agreed Materials Benchmark for such Agreed Materials on or after the Contract Date (the “Maximum Increase Tolerance”) and - decreases to the Agreed Materials Benchmark for such Agreed Materials on or after the Contract Date (the “Maximum Reduction Tolerance”). X1.2 If, on or after the Contract Date, the Contractor can demonstrate to the Project Manager on an open-book basis that as at the date that the Contractor has placed an order with the relevant Materials Supplier for any Agreed Materials in connection with the works (a “Materials Order”) - the Contractor has first secured quotations from at least three (3) potential Materials Suppliers for the Agreed Materials, unless the Contractor can demonstrate to the satisfaction of the Project Manager (acting reasonably) that - fewer than three (3) potential Materials Suppliers are able to provide the Agreed Materials in the then current market, before placing the order with relevant Materials Supplier and - placing the order with that Materials Supplier represents the best value for money for the Client and the works in the prevailing market for the Agreed Materials as at the date of the Materials Order, - the current market price (excluding any profit and/or overheads of the relevant Materials Supplier and the Contractor) for that class of Agreed Materials, as determined by reference to the Agreed Materials Benchmark, exceeded the Benchmark Market Price for such Agreed Materials (the “Current Market Price”), - the then Current Market Price was applied by the Materials Supplier to the Agreed Materials as part of the Materials Order, - the Contractor paid the Materials Supplier for the Agreed Materials at the same time as it placed the Materials Order, - the difference between the then Current Market Price and the Benchmark Market Price paid (or payable) by the Contractor to the Materials Supplier for the Agreed Materials exceeded (or exceeds) the Maximum Increase Tolerance (the “BMP Difference”), - the Materials Order was placed no later than the Latest Order Date for the relevant Agreed Materials (or, if it was not placed by such date, the Contractor can demonstrate that the failure was not attributable to any act, omission or default of the Contractor), - the Contractor can demonstrate to the Project Manager (acting reasonably) that the Contractor has experienced (or is experiencing) similar cost increases on other projects in relation to materials of a same and/or similar type as the Agreed Materials, - the Contractor used reasonable endeavours to mitigate the impact of the BMP Difference where, based on its on-going assessment of the historic market price(s) (excluding any profit and/or overheads of the relevant Materials Supplier and the Contractor) of the Agreed Materials as from the Contract Date, it would have been reasonable foreseeable to a contractor exercising the Standard of Care that, on or before the Latest Order Date for the Agreed Materials, the difference between the then Current Market Price and the Benchmark Market Price would exceed the Maximum Increase Tolerance, including by - placing the Materials Order earlier than the Latest Order Date; and - (subject to clause X1.3) in advance of placing the relevant Materials Order, where, insofar as is reasonable practicable in the circumstances, proposing to the Project Manager to substitute the relevant Agreed Materials for alternative materials at the same cost or at a lower cost as was allowed for in the Prices for the Agreed Materials as at the Contract Date, then - the Contractor shall be entitled to an adjustment to the Agreed Materials Costs for the Agreed Materials that are the subject of the Materials Orders to reflect the BMP Difference for which the Contractor has been required to pay to the Materials Supplier only (the “Agreed Materials Increase”) and - the Prices will be adjusted accordingly to reflect the Agreed Materials Increase, - in each case with such adjustment being assessed and determined by the Project Manager, acting reasonably (and the Contractor acknowledges and agrees that, in making such determination, a nil adjustment may be made by the Project Manager where it is not satisfied that the Contractor is able to demonstrate that the above preconditions have been satisfied in full). - If, following the submission of any proposals by the Contractor to the Project Manager pursuant to clause 2.2.7(b), the Client accepts all or part of the Contractor’s proposal, the Project Manager shall issue an instruction to the Contractor changing the Scope pursuant to clause 60.1(1) instructing the implementation of the accepted element(s) of the proposal and the Contractor acknowledges and agrees that - if the proposal as implemented (on the basis proposed by the Contractor) results in a cost saving when comparing the amount allowed for in the Activity Schedule and/or the Prices for the original Agreed Materials against the alternative materials (as approved), the Prices shall be reduced to reflect this difference and - if the proposal as implemented (on the basis proposed by the Contractor) results in a cost increase when comparing the amount allowed for in the Activity Schedule and/or the Prices for the original Agreed Materials against the alternative materials (as approved), the Prices shall be increased to reflect the difference, with the Contractor not being entitled to any other adjustment to the Prices, the Completion Date and/or any Key Dates arising out of or in connection with the instruction. X1.3 If, on or after the Contract Date, and as the date that the Contractor has placed a Materials Order - the current market price (excluding any profit and/or overheads of the relevant Materials Supplier and the Contractor) for that class of Agreed Materials, as determined by reference to the Agreed Materials Benchmark, was less than the Benchmark Market Price for such Agreed Materials (the “Current Market Price”), - the Contractor paid the Materials Supplier for the Agreed Materials as part of the Materials Order and - the difference between the then Current Market Price and the Benchmark Market Price paid (or payable) by the Contractor to the Materials Supplier for the Agreed Materials exceeded (or exceeds) Maximum Reduction Tolerance (the “BMP Difference”), then - the Agreed Materials Costs for the Agreed Materials that are the subject of the Materials Orders shall be adjusted to reflect the BMP Difference for which the Contractor has been required to pay to the Materials Supplier only (the “Agreed Materials Reduction”) and - the Prices will be adjusted accordingly to reflect the Agreed Materials Reduction, in each case with such adjustment being assessed and determined by the Project Manager, acting reasonably. X1.4 The Contractor acknowledges and agrees that, notwithstanding any other provision of this contract, the application of any Agreed Materials Increase to the Agreed Materials Costs (and the Prices) pursuant to this Option X1 shall represent the Contractor’s sole and exclusive entitlement in respect of any adjustment to the Agreed Materials Costs for the relevant Agreed Materials for the reasons stated in this Option X1 and the Contractor shall have no entitlement to any another adjustment to the Prices, the Completion Date and/or any Key Date arising out of or in connection with the same (or otherwise in connection with any Agreed Materials Reduction).”] |
|  | Option X2 – Changes in the law Replace the wording of Option X2 in its entirety with the following: "Option X2 – Changes in the applicable law A change in the applicable law of the country in which the Site is located is a compensation event if it occurs after the Effective Date and except where - the change would have been reasonably foreseeable at the Change in Law Base Date to a contractor exercising the Standard of Care (and in the capacity of a contractor, not a professional designer) and - the change would not affect the supply and/or provision of works and/or services by the Contractor to another customer in connection with the design and construction of a project of a similar size, scope, nature and complexity to the works, provided that a change in the applicable law is treated as occurring before the Change in Law Base Date if it is stated in a statute or statutory instrument before but comes into force after the Change in Law Base Date. If the effect of a compensation event which is a change in the law is to reduce the total of the Defined Cost, the Prices are reduced." |
|  | [Option X4 – Ultimate holding parent company guarantee Replace the wording of Option X4 in its entirety with the following: "Option X4 – Parent Company Guarantee X4.1 Where the Contract Data states that Option X4 applies to the contract, at the same time as entering into the contract the Contractor provides to the Client the Parent Company Guarantee executed by the Contractor's Parent Company. X4.2 The Contractor's compliance with Option X4.1 is a condition precedent to any obligation on the part of the Client to make any payment that might otherwise be due under this contract, and the Contractor acknowledges that it has no entitlement to receive payment under this contract unless and until the Contractor has provided a Parent Company Guarantee in accordance with Option X4.1 (where Contract Data: Part One states that Option X4 applies)."] |
|  | [Option X7 – Delay damages Replace the wording of Option X7 in its entirety with the following: "Option X7 – Delay Damages X7.1 The Contractor pays delay damages at the rate stated in the Contract Data from the Completion Date for each day until the earlier of - Completion, - the date on which the Client takes over the works and - the date on which the Project Manager issues (or is treated as issuing) a termination certificate. X7.2 If the Completion Date is changed to a later date after delay damages have been paid, the Client repays the overpayment of damages without interest. X7.3 If the Client takes over a part of the works before Completion, the delay damages are reduced from the date on which the part is taken over. The Project Manager assesses the benefit to the Client of taking over the part of the works as a proportion of the benefit to the Client of taking over the whole of the works not previously taken over. The delay damages are reduced in this proportion. X7.4 The Contractor agrees that the delay damages are fair and reasonable in all respects and represent the Client's genuine pre-estimate of all losses the Client may sustain as a result of late Completion except for those losses referred to in Option X7.7. X7.5 The Client may at its option recover delay damages by way of deductions from any sum due to the Contractor under the contract and/or by inclusion in any pay less notice. X7.6 The delay damages - are, subject to Option X7.7, the Client's sole and exclusive remedy in respect of any failure by the Contractor to achieve Completion for any section of the works by the Completion Date other than in the event of termination before Completion of the whole of the works, - are in addition to any damages or other sums for which the Contractor is liable under the contract and - do not relieve the Contractor from its obligation to Provide the Works, or from any other duties, obligations or responsibilities which the Contractor may have under the contract. If these delay damages are found for any reason to be void, invalid or otherwise inoperative so as to disentitle the Client from claiming delay damages as liquidated damages on account of delay to Completion of the whole of the works or any section of the works, the relevant provisions are deemed to be deleted from the contract and the remainder of the contract remains in full force and effect. For the avoidance of doubt, the Client is entitled to recover from the Contractor general damages in respect of all losses which the Client will sustain as a result of any delay in reaching Completion of the whole of the works or any section of the works, provided that such general damages, except for those losses referred to in Option X7.7, do not exceed the delay damages which would have been due under the contract had Option X7.1 (or the relevant part thereof) remained enforceable. X7.7 No allowance has been made in the delay damages or in the general damages referred to in this clause for the costs of delay, disruption, interference or interruption incurred by the Client to Others as a result of the Contractor's failure to comply with its obligations and all such costs (including the costs of acceleration measures agreed by the Client with such persons) are recoverable as general damages in addition to any delay damages under this clause (or any general damages referred to above)."] |
|  | Option X8 – Undertakings to the Client or Others Replace the wording of Option X8 in its entirety with the following: "Option X8 – Collateral Warranties X8.1 Within twenty-one (21) days of receiving a written request from the Project Manager, the Contractor enters into a deed or deeds of Contractor Collateral Warranty in favour of any Beneficiary (excluding the Client), up to a maximum of six (6) Contractor Collateral Warranties in the aggregate. The Contractor acknowledges and agrees that if the Contractor fails to deliver any such collateral warranty under this Option X8.1 within the time required, the Client may withhold twenty-five per cent (25%) from any further sums due and payable to the Contractor under the contract until such time as the outstanding Contractor Collateral Warranty is provided. X8.2 Within five (5) days of entering into a subcontract with a Subcontractor, the Contractor shall notify the Project Manager of the same. The Contractor shall then procure that the relevant Subcontractor executes a Subcontractor Collateral Warranty or a Subconsultant Collateral Warranty (as applicable) (with any such amendments that the Client may agree in advance and in writing, acting reasonably) in favour of - the Client, - each Beneficiary previously notified to the Contractor by the Project Manager in writing as having an interest in the subcontracts for the works and - any Beneficiary thereafter notified to the Contractor by the Project Manager in writing (following its receipt of the Contractor's notification) as having an interest in the subcontracts for the works, (up to a maximum of seven (7) Subcontractor Collateral Warranties in the aggregate for any one (1) Subcontractor) within - in the case of the Client, twenty-one (21) days of the date of the relevant subcontract, - in the case of each Beneficiary falling within the class of previously-notified Beneficiaries covered by the second bulleted item above, twenty-one (21) days of the date of the relevant subcontract and - in the case of each Beneficiary falling within the class of newly-notified Beneficiaries covered by the third bulleted item above, twenty-one (21) days of the date of the Project Manager's notification. The Contractor acknowledges and agrees that if the Contractor fails to deliver any such collateral warranty under this Option X8.2 within the time required, the Client is entitled to withhold payment of the sum of ten thousand pounds (£10,000) from any further sums claimed by (or due to) the Contractor under the contract for each Subcontractor Collateral Warranty or Subconsultant Collateral Warranty that is outstanding at the relevant time until each such outstanding Subcontractor Collateral Warranty or Subconsultant Collateral Warranty (as applicable) is provided. X8.3 Within five (5) days of becoming aware of a Subcontractor entering into a subsubcontract with a subsubcontractor in connection with the works, the Contractor shall notify the Project Manager of the same. The Contractor shall then procure that the relevant Subcontractor procures that that subsubcontractor executes a Subsubcontractor Collateral Warranty (with any such amendments that the Client may agree in advance and in writing, acting reasonably) in favour of - the Client, - each Beneficiary previously notified to the Contractor by the Project Manager in writing as having an interest in the subsubcontracts for the works and - any Beneficiary thereafter notified to the Contractor by the Project Manager in writing (following its receipt of the Contractor's notification) as having an interest in the subsubcontracts for the works, (up to a maximum of seven (7) Subsubcontractor Collateral Warranties in the aggregate for any one Subsubcontractor) within - in the case of the Client, thirty (30) days of the date of the relevant subsubcontract, - in the case of each Beneficiary falling within the class of previously-notified Beneficiaries covered by the second bulleted item above, thirty (30) days of the date of the relevant subsubcontract and - in the case of each Beneficiary falling within the class of newly-notified Beneficiaries covered by the third bulleted item above, thirty (30) days of the date of the Project Manager's notification. The Contractor acknowledges and agrees that if the Contractor fails to deliver any such collateral warranty under this Option X8.3 within the time required, the Client is entitled to withhold payment of the sum of ten thousand pounds (£10,000) from any further sums claimed by (or due to) the Contractor under the contract for each Subsubcontractor Collateral Warranty that is outstanding at the relevant time until each such outstanding Subsubcontractor Collateral Warranty is provided. X8.4 In the event that the Contractor has not procured or provided (as the context requires) one or more of any Contractor Collateral Warranty, Subcontractor Collateral Warranty, Subconsultant Collateral Warranty and/or Subsubcontractor Collateral Warranty that are required to be provided (or procured) by the Contractor pursuant to Option X8.1 to Option X8.3 (inclusive) within twenty-five (25) Working Days of a notification from the Project Manager of such failure - the Client (or the Project Manager on its behalf) or another Beneficiary may, but is not obliged to, by written notice to the relevant party (the "relevant party" being the Contractor or the relevant Subcontractor (including a subconsultant) or subsubcontractor) in the form set out in the Third Party Rights Schedule (or in such equivalent form as may be set out in the relevant subcontract or subsubcontract) and - such notice shall confirm the granting of the rights referred to in the part of the Third Party Rights Schedule appropriate to that relevant party (or such equivalent rights as may be set out in the relevant subcontract or subsubcontractor) by the relevant party to the relevant Beneficiary, provided always that - the relevant Beneficiary does not already have the benefit of a Contractor Collateral Warranty, Subcontractor Collateral Warranty, Subconsultant Collateral Warranty or Subsubcontractor Collateral Warranty (as the context permits) from that relevant party, - where a notice is issued to a Subcontractor or a Subsubcontractor, the Client or the Project Manager shall notify the Contractor of the same as soon as reasonably practicable after its issue (and in any event within ten (10) Working Days of that date) for its records (provided that the provision of such notice shall not be a precondition to the effectiveness of the relevant notice) and - the issue of any notice under this Option X8.4 shall be subject to the limitations on the number of (as applicable) Contractor Collateral Warranties, Subcontractor Collateral Warranties and Subsubcontractor Collateral Warranties referred to in Option X8.1 to Option X8.3 (inclusive) and be treated as counting towards the total number of any such applicable class of document for the purposes of determining this number. Any notice issued pursuant to this Option X8.4 shall take effect on the date of the notice and state the name of the Beneficiary to whom the rights stated in that notice are granted and their interest in the works. In order to give effect to the intention of this Option X8.4, the Contractor shall ensure that - any subcontract (including consultant appointment) that it enters into with a Subcontractor (including a subconsultant) includes an equivalent right for a Beneficiary (or a party acting on its behalf) to serve a written notice on such relevant on the basis described above and - any subsubcontracts entered into by a Subcontractor (excluding subconsultants) in connection with the works also includes an equivalent right in favour of any Beneficiary, in materially in the same form and manner as prescribed above." |
|  | Option X10 – Information Modelling Replace the wording of Option X10 in its entirety with the following: "Option X10 – Information Modelling X10.1 The Contractor shall comply with the BIM Requirements at all times in the provision of the works." |
|  | Option X11 – Termination by the Client In Option X11.2: - replace "P1 and P2" with "P1, P2 and P5"; and - replace "A1, A2 and A4" with "A1 and A2". |
|  | [Option X13 – Performance Bond Replace the wording of Option X13 in its entirety with the following: "Option X13 – Performance Bond X13.1 Where Contract Data: Part One states that Option X13 applies to this contract then, on the Effective Date, the Contractor provides (at its own cost) to the Client a Performance Bond executed by a bank, insurance company or other surety which the Client has approved in advance. X13.2 A reason for the Client not accepting the bank, insurance company or other surety is that its commercial position is not strong enough to carry the bond. X13.3 The Contractor's compliance with Option X13.1 is a condition precedent to any obligation on the part of the Client to make any payment that might otherwise be due under this contract, and the Contractor acknowledges that it has no entitlement to receive payment under this contract unless and until the Contractor has provided a Performance Bond in accordance with Option X13.1 (where Contract Data: Part One states that Option X13 applies)."] |
|  | Option X15 – The Contractor's design In Option X15: - replace the wording of Option X15.1 in its entirety with the following: "The Contractor is not liable for Defects in the works due to its design (including the preparation by it of any specifications and the selection by the Contractor of any Plant and Materials and including design for which it is responsible pursuant to the contract), unless it failed to carry out that design using the Standard of Care."; - replace the wording of Option X15.3 in its entirety with "Not used."; - replace the wording of Option X15.4 in its entirety with the following: "The Contractor retains copies of the Alliance Member Materials for the period of retention. The copies are retained in the form stated in the Scope (or as otherwise notified by the Project Manager to the Contractor in writing before Completion, acting reasonably)."; and - replace the wording of Option X15.5 in its entirety with "Not used.". |
|  | Option X16 – Retention Replace the wording of Option X16.3 in its entirety with the following: "The Client has the full beneficial interest in the amount retained, without any fiduciary obligation, and the relationship of the Client and Contractor with regard to the amount is solely that of debtor and unsecured creditor, subject to the terms of the contract." |
|  | Option X18 – Limitation of liability In Option X18.5, insert the following bulleted items before the bullet point starting "loss of or damage to": "· personal injury or death, · interest on any debt or damages, · fraud or wilful default, · costs in any proceeding,". |
|  | Option X20 – Key Performance Indicators Replace the wording of Option X20 in its entirety with the following: "Option X20 – Key Performance Indicators X20.1 A "Key Performance Indicator" is an aspect of performance by the Contractor in connection with the works for which a target is stated in the KPI Schedule (and identified as a Key Performance Indicator or other equivalent wording therein). X20.2 From the starting date until the Defects Certificate has been issued, the Contractor reports to the Project Manager on its performance against each of the Key Performance Indicators on the basis set out in the Scope and/or the KPI Schedule (and on such other basis as the Project Manager, acting reasonably, may reasonably request from time to time). Reports are provided at the KPI Reporting Interval and include the forecast final measurement against each Key Performance Indicator (as well as any other information stated as needed to be provided by the Contractor in the KPI Schedule). X20.3 If the Contractor's forecast final measurement against a Key Performance Indicator will not achieve the target stated in the KPI Schedule (whether by reference to any specified timeframe or any other measure), it submits to the Project Manager its proposals of improving performance and for (if possible) achieving the relevant measure (whether in whole or in part). X20.4 The Contractor's entitlement to be paid any sum(s) in connection with the Key Performance Indicators (by reference to any stated target(s) in the KPI Schedule), as well as the basis (and frequency / time) upon which sums shall become payable under this contract, shall be governed by the rules and procedure set out in the KPI Schedule. X20.5 Any sums payable to the Contractor under or in connection with this Option X20 are in addition to the Prices for the works and the Prices shall not be reduced where the Contractor fails to achieve one (1) or more of the targets for the Key Performance Indicators set out in the KPI Schedule by reference to this Option X20 and/or the KPI Schedule alone." |
|  | Option Y(UK)2 – The Housing Grants, Construction and Regeneration Act 1996 In Option Y(UK)2: - in the first sentence of Option Y2.2, insert "(7)" after "(seven)"; - replace the second sentence of Option Y2.2 with "The date on which the final payment becomes due is as set out in Contract Data: Part One"; - replace the third sentence of Option Y2.2 with "The final date for payment is the date as specified in Contract Data: Part One"; - in Option Y2.4, insert "(or pursuant to Option X11)" after "R22"; and - in Option Y2.4, insert "(including R5A)" after "R10". |
|  | Option Y(UK)3 – The Contracts (Rights of Third Parties) Act 1999 Replace the wording of Option Y(UK)3 in its entirety with the following: "Option Y(UK)3 – The Contracts (Rights of Third Parties) Act 1999 Y3.1 The Client may, at any time prior to Completion of the whole of the works, novate the contract to any person taking over the whole of the Client's interest in the works. Y3.2 The rights of the Parties to terminate, rescind or agree any variation, waiver or settlement under the contract are not subject to the consent of any other person. Y3.3 Other than as granted pursuant to this Option Y(UK)3 and/or the Contract Terms, a person who is not a party to the contract shall have no rights under the Contracts (Rights of Third Parties) Act 1999 to enforce any term of the contract unless it is stated expressly in the Contract Data that an identified third party may enforce such rights and those rights are identified." |

DRAFTING NOTE: This list will be updated on a case-by-case basis as appropriate.

DRAFTING NOTE: See drafting note 25 below in relation to X1.

DRAFTING NOTE: The requirement of a PCG to be determined on a case-by-case basis.

DRAFTING NOTE: The requirement of a performance bond to be determined on a case-by-case basis.

DRAFTING NOTE: The treatment of payment for such works and services will be updated on a case-by-case basis.

DRAFTING NOTE: To be confirmed on a case-by-case basis.

DRAFTING NOTE: The Client's position is that the Contractor will be required to procure all consents in connection with the works.  However, specific (and limited) exclusions from this position may be agreed on a case-by-case basis to reflect works-specific circumstances.

DRAFTING NOTE: to be updated on a case-by-case basis.

DRAFTING NOTE: The Client's position is that the works should have a single completion date but it reserves the right to update the Contract Data (and, as required, the Main Works Terms) to incorporate sectional completion (and associated delay damages) on a case-by-case basis.

DRAFTING NOTE: To be populated on a case-by-case basis but note that this entry will not be updated to cover wind-related measurements.

DRAFTING NOTE: The Client is cognisant of prevailing insurance market conditions in the United Kingdom relating to infrastructure and construction requirements and is currently undertaking an insurance due diligence to review. The results of the review will determine the scope and levels of required insurances to protect the Client's separate interests and the insurable risk profile of the works to be covered by these Main Works Terms. The outcome of the review will also determine the appropriate contractual articulation of the Client's minimum insurance requirements under each Notice to Proceed to Stage 2 to be governed by these Main Works Terms. Accordingly, the precise insurance provisions in these Main Works Terms (and the expression of required insurance coverage, both in description and value) will be finalised on a case-by-case basis in due course.

DRAFTING NOTE: See drafting note 25 below in relation to X1.

DRAFTING NOTE: The requirement of a PCG to be determined on a case-by-case basis.

DRAFTING NOTE: See the earlier comment in relation to sectional completion (if required).

DRAFTING NOTE: This is an indicative figure based on previous projects of the Client.  However, the final amount will be confirmed on a project-specific basis based on the information that is available as at the date of the Works Package Procedure.

DRAFTING NOTE: The requirement of a performance bond to be determined on a case-by-case basis.

DRAFTING NOTE: To be populated in due course to reflect the final form of KPI Schedule and measures etc.

DRAFTING NOTE: The Client reserves the right to amend and update Option Y(UK)1 (and its associated schedules) to reflect any changes to the October 2020 wording of the Option published by NEC that it may require to reflect any guidance from the Cabinet Office in connection with the use of project bank accounts on public sector projects, as well as any specific requirements that the Client might have in respect of the same in connection with a specific works package.

DRAFTING NOTE: This entry has been included in the event that further clarification on the intended application of the contracts terms is required in the context of the specific works package in question only.  The Alliance Member acknowledges and agrees that it is not the intention of the Client to use this entry to make any material changes to the duties and obligations of the Parties under the Notice to Proceed to Stage 2 as already set out in the terms and conditions.

DRAFTING NOTE: To be reviewed on a case-by-case basis to reflect the circumstances in respect of the site.

DRAFTING NOTE: To be updated to reflect any pre-construction services and/or early works undertaken prior to the date of the Notice to Proceed to Stage 2.

DRAFTING NOTE: See the earlier comment on the treatment of insurance in the Main Works Terms.

DRAFTING NOTE: This wording deals with recent changes to legislation regarding a supplier's right to terminate a contract where its employer is insolvent.  This situation will not apply to the Client as a Crown body but it is included for completeness.

DRAFTING NOTE:  This section may be updated to reflect any sectionalisation of the works and/or (dis)application of the options stated.

DRAFTING NOTE: The Client has included this drafting as it recognises the current volatility of pricing across building materials and how this impacts on those participating within this Tender. Throughout Stage 1 and prior to the issue of any Notice to Proceed to Stage 2, the Client will work with the Alliance Member to continually review and ascertain the market prices for the undernoted items only based upon the prevailing market conditions at the time. It will be determined on a case-by-case basis as to whether the prevailing market prices at the time justify the inclusion of this provision. The Client is considering listing some or all of the following materials within the Materials Schedule: steel and timber.