- SCHEDULE 5

- TRANSITION PLANS

- Definitions

  - Without prejudice to Schedule 1 (Definitions and Interpretations), for the purposes of this Schedule 5, the following terms shall have the following meanings:

| - Term | - Definition |
| --- | --- |
| Contractors Exit Plan | Means the Contractors Exit Plan as contained in the Contractors Deliverable Quality Plan; |
| Establishment Orders | Means any directive or instruction issued formally in writing by or on behalf of the Commanding Officer; |
| Exit Communications Plan | Means the Contractor’s document that describes how stakeholders will be kept informed during the Exit Period; |
| Exit Manager | Means the Contractor’s representative responsible for the implementation of the Contractors Exit Plan; |
| Exit Period | Has the meaning set out in Annex A (Exit Requirements); |
| Exit Programme | Means the schedule of events during the Exit Period set out in Appendix 1 to Annex A of this Schedule 5; |
| Exit Requirements | Means the requirements on the Contractor upon the earlier of the Expiry Date or Termination Date detailed in Annex A to this Schedule 5; |
| Full Service Provision | Means the provision of all the Training Services in accordance with Schedule 2 (Statement of Requirements); |
| Implementation Key Milestones | Means the events critical to the transition from the Previous Contract to this Contract as identified in paragraph 4.2 of this Schedule 5 and the Implementation Programme; |
| Implementation Project Manager | Means the Contractor’s representative responsible for the implementation of the Implementation Plan; |
| Necessary Agreements | Means licences, wayleaves, permissions or other legal provisions applicable to the provision of the Training Services; |
| Recompetition | Means where the Authority re-competes its requirement for either the whole or part of the Training Services or their replacement or equivalent; |
| Recompetition Data | Means the provision of the following subject to the limitations set out in clause 69 (Co-operation on Expiry or Termination of Contract) of the Contract in respect of Commercially Sensitive Information: a. copies of all documentation, in hard and electronic copy, relevant to the Training Services for the purposes of Recompetition the data and information listed at paragraph 11 to this Schedule 5; b. any information in the Contractor’s possession or under its control which the Authority is legally required to produce at the time of Recompetition; c. summary details of any Necessary Agreements; and d. details of all Intellectual Property Rights relevant to the provision of the Training Services; |
| Resource Management Plan | Means a detailed plan of all the resource (equipment, finance, personnel etc) required to undertake the Training Services; and |
| Termination Programme | Has the meaning given in paragraph 10.1 of this Schedule 5. |

Introduction

  - In accordance with clause 14 (Implementation) and clause 72 (Exit Requirements) this Schedule 5 sets out the Contractor’s obligations in respect of its implementation of the Training Services and its exit from this Contract on the earlier of the Expiry Date or the Termination Date.

- Implementation

Implementation Plan

  - This Schedule 5 is supported by the Contractor’s Implementation Plan identified in Schedule 26 (Contractor’s Proposals). The Implementation Plan shall be submitted by the Contractor to the Authority within 5 days of  the Effective Date and be agreed with the Authority, such agreement shall not be unreasonably withheld or delayed.

  - The Contractor shall be responsible for the overall management of the Implementation Phase, managing the resolution of any problems encountered relating to Implementation Phase. The Contractor is solely responsible for meeting the requirements of the Implementation Plan and the milestones stated therein, unless obligations and/or dependencies on the Authority or any third party (other than any Subcontractor, employee or representative of the Contractor) are identified, and for ensuring that Full Service Provision is achieved by the Service Commencement Date.

  - The Contractor shall appoint an experienced Implementation Project Manager, who shall hold regular onsite meetings (accompanied by at least 2 members of its Implementation team) throughout the Implementation Phase with the Authority’s Representative, including at the Authority’s Representative’s request, in order to manage the effective implementation of the Implementation Plan.

  - If the Contractor wishes to make any changes to the Implementation Plan, then the Contractor shall submit a copy of the proposed revised Implementation Plan to the Authority as soon as reasonably practicable following such revisions.

  - Following receipt of the proposed revisions to the Implementation Plan pursuant to paragraph 3.4, the Authority shall be entitled, but not obliged, to comment on any or all of the proposed revisions.

  - Where the Authority raises any comments in accordance with paragraph 3.5 it may also indicate its preferred solutions and amendments to the Implementation Plan together with an explanation of the concerns which have given rise to such comments in sufficient detail to enable the Contractor to understand and to consider the Authority's comments.

  - The Contractor shall have due regard to any comments made by the Authority pursuant to paragraph 3.5 and shall, to the extent it considers appropriate, take the same into account when, and if, amending the Implementation Plan. If the Contractor decides not to take such comments into account it shall provide its reasons for so doing in writing to the Authority within 5 Business Days.

  - The Contractor shall not make any changes to the Implementation Plan unless such proposed changes have been agreed with the Authority’s Representative.

  - In the event that the Contractor proceeds to vary the Implementation Plan following consultation with the Authority pursuant to this paragraph 3 it shall submit a copy of the amended Implementation Plan to the Authority within five Business Days of the agreed amendments being made.

  - The Contractor may access such parts of the Establishments in accordance with the Implementation Plan as to the timing, nature and extent of such access to enable the Contractor properly to execute the Implementation Plan and achieve the Service Commencement Date. Any changes to the timings and nature of such access shall be first agreed with the Authority.

  - The Contractor shall take all necessary steps to ensure that during the Implementation Period there is no disruption to the Authority or its operations unless the Contractor has obtained the Authority’s prior written consent in respect of such disruption.

  - No later than five Business Days prior to the end of each calendar month during the Implementation Phase, the Contractor shall deliver to the Authority a report with:

    - details of progress against the Implementation Key Milestones;

    - whether the Contractor believes that the service provision can begin on the Service Commencement Date; and

    - where any Implementation Key Milestones have not been achieved, details of the tasks to be carried out in order to meet those requirements by the Service Commencement Date and the timescales for such tasks.

  - On receipt of the report issued by the Contractor pursuant to paragraph 3.12 the Authority shall review the report and if necessary, provide comments on the contents of the report including, without limitation, whether it agrees that the Implementation Key Milestones have been achieved and, if not, identify what work the Authority believes is required to achieve compliance with the Implementation Plan and achieve the provision of the Training Services by the Service Commencement Date.

  - If the Contractor has not achieved any or some of the Implementation Plan dates it shall carry out all such actions as may be necessary to meet the remaining Implementation Plan dates and achieve the Service Commencement Date. The Contractor shall keep the Authority updated weekly as to such actions in the same format as the report issued pursuant to paragraph 3.12.

  - If at any time during the Implementation Period the Contractor reasonably believes that it will not achieve the Service Commencement Date it shall immediately provide the Authority with details of the reasons why the Service Commencement Date cannot be achieved, the estimated delay to the Service Commencement Date and details of the remedial actions as the Contractor deems necessary in order to perform its obligations under this Contract. Where any failure to meet the Service Commencement Date is not as a direct result of any act or omission of the Authority, any such remedial actions shall be at the expense of the Contractor and the Contractor shall indemnify the Authority for any losses, claims, costs, demands and liabilities it incurs as a result of the Contractor’s failure to achieve the Service Commencement Date. Where any failure to meet the Service Commencement Date is a direct result of any act or omission of the Authority, then the Authority shall seek to agree in good faith a fair apportionment of the cost of any remedial action. Any dispute relating to such apportionment shall be determined pursuant to Clause 88 (Dispute Resolution Procedure)

  - The Contractor shall at the request of the Authority, provide any and all documentation or information in relation to the tasks being carried out by or on behalf of the Contractor during the Implementation Period including without limitation details of any tasks being carried out to meet the requirements of the Implementation Plan which have yet to be met.

  - Notwithstanding the provisions of this paragraph 3, it remains the responsibility of the Contractor to meet the requirements of this Contract, including without limitation Schedule 2 (Statement of Requirements) and Schedule 5 (Transition Plans) and to achieve the provision of the Training Services by the Service Commencement Date. Save as otherwise provided for in this Contract the Authority shall not accept any liability for any delay or reduction in the standard of the quality of the Training Services arising or claimed to arise as a result of any communication or lack of communication between the Authority and the Contractor made pursuant to this paragraph 3 nor any comment or lack thereof in relation to any progress report submitted or other communication with the Authority during the Implementation Phase.

  - Nothing in this paragraph 3 shall prevent the Authority proposing a change in accordance with Schedule 4 (Change and Change Management) at any time.

  - The Implementation Plan shall include but not be limited to:

    - the implementation team;

    - the Implementation Programme;

    - the Implementation Key Milestones at paragraph 4.2;

    - the management of staff;

    - the management of transition of the Training Services from the Previous Contract to this Contract; and

    - a Resource Management Plan

Implementation Programme

  - The Contractor shall provide, as part of the Implementation Plan, an Implementation Programme which shall allocate times to the activities to be undertaken by the Contractor during the Implementation Phase.

  - The Implementation Programme identifies Implementation Key Milestones critical to the successful transition from the Previous Contract to this Contract. These Implementation Key Milestones are as follows:

| Implementation Milestones | Implementation Date |
| --- | --- |
| Provide Implementation Plan (including Implementation Programme) to the Authority | 5 Business Days after the Effective Date |
| Complete staff communications | Service Commencement Date (SCD) |
| Complete upload of staff competencies into Competency Management System | SCD |
| Complete handover of GFA (in accordance with Part 7 Government Furnished Assets of the Contract) | SCD |
| Achieve ISO 9001:2015 certification (in accordance with clause 79 (Quality Assurance) | Prior to SCD |
| Achieve ISO 14001:2015 certification (in accordance with clause 79 (Quality Assurance) | Prior to SCD |
| Deliver Quality Plan (in accordance with clause 79 (Quality Assurance) | 3 months prior to SCD |

Staff

- Skills Audit

  - Commencing at the Effective Date, the Contractor shall undertake a skills audit of the training staff engaged in the delivery of the Previous Contracts. The results of the skills audit shall be compared to those competencies detailed in Schedule 2 (Statement of Requirements) required in the delivery of this Contract.

  - The Contractor shall use the information obtained through the skills audit to populate its Competency Management System and implement a personnel change programme to cover any training and competency gaps.

- Redundancy Plan

  - The Contractor shall implement any Redundancy Plan in accordance with the Implementation Programme.

- Communications

  - The Contractor shall implement, as part of the Implementation Programme, a series of communications to ensure that all stakeholders are informed in advance of changes that could affect them. Such communications shall consist of presentations, meetings, briefings or one to one interviews, as appropriate to the topic and circumstances.

  - To demonstrate a collaborative working approach, the Parties shall deliver a joint presentation on at least one occasion at each Establishment.

- Contract Handbook

  - The Parties shall work jointly in the production of a contract handbook designed to describe the key features of this Contract and identify nominated points of contact to assist with any queries. The contract handbook shall be made available to all relevant staff engaged in the delivery of the Training Services no later than one month prior to the Service Commencement Date, and to ensure easy access, shall be posted on the Establishment intranets.

Technology

  - The Implementation Programme shall include the installation and testing of technology which the Contractor introduces in addition to the Authority supplied GFA as detailed in Schedule 10 (Authority Obligations) and Schedule 2 (Statement of Requirements).

  - The Contractor shall be responsible for all costs associated with equipment installed by the Contractor.

Quality

- Deliverable Quality Plan

  - In accordance with clause 79 (Quality Assurance), the Contractor shall, 3 months prior to Service Commencement Date, produce the Deliverable Quality Plan and deliver it to the Authority’s Representative.

  - The Contractor shall ensure that the processes identified in the Deliverable Quality Plan are ready for implementation at Service Commencement Date.

  - Six months following the Service Commencement Date, the Contractor shall review the Deliverable Quality Plan and incorporate any necessary changes to reflect the experience of the first six months of delivery of the Training Services.

  - The Contractor shall have due regard to any comments made by the Authority at any time in relation to any Deliverable Quality Plan and shall, to the extent it considers appropriate, take the same into account when, and if, amending the Deliverable Quality Plan. If the Contractor decides not to take such comments into account it shall provide its reasons for so doing in writing to the Authority within 5 BusinessDays.

- ISO Certification

  - In accordance with clause 79 (Quality Assurance), the Contractor is required to achieve certification to BN EN ISO 14001:2015 (Environmental Management Systems) in accordance with table at 4.2.

  - In accordance with clause 79 (Quality Assurance), the Contractor is required to achieve certification to BN EN ISO 9001:2015 (Quality Management Systems) in accordance with table at 4.2.

  - During the Implementation Phase, the Authority shall co-operate with the Contractor in meeting the requirements of the certification.

- Establishment Orders

  - Both Parties recognise that the Contractor’s processes for the delivery of Training Services may require an amendment to the Establishment Orders.

  - These processes shall be identified in the Deliverable Quality Plan. Where the implementation of these processes require an amendment to the Establishment Orders to ensure the compatibility of the Contractor and Authority’s processes, the Authority shall reasonably consider such amendment, and where it agrees amendment is appropriate, proceed to amend the Establishment Orders.

  - The Authority and the Contractor shall cooperate fully in the transition from the processes within the Establishment Orders to those defined in the Deliverable Quality Plan.

- Exit

Exit from this Contract

  - In accordance with clause 69 (Co-operation on Expiry or Termination of Contract), clause 72 (Exit Requirements) and Schedule 16 (TUPE), the Contractor shall co-operate fully with the transfer of responsibility for provision of the Training Services (or any part) from the Contractor to a Follow–On Contractor or to the Authority as so directed by the Authority upon the earlier of the Expiry Date or the Termination Date.

  - To provide for the possibility of a transfer to a Follow-On Contractor on the earlier of the Expiry Date or Termination Date, or the transfer back of responsibility for the Training Services to the Authority throughout the Contract Period, the Contractor shall maintain all necessary records to facilitate such a hand-over.

  - The Contractors Exit Plan shall be provided by the Contractor to the Authority at the Effective Date.

  - The Contractors Exit Plan and the Recompetition Data shall be reviewed, maintained and updated by the Contractor throughout the Contract Period as necessary, and in any event no less frequently than at annual intervals. The Contractor shall provide an updated version of the Contractors Exit Plan and the Recompetition Data to the Authority on each anniversary of the Service Commencement Date (or more frequently as may be requested by the Authority). Revised versions of the Exit Plan and Recompetition Data shall, without limitation, take into account changes to the Public Store Account either planned or in place.

  - The Authority shall review any Contractors Exit Plan submitted to it within ten Business Days of receipt and shall notify the Contractor of any required revisions. Revisions shall be discussed with the Authority and incorporated by the Contractor into the Contractors Exit Plan within ten Business Days of receipt of such required revisions. If the Parties cannot agree on any such revision to the Contractors Exit Plan, the matter shall be escalated through the dispute resolution procedure set out in clause 88 (Dispute Resolution Procedure).

  - At least (i) three months before the Expiry Date, or (ii) within ten Business Days of the Contractor receiving a Termination Notice , the Contractor shall provide to the Authority an up to date Contractors Exit Plan to enable the Contractor to comply with its obligations under this paragraph 8. The provisions of paragraph 8.2 shall apply to any such revisions.

  - The Contractor shall:

    - on request provide the latest version of the Contractors Exit Plan to the Authority or such other person as the Authority may specify;

    - keep complete and up to date and provide to the Authority on demand:

      - any information in the Contractor’s possession or under its control which the Authority requires to produce at the time of a Recompetition; and

      - copies of all relevant documentation, in hard and electronic copy, relevant to the Training Services for the purposes of Recompetition;

    - whenever reasonably requested by the Authority, supply the Recompetition Data and all such information referred to in this paragraph 8 to the Authority both in hard and electronic copy within  Months (or such other period as the Parties acting reasonably may agree) of being requested to do so by the Authority. By entering into this Contract the Contractor acknowledges and agrees that the Recompetition Data and such other information will be transferred to potential participants in any Recompetition and undertakes not to take any steps to prevent or hinder such transfer;

    - upon the earlier of the Expiry Date or Termination Date, assign, transfer or novate in favour of the Authority or a Follow-On Contractor any Necessary Agreements as required by the Authority;

    - cooperate in any arrangements notified to it by the Authority, including but not limited to site visits by representatives of companies, participating in the Recompetition, condition surveys, and performance checks on all GFA used for the purposes of this Contract or to be used in relation to a Replacement Contract;

    - comply with all Legislation and Good Industry Practice relating to staff employed in connection with this Contract whether by the Contractor or someone else, and subject to obtaining appropriate consents in particular in accordance with the Data Protection Act 1998, fully and accurately disclose to the Authority all information relating to staff and other relevant Contractor Employees as may be reasonably requested by the Authority. The Contractor warrants that information supplied pursuant to this paragraph 8.8.f shall be complete and accurate in all respects: and

    - as requested by the Authority and in strict compliance with instructions from the Authority, liaise with any bidders involved in a Recompetition.

  - The Contractor warrants that the Recompetition Data, is in all material respects true, accurate, complete and not misleading.

  - Without prejudice to the provisions of paragraph 8.7 above, or at the end of the Contract Period the Contractor shall have the following duties:

    - as soon as reasonably practicable to vacate the Establishments and deliver to the Authority all relevant keys to the Establishments and shall leave the Establishments  in a clean and orderly condition;

    - to carry out any reasonable instructions of the Authority required to give effect to and comply with this paragraph 8;

    - to provide any information to the Authority in relation to Intellectual Property Rights for the purposes of exercising its rights under clause 49 (Intellectual Property Rights);

    - to comply with the Contractors Exit Plan agreed by the Authority in accordance with this paragraph 8; and

    - as required provide the Authority with the documents and records set out in clause  35 (Contractor’s Records).

Exit Steering Group

  - 12 months prior to the Expiry Date, or upon notice of termination in accordance with clause 65 (Failure of Performance), whichever is the earlier, the Contractor shall hold monthly exit steering group meetings to be attended by the Level 1 Representatives, which shall be responsible for management of the transfer of the Training Services in accordance with the Contractors Exit Plan.

  - The exit steering group meetings shall be chaired by the Level 1 Chairman and held monthly on the 30th of the month, or next Business Day, unless such meeting is convened as a consequence of notice of termination. In such an event, the frequency of the exit steering group meetings shall be determined by the Level 1 Chairman.

Termination Programme

  - The Parties recognise that in the event of Termination Notice in accordance with clause 65 (Failure of Performance), the Contractor shall be required to develop, agree and implement a detailed programme for the transfer of data and information associated with the Training Services, which would otherwise have been provided in accordance with the Exit Requirements and in accordance with clause 69.6 (Co-operation on Expiry or Termination of Contract) (the “Termination Programme”).

  - Should the Level 1 Representatives be unable to agree on the Termination Programme, the matter shall be escalated in accordance with Schedule 3 (Governance and Contract Management).

Data and Information

  - Notwithstanding the provision of TUPE information required by Schedule 16 (TUPE), in accordance with the Exit Requirements and clause 69.6 (Co-operation on Expiry or Termination of Contract), the Contractor shall provide data and information relevant to the provision by the Contractor of Training Services set out below:

    - all information relating to Contractor and Military Instructor SQEP competencies held on whatever Authority mandated software systems are in use for this purpose.;

    - identification of any licence requirements necessary to enable the continuation of the delivery of the Training Services;

    - Contractor operational and maintenance documentation for the Training Equipment, for example, all information contained on the Contractor’s asset management system, which includes the schedule of maintenance and inspection;

    - working with the Authority to produce a status report of the current Training Documentation maintenance and revalidation cycle;

    - status of Civilian Accreditation for all courses contained in Schedule 2 (Statement of Requirements);

    - the current Training Plan;

- General

    - a list of all Sub-Contractors used by the Contractor in performance of this Contract;

    - a copy of any interface agreements;

    - the IPR register;

    - list of GFA;

    - the programme risk register;

    - the Six Monthly Reports;

    - all databases and software procured by the Contractor on behalf of the Authority over the Contract Period;

    - details of the return, retention or destruction of any confidential or other Authority data; and

    - or any other information agreed between the Parties.

  - Where the data and information provided in accordance with paragraph 11.1 is incomplete, the Authority shall, through the exit steering group, the Contractor shall, at the Authority’s request, revise the submission.

  - Should any dispute arise in the provision of data and information in accordance with paragraph 11, the matter shall be escalated in accordance with Schedule 3 (Governance and Contract Management).

Contractor Support beyond Expiry Date or Termination Date

  - In accordance with the provisions of clause 69 (Co-operation on Expiry and Termination), the Contractor shall continue to provide, for a period six months after the Expiry Date or the Termination Date, all reasonable assistance, guidance and information to any Follow-on Contractor or the Authority in order to facilitate a smooth transition of the Training Services.

  - The Contractor shall be paid monthly in arrears its reasonable costs, properly supported by documentary evidence, actually incurred and directly arising from such provision, subject to clause 69 (Co-operation on Expiry and Termination), in accordance with Schedule 13 (Payment Mechanism).

Exit REQUIREMENTS

- Introduction

  - Part 15 of the Contract (Expiry and Termination) sets out the Parties’ rights and obligations in respect of expiry and termination. In particular, clause 69 (Co-Operation on Expiry or Termination of Contract) sets out the rights of the Authority to information, data and access required during the final 12 months or during any period applying to earlier termination. In addition to these provisions, these Exit Requirements shall apply in the final 12 months of the Contract Period (the “Exit Period’).

  - The Contractors Exit Plan shall be based upon the content of this Schedule 5 and compiled in accordance with Schedule 30 (Deliverable Quality Plan). The Contractor’s Exit Plan describes the Contractor’s required support to the seamless transfer of service delivery to the Authority or Follow-On Contractor in the event of expiry of this Contract.

  - These Exit Requirements detail:

    - the key activities to be undertaken by the Contractor upon exit;

    - the relevant management structures; and

    - the transfer and cessation of activities.

  - These Exit Requirements shall be initiated in accordance with the timescales detailed in the Exit Programme at ‎Appendix 1.

  - The Contract Manager, as identified in Schedule 3 (Governance and Contract Management), shall be responsible for the review, maintenance and implementation of the Contractors Exit Plan.

- Termination

  - These Exit Requirements and the Exit Programme are based on expiry of this Contract at the Expiry Date, however if a Termination Notice is issued by the Authority, the activities detailed in these Exit Requirements and the timescales specified within the Exit Programme shall be revised, based on the Termination Date.

  - It shall be the responsibility of the Contract Manager and the Level 1 Chairman to develop, agree and implement a Termination Programme that meets the Termination Date.

- Exit Management

  - Unless notified in writing by the Authority that the Expiry Date shall be extended in accordance with clause 3.3 (Duration), 12 months prior to the Expiry Date, the Contractor shall:

    - appoint an Exit Manager to oversee the successful transition to the Authority or a Follow-on Contractor;

    - initiate the transition events in the Exit Programme, working closely with the Authority; and

    - hold monthly exit steering group meetings.

  - The exit steering group meetings shall be attended by the Level 1 Representatives and chaired by the Level 1 Chairman and shall monitor progress against the Exit Programme. The frequency of the exit steering group meetings can be altered by agreement between the Contract Manager and Level 1 Chairman.

- Communications

  - The Contractor shall implement a clear and comprehensive Exit Communications Plan and process for imparting information to all stakeholders. This Exit Communications Plan shall detail the activities to be undertaken during the Exit Period to the Authority and Contractor Employees.  The Exit Communications Plan shall make clear to all staff engaged in the delivery of the Training Services that, whilst the exit process is a major milestone, day-to-day service delivery operations must continue as normal throughout. The Contractors Exit Plan shall detail the management of the Training Services during this Exit Period to ensure continuity of service delivery.

  - The Exit Communications Plan shall identify both internal and external stakeholders, the communication triggers and the key messages that need to be imparted. The Exit Communications Plan shall also contain the timings for TUPE consultations, the issue of company notices, team briefs, bulletins, presentations, letters, press releases, question and answer sessions and face-to-face meetings. The Exit Communications Plan shall also address the following:

    - informing Contractor Employees individually and collectively via:

      - workforce presentations;

      - team leader meetings;

      - cascading team briefings;

      - regular newsletters; and

      - Authority and Follow-On Contractor representation at Contractor training delivery and support management weekly planning meetings;

    - informing the Authority, and Follow-On Contractor where necessary, individually and collectively via:

      - regular briefings to Authority and Follow-On Contractor;

      - management and governance meetings;

      - Contractor representation at appropriate Authority meetings; and

      - support to the Authority as they seek to inform the wider stakeholder community; and

    - informing and consulting the Trades Unions, as and when appropriate.

- Assets

- Audit of Asset Registers

  - On request  or not less than 11 months before the Expiry Date, the Contractor shall provide the Authority with a list of assets, held on the Contractor’s asset management system and updated in accordance with Schedule 30 Deliverable Quality Plans), to enable the Authority to conduct a preliminary audit of the all the GFA held by the Contractor.

  - Any shortcomings identified by the Authority as a result of this audit shall be addressed by the Contractor in time for the final audit, which shall be conducted by the Authority not less than three months before the Expiry Date.

- Transfer of Assets

  - In accordance with clause 69.5 (Co-operation on Expiry or Termination), during the final 12 months before the Expiry Date, the Contractor shall protect and preserve property in its possession in which the Authority has an interest.

  - On the Expiry Date, the Contractor shall transfer to the Authority the risk or ownership of all assets:

    - provided to the Contractor by the Authority as Issued Property under this Contract; or

    - procured by the Contractor on behalf of the Authority solely for the purposes of delivering the Training Services.

- Documentation

- Training Equipment Documentation

  - The Contractor shall provide to the Authority on request or not less than six months before Expiry Date, a list of the following Training Equipment documentation held by the Contractor for systems and equipment in service on the Expiry Date:

    - operator manuals;

    - maintenance manuals;

    - schedule of items of routine maintenance and inspection held on the Contractor’s equipment maintenance system, together with records of maintenance and inspection that have been undertaken to date, including availability data; and

    - all systems security related information, including accreditation certificates where appropriate.

- Confidential or other Authority Provided Data

  - The exit steering group shall agree upon the return, retention or destruction of any confidential or Authority provided data by the Contractor at the Expiry Date.

- IPR

  - During the Contract Period the Contractor shall update and maintain an IPR register. The IPR register shall be based upon the information provided by the Authority to the Contractor prior to Service Commencement Date and capture all Intellectual Property subsequently used or generated by the Contractor.

  - The IPR register shall also record, where applicable, the terms of any licence granted to the Contractor by the Authority, an Authority Contractor (i.e. Authority supplied Third Party Intellectual Property) or Sub-Contractor to utilise their respective Background Intellectual Property.

  - The Contractor shall provide to the Authority a copy of the information held on the IPR register on request or not less than 11 months before the Expiry Date.

  - Where the Contractor utilises its Background Intellectual Property, this shall also be recorded and, in the event of termination of the Contract (in whole or in part), clause 51.2 of this Contract shall apply to any continued use by or on behalf of the Authority of that Background Intellectual Property.

  - Once the Follow-On Contractor has been confirmed, the Contractor shall work with the Follow-On Contractor to ensure a smooth transition of IPR matter.

- Training Planning Process

  - Recognising the importance of the training planning service in ensuring continuity of training during the transition to a Follow-On Contractor, the Contractor shall cooperate in any Authority led preparation for relet to a Follow on Contractor as soon as possible in the training planning cycle (SOTR/SOTT round) prior to the Expiry Date.

- Personnel

- SQEP

  - The Contractor shall provide to the Authority, on request or not less than six months before the Expiry Date, information relating to Contractor and Military Instructor SQEP competencies engaged in the delivery of the Training Services.

- TUPE

  - Information concerning personnel to whom TUPE may apply shall be provided to the Authority in accordance with Schedule 16 (TUPE).

- Government Furnished Resources

  - Within one month of the Expiry Date the Contractor shall provide a written report on the performance of all GFR to their Authority line manager such that there is continuity of reporting and the individuals are not disadvantaged by the change of service provider.

- Sub-Contractors

  - The term of any Sub-Contract shall not extend beyond the Expiry Date, unless otherwise agreed with the Authority.

  - The Contractor shall provide to the Authority, not less than 11 months before the Expiry Date, a list of suppliers including details of services provided, subject to any third party restrictions on release of commercially sensitive data or confidentiality.

- Interface Agreements

  - The Contractor shall provide to the Authority, not less than 11 months before the Expiry Date, a copy of all interface agreements entered into with other Authority Contractors in accordance with clause 82 (Working with Other Authority Contractors).

- Vacation of the Licensed Premises

  - On the Expiry Date the Contractor shall vacate the Licensed Premises in accordance with the terms of the Schedule 27 (Licence).

  - With the Authority’s consent, the Contractor shall be allowed reasonable access to the Establishment and/or the Licensed Premises in order to carry out winding-down activities in accordance with clause 69.4 (Co-operation on Expiry or Termination).

- Finance

  - Closing accounts shall be produced by the Contractor and submitted in accordance with Schedule 6 (Pricing Mechanism).

  - In the event a Termination Notice is served to the Contractor by the Authority, the Contractor shall submit a claim for costs reasonably and actually incurred in accordance with clause 66 (Break) or Schedule 4 (Change and Change Management) which the Authority shall agree. Any dispute in relation to such costs shall be resolved in accordance with clause 88 (Dispute Resolution).

- Ongoing Contractor Support

  - In accordance with clause 69.2 (Co-operation on Expiry or Termination), for a period of six months after the Expiry Date or Termination, Date the Contractor is required to provide all reasonable assistance, guidance and information to the Follow-On Contractor or the Authority, as the case may be, and shall be paid reasonable costs arising from such provision.

- Continuing Obligations

  - Following the Expiry Date or Termination Date, the obligations of the Contractor and the Authority under certain provisions of the Contract shall continue. Such provisions are detailed at clause 71 (Continuing Obligations).

- Review

  - The Contractors Exit Plan shall be reviewed in accordance Paragraph 8 of this Schedule 5.

- EXIT PROGRAMME

| - Activity | - Action | - Date (+/- Expiry Date) |
| --- | --- | --- |
| - Provide TUPE information required for re-tendering in accordance with Schedule 16 (TUPE) | - Contractor | - -24 months |
| - Appoint Exit Manager | - Contractor & Authority | - -12 months |
| - Implement Contractors Exit Plan and Exit Programme | - Contractor & Authority | - -12 months |
| - Conduct initial steering group meeting | - Contractor | - - 12 months |
| - Produce and implement Exit Communications Plan | - Contractor | - - 11 months |
| - Provide Authority with asset lists | - Contractor | - - 11 months |
| - Conduct preliminary audit on asset list | - Authority | - - 14 months |
| - Provide IPR information held on IPR register | - Contractor | - - 11 months |
| - Provide a list of Sub-Contractors | - Contractor | - - 11 months |
| - Provide a list of interface agreements | - Contractor | - - 11 months |
| - Provide SQEP information for Contractor and Military Instructors held on whatever Authority mandated software systems are in use for this purpose. | - Contractor | - - 10 months |
| - Provide a list of training equipment documentation | - Contractor | - - 6 months |
| - Conduct final audit on asset list | - Authority | - - 3 months |
| - Transfer Issued Property | - Contractor & Authority | - Expiry Date |
| - Vacate premises | - Contractor | - Expiry Date |
| - Complete all Sub-Contracts | - Contractor | - Expiry Date |
| - Return, retain or destroy confidential or other Authority data as agreed (including training equipment documentation). | - Contractor | - Expiry Date |
| - Provide closing accounts | - Contractor | - In accordance with Schedule 6 (Pricing Mechanism) |
| - Ongoing Contractor support | - Contract | - + 6 months in accordance with clause 69.2 |

- Notes:

- Timings may be reviewed once the actual exit process is underway and adjusted to suit the circumstances.