## Timeline & Fee Drawdown
Britten Pears Arts
| ACOUSTICS CONSULTANT (CH1, CH3, BP1, AC1) | [16 empty] | Workstream key: |  |  | Concert Hall (CH1) | [10 empty] | Concert Hall FOH (CH3)
| RESOURCE SUMMARY AND PRICING SCHEDULE | [19 empty] | Britten Pears Building (BP1) | [10 empty] | Accommodation (AC1)
|  |  |  | 2021 |  |  |  |  | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027 | [11 empty] | 2028 | [11 empty] | Total
|  |  |  | M | A | M | J | J | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
| Task |  | Duration
SINGLE CONTRACT TRADITIONAL PROCUREMENT
Stage 0 - Strategic Definition and Stage 1 - Preparation and Brief
Stage 2 - Concept Design
Stage 3 - Developed Design
Stage 4 - Technical Design
Tender Period / Evaluation / Appointment
Stage 5 - Mobilisation
Stage 5 - Construction
Stage 6 - Handover and Closeout
Stage 7 - In Use (Rectification Period)
| AVERAGE DAYS PER MONTH |  |  | 2024 J: 2024; 2025 J: 2025; 2026 J: 2026; 2027 J: 2027; 2028 J: 2028 | Total
|  |  |  | M | A | M | J | J | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
| Name | Role
#REF! | A | X | [6 empty] | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [19 empty] | 41
| B | Y | [6 empty] | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [19 empty] | 42
#REF! | C | Z | [6 empty] | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [19 empty] | 43
0
| TOTAL DAYS PER MONTH |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126
FEE DRAWDOWN PER MONTH
|  |  |  | 2024 J: 2024; 2025 J: 2025; 2026 J: 2026; 2027 J: 2027; 2028 J: 2028 | Total
|  |  |  | M | A | M | J | J | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
| Resource | Year | Rate
| A | 2024 | 100 | M: 0; A: 0; M: 0; J: 0; J: 0; 2024 J: 200; 2024 F: 100; 2024 M: 100; 2024 A: 100; 2024 M: 100; 2024 J: 100; 2024 J: 100; 2024 A: 100; 2024 S: 100; 2024 O: 100; 2024 N: 100; 2024 D: 0; 2028 A: 0; 2028 M: 0; 2028 J: 0; 2028 J: 0; 2028 A: 0; 2028 S: 0; 2028 O: 0; 2028 N: 0; 2028 D: 0 | 1200
|  | 2025 | 100 | 2025 J: 100; 2025 F: 100; 2025 M: 100; 2025 A: 100; 2025 M: 100; 2025 J: 100; 2025 J: 100; 2025 A: 100; 2025 S: 100; 2025 O: 100; 2025 N: 100; 2025 D: 100; 2028 A: #VALUE!; 2028 M: #VALUE!; 2028 J: #VALUE!; 2028 J: #VALUE!; 2028 A: #VALUE!; 2028 S: #VALUE!; 2028 O: #VALUE!; 2028 N: #VALUE!; 2028 D: #VALUE! | 1200
|  | 2026 | 100 | 2026 J: 100; 2026 F: 100; 2026 M: 100; 2026 A: 100; 2026 M: 100; 2026 J: 100; 2026 J: 100; 2026 A: 100; 2026 S: 100; 2026 O: 100; 2026 N: 100; 2026 D: 100 | 1200
|  | 2027 | 100 | 2027 J: 100; 2027 F: 100; 2027 M: 100; 2027 A: 100; 2027 M: 100; 2027 J: 0; 2027 J: 0 | 500
| B | 2024 | 100 | M: 0; A: 0; M: 0; J: 0; J: 0; 2024 J: 300; 2024 F: 100; 2024 M: 100; 2024 A: 100; 2024 M: 100; 2024 J: 100; 2024 J: 100; 2024 A: 100; 2024 S: 100; 2024 O: 100; 2024 N: 100; 2024 D: 0; 2028 A: 0; 2028 M: 0; 2028 J: 0; 2028 J: 0; 2028 A: 0; 2028 S: 0; 2028 O: 0; 2028 N: 0; 2028 D: 0 | 1300
|  | 2025 | 100 | M: 0; A: 0; M: 0; J: 0; J: 0; 2025 J: 100; 2025 F: 100; 2025 M: 100; 2025 A: 100; 2025 M: 100; 2025 J: 100; 2025 J: 100; 2025 A: 100; 2025 S: 100; 2025 O: 100; 2025 N: 100; 2025 D: 100; 2028 A: 0; 2028 M: 0; 2028 J: 0; 2028 J: 0; 2028 A: 0; 2028 S: 0; 2028 O: 0; 2028 N: 0; 2028 D: 0 | 1200
|  | 2026 | 100 | 2026 J: 100; 2026 F: 100; 2026 M: 100; 2026 A: 100; 2026 M: 100; 2026 J: 100; 2026 J: 100; 2026 A: 100; 2026 S: 100; 2026 O: 100; 2026 N: 100; 2026 D: 100 | 1200
|  | 2027 | 100 | 2027 J: 100; 2027 F: 100; 2027 M: 100; 2027 A: 100; 2027 M: 100; 2027 J: 0; 2027 J: 0 | 500
| C | 2024 | 100 | M: 0; A: 0; M: 0; J: 0; J: 0; 2024 J: 400; 2024 F: 100; 2024 M: 100; 2024 A: 100; 2024 M: 100; 2024 J: 100; 2024 J: 100; 2024 A: 100; 2024 S: 100; 2024 O: 100; 2024 N: 100; 2024 D: 0; 2028 A: 0; 2028 M: 0; 2028 J: 0; 2028 J: 0; 2028 A: 0; 2028 S: 0; 2028 O: 0; 2028 N: 0; 2028 D: 0 | 1400
|  | 2025 | 100 | M: 0; A: 0; M: 0; J: 0; J: 0; 2025 J: 100; 2025 F: 100; 2025 M: 100; 2025 A: 100; 2025 M: 100; 2025 J: 100; 2025 J: 100; 2025 A: 100; 2025 S: 100; 2025 O: 100; 2025 N: 100; 2025 D: 100; 2028 A: 0; 2028 M: 0; 2028 J: 0; 2028 J: 0; 2028 A: 0; 2028 S: 0; 2028 O: 0; 2028 N: 0; 2028 D: 0 | 1200
|  | 2026 | 100 | 2026 J: 100; 2026 F: 100; 2026 M: 100; 2026 A: 100; 2026 M: 100; 2026 J: 100; 2026 J: 100; 2026 A: 100; 2026 S: 100; 2026 O: 100; 2026 N: 100; 2026 D: 100 | 1200
|  | 2027 | 100 | 2027 J: 100; 2027 F: 100; 2027 M: 100; 2027 A: 100; 2027 M: 100; 2027 J: 0; 2027 J: 0 | 500
| Travel & Disbursements |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0
|  |  | Fee £ | 0 | 0 | 0 | 0 | 0 | 900 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 0 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 12600
#REF!
32000000
#REF!
2

## Resource Summary
RESOURCE SCHEDULE
ACOUSTICS CONSULTANT (CH1, CH3, BP1, AC1)
Notes:
1. Please insert the number of days per RIBA stage and per workstream.
2. Please adapt rows for resources if required.
3. Please only adapt fields left in white.
Concert Hall (CH1)
Resource Level | Resource Name | Resource Dayrate | RIBA STAGE
|  |  | Preparation |  | Design | [5 empty] | Construction |  | Handover & Close out |  | Use |  | TOTAL
|  |  | 0-1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7
|  |  | Days | Cost | Days | Cost | Days | Cost | Days | Cost | Days | Cost | Days | Cost | Days | Cost | Total Days Per Resource Head | % | Total Cost Per Resource Head | %
Director |  | 100 | 1 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100% | 100 | 100%
Associate |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0%
Senior Professional |  | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0%
Project Professional |  | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0%
| Total No.of Days per RIBA stage |  | 1 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100% | 100 | 100%
[13 empty] | Total Days |  |  |  | 1
[13 empty] | Total Cost |  |  |  | 100
Britten Pears Building (BP1)
Resource Level | Resource Name | Resource Dayrate | RIBA STAGE
|  |  | Preparation |  | Design | [5 empty] | Construction |  | Handover & Close out |  | Use |  | TOTAL
|  |  | 0-1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 1 - 6
|  |  | Days | Cost | Days | Cost | Days | Cost | Days | Cost | Days | Cost | Days | Cost | Days | Cost | Total Days Per Resource Head | % | Total Cost Per Resource Head | %
Director |  | 300 | 1 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100% | 300 | 100%
Associate |  | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0%
Senior Professional |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0%
Project Professional |  | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0%
| Total No.of Days per RIBA stage |  | 1 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100% | 300 | 100%
[13 empty] | Total Days |  |  |  | 1
[13 empty] | Total Cost |  |  |  | 300
Concert Hall FOH (CH3)
Resource Level | Resource Name | Resource Dayrate | RIBA STAGE
|  |  | Preparation |  | Design | [5 empty] | Construction |  | Handover & Close out |  | Use |  | TOTAL
|  |  | 0-1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 1 - 6
|  |  | Days | Cost | Days | Cost | Days | Cost | Days | Cost | Days | Cost | Days | Cost | Days | Cost | Total Days Per Resource Head | % | Total Cost Per Resource Head | %
Director |  | 100 | 1 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100% | 100 | 100%
Associate |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0%
Senior Professional |  | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0%
Project Professional |  | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0%
| Total No.of Days per RIBA stage |  | 1 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100% | 100 | 100%
[13 empty] | Total Days |  |  |  | 1
[13 empty] | Total Cost |  |  |  | 100
Accommodation (AC1)
Resource Level | Resource Name | Resource Dayrate | RIBA STAGE
|  |  | Preparation |  | Design | [5 empty] | Construction |  | Handover & Close out |  | Use |  | TOTAL
|  |  | 0-1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 1 - 6
|  |  | Days | Cost | Days | Cost | Days | Cost | Days | Cost | Days | Cost | Days | Cost | Days | Cost | Total Days Per Resource Head | % | Total Cost Per Resource Head | %
Director |  | 100 | 1 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100% | 100 | 100%
Associate |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0%
Senior Professional |  | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0%
Project Professional |  | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0%
| Total No.of Days per RIBA stage |  | 1 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100% | 100 | 100%
[13 empty] | Total Days |  |  |  | 1
[13 empty] | Total Cost |  |  |  | 100

## Fee Summary
|  | Concert Hall (CH1) |  |  | BPA Building (BP1) |  |  | Concert Hall FOH (CH3) |  |  | Accommodation (AC1) |  | TOTAL
| Construction Cost | 1597000 |  | Construction Cost | 2062000 |  | Construction Cost | 546000 |  | Construction Cost | 720000 |  | 4925000
| Fee % | 0.006262% |  | Fee % | 0.01455% |  | Fee % | 0.01832% |  | Fee % | 0.01389% |  | 0.01218%
| Total | 100 |  | Total | 300 |  | Total | 100 |  | Total | 100 |  | 600
Gateway | % |  |  | % |  |  | % |  |  | %
RIBA 0&1 | 100% |  | 100 | 100% |  | 300 | 100% |  | 100 | 100% |  | 100 | 600
RIBA 2 | 0% |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% |  | 0 | 0
RIBA 3 | 0% |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% |  | 0 | 0
RIBA 4 & Procurement | 0% |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% |  | 0 | 0
RIBA 5 | 0% |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% |  | 0 | 0
RIBA 6 | 0% |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% |  | 0 | 0
RIBA 7 | 0% |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% |  | 0 | 0
Totals | 100% |  | 100 | 100% |  | 300 | 100% |  | 100 | 100% |  | 100 | 600