# Annex A

| Title of project: | Optimisation of benthic image analysis approaches |
| --- | --- |
| Date and time for return of tenders: | Monday 26 November 2018@ 16:00 hours |
| Contract Reference No: | C18-0355-1281 |
| Address for tender submission: | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk or PLEASE DO NOT SEND TENDERS DIRECTLY TO HENK VAN REIN, HAYLEY HINCHEN OR DORA IANTOSCA VIA THEIR PERSONAL EMAIL ADDRESSES, AS THIS WILL INVALIDATE YOUR TENDER Tender responses must be less than 10 MB in size. On receipt of your tender, you will receive an automated e-mail to confirm receipt by JNCC Support Co. If you do not receive this automated email, please contact, in the following order: Sue Wenlock (00 44 1733 866880) Chris Downes (00 44 1733 866877) |
| Contacts for technical information relating to this project specification: | Henk van Rein Marine Monitoring and Evidence Team Joint Nature Conservation Committee Email: henk.vanrein@jncc.gov.uk Tel: +44 (0)1733 866 904 Hayley Hinchen Marine Monitoring and Evidence Team Joint Nature Conservation Committee Email: hayley.hinchen@jncc.gov.uk Tel: +44 (0)1733 866 925 |
| Contact for any queries regarding the tendering procedure: | Dora Iantosca Finance Team Joint Nature Conservation Committee Email: Dora.Iantosca@jncc.gov.uk Tel: 01733 866894 |
| Proposed start-date: | 3 December 2018 |
| Proposed end-date: | 8 March 2019 |

Title of Project

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Aims	3

3.	Project Background	3

4.	Project Objectives	5

5.	Project Objectives: Detailed tasks	5

6.	Outputs	12

7.	Dissemination	12

8.	Timescale	12

9.	Health and safety	13

10.	Product specification	13

11.	Project management	13

12.	Instructions for tender submission	14

13.	Evaluation Criteria	15

14.	Payment	16

15.	Additional Contractor requirements	16

16.	References	16

17.	Appendix A – Example of summary data extraction table	18

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation. Its work contributes to maintaining and enriching biological diversity, conserving geological features and sustaining natural systems.

Our role is to provide evidence, information and advice so that decisions are made that protect natural resources and systems. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on the JNCC intranet: http://jncc.defra.gov.uk/page-1729

## Project Aims

To recommend the optimum non-automated, data extraction approach for benthic imagery acquired from marine benthic habitats by drop-down camera systems.

## Project Background

  - UK Marine Biodiversity Monitoring R&D Programme

There are multiple policy drivers for marine biodiversity monitoring within the UK, including the EU Marine Strategy Framework Directive (2008), the EU Habitats Directive (1992) and the EU Birds Directive (1979 amended 2009). The key elements of these directives have been enshrined in national legislation such as the Conservation (Natural Habitats, &c) Regulations (Northern Ireland) 1995, UK Marine and Coastal Access Act 2009, the Marine (Scotland) Act 2010, the Marine Act (Northern Ireland) 2013, The Conservation of Habitats and Species Regulations 2017 and the Conservation of Offshore Marine Habitats and Species Regulations 2017. All of these drivers have individual requirements for assessment and reporting which cover varying geographical scales and different aspects of biodiversity (Hinchen, 2014).

To meet these requirements, the UK Marine Biodiversity Monitoring Programme (hereafter referred to as ‘the UK MBMP’) was established by the UK Marine Monitoring and Assessment Strategy (UKMMAS) to provide a coordinated and integrated approach to monitoring UK marine biodiversity, both in protected sites and the wider environment. JNCC is leading on a number of the elements of this Programme, including benthic habitat monitoring of offshore marine habitats (> 12 nm offshore). The UK MBMP aims to improve the quality of evidence on the state of marine biodiversity and to focus research into whether and how the biodiversity elements are changing in response to both natural and human induced pressures. The Programme will support the Defra 25 Year Environment Plan: to enable the UK to design a world-class, cost-effective marine monitoring system, to meet the full range of legislative and policy requirements in an integrated fashion upon exit from the EU.

  - Benthic habitat monitoring using imagery

Benthic imagery, in the form of still images and video, is collected across a range of depths and from a variety of sampling platforms, including SCUBA divers, drop-down cameras, camera sledges, remotely operated vehicles (ROVs) and autonomous underwater vehicles (AUVs). Still images (‘stills’) are considered the most suitable sample type used to represent the seabed communities present on consolidated and sensitive substrata, such as rocky reefs, biogenic reefs and seagrass beds. Owing, in part, to the wide variety of applications, however, it has proven difficult to standardise the collection and interpretation of benthic imagery (stills and video) for marine monitoring programmes.

The Epibiota Sub-group of the North-East Atlantic Marine Biological Analytical Quality Control Scheme (NMBAQC), led by JNCC, have started to tackle these issues. The ‘Operational Guidelines’ (Hitchin et al., 2015) summarise imagery acquisition approaches for stills and video and recommend those considered as best practice across the UK. The ‘Interpretation Guidelines’ (Turner et al., 2016) follow on from this work but focus on the analysis of the imagery, i.e. what to do with the imagery once it’s collected. Imagery analysis approaches are summarised and those considered best practice are recommended, such as the need to assess image quality, determine the field of view, improve taxonomic identification standards and develop image reference collections (Turner et al., 2016).

The NMBAQC ‘Interpretation Guidelines’ also discuss approaches for enumerating taxa from benthic imagery, recommending data extraction methods that are quantitative, simple to conduct and less affected by the subjectivity of observers (Turner et al., 2016). However, many choices of data extraction method remain with no agreement on any single approach being more suitable than the others. Method comparison studies agree that monitoring methods must provide data that are accurate, precise and statistically robust to better detect changes over time, while also being efficient to collect and cost-effective to use in a monitoring programme (Drummond and Connell, 2005; Beaumont et al., 2007; van Rein et al., 2011; van Rein et al., 2012). Others add that inter-observer variability needs to be reduced so that patterns in the monitoring data better reflect community changes and not differences in the opinion of observers (Benedetti-Cecchi et al., 1996; Ninio

et al., 2003; Moore et al., 2015; Durden et al., 2016). Clearly, a significant amount of research and development work is needed to ensure that optimum approaches to data extraction from imagery, that account for inter-observer variability, are recommended for marine benthic monitoring programmes.

  - Developing optimum data extraction approaches for benthic imagery

This contract aims to further understand how the most commonly used data extraction methods for stills imagery perform when compared against each other. Rather, the data they generate will be analysed and compared using several metrics useful to monitoring programmes, such data precision, power, efficiency and inter-observer variability. Conclusions from these analyses will be used to recommend the optimum approach(es). This work will feed into the recommendations of NMBAQC and progress the efforts of the UK MBMP, ultimately progressing the development of a world-class, cost effective marine monitoring system in the UK.

## Project Objectives

The successful contractor is required to deliver on all of the following objectives:

| Objective | Objective overview | Objective output |
| --- | --- | --- |
| 1 | Extract biological community data from a set of benthic images using different data extraction methods and different observers. | - Biological community data for 100 sample images extracted by Observer 1 using six data extraction methods (Task 1.1); - Biological community data for 20 sample images extracted by Observers 2, 3, 4, 5 and 6 using six data extraction methods (Task 1.2). |
| 2 | Analyse biological community data and calculate metrics to compare data extraction methods and assess inter-observer effects. | - Summary tables to show comparison metrics from each data extraction method and observer (Task 2.1); - Results of metric comparison to indicate data extraction method precision, power, efficiency, taxonomic richness, taxonomic accumulation, community impression and consistency between observers (Task 2.2). |
| 3 | Write a report to summarise results and collate recommendations. | - Final report to summarise findings of study (Task 3.1). |

## Project Objectives: Detailed tasks

The specific tasks required to fulfil each objective are outlined below. The tender submissions must provide a description of how the tasks will be delivered and propose any additional aspects which may be necessary to meet the objectives. Sufficient time and resources (including financial) should include requesting and collating relevant information from suitable organisations; tenderers should specify which information they intend to consider and where they intend to source such information from. Tenderers should also include a detailed project plan and timeline for the delivery of each task under each objective.

Definitions:

Sample image – the still image ‘sample’ that has been collected by a drop-down camera system from the seabed.

Data extraction method – the method by which biological community data are extracted from the sample image. These are sometimes also referred to as ‘image analysis methods’ or ‘image annotation methods’, but in this contract specification they are termed data extraction methods.

  - Objective 1

| Objective | Objective overview | Objective output |
| --- | --- | --- |
| 1 | Extract biological community data from a set of benthic images using different data extraction methods and different observers. | - Biological community data for 100 sample images extracted by Observer 1 using six data extraction methods (Task 1.1); - Biological community data for 20 sample images extracted by Observers 2, 3, 4, 5 and 6 using six data extraction methods (Task 1.2). |

Task 1.1: Extract biological community data from 100 sample images using a single experienced senior analyst (Observer 1).

- JNCC will supply 100 sample images for this contract. They will be from a rocky reef habitat deeper than the photic zone in which bedrock and stony reef communities can be expected. The sample images will have fields of view ranging from 0.3 – 1.0 m2 and will be of ‘good’ or ‘excellent’ image quality.

- The primary image analyst, Observer 1, must have excellent taxonomic identification skills, especially in identifying epifauna from benthic imagery, and over 10 years’ experience extracting data from benthic imagery (i.e. considered a senior analyst).

- Biological community data must be extracted from the sample images in a random order and using a random data extraction method order. The six data extraction methods proposed in Table 1 must be used, although the contractor may wish to add additional methods if they have a strong evidence to do so. Any proposals for additional extraction methods and  evidence must be stated in the tender as well as the costs of using any additional methods. They must be costed up separately to the original methods in Table 1 so that JNCC can decide if resources and budget allow for their inclusion in the contract.

Table 1. Data extraction methods proposed for this study.

| Data extraction method | Brief description of method |
| --- | --- |
| Percentage cover | An estimate of the approximate spatial coverage relative to the total area of a sample image that all organisms of the same taxonomic classification occupy, expressed as a percentage value. This measure normally applies to colonial organisms, such as sponges and encrusting organisms, however, there are many exceptions. For consistency of approach, the contractor should follow the NMBAQC guidelines to estimate this measure (see section 4.1 and Annex 4 by Turner et al., 2016, for guidance). |
| Abundance count | The estimated number of individuals of the same taxonomic classification within the total area of a sample image. Usually this measure applies to solitary organisms, such as anemones, solitary hydroids or mobile fauna, however there are also exceptions to this rule. For consistency of approach, the contractor should follow the NMBAQC guidelines to estimate this measure (see section 4.1 and Annex 4 by Turner et al., 20163, for guidance). |
| The SACFOR (Super-abundant, Abundant, Common, Frequent, Occasional, Rare) scale | This is a semi-quantitative measure used to estimate the relative occurrence of all organisms of the same taxonomic classification within a sample image. For consistency of approach, the contractor should also follow the NMBAQC guidelines to estimate this measure (see section 4.1 and Annex 4 by Turner et al., 20163, for guidance). |
| Point intercept | An estimate of the benthic community made using 100 points systematically (i.e. in a 10 x 10 grid) distributed across the sample image. The observer must only record the taxon that are directly present under each point in the sample image. As the results are scored as occurrence out of 100, each occurrence under a point may be recorded as 1%. The contractor must ensure that all point intercept data are recorded in such a way that the data from each point may be checked at a later date. |
| Frequency of occurrence | As estimate of the benthic community made by dividing the sample image up into equal areas and recording the presence of any unique taxa within each of the equal areas. For example, the image may be divided into 100 cells of equal area (10 x 10 grid) or 25 cells of equal area (5 x 5 grid). In the 100-cell grid, each occurrence of a taxon may be recorded as representing 1% while in the 25-cell grid, each occurrence may be recorded as representing 4%. Note that using the frequency of occurrence measure, the same individual may be recorded more than once. For instance, if a solitary individual occurs in the corner of where four adjacent cells meet that individual will be recorded as occurring 4 times. In this study, two frequency of occurrence methods are proposed: - Frequency of occurrence 25 cell grid (5 x 5 grid); - Frequency of occurrence 100 cell grid (10 x 10 grid); |

- Observer 1 must record the following data fields when using each of the six data extraction methods:

  - Data extraction method;

  - Observer experience level – either ‘Senior’ or ‘Junior’;

  - Observer initials;

  - Sample image number (as stated above, samples should be analysed in a random order);

  - Taxon – all unique taxa must be identified in each sample image to the lowest taxonomic unit that the observer is confident using. Note that there will be some data extraction methods that do not apply to the identification of some taxa. For example, many colonial taxa are not enumerated using abundance counts and percentage cover is not estimated for many solitary individuals. Therefore, there will be some gaps in the data extracted by the methods: these should be recorded as ‘NA’;

  - Measurement – the value of measurement or score that is the recorded, e.g. if ten individuals occur in the image their abundance is ‘10’, % cover may be ‘NA’, SACFOR score may be ‘O’. This will change depending on the type of data extraction method;

  - Time taken – this is the time in minutes and seconds (can be rounded to the nearest 10 seconds) for the observer to extract all the data from each sample image using one data extraction method.

- The data extracted in Task 1.1. must be summarised into a data table. An example of a suitable table is provided in Appendix A of this specification. The contractor may prefer to organise the data in a different way: if so they should discuss this with the contract manager they must approve this

Task 1.2: Extract biological community data from 20 sample images using senior and junior analysts.

- Secondary observers (Observers 2, 3, 4, 5 and 6) must repeat Task 1.1 except they will only extract data from a selection of 20 images from the original set of 100 images. They must all work from this same selection of 20 sample images (i.e. data must be extracted from the same images) so that the data are comparable afterwards.

- Observers 2 and 3 must be considered of a significantly higher experience level (i.e. senior analysts) than Observers 4, 5 and 6, who must be considered as having a lower experience level (i.e. junior analysts).

  - Objective 2

| Objective | Objective overview | Objective output |
| --- | --- | --- |
| 2 | Analyse biological community data and calculate metrics to compare data extraction methods and assess inter-observer effects. | - Summary tables to show comparison metrics from each data extraction method and observer (Task 2.1); - Results of metric comparison to indicate data extraction method precision, power, efficiency, taxonomic richness, taxonomic accumulation, community impression and consistency between observers (Task 2.2). |

- The design for the analysis allows for comparison of the data extracted by the data extraction methods as well as an assessment of inter-observer effects (Figure 1). The contractor may propose an alternative design in the tender, which if accepted, may be discussed in the start-up meeting.

Figure 1. Experimental design for analysis of data from different data extracted extraction methods. Experimental factors are shown to the left-hand border and levels across the figure. Note all levels must be repeated for each data extraction method (not shown here).

Task 2.1: Calculate the data extraction methods’ comparison metrics.

- The contractor must use all the data extracted from the imagery (using the six methods and six observers) to calculate metrics to aid comparison of the methods. The contractor must describe the methods/approach they will use to calculate these metrics in their tender.

- The data comparison metrics in Table 2 must be calculated, although the contractor can propose additional ones if they are suitable (any proposals for these must be included in the tender):

Table 2. Metrics to be used to compare the data from the different extraction methods.

| Comparison metric | Brief description of metric |
| --- | --- |
| Precision | Relates to the variation between the data extracted from different sample images and hints to the consistency of a sampling approach. For example, data collected with a high precision achieve similar results consistently between samples and analysts, and are therefore able to detect changes in marine benthic communities with greater reliability than data collected with low precision. |
| Sampling power | Relates to the number of samples required to detect meaningful change over time. Comparison of this metric will show which approaches require the least number of samples to detect a certain amount of change and will, therefore, be more cost-effective in a monitoring programme. |
| Efficiency | Relates to the time taken to extract data from each sample image by each data extraction approach. Approaches requiring the least amount of time per sample image will be more efficient and cost-effective than those that take more time. |
| Taxonomic richness | Relates to the number of positively identified taxa in each image. |
| Taxonomic accumulation | Relates to the cumulative number of positively identified taxa using the image data extraction approach. It assumes taxa are identified to their lowest possible classification, i.e. ideally species level. Comparison of this metric allows selection of data extraction approaches that record the highest numbers of positively identified taxa, and are therefore most able to represent the community present on the seabed. |
| Community impression | Relates to the ‘impression’ or expression of the actual community in the extracted data. Bearing in mind that all sampling aims to get a representation of the actual community, each annotation approach will create a slightly different version of the community based on its principles of data extraction. Comparison of these impressions will reveal which data extraction approaches generate the most ‘accurate’ impressions of the sampled community. |
| Consistency | In this context consistency relates to the variability of data between different analysts. A data extraction approach that has a high level of consistency indicates that the data collected by different analysts are more similar and, therefore, are more likely to allow detection of meaningful change in the data over time i.e. not just differences between analysts. |

Task 2.2. Carry out data analysis and comparison of metrics.

- The contractor must conduct a series of analyses using the data extracted by the methods and different observers. In the first set of analyses, only the data from Observer 1 will be used (six data extraction methods; 100 replicates of each method; N = 600). Results from this analysis will represent an Experienced Individual Analyst and aim to explore the costs and benefits of the data extraction methods when used by highly skilled image analysts.

- In the second set of analyses, data from all six observers must be used (six data extraction methods; six observers (three senior/three junior); 20 replicates of each method; N = 720). Note that only 20 sample images are used from the 100 available for Observer 1. These 20 sample images are common between all six observers.

- The results of the second set of analyses must be grouped in three ways to explore an inter-observer effects as well as the effect of the experience level of those observers. The first group will represent All Analysts (Observers 1, 2, 3, 4, 5, 6), the second ‘Senior Analysts’ (Observers 1, 2 and 3) and ‘Junior Analysts’ (Observers 4, 5 and 6). Each group of results will still aim to explore the costs and benefits of the data extraction methods, but will be more focused on those effects within the three groups.

- The contractor must answer the following questions using the results from all analyses separately. These responses must be reported as ‘Experienced Individual Analyst’, ‘All Analysts’, ‘Senior Analysts’ and ‘Junior Analysts’:

- Which of the data extraction methods is the most precise?

- Which of the data extraction methods requires the least number of samples to detect a 20% change in community data with a power of 0.8 (the exact metric for the power analysis may be decided after the contract is awarded, although it is likely to be ‘taxonomic richness’)?

- Which of the data extraction methods is the most efficient, i.e. takes the least time on average to process a single image?

- Which of the data extraction methods record the greatest taxonomic richness?

- Which of the data extraction methods has the highest consistency between observers (applies to ‘All Analysts’, ‘Senior Analysts’ and ‘Junior Analysts’ only)?

- The contractor must also explore and describe the differences in data extracted by different methods and by different observers, especially any differences in ‘community impression’ and ‘taxonomic accumulation.’ The contractor should propose methods for comparison of the data and description of the results for this task, and describe them in the tender.

- For example, potential analyses include carrying out ANOVAs, plotting metrics on different graphs or producing similarity matrices (e.g. Bray-Curtis) to run cluster analyses, nMDS plots and ANOSIMs/PERMANOVAs.

  - Objective 3

| Objective | Objective overview | Objective output |
| --- | --- | --- |
| 3 | Write a report to summarise results and collate recommendations. | - Final report to summarise findings of study (Task 3.1). |

Task 3.1. Write a report to summarise results and collate recommendations.

- The contractor must produce a short report (~10-15 pages) summarising this study. It should include the following:

- A brief executive summary of the study;

- A brief introduction to the study;

- The particulars of the methods, including a description of data extraction measures, comparison metrics and data analysis approach;

- Key results presented in figures, tables and summaries as appropriate (these may be annexed if appropriate);

- Any conclusions and recommendations arising from the study.

- If the contract manager decides the report is not at the desired standard, the contractor will be required to make the necessary amendments until this standard is reached.

## Outputs

The following outputs are expected from this contract:

| Objectives | Output |
| --- | --- |
| 1 | - Biological community data sheet for 100 sample images extracted by Observer 1 using six data extraction methods (Task 1.1); - Biological community data sheet for 20 sample images extracted by Observers 2, 3, 4, 5 and 6 using six data extraction methods (Task 1.2). |
| 2 | - Summary tables to show comparison metrics from each data extraction method and observer (Task 2.1); - Results of metric comparison to indicate data extraction method precision, power, efficiency, taxonomic richness, taxonomic accumulation, community impression and consistency between observers (Task 2.2). - All files relating to the analysis of the data (e.g. PRIMER files, R script, Excel spreadsheets etc). |
| 3 | - Final report to summarise findings of study (Task 3.1). |

## Dissemination

The brief summary report produced under this contract will be a JNCC product and shall not be published or disseminated without the written permission of JNCC. It may at some point be published on the JNCC website and all material supplied as part of this contract shall remain copyright of JNCC.

## Timescale

Provisional dates for delivery of the contact outputs are set out below. Exact dates are to be agreed at start-up meeting based on Contractor and JNCC staff availability.

| Milestones | Provisional dates |
| --- | --- |
| Start-up meeting (UK) | As soon as contract is awarded (possibly 3-10 December) |
| Completion of all data extraction (Objective 1) | 1 February 2019 |
| Completion of data analysis (Objective 2) | 22 February 2019 |
| Submission of all final report and all contract outputs (Objective 3) | 8 March 2019 |

## Health and safety

The Contractor is expected to follow appropriate Health & Safety procedures and undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by JNCC H&S advisor)

Any incidents occurring within the contract should be immediately reported to JNCC.

## Product specification

The final report must adhere to the JNCC report template and house style guidance unless stated otherwise. The draft and final reports should be provided electronically via email both as a Microsoft Word document and an Adobe PDF. The JNCC report template will be provided to the successful contractor.

## Project management

The Contractor shall nominate a project manager, who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Henk van Rein

Marine Monitoring and Evidence Manager

Marine Monitoring and Evidence Team

Joint Nature Conservation Committee

Monkstone House

City Road

Peterborough

PE1 1JY

Email: henk.vanrein@jncc.gov.uk

Tel: +44 (0)1733 866 904

Hayley Hinchen

Marine Monitoring and Evidence Manager

Marine Monitoring and Evidence Team

Joint Nature Conservation Committee

Monkstone House

City Road

Peterborough

PE1 1JY

Email:  hayley.hinchen@jncc.gov.uk

Tel: +44 (0)1733 866 925

## Instructions for tender submission

The tender submission should include the following:

A brief summary of the potential Contractor’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract (and delivering the detailed tasks identified within each objective). This should be sufficiently detailed allow assessment against the evaluation criteria (Section 14);

A detailed project plan (including Gantt chart), including the proposed work programme and an estimate of time required to achieve each objective;

A draft Table of Contents for the final report;

Details of Quality Control procedures to be followed;

Details of the Contractor’s own internal Quality Management System;

Details of the Project Team, including their roles and experience, an estimate of their time input into each task, and CVs of all personnel involved in the contract;

Availability of the Project Team for a start-up meeting in Peterborough during the week 10-14 December.

Overall quote for the contract, to include:

  - Daily rates for all members of the Project Team;

  - Rates for attending start-up, interim and final meetings in Peterborough or Aberdeen (costs for travel and accommodation are attached and should be used. These rates are analogous to the civil service rates);

  - Costs and time allocation should be clearly allocated to specific tasks within this contract; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and to provide their company’s VAT registration number.

The following documentation:

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates; and

  - Copies of any appropriate risk assessments.

  - Copies of any environmental policies should you have them

In addition, note that the tender submission should provide sufficient information to allow assessment against the criteria outlined in Section 14.

## Evaluation Criteria

JNCC are not bound to accept the lowest priced or any tender.  Having the technical expertise and experience to complete the work to a high standard, and being able to complete it within the timescale, are of the essence for this contract.

Tenders will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Max Score | Score |
| --- | --- | --- | --- |
| 1. Quality of proposal, (50% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal (particularly work plan and deliverables) | 10 |  |
|  | Understanding of, and relevance to, the requirements (in particular, the adequacy of outputs and experience, and understanding, of benthic imagery analysis and taxonomic identification of epifauna) | 15 |  |
|  | Realism and measurability of milestones | 10 |  |
|  | Identification and proposed solutions to potential problems/risks | 8 |  |
|  | Probability of success | 7 |  |
|  | Sub Totals | 50 |  |
| 2. Details of Contractor (25 % of the three assessment categories) |  |  |  |
|  | Expertise, experience and balance of team in relation to the objectives of the contract | 15 |  |
|  | Risks if important team members drop out | 10 |  |
|  | Sub Totals | 25 |  |
| 3. Cost (25% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation | 10 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 5 |  |
|  | Clarity of each team member’s contribution and value added | 10 |  |
|  | Sub Totals | 25 |  |
| Total score |  | 100 |  |

## Payment

Payment will be made on completion of the objectives, following the submission of an invoice(s); and based on satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Contract Manager.

## Additional Contractor requirements

All tenderers are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key milestones.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates and fees given.

The Contractor is expected to supply all necessary equipment, software, licences etc. to carry out the obligations required under the contract.

## References

Beaumont, J.C., Brown, C.J. & Sayer, M.D.J. 2007. Evaluation of techniques used in the assessment of subtidal epibiotic assemblage structure. Biofouling 23 (5): 343-356.

Benedetti-Cecchi, L., Airoldi, L., Abbiati, M. & Cinelli, F. 1996. Estimate the abundance of benthic invertebrates: a comparison of procedures and variability between observers. Marine Ecology Progress Series 138: 93-101.

Drummond, S.P. & Connell, S.D. 2005. Quantifying percentage cover of subtidal organisms on rocky coasts: a comparison of the costs and benefits of standard methods. Marine and Freshwater Research 56: 865-876.

Durden, J.M., Bett., B.J., Schoening, T., Morris, K.J., Nattkemper, T.W. & Ruhl., H.A. 2016. Comparison of image annotation data generated by multiple investigators for benthic ecology. Marine Ecology Progress Series 552: 61-70.

Hinchen, H., 2014. Review of marine biodiversity assessment obligations in the UK. Part I: A summary of the marine biodiversity assessment obligations stipulated within national and international legislative and policy instruments, JNCC Report 497, Available from: http://jncc.defra.gov.uk/page-6673 (Accessed 24 July 2017).

Hitchin, R., Turner, J.A. & Verling, E. 2015. Epibiota remote monitoring from digital imagery: Operational guidelines.

Moore, J.J., Bunker, F., van Rein, H. & Jones, J. 2015. Methodological trials: Recording

subtidal epibiota in situ and in photographs, Portrush, August 2013 and Sound of Mull

August 2014. JNCC Report, No. 561.

Ninio R, Delean S, Osborne K, Sweatman H. 2003. Estimating cover of benthic organisms from underwater video images: variability associated with multiple observers. Marine Ecology Progress Series 265: 107-116.

Turner, J.A., Hitchin, R., Verling, E., van Rein, H. 2016. Epibiota remote monitoring from digital imagery: Interpretation guidelines.

Van Rein, H., Schoeman, D.S., Brown, C. J., Quinn, R. & Breen, J. 2011. Development of

benthic monitoring methods using photoquadrats and SCUBA on heterogeneous hard substrata: A boulder-slope community case study. Aquatic Conservation 21 (7): 676-689.

Van Rein, H.B., Schoeman, D., Brown, C.B., Quinn, R. & Breen, J. 2012. Development of low-cost image mosaics of hard-bottom sessile communities using SCUBA: comparisons of

optical media and proxy measures of community structure. Journal of the Marine Biological

Association of the United Kingdom 92 (1): 49-62.

## Appendix A – Example of summary data extraction table

| Data extraction method | Observer experience level | Observer initials | Sample image no. | Taxon | Measurement | Time to sample image (mins) |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Percentage cover | Senior | HVR | Image001 | Caryophyllia smithii | NA | NA |
| 2. Abundance count | Senior | HVR | Image001 | Caryophyllia smithii | 15 | 15 |
| 3. SACFOR | Senior | HVR | Image001 | Caryophyllia smithii | C | 10 |
| 4. Point intercept | Senior | HVR | Image001 | Caryophyllia smithii | 3 | 8 |
| 5. Frequency of occurrence (25 cells) | Senior | HVR | Image001 | Caryophyllia smithii | 15 | 8 |
| 6. Frequency of occurrence (100 cells) | Senior | HVR | Image001 | Caryophyllia smithii | 50 | 15 |
| 1. Percentage cover | Junior | JB | Image001 | Caryophyllia smithii | NA | NA |
| 2. Abundance count | Junior | JB | Image001 | Caryophyllia smithii | 15 | 15 |
| 3. SACFOR | Junior | JB | Image001 | Caryophyllia smithii | C | 10 |
| 4. Point intercept | Junior | JB | Image001 | Caryophyllia smithii | 3 | 8 |
| 5. Frequency of occurrence (25 cells) | Junior | JB | Image001 | Caryophyllia smithii | 15 | 8 |
| 6. Frequency of occurrence (100 cells) | Junior | JB | Image001 | Caryophyllia smithii | 50 | 15 |

NMBAQC Epibiota Operational Guidelines, URL: http://www.nmbaqcs.org/media/1591/epibiota_operational_guidelines_final.pdf

NMBAQC Epibiota Interpretation Guidelines, URL: http://www.nmbaqcs.org/media/1643/nmbaqc_epibiota_interpretation_guidelines_final.pdf

NMBAQC Epibiota Interpretation Guidelines, URL: http://www.nmbaqcs.org/media/1643/nmbaqc_epibiota_interpretation_guidelines_final.pdf