# Annex A

| Title of project: | Using radar based terrain mapping to model the vulnerability of 5 UK Overseas Territories to natural hazards and the value of natural capital in mitigating impacts. |
| --- | --- |
| Date and time for return of tenders: | Wednesday 11 January 2017 @ 16:00 hours |
| Contract Reference No: | C16-0280-1070 |
| Address for tender submission: | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND TENDERS DIRECTLY TO TONY WEIGHELL or DORA IANTOSCA OR GORDON GREEN VIA THEIR PERSONAL EMAIL ADDRESSES, AS THIS WILL INVALIDATE YOUR TENDER Tender responses must be less than 10 MB in size. On receipt of your tender, you will receive an automated e-mail to confirm receipt by JNCC Support Co. If you do not receive this automated email, please contact, in the following order: Sue Wenlock (00 44 1733 866880) Chris Downes (00 44 1733 866877) |
| Contacts for technical information relating to this project specification: | Tony Weighell Joint Nature Conservation Committee Email: tony.weighell@jncc.gov.uk Tel: 01733 866852 OR Joint Nature Conservation Committee Email: Tel: |
| Contact for any queries regarding the tendering procedure: | Dora Iantosca or Gordon Green Finance Team Joint Nature Conservation Committee Email: Dora.Iantosca@jncc.gov.uk or Gordon.green@jncc.gov.uk Tel: 01733 866894 or 01733 866806 |
| Proposed start-date: | Phase 1: 16 January 2017 |
| Proposed end-date: | Phase 1: 28 March 2017 |

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation. Its work contributes to maintaining and enriching biological diversity, conserving geological features and sustaining natural systems.

Our role is to provide evidence, information and advice so that decisions are made that protect natural resources and systems. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally:

advising Government  on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminate knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on the JNCC intranet:

http://cms/JNCCIntranet63/defalut.aspx?page=1569

## Project Aims

The Caribbean Overseas Territories (Anguilla, British Virgin Islands, Cayman Islands, Montserrat and Turks and Caicos) the South Atlantic Overseas Territories (Falkland Islands, St Helena, Ascension, Tristan and South George) are highly dependent on the natural environment for their economic and social wellbeing. The Territories are also reliant on very limited manmade assets. In the Caribbean in particular these manmade capital assets, and human life, are vulnerable to both natural and manmade disasters. The natural environment is itself susceptible to damage from human activities – resulting in loss of value to the economies of the Territories – but also provides a key role in protecting man made assets and protecting human well being.

JNCC is initiating a suite of projects to integrate satellite data, Geographic Information Systems (GIS) and economic assessments of environmental goods and services (derived from natural capital) with the following objectives:

i.	establish the Total Economic Value (TEV) of the terrestrial and marine natural environment to each of the ten listed Territories;

ii.	identify the priority natural capital assets and measurable attributes (Natural Capital Metrics) to monitor changes in value through time;

iii.	 integrate natural capital valuations into national mapping (GIS) to define the spatial distribution of these natural assets (Value Mapping) and to promote the integration of such valuations into planning and policy making to improve long-term economic growth;

Within the context of the Caribbean in particular JNCC wishes to assess the role and value of natural capital in protection of manmade capital through a terrain based model which assesses the vulnerability (susceptibility) of this manmade capital to natural hazards such as (but not limited to) storm surge or tsunami waves in the coastal zone and landslip or flash flooding in the terrestrial environment.

## Project Objectives

The objectives of the work to be done under this contract are to use satellite derived radar data to undertake detailed terrestrial and coastal zone terrain mapping of five UK Overseas Territories namely:

Anguilla

British Virgin Islands (BVI)

Tristan da Cunha

Montserrat

Turks and Caicos Islands

with the intention of subsequently:

i. undertaking island specific assessments of the vulnerability of terrestrial and coastal man-made assets and human life to a range of natural disasters;

ii. establishing the role, and monetary value, of coastal and terrestrial ecosystems in protecting man-made assets and human life

## Project Objectives: Detailed tasks

The work will be undertaken in two phases, with Phase I to be completed by March 31st 2017.  Phase II will be initiated after May 2017 subject to satisfactory contractor performance of Phase 1 work and JNCC committing funding for this second Phase.

Phase 1

Stage 1: Purchase of radar satellite data

Purchase of radar satellite data suitable for generating a digital terrestrial elevation model of the five listed Territories under an appropriate licensing agreement which will permit use of the derived terrain maps by JNCC and its OT partners in development of vulnerability maps, vulnerability models or other related uses.

Stage 2: Detailed terrain mapping of all 5 Territories listed above (Section 3) to define drainage patterns, slope angles and other relevant surface features to produce digital contour maps at appropriate intervals, slope and aspect layers and additional map layers relevant to modelling water flow in coastal and inland environments. The terrestrial maps to be merged with bathymetry data where available to provide the basis for subsequent marine storm surge modelling.

Stage 3: Develop a vulnerability assessment procedure

Develop a vulnerability assessment procedure that is based on the terrain mapping and subsequent integration of available key data sets, this procedure to define:

a. what data is essential in the context of vulnerability assessments related to specific hazards in the listed OTs, these hazards to include as a minimum  storm surge waves and tsunami in the coastal zone and landslip and flash flooding in the terrestrial environment;

b. how the vulnerability to specific hazards can be mapped in the terrestrial and coastal zones of small islands in general;

c. available tools for analysis of hazard vulnerability, especially those which are open sourced, to be assessed and recommendations given for the best tool for each task;

c. how modelling may be used to assess vulnerability under different hazard scenarios, for example  storm surge, extreme rainfall, volcanic eruption including scenarios related to likely climate change in the region;

d. how to integrate data on natural features (other than basic terrain and bathymetry) such as reef structure and function, coastal lagoons, nearshore sediment bodies, coastal lagoons, coastal and terrestrial vegetation etc to help provide baseline data as the basis for modelling the role of natural capital in protecting man made capital and human life;

e. generic procedures to assess the economic value of natural capital in the marine, coastal and terrestrial environment in protecting man made capital illustrated with practical examples, drawn from Caribbean islands or UK OTs where possible, to demonstrate the practical application of such techniques including the estimated monetary value of the natural environment in disaster mitigation/avoidance.

Stage 4: Application of the procedure – Anguilla case study

- Initially working with Anguilla, combine terrain mapping (including bathymetry) with all existing, available and relevant data on soils, vegetation, infrastructure, settlement patterns rainfall etc. to demonstrate the assessment procedure and its actual or potential outputs in the context of risks specific to this island including an assessment of the value of natural capital in disaster mitigation;

- Critically assess the model created using satellite derived radar against interpretations and models already developed though the Anguilla NEA using high resolution LiDAR and evaluating the effectiveness of the radar based solution.

Stage 5: Application of the procedure – other islands

Subject to time and data limitations apply the model to one other of the listed OTs in its entirely, or a limited geographical area within one of the islands, this to be chosen in consultation with JNCC and with the objective of highlighting functions of the model not demonstrable though the Anguilla detailed modelling.

Stage 6: Demonstration in Anguilla, 2017.

The contractor will be expected to attend a workshop in Anguilla at a date to be agreed in 2017, spending up to 5 days on the island plus travel time. The contractor will demonstrate the methodology involved and the results of the individual case studies to UK OT representatives and the representatives of other regional states and organisations. The contractor will make all necessary travel arrangements and bear all costs associated with their participation in this event.

## Potential follow-on work - Phase 2

Tenderers should be aware that there is the potential for the successful contractor to be requested by JNCC to undertake additional work (Phases 2) on this contract into the financial year 2017/18 as follows:

Extend the application of the model to up to three other of the listed Territories using radar data or, where available, Lidar or other sources.

Please note however that the potential for additional work to be undertaken is subject to a continuing need, availability of funds, and satisfactory contractor performance. For the avoidance of doubt, no guarantee can be given, that you will be asked to undertake the potential additional work outlined within this Annex A document. Tenderers are not asked to provide detailed project plans for these follow-on aspects at this stage.

## Outputs

- Digital terrain maps for the five listed Territories;

- A detailed vulnerability assessment procedure as described in Section 4;

- A functioning, GIS based, model for the island of Anguilla which applies the assessment procedure including assessment of the value of the natural environment in disaster mitigation;

- A critical assessment of the respective merits of radar and Lidar based modelling;

- At JNCC’s request a ‘partial’ model for one of the listed OTs other than Anguilla designed to illustrate applications not apparent through the Anguilla case study itself;

- A set of succinct recommendations for further applications of the model in the context of the UK OTs and other small islands in the Caribbean and South Atlantic.

## Timescale

Provisional dates for delivery of the contact outputs are set out below. Exact dates are to be agreed at start-up meeting based on Contractor and JNCC staff availability.

| Milestones | Provisional dates |
| --- | --- |
| Start-up meeting (UK) | 16 January 2017 |
| Draft assessment procedure available | 24 February 2017 |
| All outputs complete | 31 March 2017 |

In agreeing exact dates please note that the potential for work under this contract to be funded into 2017/18 is subject to availability of funds.

## Health and safety

The Contractor is expected to follow appropriate Health & Safety procedures and undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by JNCC H&S advisor)

Any incidents occurring within the contract should be immediately reported to JNCC.

## Product specification

The final report must adhere to the JNCC report template and house style guidance unless agreed otherwise with the nominated JNCC project officer. The draft and final reports should be provided electronically via email both as a Microsoft Word document and an Adobe PDF.

## Project management

The Contractor shall nominate a project manager, who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact point will be:

Dr Tony Weighell

Email: Tony.Weighell@jncc.gov.ukTel: +44 (0)1733 8666852

## Instructions for tender submission

The tender submission should include the following:

A brief summary of the potential Contractor’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract (and delivering the detailed tasks identified within each objective). This should be sufficiently detailed allow assessment against the evaluation criteria (Section 14);

A detailed project plan (including Gantt chart), including the proposed work programme and an estimate of time required to achieve each objective;

A draft Table of Contents for the final report;

Details of Quality Control procedures to be followed;

Details of the Contractor’s own internal Quality Management System;

Details of the Project Team, including their roles and experience, an estimate of their time input into each task, and CVs of all personnel involved in the contract;

Availability of the Project Team representative for a start-up meeting in Peterborough on  or around January 16th 2017 (remote meeting via telephone or Skype acceptable)

Overall quote for the contract, to include:

  - Daily rates for all members of the Project Team;

  - Rates for attending start-up, interim and final meetings in Peterborough or Aberdeen and also in Anguilla (costs for travel and accommodation are attached and should be used. These rates are analogous to the civil service rates);

  - Costs and time allocation should be clearly allocated to specific tasks within this contract; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and to provide their company’s VAT registration number.

The following documentation:

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates; and

  - Copies of any appropriate risk assessments.

  - Copies of any environmental policies should you have them

In addition, note that the tender submission should provide sufficient information to allow assessment against the criteria outlined in Section 14.

## Evaluation Criteria

## JNCC are not bound to accept the lowest priced or any tender.  Having the technical expertise and experience to complete the work to a high standard, and being able to complete it within the timescale, are of the essence for this contract.

Tenders will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Max Score | Score |
| --- | --- | --- | --- |
| 1. Quality of proposal, (55% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal (particularly work plan and deliverables) | 15 |  |
|  | Understanding of, and relevance to, the requirements in particular, the adequacy of the details of the proposed process for achieving the required outputs and clarity of proposal in respect of mechanisms to access the necessary data to undertake the work in the listed OTs in particular those identified for detailed modelling studies. | 25 |  |
|  | Soundness and logicality of methods | 5 |  |
|  | Identification of potential problems/risks to delivery | 5 |  |
|  | Proposed solutions to identified problems/risks | 5 |  |
|  | Sub Totals | 55 |  |
| 2. Details of Contractor (20 % of the three assessment categories) |  |  |  |
|  | Expertise, experience and balance of team, including demonstrable experience of working with small islands in general and the listed UK OTs in particular. | 10 |  |
|  | Risks if important team members drop out | 5 |  |
|  | Adequacy of subcontractors (if any) | 5 |  |
|  | Sub Totals | 20 |  |
| 3. Cost (25% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation | 10 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 5 |  |
|  | Appropriateness of ratio of senior to junior staff time | 5 |  |
|  | Clarity of each team member’s contribution and value added | 5 |  |
|  | Sub Totals | 25 |  |
| Total score |  | 100 |  |

## Payment

Payment will be made in two instalments each representing 50% of the total contract value including VAT on the basis of the following schedule:

- On satisfactory completion of the first three stages of the project as defined in Section 4, expected to be late in February 2017;

- On satisfactory completion of the stages 4 and 5 as defined in Section 4, expected to be end of March 2017;

In each case payment will follow the submission of invoices, and based on satisfactory undertaking of the relevant contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Contractor requirements

All tenderers are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key milestones.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates and fees given.

The Contractor is expected to supply all necessary equipment, software, licences etc. to carry out the obligations required under the contract.