# Annex A

| Title of project: | Reviewing Metabarcoding Guidelines and Understanding Sources of Error |
| --- | --- |
| Date and time for return of tenders: | Friday 18h December 2020 @ 13:00 hours |
| Contract Reference No: | C20-0382-1504 |
| Address for tender submission: | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND TENDERS DIRECTLY TO PAUL WOODCOCK OR DORA IANTOSCA VIA THEIR PERSONAL EMAIL ADDRESSES, AS THIS WILL INVALIDATE YOUR TENDER Tender responses must be less than 10 MB in size. On receipt of your tender, you will receive an automated e-mail to confirm receipt by JNCC Support Co. If you do not receive this automated email, please contact, in the following order: Sue Wenlock (00 44 1733 866880) Chris Downes (00 44 1733 866877) |
| Contacts for technical information relating to this project specification: | Joint Nature Conservation Committee Email: Paul.Woodcock@jncc.gov.uk Tel: 01733 866953 |
| Contact for any queries regarding the tendering procedure: | Dora Iantosca Finance Team Joint Nature Conservation Committee Email: Dora.Iantosca@jncc.gov.uk Tel: 01733 866894 |
| Proposed start-date: | Jan 2021 |
| Proposed end-date: | March 2021 |

Reviewing Metabarcoding Guidelines and Understanding Sources of Error

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Aims	3

3.	Project Background	3

4.	Project Objectives	4

5.	Project Objectives: Detailed tasks	4

6.	Outputs	7

7.	Dissemination	8

8.	Timescale	8

9.	Health and safety	8

10.	Product specification	8

11.	Project management	9

12.	Instructions for tender submission	9

13.	Evaluation Criteria	10

14.	Payment	11

15.	Additional Contractor requirements	12

16.	References	12

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation. Its work contributes to maintaining and enriching biological diversity, conserving geological features and sustaining natural systems.

Our role is to provide evidence, information and advice so that decisions are made that protect natural resources and systems. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminate knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found at: https://jncc.gov.uk/about-jncc/

## Project Aims

The overall project aim is to contribute to greater use of DNA-based methods for monitoring species and ecosystems by environmental public bodies. This project will focus particularly on metabarcoding, and aims to improve end user understanding and awareness of:

- What guidance documents and standards for using metabarcoding in environmental exist and what the strengths and weaknesses of these documents are

- Why metabarcoding results can differ from conventional methods, and potential approaches to mitigation where these differences may arise from error or bias in metabarcoding.

## Project Background

DNA-based methods for detecting and identifying species have many potential applications within the Defra group of organisations (APHA, Defra, CEFAS, Environment Agency, Forest Research, JNCC, Kew, Marine Management Organisation, Natural England). These include surveillance for invasive or rare species, characterising communities to assess the condition of protected sites, understanding the effects of management interventions, and describing ecosystem functioning and resilience. However, operational use by public bodies faces several challenges. To contribute to addressing these challenges, Defra have established a Centre of Excellence (CoE) to support projects that will help facilitate greater uptake of DNA-based methods for monitoring species and ecosystems. The CoE brings together expertise and interests from across the Defra group of organisations to identify and tackle shared priorities through a series of projects.

As with all environmental monitoring carried out by public bodies, practical implementation of DNA-based methods requires agreed guidelines and protocols that give confidence the results are robust and are spatially and temporally comparable. However, whilst CoE organisations are aware of and have contributed to several existing guidelines and protocols for using DNA in monitoring, there is less knowledge of documents developed by other organisations – particularly in relation to metabarcoding. A better understanding amongst end users of what metabarcoding guidelines and standards exist would therefore be beneficial for several reasons:

- Brings together key resources to make it easier to find relevant documents

- Provides opportunities to learn from existing guidelines

- Avoids duplicating effort or producing conflicting documents

- Allows new guidance documents to be targeted to key remaining gaps

A related important knowledge gap for several CoE organisations is understanding how, when, and why metabarcoding results can differ from conventional methods. Understanding the sources of error and bias in metabarcoding, and being able to distinguish these from situations in which metabarcoding and conventional methods give different results because each samples a different portion of the community, is particularly important for end user interpretation of results from DNA-based methods.

## Project Objectives

To meet the overall aims of this project (Section 2), the objectives are to:

- Review the strengths, weaknesses, and usefulness of existing metabarcoding protocols, standards, and guidance documents (see Section 5 for further information on scope). If appropriate, identify any key documents and initiatives that it would be beneficial to align future methods development work with, including nationally and internationally.

- Produce a resource that non-specialist end users with interest in applying metabarcoding in environmental monitoring can search to find relevant protocols, standards, and guidance documents.

- Make initial recommendations on metabarcoding protocols, standards, and guidance. The nature of these recommendations can be discussed to ensure feasibility, but might relate to (for example) one or more of the following: minimum requirement ‘basic’ guidance that should always be followed; what key features should be included within any guidance document developed in future; information that should be reported to allow end users to understand confidence in results.

- Describe the main reasons that metabarcoding and conventional methods may differ. Where these problems are caused by error or bias, describe approaches to mitigation

## Project Objectives: Detailed tasks

The specific tasks required for each objective are described below. Tender submissions should explain how these tasks will be carried out, and propose any additional activities that may be necessary.

Objectives (i-iii): Review of Existing Protocols, Standards and Guidance

To meet Objectives (i-iii), a review is required covering existing protocols, standards, and guidance for using metabarcoding (DNA or eDNA) in environmental monitoring. This should include documents that are not specific to particular habitats as well as documents that relate primarily to terrestrial, marine or freshwater systems. It should also span field, laboratory, and bioinformatics stages.

Scope of the Review

- The review should encompass three broad types of methods document that describe how metabarcoding should be applied in environmental monitoring. It should prioritise documents that are published and in use but also attempt to include documents that are in the later stages of development but not yet fully published. The three broad types of documents to consider are:

  - Protocols in operational use for metabarcoding environmental samples. For this project, ‘protocol’ refers to documents that are being used operationally for monitoring by public bodies in the UK or elsewhere, and to documents that are in development for this purpose but have not yet been fully formally published.

- These documents will typically contain detailed recommendations on how the method should be carried out (Biggs et al. 2014 provides an example in a single-species context). The primary focus is therefore on use for surveys and monitoring (e.g. by public bodies) rather than research use. Although the latter is also potentially informative, describing and evaluating the methods used by every individual metabarcoding study is not considered feasible given the time constraints and so is less of a priority for this review.

  - Standards intended to apply for multiple potential uses (e.g. https://standardsdevelopment.bsigroup.com/projects/9020-04348#/section).

  - General guidance documents (e.g. Liu et al. 2019)

- The review should include UK and international documents as far as possible.

- The review should include peer-reviewed literature as well as grey literature (e.g. government reports). Key information may not be easily findable using conventional academic databases, and so discussions with relevant agencies and ongoing projects are likely to be necessary.

Contents of the Review

The review should include descriptive information from each relevant document and clear links to the appropriate sources. The information to include can be discussed and refined to ensure feasibility, but is likely to involve presenting at least some of the following for each document:

- The system(s)/habitat(s) the document relates to

- The species / assemblage(s) and sample medium (e.g. water, soil, organisms collected directly from traps etc.)

- How the document is intended to be used

- Brief summary of any recommendations made by the document on:

  - Sample collection, preservation and storage

  - DNA extraction and sequencing

  - Data analysis procedures recommended by the document

  - Reporting results from DNA analyses

The review should also provide expert judgement on the contents of each document (e.g. strengths, weaknesses, costs, practicality etc.).

The information gathered during the review should be synthesised to identify any commonalities and conflicts across documents and to highlight key documents and initiatives that it would be beneficial to align future methods development work with. The review should also make initial recommendations on metabarcoding protocols, standards and/or guidance. The nature of these recommendations can be discussed but might relate to (for example): minimum requirement ‘basic’ guidance that should always be followed; what key features should be included within any guidance document developed in future;  information that should be reported to allow end users to understand confidence in results. The review contents, including details on each relevant methods document should be presented in a format that can be easily accessed and searched by non-specialists.

Required Information from Proposals

Proposals should explain the process for finding relevant protocols, standards, and guidance. In addition to conventional searches, this is likely to involve discussions with relevant public bodies and project leads in the UK and elsewhere to identify ongoing work and documents not fully published. Please indicate any existing links and familiarity with these initiatives that would help with obtaining relevant information. Proposals should also suggest what information would be important to extract from each document and how this will be presented in an accessible and easily searchable format. Lastly, proposals should describe any potential peer-review (internal or external) and/or other quality assurance that will be undertaken in order to ensure the outputs are robust.

As noted previously, ‘protocols’ relates primarily to documents in routine use or intended to be used routinely and not to the methods being used by individual research papers. Also note that a fully comprehensive review is not expected given the timescales. However, efforts should be made to ensure the review is as complete as possible across terrestrial, marine and freshwater habitats, and that information about each relevant document is extracted in a consistent and objective way.

Objective (iv): Understanding sources of error and bias in metabarcoding

To meet Objective (iv), a concise review is required summarising the key reasons for differences in results between metabarcoding and conventional methods. The review should distinguish between differences that occur because the different techniques sample different portions of the community (i.e. both approaches are correct on their own terms but give a different answer) and differences that can occur due to error and bias in metabarcoding.

Where differences are due to error and bias in metabarcoding, the review should briefly explain the causes and consequences of these problems, possible approaches to mitigation, and remaining uncertainties that require further research. The review may include reference to studies comparing metabarcoding with other monitoring methods but should aim to give a balanced representation of the literature (e.g. the importance/scale of any problems should reflect the general consensus rather than the findings from one or two individual studies). Relevant literature on sources of error and bias in metabarcoding should also be highlighted and built on where appropriate (e.g. Furlan et al. 2020).

Required Information from Proposals

Given the time available, this task is anticipated to provide an overview rather than to be comprehensive, but proposals should briefly explain what steps will be taken to ensure the outputs give as objective and representative synthesis of the current evidence as possible. Proposals should also describe any potential peer-review (internal or external) and/or other quality assurance that will be undertaken in order to ensure the outputs are robust.

## Outputs

Outputs should be in a format that can be easily accessed and understood by non-specialists

Objectives (i-iii)

- Review that includes an assessment of strengths, weaknesses, commonalities and conflicts in metabarcoding methods documents, an identification of key documents, and caveats and limitations with the review. The review should make recommendations on metabarcoding and should also include a short (1 side maximum) executive summary.

- A resource based on the review that allows non-specialist end users to find any relevant methods documents on applications of interest, and to understand the strengths and weaknesses of these documents. This may be presented within the review or provided as a standalone product (e.g. database or spreadsheet). The resource should contain consistent information about each relevant methods document, potentially including: the system/habitat; the species / assemblage(s) and sample medium; brief summary of the recommendations made by the document; brief expert judgement on strengths and weaknesses of the document.

- Any consensus-building and peer-review required for quality assurance and acceptability of any recommendations across different stakeholders should be incorporated as far as possible, with any necessary future work in this respect identified.

Objective (iv)

- Short review that allows non-specialists to understand key potential reasons for differences between metabarcoding and conventional methods, sources of error in metabarcoding, and potential approaches to mitigation.

The structure of the outputs should be agreed with the Project Steering Group (Section 11) after the contract has been awarded.

All outputs are subject to approval and sign-off by the Project Steering Group, and the final outputs will be published. The Contractor will be responsible for ensuring the quality of the work as well as the presentation of the material (e.g. proof-reading, formatting). Any planned publication of outputs by the Contractor should be notified to JNCC prior to initial submission. Please see Section 10 for specifications of final products.

## Dissemination

Outputs produced under this contract will be JNCC products and shall not be published or disseminated without the written permission of JNCC. Outputs may at some point be published on the JNCC website and all material supplied as part of the contract shall remain copyright of JNCC. The findings from this contract will also be made available to all organisations participating in the Centre of Excellence (APHA, Defra, CEFAS, Environment Agency, Forest Research, JNCC, Royal Botanic Gardens Kew, Marine Management Organisation, Natural England) as well as other public bodies (including NatureScot, SEPA, Scottish Forestry, NRW)

## Timescale

Provisional dates for the contract outputs are set out below. Exact dates are to be agreed at a start-up meeting, based on Contractor and JNCC staff availability. Please note, due to the ongoing situation with COVID-19, it is anticipated that all meetings will be held remotely. Please state your preference of software for virtual meetings on your tender.

| Milestones | Provisional dates |
| --- | --- |
| Inception meeting | As soon as possible after start of contract |
| Agreed scope and structure for outputs | Mid-January 2021 |
| Draft outputs circulated to Project Steering Group for comment | End February 2021 |
| Final drafts circulated to Project Steering Group for any minor revisions and quality assurance | 5th March 2021 |
| Submission of final outputs | 19th March 2021 |

## Health and safety

The Contractor is expected to follow appropriate Health & Safety procedures and undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by JNCC H&S advisor).

Any incidents occurring within the contract should be immediately reported to JNCC.

## Product specification

The final outputs must adhere to the JNCC report template and house style guidance unless stated otherwise. The draft and final reports should be provided electronically via email both as a Microsoft Word document and an Adobe PDF. Outputs should comply with JNCC Evidence Quality Assurance policy (https://jncc.gov.uk/about-jncc/corporate-information/evidence-quality-assurance/)

## Project management

The contract will be managed by a JNCC Project Officer who will be responsible for signing off deliverables and will be the main contact point. The Contractor shall nominate a Project Manager, who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

A Project Steering Group has been established comprising of representatives of Centre of Excellence organisations that are potential users of the project outputs. The Steering Group will monitor progress and provide guidance. The Contractor will be responsible for organising meetings with the Project Steering Group and for providing administrative support as needed, including maintaining records of key correspondence. A project inception meeting between JNCC and the Contractor will be required at the start of the project. We envisage that all meetings will be held remotely. Please state your preference of software for virtual meetings on your tender.

JNCC’s main contact point will be: Paul Woodcock

Email: Paul.Woodcock@jncc.gov.uk

Tel: +44 (0)1733 866953

## Instructions for tender submission

The tender submission should include the following:

A brief summary of the potential Contractor’s experience in relation to the requirements of this contract. Knowledge and links with efforts to develop metabarcoding methods guidance documents in the UK and elsewhere would be particularly beneficial;

A proposed approach for achieving the objectives of the contract and how the tasks outlined in Section 5 would be tackled. This should be sufficiently detailed to allow assessment against the evaluation criteria (Section 13);

A short project plan (including Gantt chart), including the proposed work programme and an estimate of time required to achieve each objective;

A draft structure for how the outputs would be presented

Details of Quality Control procedures to be followed. These should be in accordance with JNCC Evidence Quality Assurance Policy (https://jncc.gov.uk/about-jncc/corporate-information/evidence-quality-assurance/), in particular see Appendix  (Bias, Conflicting Evidence and Uncertainty) and Appendix 3 (Quality Assurance of Expert Opinion)

Details of the Contractor’s own internal Quality Management System;

Details of the Project Team, including their roles and experience, an estimate of their time input into each task, and CVs of all personnel involved in the contract;

Availability of the Project Team for a start-up meeting

Overall quote for the contract, to include:

  - Daily rates for all members of the Project Team;

  - Costs and time allocation should be clearly allocated to specific tasks within this contract; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and to provide their company’s VAT registration number. The total value of this project is £15,000 including any applicable VAT.

The following documentation:

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates; and

  - Copies of any appropriate risk assessments.

  - Copies of any environmental policies should you have them.

In addition, note that the tender submission should provide sufficient information to allow assessment against the evaluation criteria outlined in Section 13.

For information on how we handle personal data please see our Privacy Notice at http://jncc.defra.gov.uk/privacypolicy

## Evaluation Criteria

JNCC are not bound to accept the lowest priced or any tender.  Having the technical expertise and experience to complete the work to a high standard, and being able to complete it within the timescale, are of the essence for this contract.

The tender evaluation will be undertaken by a panel consisting of JNCC staff and staff members from other Centre of Excellence organisations (including Natural England and the Environment Agency) Unless otherwise stated in your tender submission, bids will be forwarded to Centre of Excellence organisations for evaluation purposes only.

Tenders will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Max Score | Score |
| --- | --- | --- | --- |
| 1. Quality of proposal, (50% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal (particularly work plan and deliverables) | 10 |  |
|  | Suitability of proposed outputs for meeting the objectives of the contract | 25 |  |
|  | Soundness of methods and probability of success | 10 |  |
|  | Identification of potential problems/risks and proposed solutions | 5 |  |
|  | Sub Totals | 50 |  |
| 2. Details of Contractor (20% of the three assessment categories) |  |  |  |
|  | Demonstration of relevant expertise and experience of Contractor (including any subcontractors), with examples of successful work in this area and links with initiatives to develop methods guidance documents | 15 |  |
|  | Risks if important team members drop out | 5 |  |
|  | Sub Totals | 20 |  |
| 3. Cost (30% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation | 10 |  |
|  | Fairness/reasonableness of costs for the level of work and expertise required | 15 |  |
|  | Clarity of each team member’s contribution and value added | 5 |  |
|  | Sub Totals | 30 |  |
| Total score |  | 100 |  |

## Payment

Payment will be made on completion of the objectives, following the submission of an invoice(s); and based on satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Contractor requirements

All tenderers are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key milestones.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates and fees given.

The Contractor is expected to supply all necessary equipment, software, licences etc. to carry out the obligations required under the contract.

## References

Biggs, J, Ewald, N, Valentini, A, Gaboriaud, C, Griffiths, RA, Foster, J et al (2014) Analytical and methodological development for improved surveillance of the Great Crested Newt. Appendix 5. Technical advice note for field and laboratory sampling of great crested newt (Triturus cristatus) environmental DNA. Freshwater Habitats Trust, Oxford.

Furlan, EM, Davis, J, and Duncan, RP (2020) Identifying error and accurately interpreting environmental DNA metabarcoding results: a case study to detect vertebrates at arid zone waterholes. Molecular Ecology Resources, 20, 1250-1276.

Liu, M, Clarke, LJ, Baker, SC, Jordan, GJ, and Burridge, CP (2020) A practical guide to DNA metabarcoding for entomological ecologists. Ecological Entomology, 45, 373-385.