Invitation to Tender: Showcases

The drawings and descriptions in the accompanying Detailed Design Plan (DDP) parts 1 and 2 are the full outline specifications for the exhibits at the Isles of Scilly Museum, Church St, Isles of Scilly. TR21 0JT.

You are invited to tender for the showcases work package.

Outline programme

- Tenders received by 12:00 Monday 18th November 2024

- Value engineering with preferred contractor (if necessary) – November/December 2024

- Contract issued – early December 2024

- Ongoing production drawings and samples produced and presented – full set of drafts complete by end February 2025 & revised, checked and signed off by end of March 2025

- Off-site production – April to November 2025

- Workshop inspections and pre-installation snagging – August to November 2025

- Pre-installation H&S paperwork – drafts submitted by end of September and checked, amended and approved by end October 2025

- Installation – Mid December 2025 to February 2026

- Practical completion – end of February 2026

- First inspection by designer and client team – end of February 2026

- Snagging 1 – complete mid March 2026

- Second inspection by designer and client team – mid March 2026

- Snagging 2 – complete end March 2026

- Third inspection by designer and client team – end March 2026

- Operational training – end March 2026

- In-case object installation April 2026

- Provision of Operation & Maintenance Manual, as-built drawings and manufacturer’s manuals – mid April 2026

- Project completion and handover end April 2026

These dates are critical so please do not tender if you are unable to meet them.

Supply and exchange of files

Relevant files will be provided by the museum designers, Imagemakers, via Box.com. Box.com will also be used for other file sharing, including production drawings.

Tender submission requirements

You are invited to submit an itemised tender costing with 3no 2-page case studies of comparable projects (with referees’ contact details). The case studies should be from the last 5 years. Please do not submit an incomplete tender as it will not be accepted and provide a single cost for each item plus a figure for prelims and installation as well as drawings and samples, using the Pricing Schedule supplied.

Your tender should be returned via e-mail to procurement@scilly.gov.uk as a single PDF document to a maximum size of 8mb plus the separate Pricing Schedule Excel doc by the tender deadline.

Late tenders cannot be accepted.

Raising questions

You are welcome to raise questions by e-mail to procurement@scilly.gov.uk

The deadline for queries is 1600 Friday 1st November. Questions and responses will be shared with all tendering contractors.

Contractual arrangements

The contract will be awarded, and invoices paid by the Council of the Isles of Scilly. Invoices with a valid Purchase Order number should be submitted for approval and payment against the invoicing schedule set out below.

Preparing your tender

Please read this document, the ITT Terms and Conditions and the accompanying DDP carefully before preparing your tender.

Activity & outputs

Please include all project/production management, attendance at an on-site start up meeting and other fortnightly meetings (online), liaison with the client, designers, other contractors including the project’s base build Principal Contractor. Also include detailed dimensioned production drawings, the production and face-to-face presentation of two sets of samples (one sent to the Isles of Scilly and one sent to the designer) of proposed materials for approval - see list below). Finally, ensure the following is included in your tender: pre-installation H&S paperwork and activity, off site fabrication, printing, equipment use/hire, all materials, supply, labour, expenses and delivery.

Floor protection

All internal floors where exhibits are being either stored or installed must be protected at all times, for example with fire protected Correx and plywood sheets. The fabrication and fit out contractor is responsible for this and they will need input form the Showcase Contractor regarding materials and stillage specifications.

Shipping, storage & waste removal

Please note that there are very specific requirements for shipping and travel to and from the Isles of Scilly and you will be responsible for arranging and paying for this. This includes weatherproof protection for all goods. All goods must be accompanied by a member of your team.

Clean materials and exhibits awaiting installation can be stored in the Town Hall (140 square metres of floor space and standard door width at point of entry). Waste can be either taken off island in your van or skips can be hired locally (contact below).

Deliveries will need to be phased due to limits on shipping capacity and on-site storage. Please include details of how you propose to handle shipping and deliveries in your tender.

One commercial vehicle per contractor is permitted on the island (maximum size – Ford Transit or equivalent).

Useful contacts

Skip hire and Island freight operator – Richard Hand Haulage https://www.islesofscillyhaulage.com/

Island freight operator: Island Carriers Contact - Isles of Scilly – Freight (islesofscillyfreight.co.uk)

Shipping – Isles of Scilly Steamship Company  https://www.islesofscilly-travel.co.uk/

Andrew Fogden
Freight and Commercial Manager
Isles of Scilly Steamship Group
T: +44 (0)1736 334218
M: +44 (0)7760 575655
E: afogden@issg.co.uk

Welfare, accommodation & subsistence

A toilet will be available adjacent to the museum building. Food and accommodation are available on the island – contractors to book direct and include all costs in the tender.

Samples

Please allow for the production and face-to-face presentation of the following samples. These will be inspected and approved prior to production taking place.

- A4 dress panel wrapped in Baumann fabric – reference tba.

- A5 piece of 11.5mm low iron, low reflective laminated glass.

- A5 piece of 9.5mm  low iron, low reflective laminated glass.

- Painted sheet of steel - reference tba.

Value engineering & post-tender variations

A value engineering exercise may be required and following this, all final figures will be agreed and a contract issued.

Post-tender, no additional costs will be agreed without written permission being given by the Council of the Isles of Scilly or its agent.

Quality

All items must be of the highest quality and be fit for purpose for a very busy museum that will be visited by a broad range of people. Finishes must be very robust and life expectancy for all items is 10 years.

The requisite cleaning and maintenance regime should not be time-consuming and onerous for the clients who are responsible for managing the site.

Paint finishes are specified to enable the client or island-based contractors to retouch/refurbish exhibits.

Health & Safety

Include all requisite H&S activity such as Risk Assessments and Method Statements and a Construction Phase Plan. The staff members you put forward to work on this project must be appropriately qualified and your team manager who is in charge of the installation, and always present on site, must hold a Site Management Safety Training Scheme certificate; please include a scan if this in your tender response document.

O&M, as-built pack & training

Include the supply of an O&M manual and a final as-built drawings pack for all items. Please note that final invoices will only be approved once this information has been received and approved.

Allow for on-site training of client staff so they are comfortable with how to operate and maintain all hardware.

Warranty

The minimum warranty period for all items is 12 months from handover. This should include a commitment and guarantee to repair or replace any item within 10 working days of a problem being reported.

Your technical input

The specifications and outline drawings in the DDP are for tender guidance. We would like contractors to share their expertise and help to refine these details, so if you feel there’s a better and/or more cost-effective way of producing an item (whilst achieving a high quality robust and fit for purpose solution) please advise in writing and allow for this in your costings.

Your team’s details

Please supply details of who will manage the project on behalf of your company – nb. an overall project manager is required so the client and designer have a single lead contact who takes full responsibility for the work carried out. Note that we do not want to deal with a range of individuals or departments. Please explain how you will resource the project to deliver to the stated timeframe and include a brief resume of the staff members you will use on the project (including relevant professional and health and safety qualifications).

Site attendance, surveys & meetings

Regular site activities will be required. This will include site surveys and briefings, online progress meetings, on-site presence during installation, inspections, snagging, final sign off and staff/volunteer training.

Contractors will take full responsibility for taking careful measurements and notes and liaising with others including the client, designer, architect and principal contractor.

Site cleaning

Following installation/delivery, the site must be left clean and clear of all debris, tools etc.

Insurance

Please provide evidence of your company’s insurance cover in the form of scans of certificates and include these in your single tender PDF (not separately). Minimum insurance cover levels are as follows: Employer’s Liability £5,000,000.00; Public and Products Liability £5,000,000.00; Professional Indemnity cover of £2,000,000.00 (per claim).

Fixed pricing

Please confirm that your costings will remain fixed until the project is completed.

Sustainability

We want this project to be as sustainable and ‘green’ as possible, and would welcome suggestions for how we can achieve this. Tenders that include the use of low energy electrical equipment, recycled materials, low VOC finishes and UK-sourced material will be appreciated.

Publicity

Contractors will not undertake any publicity activities in relation to this contract without getting approval to do so from the Isles of Scilly Council. Client and designer to approve all copy and be credited in all publicity materials issued by contractors (including a live link to the relevant web site).

Invoicing arrangements (dates below are invoice submission timings). Payment terms – 30 days.

- Invoice 1 – 10% on receipt of contract.

- Invoice 2 -  10% on approval of all production drawings and samples.

- Invoice 3  - 15% during month 1 of off-site fabrication.

- Invoice 4 – 10% during month 3 off-site fabrication.

- Invoice 5 – 15% during the final month of off-site fabrication.

- Invoice 6 – 10% on commencement of on-site installation.

- Invoice 7 – 20% on practical completion and first inspection.

- Invoice 8 – 5% on final approval of all works, operational training and the supply of the O&M manual.

- Invoice 9 – 5% retention 12 months following invoice 8.

Tender response checklist

Annex A

- Completed Standard Selection Questionnaire

- Evidence of insurances

Annex B

- Pricing schedule

- Confirmation that your costs will remain fixed for the duration of the contract.

- Responses to qualitative questions D1 to D3 detailed in ITT Terms and Conditions document.

Annex C

- Certificate of bona fide tender

Expression of interest form. To be submitted as soon as possible to procurement@scilly.gov.uk to ensure that any clarifications can be received.