# Annex A

| Title of Project | Communicating environmental resilience in a changing climate through biodiversity conservation in the UK Overseas Territories |
| --- | --- |
| Date and Time for Return of Bids | 7 November 2022 @ 09:00 hours |
| Contract Reference Number | C22-0481-1687 |
| Address for Bid Submission | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND BIDS DIRECTLY TO (name of project officers) OR PROCUREMENT VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the number below. (00 44 1733 866 988) |
| Contacts for Technical Information relating to this Project Specification | Joint Nature Conservation Committee Name: Abbie Dosell Email: Abbie.Dosell@JNCC.gov.uk Tel: 01733 866930 OR Name: Shelley Cant Email: Shelley.Cant@JNCC.gov.uk Tel: 01733 866956 |
| Contact for Queries Regarding the Procurement Procedure | Finance and Planning Team Joint Nature Conservation Committee Email: @jncc.gov.uk or contractqueries@jncc.gov.uk Telephone: 01733 866894 |
| Proposed Start Date | 21st November 2022 |
| Proposed End Date | 28th February 2023 |

Title of Project

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Aims	3

3.	Project Background	3

4.	Project Objectives	5

5.	Project Objectives: Detailed Tasks	5

6.	Potential Follow-On Work There is no potential for follow-on work.	6

7.	Outputs	6

8.	Product Specification	6

9.	Dissemination	7

10.	Timescale	8

11.	Health and Safety	8

12.	Project Management	8

13.	Instructions for Bid Submission	9

14.	Evaluation Criteria	10

15.	Payment	11

16.	Additional Requirements	11

17.	References	12

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation

Our role is to provide scientific evidence, information, and advice to inform decisions to protect the natural environment. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally, by:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally.

providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally.

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/

## Project Aims

The UK’s Overseas Territories (UKOT’s) are highly dependent on the natural environment for their economic and social wellbeing.  They are also reliant on limited infrastructure.  In the Caribbean in particular, this infrastructure, and human life, are vulnerable to both natural and anthropogenic hazards.  The natural environment is itself susceptible to damage from human activities – resulting in loss of value to the economy and reducing its ability to protect assets and human well-being.

Building upon work to date, carried out under Joint Nature Conservation Committee’s (JNCC) Natural Capital in the Overseas Territories programme, and the current Conflict, Stability & Security Fund (CSSF) Disaster Resilience Project and Implementing Coral Reef Action Plans Project aim to: develop and disseminate targeted messages and communications materials to inform key stakeholders of:

- the role and value of the natural environment in providing environmental resilience.

- the pressures upon the natural environment; and

- the role stakeholders can play in protecting the natural environment.

This project aims to develop the necessary graphics to facilitate education and outreach activities which will be executed in six (6) UKOTs within the Caribbean, namely within Anguilla, Bermuda, British Virgin Islands (BVI), Cayman Islands (CI), Montserrat, and the Turks and Caicos Islands (TCI).

## Project Background

Climate change poses a serious threat to biodiversity and over the next few decades, may even surpass habitat destruction to become the leading global threat to life on earth (Bellard et al, 2012). The UKOT’s are particularly vulnerable to the impacts of climate change as they are small islands, often very low-lying islands and have over 80% of their populations living in the hurricane prone Caribbean and Western Atlantic. It was estimated that in 2017 severe weather generating extreme winds, inland flooding from intense rainfall and storm surge resulted in damages estimated at £2 billion in the three most affected Territories.

Healthy ecosystems provide services that help to minimise the impacts of climate change and especially from severe weather. Coral reefs and coastal mangrove forests buffer the storm waves; inland vegetation and associated habitats reduce surface water flows and facilitates absorption of flooding waters; and all of these habitats combined continue to offer other benefits that sustain biodiversity and livelihoods. It is these natural features and the services they provide that is often referred to as the ‘natural capital’ of an area. However, significant habitat loss, geomorphological modification, pollution, invasive species and diseases like Stony Coral Tissue Loss Disease (SCTLD) have weakened and, in many cases, completely removed these naturally resilient and adaptive systems; resulting in chronic flooding, damages to property and loss of human life (Martinez et al., 2017; Beck et al., 2018; Beck et al., 2020). The flood protection role and economic value of these natural environments is not always fully realised within policy making and planning institutions, nor at the community level within the OTs which has resulted in the loss of key protective features.

The JNCC has obtained funding through the CSSF, and other funding sources, to assist the UKOT Government’s in:

- Identifying communities at risk from flooding and key habitats that reduce the risks – maps of high-risk areas, and of the habitats that provide protection, will be used to communicate results to local communities and relevant government agencies.

- Demonstrating the economic (monetary) value of the natural environment in mitigating flood risk to all sectors of society.

- Training local communities and national agencies to gather and use data in computer-based modelling to support national and local disaster preparations to update risk assessments and environmental economic valuations.

- Implementing coral reef action plans developed by the UKOTs to restore and protect coral reefs through training, coral reef monitoring and reducing pressures including from SCTLD.

However, there remains a lot of misunderstanding and misinformation on climate change and environmental resilience, the role that healthy, native ecosystems play in climate resilience and adaptation, and what people can do to combat these issues as individuals or as a nation. A communications programme has been initiated to accompany the disaster resilience planning and coral reef work, which is being implemented across six (6) UKOTs. This programme seeks to:

- Highlight the disaster resilience and implementation of coral reef action plan work occurring across the Territories; and

- Develop and disseminate nationally relevant and targeted communications materials.

This project will build on this communications programme and produce. a range of communications to facilitate the awareness and improve overall understanding of the role of the natural environment to people throughout the Territories.

## Project Objectives

To meet the overall aims of this project (Section 2), the objectives are:

- Ensure regular communications with JNCC;

- Develop individual vector drawing infographics for all 6 UKOTs;

- Develop an A2-sized poster (including design and graphics); and

- Develop a CSSF trifold project pamphlet.

## Project Objectives: Detailed Tasks

- Ensure regular communications with JNCC:

  - Organise and attend a project start-up meeting with JNCC as soon as possible after start date.

  - Organise and attend regular meetings with JNCC staff for the whole duration of the project (frequency to be decided at kick off).

- Develop individual vector drawing infographics for all 6 UKOTs, which comprise all key messages from the CSSF project and demonstrate ecological linkages between human activities and OT ecosystems. The graphics will be used in social media, posters, reports and websites.

  - With technical input from JNCC, develop graphics that:

    - Illustrate ridge to reef concept.

    - Illustrate ecosystem functions.

    - Illustrate key habitats for environmental resilience.

    - Illustrate pressures and threats to those key habitats.

  - The graphic should be comprised of several smaller graphics that can fit together to tell a complete story, but each graphic should also be able to be used individually for future focused topics on outputs.

- With technical input from JNCC, develop a public-facing A2 poster (including design and engaging graphic) which depicts fisheries best practices.

- Develop a digital CSSF trifold project pamphlet aimed at the public of UKOTs and UK.

  - A5 tri-fold sized pamphlet.

  - Summary of entire project (JNCC to provide technical text).

## Potential Follow-On Work There is no potential for follow-on work.

## Outputs

Any products or outputs submitted to JNCC [for publication] should adhere to JNCC’s house-style and should be produced in an accessible format (see product specification for more information).

- A vector drawing infographic which comprises all of the key messages from the CSSF project including:

  - Delivery of editable files (Photoshop, InDesign or if using another format, this must be agreed with JNCC before delivery);

  - Delivery of final products (JPEGs, GIFs, or PDFs)

- The design and graphics for an A2-sized poster:

  - Delivery of editable files (Photoshop, InDesign or if using another format, this must be agreed with JNCC before delivery);

  - Delivery of final products (JPEGs, GIFs, or PDFs)

- A digital CSSF trifold project pamphlet:

  - Delivery of editable files (Photoshop, InDesign or if using another format, this must be agreed with JNCC before delivery);

  - Delivery of final products (JPEGs, GIFs, or PDFs)

## Product Specification

Target audiences to guide the above-mentioned outputs:

- Broad, non-technical audiences including the general public, marine users and school children. Aiming to help audiences understand the complex linkages between ecosystems and their actions, and the potential consequences of human activities on the natural environment.

- Broad, non-technical audiences including the general public, marine users and school children and interested parties such as divers, non-governmental organisations, academia and funders. Aiming to communicate complex technical information in digestible and engaging ways.

- Technical audiences including non-governmental organisations, project funders, project partners, academia, scientific agencies. Aiming to communicate the aims and achievements of the CSSF programme and the value of the work and UK Government funding.

JNCC is committed to making its publicly available resources and documents accessible, in accordance with the Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.

Making material accessible means making sure it can be used by as many people as possible.  This includes those with:

- impaired vision

- motor difficulties

- cognitive impairments or learning disabilities

- deafness or impaired hearing

The outputs and material that JNCC publishes should be compliant with the Web Content Accessibility Guidelines version 2.1 AA standard.

To meet this standard, all reports and other documentation which are to be made publicly available must adhere to JNCC’s house-style (to be provided) and be produced using a JNCC template (to be provided), unless otherwise stated. (Project managers to note – there are two templates, please decide which is most appropriate, either the ‘standard’ template rather than the JNCC report template).  All reports (draft and final) should be provided electronically via email both as a Microsoft Word document and an Adobe PDF.  All graphics should be provided in both editable and PDF versions, using either Adobe Photoshop or InDesign for editable versions.

Copies of documentation associated with case studies should be provided in electronic format with an associated reference catalogue.

For any other outputs or products which are to be made publicly available through JNCC, evidence regarding how the accessibility standard will be reached should be included.

We envisage only one review but please include cost of any addition reviews for outputs 3 and 4.

JNCC will provide OT specific communications plans, pre-made social media graphics, pre-made OT specific videos, relevant logos and some images. JNCC will also lead on engagement and consultation with OT stakeholders on behalf of the contractor. Further details will be provided at the project start up meeting. JNCC will provide the majority of the technical text and the contractor is expected to work with JNCC to amend the text to suit the target audiences.

(Note for author if research project/contract: see EQA Policy Appendix 4 (Communicating Evidence Quality). Ensure that data management and storage requirements are stipulated taking into account relevant policy for data access. See https://jncc.gov.uk/about-jncc/corporate-information/evidence-quality-assurance/

## Dissemination

The products/outputs produced under this contract will be jointly owned by the JNCC and relevant Overseas Territory.  Products/outputs shall not be published or disseminated without the written permission of JNCC and relevant Overseas Territory.  The various outputs will be distributed on a variety of platforms and venues and all material supplied as part of this contract shall remain copyright of JNCC and relevant Overseas Territory.  The products/outputs will be made available to UK Overseas Territories (UKOT) and the UK Overseas Territories Association (UKOTA) for their use.  The findings from this contract will also be made available to staff within JNCC, the UK country nature conservation bodies, the UKs Overseas Territories, Defra and the FCDO.

All footage and documentation delivered by JNCC, UKOTs and UKOTA to the contractor for inclusion in the videos or products, in the course of this work, which is then not used, should be treated as commercial-in-confidence, and the contractor should seek JNCC permission before distributing any footage or graphics to any third parties.

All documentation delivered by JNCC to the contractor should be treated as commercial-in-confidence, the contractor should seek JNCC permission before distributing the documentation to any third parties.

Any information or materials delivered to the contractor should not be used for any purposes outside the scope of this contract and should be destroyed on completion of the contract.

## Timescale

Provisional dates for delivery of the contact outputs are set out below. Exact dates are to be agreed at the start-up meeting based on Contractor and JNCC staff availability.

| Output | Provisional Date |
| --- | --- |
| Start-up meeting with JNCC and contractor | W/C 21st November 2022 |
| Delivery of a vector drawing infographic. | 9th January 2023 |
| Delivery of poster (digital). | 9th January 2023 |
| Delivery of a CSSF trifold project pamphlet. | 23rd January 2023 |

In agreeing exact dates please note that the potential for work under this contract to be funded into 2022/23 is subject to availability of funds.

## Health and Safety

The successful bidder is expected to follow appropriate Health & Safety procedures including adhering to JNCC’s policy on safeguarding. For further information  https://jncc.gov.uk/about-jncc/corporate-information/safeguarding/ and to be able to undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by the JNCC H&S Advisor).

Any incidents occurring within the contract period should be immediately reported to JNCC.

## Project Management

The successful Contractor shall nominate a project manager who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Abbie Dosell

Joint Nature Conservation Committee

Email: Abbie.Dosell@JNCC.gov.uk

Tel: +44 (0)1 1733 866930

Shelley Cant

Joint Nature Conservation Committee

Email: Shelley.Cant@JNCC.gov.uk

Tel: +44 (0)1 1733 866956

## Instructions for Bid Submission

The bid submission should include the following:

A brief summary of the bidder’s experience in relation to the requirements of this contract including providing samples of similar previous work;

A proposed approach for achieving the objectives of the contract and delivering the detailed tasks identified within each objective. This should be sufficiently detailed to allow assessment against the evaluation criteria (Section 14).

A detailed project plan (including Gantt chart) with proposed work programme and an estimate of time required to achieve each objective.

A draft Table of Contents for the final report.

Details of Quality Control procedures to be followed.

Details of the bidder’s own internal Quality Management System.

Details of the Project Team including their roles and experience, an estimate of their time input into each task and CVs of all personnel who will be involved in the contract/project; please ensure all CVs MUST be attached as a separate PDF documentation from the proposal, so that we can meet our JNCC GDPR retention policy requirements.

Availability of the Project Team for a start-up meeting to be held virtually.

Overall quote for the contract to include:

  - Day rates for all members of the Project Team.

  - Rates for attending start-up, interim and final meetings in Peterborough or Aberdeen (costs for travel and accommodation are attached and should be used. These rates are analogous to the civil service rates).

  - Costs and time allocation should be clearly allocated to specific tasks within this contract/project; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and if so, provide their VAT registration number.

The following documentation:

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting.

  - Copies of current public and employer liability insurance certificates.

  - Copies of any appropriate risk assessments; and

  - Copies of any environmental policies should you have them.

In addition, note that the bid submission should provide sufficient information to allow assessment against the evaluation criteria outlined in Section 14.

## Evaluation Criteria

JNCC is not bound to accept the lowest priced or any bid. Having the technical expertise and experience to complete the work to a high standard and being able to complete it within the timescale are of the essence for this contract.

The bid evaluation may be undertaken by a panel consisting of JNCC staff and staff members from Natural England, Natural Resources Wales, NatureScot, DAERA-NI and Defra.  Unless otherwise stated in your bid submission, bids will be forwarded to these agencies for evaluation purposes only.

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Maximum Score | Score |
| --- | --- | --- | --- |
| 1. Quality of Bid (50% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal particularly work programme and deliverables | 10 |  |
|  | Understanding of, and relevance to, the requirements in particular the adequacy of outputs and understanding of stakeholder engagement and communications principles, Caribbean biodiversity, and challenges to conservation. | 10 |  |
|  | Soundness and logicality of methods | 5 |  |
|  | Realism and measurability of outputs | 5 |  |
|  | Evidence provided of how accessibility standards will be met | 5 |  |
|  | Identification and proposed solutions to potential risks/issues | 5 |  |
|  | Serious weaknesses which threaten success | 5 |  |
|  | Probability of success | 5 |  |
|  | Sub Total | 50 |  |
| 2. Details of Contractor (20% of the total for the three assessment categories) |  |  |  |
|  | Expertise, experience, and balance of team | 9 |  |
|  | Risks if important team members drop out | 5 |  |
|  | Adequacy of subcontractors if any | 6 |  |
|  | Sub Total | 20 |  |
| 3. Cost (30% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation what does presentation mean here in relation to cost? | 10 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 6 |  |
|  | Appropriateness of ratio of senior to junior staff time | 6 |  |
|  | Clarity of each team member’s contribution and value added | 8 |  |
|  | Sub Total | 30 |  |
| Total Score |  | 100 |  |

## Payment

Unless a payment schedule is stated in your submission and agreed by JNCC project manager. Payment will be made on completion of the outputs stated below following the submission of invoice(s) and based on the satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

    - On satisfactory completion of vector infographic, expected to be 9th January 2023; and

    - On satisfactory completion of the final output, expected 23rd February 2023.

## Additional Requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key outputs.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates/fees given.

The bidder is expected to supply all necessary equipment, software, licences, etc. to carry out the obligations required under the contract.

## References

Beck, M. W., Losada, I. J., Menéndez, P., Reguero, B. G., Díaz-Simal, P. and Fernández, F. (2018) 'The global flood protection savings provided by coral reefs', Nature communications, 9(1), pp. 1-9.

Beck, M. W., Torres-Ortega, S., Losada, I., Narayan, S. and Menéndez, P. (2020) 'the Global flood protection Benefits of Mangroves'.

Bellard, C., Bertelsmeier, C., Leadley, P., Thuiller, W. & Courchamp, F. 2012. Impacts of climate change on the future of biodiversity. Ecology letters, 15, 365-377.

Brown, N. 2008. Climate change in the UK Overseas Territories: An Overview of the Science, Policy and You. Peterborough,UK: Joint Nature Conservation Committee

Martinez, M. L., Silva, R., Lithgow, D., Mendoza, E., Flores, P., Martínez, R. and Cruz, C. (2017) 'Human impact on coastal resilience along the coast of Veracruz, Mexico', Journal of Coastal Research, (77), pp. 143-153.