- Request for Quotation

Testing problem solving in response to Protected Area pressures

17 June 2024

- Request for Quotation:

Testing problem solving in response to Protected Area pressures

You are invited to submit a quotation for the requirement described in the specification, Section 2. Please confirm by email, receipt of these documents and whether you intend to submit a quote or not.

Your response should be returned to the following email address by the date shown:

Email: jennifer.mailley@naturalengland.org.uk

Date: 09/07/2024

Time: 12 noon

Ensure you include the name of the quotation and ‘Final Submission’ in the email subject field to make it clear that it is your response.

Contact Details and Timetable

Jennifer Mailley will be your contact for any questions linked to the content of the quote or the process. Please submit any clarification questions via email and note that, unless commercially sensitive, both the question and the response will be circulated to all tenderers.

| Action | Date |
| --- | --- |
| Date of issue of RFQ | 17-06-2024 at 23:55 BST / GMT |
| Deadline for clarifications questions | 02-07-2024 at 23:55 BST / GMT |
| Deadline for receipt of Quotation | 09-07-2024 at 23:55 BST / GMT |
| Intended date of Contract Award | 12-07-2024 |
| Intended Contract Start Date | 15-07-2024 |
| Intended Delivery Date / Contract Duration | 31-03-2025 |

- Section 1: General Information

Glossary

Unless the context otherwise requires, the following words and expressions used within this Request for Quotation shall have the following meanings (to be interpreted in the singular or plural as the context requires):

| “Authority” | means Natural England who is the Contracting Authority. |
| --- | --- |
| “Contract” | means the contract to be entered into by the Authority and the successful supplier. |
| “Response” | means the information submitted by a supplier in response to the RFQ. |
| “RFQ” | means this Request for Quotation and all related documents published by the Authority and made available to suppliers. |

Conditions applying to the RFQ

You should examine your Response and related documents ensuring it is complete and in accordance with the stated instructions prior to submission.

Your Response must contain sufficient information to enable the Authority to evaluate it fairly and effectively. You should ensure that you have prepared your Response fully and accurately and that prices quoted are arithmetically correct for the units stated.

By submitting a Response, you, the supplier, are deemed to accept the terms and conditions provided in the RFQ. Confirmation of this is required in Annex 2.

Failure to comply with the instructions set out in the RFQ may result in the supplier’s exclusion from this quotation process.

Acceptance of Quotations

By issuing this RFQ the Authority does not bind itself to accept any quotation and reserves the right not to award a contract to any supplier who submits a quotation.

Costs

The Authority will not reimburse you for any costs and expenses which you incur preparing and submitting your quotation, even if the Authority amends or terminates the procurement process.

Self-Declaration and Mandatory Requirements

The RFQ includes a self-declaration response (Annex 1) which covers basic information about the supplier, as well as any grounds for exclusion. If you do not comply with them, your quotation will not be evaluated.

Any mandatory requirements will be set out in Section 2, Specification of Requirements and, if you do not comply with them, your quotation will not be evaluated.

Clarifications

Any request for clarification regarding the RFQ and supporting documentation must be submitted via email no later than the deadline for clarifications set out in the Timetable. The Authority shall be under no obligation to respond to queries raised after the clarification deadline.

The Authority will respond to all reasonable clarifications as soon as possible but cannot guarantee a minimum response time. The Authority will publish all clarifications and its responses to all suppliers via email unless deemed commercially sensitive.

If a supplier believes that a request for clarification is commercially sensitive, it should clearly state this when submitting the clarification request. However, if the Authority considers either that:

the clarification and response are not commercially sensitive; and

all suppliers may benefit from its disclosure,

then the Authority will notify the supplier (via email), and the supplier will have an opportunity to withdraw the request for clarification by sending a further message requesting the withdrawal of the clarification request. If not withdrawn by the supplier within 2 working days of the Authority’s notification, the Authority may publish the clarification request and its response to all suppliers and the Authority shall not be liable to the supplier for any consequences of such publication.

The Authority reserves the right to seek clarification of any aspect of a quotation and/or provide additional information during the evaluation phase to carry out a fair evaluation. Where the Authority seeks clarification on any aspect of the quotation, the supplier must respond within the timeframe requested by the Authority.

Amendments

The Authority may amend the RFQ at any time prior to the deadline for receipt. If it amends the RFQ the Authority will notify you via email.

Suppliers may modify their quotation prior to the deadline for Responses. No Responses may be modified after the deadline for Responses.

Suppliers may withdraw their quotations at any time by submitting a notice via the email to the named contact.

Conditions of Contract

The Authority’s Standard Good and Services Terms & Conditions (used for purchases under £50k) can be located on the Procurement at Natural England - Natural England - GOV.UK (www.gov.uk)) and will be applicable to any contract awarded as a result of this quotation process. The Authority will not accept any changes to these terms and conditions proposed by a supplier.

Suppliers should note that the quotation provided by the successful bidder will form part of the Contract.

Prices

Prices must be submitted in £ sterling, exclusive of VAT.

Disclosure

All Central Government Departments, their Executive Agencies and Non Departmental Public Bodies are subject to control and reporting within Government. In particular, they report to the Cabinet Office and HM Treasury for all expenditure. Further the Cabinet Office has a cross-Government role delivering overall Government policy on public procurement, including ensuring value for money and related aspects of good procurement practice. For these purposes, the Authority may disclose within Government any details contained in your quotation. The information will not be disclosed outside Government during the procurement.

In addition, the Authority is subject to the Freedom of Information Act 2000 and the Environmental Information Regulations 2004, which provide a public right of access to information held by public bodies. In accordance with these two statutes, the Authority may be required to disclose information contained in your quotation to any person who submits a request for information pursuant to those statutes.

Further to the Government’s transparency agenda, all UK Government organisations must advertise on Contract Finder in accordance with the following publication thresholds:

Central Contracting Authority’s: £12,000

Sub Central Contracting Authority’s and NHS Trusts: £30,000

For the purpose of this RFQ the Authority is classified as a Central Contracting Authority with a publication threshold of £12,000 inclusive of VAT.

If this opportunity is advertised via Contracts Finder, we are obliged to publish details of the awarded contract including who has won the contract, the contract value, and indicate whether the winning supplier is a small and medium-sized enterprise (“SMEs”) or voluntary organisation or charity. A copy of the contract must also be published with confidential information redacted.

By submitting a Response, you consent to these terms as part of the procurement.

Disclaimers

Whilst the information in this RFQ and any supporting information referred to herein or provided to you by the Authority have been prepared in good faith the Authority does not warrant that this information is comprehensive or that it has been independently verified.

The Authority does not:

make any representation or warranty (express or implied) as to the accuracy, reasonableness or completeness of the RFQ;

accept any liability for the information contained in the RFQ or for the fairness, accuracy or completeness of that information; or

accept any liability for any loss or damage (other than in respect of fraudulent misrepresentation or any other liability which cannot lawfully be excluded) arising as a result of reliance on such information or any subsequent communication.

Any supplier considering entering into contractual relationships with the Authority following receipt of the RFQ should make its own investigations and independent assessment of the Authority and its requirements for the goods and/or services and should seek its own professional financial and legal advice.

Protection of Personal Data

In order to comply with the General Data Protection Regulations 2018 the supplier must agree to the following:

You must only process any personal data in strict accordance with instructions from the Authority.

You must ensure that all the personal data that we disclose to you or you collect on our behalf under this agreement are kept confidential.

You must take reasonable steps to ensure the reliability of employees who have access to personal data.

Only employees who may be required to assist in meeting the obligations under this agreement may have access to the personal data.

Any disclosure of personal data must be made in confidence and extend only so far as that which is specifically necessary for the purposes of this agreement.

You must ensure that there are appropriate security measures in place to safeguard against any unauthorised access or unlawful processing or accidental loss, destruction or damage or disclosure of the personal data.

On termination of this agreement, for whatever reason, the personal data must be returned to us promptly and safely, together with all copies in your possession or control.

General Data Protection Regulations 2018

For the purposes of the Regulations the Authority is the data processor.

The personal information that we have asked you provide on individuals (data subjects) that will be working for you on this contract will be used in compiling the tender list and in assessing your offer. If you are unsuccessful the information will be held and destroyed within two years of the award of contracts. If you are awarded a contract it will be retained for the duration of the contract and destroyed within seven years of the contract’s expiry.

We may monitor the performance of the individuals during the execution of the contract, and the results of our monitoring, together with the information that you have provided, will be used in determining what work is allocated under the contract, and in any renewal of the contract or in the award of future contracts of a similar nature. The information will not be disclosed to anyone outside the Authority without the consent of the data subject, unless the Authority is required by law to make such disclosures.

Equality, Diversity & Inclusion (EDI)

The Client is striving to create a diverse and inclusive working environment where every individual has equality of opportunity to progress and to apply their unique insights to making the UK a great place for living. The Service Provider is expected to respect this commitment in all dealings with Natural England staff and service users.

Suppliers are expected to;

support Defra group to achieve its Public Sector Equality Duty as defined by the Equality Act 2010, and to support delivery of Defra group’s Equality & Diversity Strategy.

meet the standards set out in the Government’s Supplier Code of Conduct

work with Defra group to ensure equality, diversity and inclusion impacts are addressed (positive and negative) in the goods, services and works we procure, barriers are removed and opportunities realised.

Sustainable Procurement

Addressing global sustainability impacts and realising additional community benefits within commercial activity is core to Defra group’s approach, working with its supply chain is key to achieving sustainable outcomes. In addition to supporting Defra group to meet its outcomes we look to understand and reduce negative sustainability impacts associated with our commercial activity and realise benefits.

The Client encourages its suppliers to share these values, work to address negative impacts and realise opportunities, measure performance and success.

Suppliers are expected to have an understanding of the Sustainable Development Goals, the interconnections between them and the relevance to the Goods, Services and works procured on the Client’s behalf

Conflicts of Interest

The concept of a conflict of interest includes but is not limited to any situation where an Involved Person or Relevant Body has directly or indirectly, a financial, economic or other personal interest which might be perceived to compromise their impartiality and independence in the context of the procurement procedure and/or affect the integrity of the contract award.

We expect suppliers to mitigate appropriately against any real or perceived conflict of interest through their work with government. A supplier with a position of influence gained through a contract should not use that position to unfairly disadvantage any other supplier or reduce the potential for future competition

Where the supplier is aware of any circumstances giving rise to a conflict of interest or has any indication that a conflict of interest exists or may arise you should inform the Authority of this as soon as possible (whether before or after they have submitted a quotation). Tenderers should remain alert to the possibility of conflicts of interest arising at all stages of the procurement and should update the Authority if any new circumstances or information arises, or there are any changes to information already provided to the Authority. Failure to do so, and/or to properly manage any conflicts of interest may result in a quotation being rejected.

Provided that it has been carried out in an open, fair and transparent manner, routine pre-market engagement carried out by the Authority should not represent a conflict of interest for the supplier.

Section 2: The Invitation

Specification of Requirements

Background to Natural England

Natural England is the government’s advisor on the natural environment. We provide practical advice, grounded in science, on how best to safeguard England’s natural wealth for the benefit of everyone.

Natural England also manage a number of geographical areas collectively referred to as Protected Sites. Types of Protected Sites include Sites of Special Scientific Interest (SSSIs), Special Areas of Conservation (SACs), Special Protection Areas (SPAs) and Ramsar sites. They contain some of our most important habitats, species and geology, and many also contain some form of public access.

Pressures on Protected Sites

Protected Sites suffer from pressures on their biodiversity. Many pressures are caused by human behaviour. They range from on-site pressures such as dogs not on their leads disturbing wildlife, to pressures caused off-site such as water polluted from farm run-off reaching the site via streams or rivers that flow around or through them.

Natural England’s on the ground presence on Protected Sites, area teams, have a dual remit to protect and restore nature on sites, and the aim of encouraging ongoing public engagement with nature. As part of the broad remit of protecting nature, they aim to decrease, prevent and/or mitigate the pressures affecting their sites. Area teams are responsible for specific geographical areas and so are well placed to observe and record pressures, and to trial place-based interventions that might decrease or prevent the harms caused by pressures.

Overall aim of the project

The aim of the project is to test a problem-solving method from the discipline of Environmental Criminology, depicted by the acronym SARA (scanning, analysis, response and assessment), or methods very similar to SARA. This will be achieved by working with one area team as a case study, to assess what the SARA process might add to current operations on Protected Sites in preventing and/or decreasing site pressures.

It is envisaged that the process of leading one team through key stages of SARA for a defined few pressures will reveal specific gaps in current processes, knowledge, and skills which can then inform recommendations for how area teams can be better supported going forwards. The Thames Solent area team has already engaged with the project lead and will be the case study for the project. Thames Solent manage an 8,300 Ha Special Protected Area (SPA) consisting of 13 separate SSIs. The specific pressures to be focused on (pressures of focus) will be decided with the NE team.

Proposed method- SARA

This project forms part of a suite of work to better understand, measure, and ultimately decrease protected site pressures. The project will assess the usefulness and relevance of the problem-solving SARA method or a closely related problem-solving concept. In what follows, the acronym SARA is used to refer to a problem-solving methodology but the precise model used may be a close relation to SARA or an adaptation it

SARA is rooted in environmental criminology and is routinely used to assess various types of harm to society, and has recently been successfully applied by some academic-practitioner partnerships to harms to wildlife (e.g. Panthera (2022) describes how SARA was used to help address Leopard poaching in Western Zambia, where fake skins have been co-designed with skin users to decrease pressure on leopard populations). However, the precise utility of SARA to Natural England area teams remains unclear and this project aims to assess that utility. Part of assessing its usefulness is to assess where current systems and processes map to SARA stages, in which case there is no need to reinvent the wheel, and where there remain gaps which need to be filled in order for problem-solving to be more fruitfully carried out.

Theoretically, SARA could be applied to commonly encountered types of pressure such as recreational harms like littering, wildlife disturbance by people letting their dogs off leads when signage requests that they do not do so. It could also be applied to less frequent pressure such as wildfires, or to pressures which originate off-site such as water pollution from farm run-off. The successful applicants to this opportunity will be able to decide with Thames Solent which of their pressures are best suited for focused attention, after the scanning stage, but the ideal is that at least one pressure caused on-site and one caused off-site be assessed so that the limitations of SARA are explored.

Key stages to the project

Scanning: a scan of the pressures affecting Thames Solent carried out by methods proposed by the applicants, in line with problem-solving principles. It is envisaged that there will be imperfect data (for example about the frequency of harmful events, or limitations to the geographic or temporal resolution of baseline data on biodiversity). Therefore, the successful applicants will most likely workshop with Thames Solent to decide which pressures to focus on for the remainder of the project, and would ideally help to inform how to make such decisions in the face of uncertainty.

Analysis: more detailed analysis of the extent and nature of at least two types of pressure agreed with Thames Solent, using the data available from Thames Solent and any other available sources. Ideally this stage will help to reveal how data recording might be improved to better enable future analysis of pressure intensity and/or harms caused by those pressures.

Response: while the timelines of the project probably do not realistically allow for the design and implementation of any novel responses to the pressures of focus, the project should aim to assess and recommend which types of responses are most likely to be effective. The body of knowledge used should include the body of literature from the field of crime prevention/ Crime Science. A literature review of the evidence base from conservation on ‘what works’ to reduce pressures from human recreation is underway, and the results will be available during this project. This project will ideally also help make recommendations regarding implementation and how to maximise the likelihood of successful implementation, where relevant evidence can help inform those recommendations.

Assessment: the timelines of the project do not realistically allow for the rigorous assessment of any novel interventions, but should aim to produce a plan for how to assess what is effective, and to work with Thames Solent to develop concepts such as Theory of change for the priority pressures and associated responses, taking in to account the data available (e.g. ranger hours spent on dog walker patrols).

While these stages have been suggested, applications with variations of these will be considered so long as there is justification for the variation and clearly identified benefits.

Any successful applications will clearly show how their proposed approach to the project would:

- Identify ways of improving the current and future measurement of pressures on the SPA.

- Assist with the strategic prioritisation of pressures in the absence of perfect data.

- Help identify promising or proven evidence-based ways to reduce one or two pressures  of focus affecting the Thames Solent SPA .

- Improve measurement of response effectiveness by providing plans of what data would be needed to measure and evaluate activities and impact, for each of the pressures of focus.

- At each stage, work closely with Thames Solent to share knowledge and to assess what they found useful and what was not, in order to inform where SARA and related concepts might fill current gaps and where it is not needed.

- Where possible, compare what SARA or a similar problem-solving method achieved that  ‘behaviour change’ models might not.

Practical considerations

The total budget for this project is a maximum of £50,000 (excluding VAT)

The Thames Solent team are engaged with the idea of testing SARA and learning from being led through its stages, and fundamentally the successful contractor will work with Thames Solent throughout the project to in effect mentor them through the problem-solving process. Face to face workshops should form some part of the successful application. It is the responsibility of the successful applicant to factor in their travel costs within the overall budget available for this project.

The overall team will consist of the successful contractor, Thames Solent area team, and the NE project lead Dr Jen Mailley (senior specialist, social science), with both Thames Solent and the project lead being involved in co-creation of the final project stages, timing and design.

The project will be overseen by a steering group who will meet two to three times over the project duration, and consist of Lorna Shaw (senior advisor, Protected Sites), Ruth Shelton (Thames Solent manager) and a member of NE’s responsible recreation network.

Timing and deadlines for the work

The work needs to commence by mid-September 2024 and be completed by the end of March 2025.

| Key milestones | Dates due by |
| --- | --- |
| Kick off meeting | By end July 2024 |
| Draft report on ‘scanning’ stage and agreement on pressures of focus | By 30 September 2024 |
| All workshops completed (e.g. scanning workshop, analysis workshop, response design workshop) | By 15 February 2025 |
| Draft report for comment by NE | 15 March 2025 |
| Final report | 24 March 2025 |
| Final presentation to NE | By 31 March 2025 |

Deliverables

The overarching requirement of the project is to lead Thames Solent through the process of problem-solving using SARA or a development thereof, as depicted above. The primary deliverable is a final report for NE internal use, consisting of the topics covered below which it is envisaged will be covered by the logical process of working through a problem-solving process with Thames Solent.

Deliverable 1: Report for NE internal use, partly informed by face-to-face workshops

The priority deliverable is a report for NE internal use, writing up the findings from each stage of the SARA (or SARA-like) process, that includes the topics detailed below. The project team is open to discussion on whether a report format is the most suitable for each of these deliverables and alternatives would be considered.

Face to face workshops should form some part of the sub-deliverables to achieve the overall aim of the project. The precise nature, topics to be covered and timing of these can be agreed with the wider project team (Thames Solent and NE social science lead), so are not stipulated here.

Topics to include in the final report: Note that the final report may not follow this same format and may for example have sections on key useful literature and evidence, useful tools and methods, and then the specific case study of working with Thames Solent.

- Scanning: A systematic analysis of the pressures faced across the SPA with options for prioritising these in the absence of perfect data.

- Analysis: A detailed analysis of at least two different pressures on the SSIs chosen. One pressure will be caused off site (e.g. water pollution by farm run off) and one caused on-site (e.g. recreational disturbance).

- Response and assessment:

  - A rapid evidence-review or summary of key evidence from the crime prevention/crime science literature about the mechanisms and approaches which work to decrease relevant harms in a place-based context. Relevant harms refers to harms with parallels to the pressures of focus. This may also include explanations of other tools, theories or frameworks which would probably be useful in future work with area teams.

  - A menu of evidence-based choices about how to respond to and decrease the pressures of focus - choices of response will either be evidence-based where a rapid evidence review reveals promising methods, or theory driven in the absence of evidence-based responses.

  - A plan for how to assess what is effective for the pressures of focus, taking in to account the data available (e.g. ranger hours spent on dog walker patrols) and a realist approach needed in evaluation in the field (i.e. which works with the best available evidence given non-perfect experimental designs).

- A gap analysis resulting in recommendations for changes to practices including data recording and training, so that lessons learnt from the project can be shared and implemented where useful.

Deliverable 2: Peer reviewed paper co-authored with NE staff including the social science lead (Dr Jen Mailley) and Thames Solent staff

It is envisaged that the project will result in a joint-authored paper between the successful applicant and NE staff, for publication in a peer reviewed journal relevant to crime science. It may be that there is also scope for another paper aimed at conservation practitioners as well. Those publications can be completed after the final report deadline of end of financial year 2024/25 but can be started as part of the project and be based on the final report for NE.

Deliverable 3: final presentation of key findings to NE on the final report

This presentation typically forms the final main interaction between NE and contractors, and allows the results of the project to be disseminated to a wider audience than the immediate NE team. It is usually online and towards the end of the financial year to coincide with the final report submission.

Requirements of contractors

Natural England is looking for contractors with significant expertise in the field of problem-solving methodologies, up to date knowledge on the evidence about effectiveness in decreasing place-based harm, and practical experience of working with teams who are tasked with decreasing place-based harms such as unwanted or criminal behaviour.

Applicants will be expected to demonstrate:

- a track record in delivering high quality research on problem-solving and its application.

- primary and secondary research expertise relating to the methods proposed.

Sustainability

Natural England protects and improves the environment and is committed to reducing the sustainability impacts of its activities directly and through its supply chains. We expect the Contractor to share this commitment and adopt a sound, proactive sustainable approach in keeping with the 25 yr environmental plan/our commitments compliant with all applicable legislation. This includes understanding and reducing direct and indirect sustainability impacts and realising opportunities, including but not restricted to; resilience to climate change, reducing greenhouse gas emissions, water use and quality, biosecurity, resource efficiency and waste, reducing the risk of pollution, biodiversity, modern slavery and equality, diversity & inclusion, negative community impacts.

As a delivery partner, the successful contractor is expected to pursue sustainability in their operations, thereby ensuring the Contracting Authority is not contracting with a supplier whose operational outputs run contrary to the Contracting Authority’s objectives.

Outputs and Contract Management

The project will be managed by a contract manager with oversight from a steering group. We envisage fortnightly updates through email and/or teams calls with the project manager (Dr Jen Mailley, Social Science) and two to three online meetings with the steering committee to support the research and enable use of the research for internal and external influencing.

| Key milestones | Dates due by |
| --- | --- |
| Kick off meeting | By end July 2024 |
| Draft report on ‘scanning’ stage and agreement on pressures of focus | By 30 September 2024 |
| All workshops completed (e.g. scanning workshop, analysis workshop, response design workshop) | By 15 February 2025 |
| Draft report for comment by NE | 15 March 2025 |
| Final report | 24 March 2025 |
| Final presentation to NE | By 31 March 2025 |

Payment

The Authority will raise purchase orders to cover the cost of the services and will issue to the awarded supplier following contract award.

The Authority’s preference is for all invoices to be sent electronically, quoting a valid Purchase Order number.  This will take place after the workshop, draft report and when the final report has been submitted and approved.

It is anticipated that this contract will be awarded for a period of up to 9 months to end no later than March the 31st. Prices will remain fixed for the duration of the contract award period. We may at our sole discretion extend this contract to include related or further work. Any extension shall be agreed in writing in advance of any work commencing and may be subject to further competition.

Evaluation Methodology

We will award this contract in line with the most economically advantageous tender (MEAT) as set out in the following award criteria:

Technical – 70%

Commercial – 30%

Evaluation criteria

Evaluation weightings are 70% technical and 30% commercial, the winning tenderer will be the highest scoring combined score.

| Award Criteria | Weighting (%) | Evaluation Topic & Weighting | Sub-Criteria | Weighted Question |
| --- | --- | --- | --- | --- |
| Technical | 70% | Service / Product Proposal | Team skills and experience | Q1.1 Provide details of the experience, knowledge and skills of the proposed team and the team structure that you intend to use to deliver the project? (40% of technical score available) Q1.2 How much time (days) will each staff member spend on the project and on which aspects? (10% of technical score available) |
|  |  |  | Methodology | Q2 What methodology (research and analysis) and approaches will you use to deliver the requirements of this project. (40% of technical score available) |
|  |  |  | Research management capacity | Q3.1 What assurances do you have in relation to ensuring delivery on time, risk management, quality assurance, research ethics and data management? (10% of technical score available) |
| Commercial | 30% | Whole life cost of the proposed Contract | Commercial Model | Q4 (100% of commercial score available) |

Technical (70%)

Technical evaluations will be based on responses to specific questions covering key criteria which are outlined below.  Scores for questions will be based on the following:

| Description | Score | Definition |
| --- | --- | --- |
| Very good | 100 | Addresses all the Authority’s requirements with all the relevant supporting information set out in the RFQ. There are no weaknesses and therefore the tender response gives the Authority complete confidence that all the requirements will be met to a high standard. |
| Good | 70 | Addresses all the Authority’s requirements with all the relevant supporting information set out in the RFQ. The response contains minor weaknesses and therefore the tender response gives the Authority confidence that all the requirements will be met to a good standard. |
| Moderate | 50 | Addresses most of the requirements with most of the relevant supporting information set out in the RFQ. The response contains moderate weaknesses and therefore the tender response gives the Authority confidence that most of the requirements will be met to a suitable standard. |
| Weak | 20 | Substantially addresses the requirements but not all and provides supporting information that is of limited or no relevance or a methodology containing significant weaknesses and therefore raises concerns for the Authority that the requirements may not all be met. |
| Unacceptable | 0 | No response or provides a response that gives the Authority no confidence that the requirement will be met. |

Technical evaluation is assessed using the evaluation topics and sub-criteria stated in the Evaluation Criteria section above.

Separate submissions for each technical question should be provided and will be evaluated in isolation. Tenderers should provide answers that meet the criteria of each technical question.

| Team skills and experience | Detailed Evaluation Criteria |
| --- | --- |
| Q1.1 Provide details of the experience, knowledge and skills of the proposed team and the team structure that you intend to use to deliver the project? Please outline - The team's past contributions that best evidence their ability to carry out the proposed project - Examples of previous outputs (provide links or DOI) - Other relevant skills, such as managing research, experience of applied and policy-related research, data management, and writing Responses should not exceed two sides of A4 (excluding CV's), and use Arial font, size 11. | Your response should demonstrate the team has: - Relevant research and analytical experience and skills and institutional track record to deliver this research project to a high standard. - Sufficient knowledge and understanding of social accountability research and practice - Produced high quality, accessible, user-friendly outputs, including reports for non-academic audiences |
| Q1.2 How much time will each staff member spend on the project and on which aspects? Responses should not exceed one side of A4, and use Arial font, size 11. | Referring to the tasks/activities outlined, your response should demonstrate: - Sufficient time allowed for each stage and task - Staff with appropriate level of experience and knowledge involved in each stage and task |

| Method | Detailed Evaluation Criteria |
| --- | --- |
| Q2.1 What methodology (research and analysis) and approaches will you use to deliver the requirements of this project. Responses should not exceed four sides of A4, and use Arial font, size 11. | Your response should - Demonstrate a clear understanding of the nature of the requirements. - Be a clear, practical, achievable, and cost-effective methodology to deliver these requirements that includes an outline of appropriate analytical approaches. - Have information in sufficient detail to allow a full appraisal of the suitability of the approach to deliver for the project. |

| Research methods capacity | Detailed Evaluation Criteria |
| --- | --- |
| Q3.1 What assurances do you have in relation to ensuring delivery on time, risk management, quality assurance, research ethics and data management? Responses should not exceed 1 side of A4, and use Arial font, size 11. | Your response should ideally include a proposed gantt chart, and to briefly indicate: - How the project will be managed, by whom, and what measures will ensure successful delivery. - Risks to project delivery and how you would mitigate these including staff continuity in case of any unforeseen absences and risks around identifying suitable case studies - How your institution will assure the quality of the delivery and outputs - Any ethics processes your organisation has and any research ethics considerations that might apply to this project |

Commercial (30%)

The Contract is to be awarded as a schedule of rates which will be paid according to the completion of the deliverables stated in the Specification of Requirements.

Suppliers are required to submit a total cost to provide the deliverables stated in the Specification of Requirements. In addition to this the Commercial Response template must be completed to provide a breakdown of the whole life costs against each deliverable used in the delivery of this requirement.

Calculation Method

The method for calculating the weighted scores is as follows:

Commercial

Score =  (Lowest Quotation Price / Supplier’s Quotation Price ) x 70% (Maximum available marks)

Technical

Score = (Bidder’s Total Technical Score / Highest Technical Score)  x 30%  (Maximum available marks)

The total score (weighted) (TWS) is then calculated by adding the total weighted commercial score (WC) to the total weighted technical score (WT): WC + WT = TWS.

Information to be returned

Please note, the following information requested must be provided. Incomplete tender submissions may be discounted.

Please complete and return the following information:

completed Commercial Response template

separate response submission for each technical question (in accordance with the response instructions)

completed Mandatory Requirements (Annex 1)

completed Acceptance of Terms and Conditions (Annex 2)

Award

Once the evaluation of the Response(s) is complete all suppliers will be notified of the outcome via email.

The successful supplier will be issued the contract, incorporating their Response, for signature. The Authority will then counter sign

- Annex 1 Mandatory Requirements

Part 1 Potential Supplier Information

Please answer the following self-declaration questions in full and include this Annex in your quotation response.

Part 1.1 Potential Supplier Information:

| Question no. | Question | Response |
| --- | --- | --- |
| 1.1(a) | Full name of the potential supplier submitting the information |  |
| 1.1(b) | Registered office address (if applicable) |  |
| 1.1(c) | Company registration number (if applicable) |  |
| 1.1(d) | Charity registration number (if applicable) |  |
| 1.1(e) | Head office DUNS number (if applicable) |  |
| 1.1(f) | Registered VAT number |  |
| 1.1(g) | Are you a Small, Medium or Micro Enterprise (SME)? | (Yes / No) |

Note: See EU definition of SME https://ec.europa.eu/growth/smes/business-friendly-environment/sme-definition_en

Part 1.2 Contact details and declaration

By submitting a quotation to this RFQ I declare that to the best of my knowledge the answers submitted and information contained in this document are correct and accurate.

I declare that, upon request and without delay you will provide the certificates or documentary evidence referred to in this document.

I understand that the information will be used in the selection process to assess my organisation’s suitability to be invited to participate further in this procurement.

I understand that the authority may reject this submission in its entirety if there is a failure to answer all the relevant questions fully, or if false/misleading information or content is provided in any section.

I am aware of the consequences of serious misrepresentation.

| Question no. | Question | Response |
| --- | --- | --- |
| 1.2(a) | Contact name |  |
| 1.2(b) | Name of organisation |  |
| 1.2(c) | Role in organisation |  |
| 1.2(d) | Phone number |  |
| 1.2(e) | E-mail address |  |
| 1.2(f) | Postal address |  |
| 1.2(g) | Signature (electronic is acceptable) |  |
| 1.2(h) | Date |  |

Part 2 Exclusion Grounds

Part 2.1 Grounds for mandatory exclusion

| Question no. | Question | Response |
| --- | --- | --- |
| 2.1(a) | Please indicate if, within the past five years you, your organisation or any other person who has powers of representation, decision or control in the organisation been convicted anywhere in the world of any of the offences within the summary below. |  |
|  | Participation in a criminal organisation. | (Yes / No) If yes please provide details at 2.1 (b) |
|  | Corruption. | ((Yes / No) If yes please provide details at 2.1 (b) |
|  | Fraud. | (Yes / No) If yes please provide details at 2.1 (b) |
|  | Terrorist offences or offences linked to terrorist activities | (Yes / No) If yes please provide details at 2.1 (b) |
|  | Money laundering or terrorist financing | (Yes / No) If yes please provide details at 2.1 (b) |
|  | Child labour and other forms of trafficking in human beings | (Yes / No) If yes please provide details at 2.1 (b) |
| 2.1(b) | If you have answered yes to question 2.1(a), please provide further details. Date of conviction, specify which of the grounds listed the conviction was for, and the reasons for conviction. Identity of who has been convicted If the relevant documentation is available electronically please provide the web address, issuing authority, precise reference of the documents. |  |
| 2.1 (c) | If you have answered Yes to any of the points above have measures been taken to demonstrate the reliability of the organisation despite the existence of a relevant ground for exclusion? (i.e. Self-Cleaning) | (Yes / No) |
| 2.1(d) | Has it been established, for your organisation by a judicial or administrative decision having final and binding effect in accordance with the legal provisions of any part of the United Kingdom or the legal provisions of the country in which the organisation is established (if outside the UK), that the organisation is in breach of obligations related to the payment of tax or social security contributions? | (Yes / No) |
| 2.1(e) | If you have answered yes to question 2.3(a), please provide further details. Please also confirm you have paid or have entered into a binding arrangement with a view to paying, the outstanding sum including where applicable any accrued interest and/or fines. |  |

Part 2.2 Grounds for discretionary exclusion

| Question no. | Question | Response |
| --- | --- | --- |
| 2.2(a) | The detailed grounds for discretionary exclusion of an organisation are set out on this webpage, which should be referred to before completing these questions. Please indicate if, within the past three years, anywhere in the world any of the following situations have applied to you, your organisation or any other person who has powers of representation, decision or control in the organisation |  |
| 2.2(b) | Breach of environmental obligations? | (Yes / No) If yes please provide details at 2.2 (f) |
| 2.2(c) | Breach of social obligations? | (Yes / No) If yes please provide details at 2.2 (f) |
| 2.2(d) | Breach of labour law obligations? | (Yes / No) If yes please provide details at 2.2 (f) |
| 2.2(e) | Shown significant or persistent deficiencies in the performance of a substantive requirement under a prior public contract, a prior contract with a contracting entity, or a prior concession contract, which led to early termination of that prior contract, damages or other comparable sanctions? | (Yes / No) If yes please provide details at 2.2 (f) |
| 2.2 (f) | If you have answered Yes to any of the above, explain what measures been taken to demonstrate the reliability of the organisation despite the existence of a relevant ground for exclusion? (Self Cleaning) |  |

- Annex 2 Acceptance of Terms and Conditions

I/We accept in full the terms and conditions appended to this Request for Quote document.

Company ____________________________________________________

Signature ____________________________________________________

Print Name ____________________________________________________

Position ____________________________________________________

Date ____________________________________________________

A literature review of the evidence base from conservation on ‘what works’ to reduce pressures from human recreation is underway, and the results will be available during this project.