## Sheet1
ARMYHQ2/00279 - VERITAS ENDURING IT SUPPORT-KEY PERFORMANCE INDICATORS (KPI) - See SC2 (Edn 11/17) Condition 50
KPI Ref | Ref | Description | MOD Dependancies | Delivery Measures | Satisfaction measures |  |  | Evidence | Review Period | MOD Monitor (Authority)
[5 empty] | Satisfactory Performance | Sub Standard Performance | Performance Failure
[5 empty] | GREEN | AMBER | RED
1 | Appendix 1 to Annex A to Schedule 2; 3.1 | The Contractor must produce and maintain a robust Issues Log covering Reporting and Prioritisation. | MOD to set priorities for Issues management. | Receipt of issue to be confirmed within 1 working day. Feedback on issue to be provided (to requester) within 3 working days. (Including resolution plan) | Delivery Measures met 95% or above all issue raised per Month | Delivery Measures met less than 95% but more than 70% for all issue raised per Month | Delivery Measures met less than 70% for all issue raised per Month | Taken directly from the system. Every month the Authority will look at all issues raised over that month to the contractor and the assement will be based on the totality again the stated percentages. | Monthly | Bus Imp Team
2a | Appendix 1 to Annex A to Schedule 2; 4.2 4.2.1 4.2.2 4.2.3 4.2.4 4.2.5 4.2.6 4.2.7 4.2.9 4.2.12 4.2.14 Annex A to Schedule 2; Paragraph 29.e | The Contractor must provide all release related documentation covered under Appendix 1 to Annex A to Schedule 2, 4.2 and Annex A to Schedule 2; Paragraph 29.e within the agreed timeframe. | MOD to review documentation within stated period and provide feedback. | Final version of the documentation, ensuring all comments have been incorporated, received by the Authority in line with the agreed Support plan. | All documents received within 2 working days of agreed date | Documents received between 3 and 7 working days of agreed date. | Documents received beyond 7 working days of agreed date. | The Authority will log each document on date of provision and assess it against Support Plan SOR Reference 1.2 dates. This timescale must include the time necessary for the Authority to comment, 2 weeks as per Annex A to Schedule 2, Paragraph 29.e | As per deliverable | Bus Imp Team
2b | Appendix 1 to Annex A to Schedule 2 4.2 4.2.8 4.2.10 4.2.11 4.2.12 4.2.15 Annex A to Schedule 2; Paragraph 29.e | The Contractor must provide all annual documentation covered under Appendix 1 to Annex A to Schedule 2, 4.2 and Annex A to Schedule 2; Paragraph 29.e within the agreed timeframe. | MOD to review documentation within stated period and provide feedback. | Final version of the documentation, ensuring all comments have been incorporated, received by the Authority in line with the agreed Support plan. | All documents received within 2 working days of agreed date | Documents received between 3 and 7 working days of agreed date. | Documents received beyond 7 working days of agreed date. | The Authority will log each document on date of provision and assess it against Support Plan SOR Reference 1.2 dates. This timescale must include the time necessary for the Authority to comment, 2 weeks as per Annex A to Schedule 2, Paragraph 29.e | As per deliverable | Bus Imp Team
3 | Appendix 1 to Annex A to Schedule 2; 6.6 | The code is delivered to the Authority within the agreed timeframe. | IAS staff availability for taking receipt of the code, testing and loading onto the Authority system | Code is delivered as agreed within the Support Plan | Code is delivered on agreed date | Code is delivered no later than 2 working days of agreed date | Code is delivered after 3 working days of agreed date. | Date of code provision against the Support Plan. | As Per Release | Bus Imp Team
4 | Appendix 1 to Annex A to Schedule 2; 6.6 | The code is tested and working on the Authority system. | Authority staff availability for testing in Pre-Production Environment. | Code runs on the Authority system. | Code runs on the Authority system, with less than 10 errors. | Code runs on the Authority system, with 10 errors or more. | Code will not run on Authority system. | Pre-Prod Testing of delivered capability on Authority system. | As Per Release | Bus Imp Team