Call-Off Schedule 13

Mobilisation Plan and Testing

Training Estate Support Contract

Call-Off SCHEDULE 13

Mobilisation PLAN AND TESTING

- Mobilisation OVERVIEW

Part 4 of Call-Off Schedule 28 (Specification (Statement of Requirement)) sets out the requirement for a Mobilisation Plan to drive mobilisation of the Supplier to perform its obligations under the Contract, as part of the Buyer’s transition from the legacy arrangements and Incumbent Supplier to the new Contract – a minimum of 6 months before ISD.

A draft Mobilisation Plan shall be provided by the Supplier as part of the bid response and agreed with the Buyer in accordance with Paragraph 2.

The Buyer will review the draft Mobilisation Plan and, at the Post Contract Award Meeting, suggest amendments the Supplier shall make to the draft Mobilisation Plan. The draft Mobilisation Plan shall only become the Mobilisation Plan when it has been Approved by the Buyer and appended as Annex A to this Schedule.

Implementation of the Mobilisation Plan shall include six payment Milestones, as set out in the Mobilisation Plan, and priced in Call-Off Schedule 5 (Call-Off Pricing) at Annex A, against which the Supplier can be paid for Deliverables during the Mobilisation Period.

The Deliverables that shall be required from the Supplier during the Mobilisation Period will be reviewed against the Buyer’s Critical Readiness Assurance Documents (the “CRADS”) which can be found in Call-Off Schedule 28 (Specification (Statement of Requirement)), Part 4, Annex 4A.  The CRADS lists:

the critical activities and dates for their achievement against a transition theme or workstream, including activities that the Buyer and Related Suppliers may need to deliver, for which the Supplier is not responsible, and

defines the conditions against which the Deliverables are considered to be capable of Acceptance by the Buyer.

The Supplier shall set out its intended Deliverables within each Milestone (as per Table 1 of Annex A), to include the Buyer’s critical activities, and to add any further work needed to achieve the Mobilisation Plan.

Throughout the Mobilisation Period, the Supplier shall submit its Deliverables as evidence of meeting its Milestones. The Buyer shall consider the Deliverables against the CRADS and approve payment, which shall be subject to the conditions of Call-Off Schedule 5 (Call-Off Pricing).

Formation of Mobilisation Plan

The Supplier shall host a Post Contract Award Meeting, to be held within five (5) Working Days of the Effective Date, unless otherwise required by the Buyer. The Mobilisation Plan will be finalised as early as reasonably practicable after the Effective Date and in any event no later than 10 Working Days after the Effective Date, unless agreed with the Buyer. The draft Mobilisation Plan will be appended as Annex A of this Schedule

The Mobilisation Plan:

- 2.2.1  must contain information at the level of detail necessary to manage the Mobilisation Period effectively and as the Buyer may otherwise require; and

    - must take account of all dependencies known to, or which should reasonably be known to, the Supplier, including the Transferring Contracts exit strategy.

Following receipt of the draft Mobilisation Plan from the Supplier, the Parties shall use reasonable endeavours to agree the contents of the Mobilisation Plan.  If the Parties are unable to agree the contents of the Mobilisation Plan within twenty (20) Working Days of its submission, then such Dispute shall be resolved in accordance with the Dispute Resolution Procedure.

  - The Supplier shall provide each of the Deliverables identified in the Mobilisation Plan by the Milestone Date assigned to that Deliverable item so as to ensure that each Milestone identified in the Mobilisation Plan is Achieved on or before its Milestone Date.

The Supplier shall monitor its performance against the Mobilisation Plan and Milestones and report to the Buyer on such performance.

Mobilisation PROCESS

During the Mobilisation Period, the Incumbent Supplier shall retain full responsibility for all existing services until the In-Service Date or as otherwise formally agreed with the Buyer. The Supplier's full-service obligations shall formally be assumed on the In-Service Date as set out in the Order Form.

In accordance with the Mobilisation Plan, the Supplier shall:

work cooperatively and in partnership with the Buyer, Incumbent Supplier and the Buyer’s other supplier(s), where applicable, to understand the scope of Services to ensure a mutually beneficial handover of the Services;

work with the Incumbent Supplier and the Buyer to assess the scope of the Services and prepare and execute the Mobilisation Plan to mobilise the Services;

make all reasonable endeavours to secure any missing asset data required in support of the Service from the In-Service Date.

In addition, the Supplier shall:

appoint a Supplier Authorised Representative who shall be responsible during the Mobilisation Period for ensuring that the Mobilisation Plan is adequately resourced and executed effectively, and who will act as a point of contact for the Buyer;

mobilise all the Services specified in the Contract at the In-Service Date, or earlier as agreed with the Buyer and the Incumbent Supplier;

construct and maintain a ‘mobilisation risk and issue register’ in conjunction with the Buyer detailing how risks and issues will be effectively communicated to the Buyer in order to avoid or mitigate them;

attend progress meetings (as set out in the Mobilisation Plan) in accordance with the Buyer's requirements during the Mobilisation Period. Mobilisation meetings shall be chaired by the Buyer.  All such meeting minutes shall be kept and published by the Supplier within 5 Working Days of the meeting or as agreed with the Buyer; and

ensure that all risks associated with the Mobilisation Period are minimised to ensure a seamless change of control between the Incumbent Supplier and the Supplier.

- changes to Mobilisation Plan

Changes to any Milestones and Milestone Payments shall only be made in accordance with the Variation Procedure.

Time in relation to compliance with the Mobilisation Plan shall be of the essence and failure of the Supplier to comply with the Mobilisation Plan shall be a material Default for the purposes of Clause 10.4.1 of the Core Terms.

- Interaction with Stakeholders during the mobilisation period

The Supplier shall familiarise itself before the In-Service Date with the Buyer’s Estate and the needs of the End Users and End User representatives (stakeholders).

As a result of the familiarisation, the Supplier shall ensure that it is appropriately equipped to deal with the level of liaison and stakeholder management required, to include, but not be limited to:

liaison;

reporting;

co-ordination and provision of services;

attendance at meetings; and

management and resolution of stakeholder issues.

The Supplier shall develop and implement a communications plan, to be agreed with the Buyer, and which shall include the frequency, responsibility for and nature of communication with the Buyer and end users of the Services

By the end of the Mobilisation Period, the Supplier shall ensure that all the necessary arrangements to facilitate the continuous performance of its obligations under the Contract are assessed and implemented.

The Supplier shall, within the Mobilisation Period, undertake a comprehensive examination and evaluation of the Estate, conducting Site visits and inspections to verify asset data where weakness or potential inaccuracy has been identified.

SERVICES DURING THE MOBILISATION PERIOD

During the Mobilisation Period, the Supplier shall refine and agree with the Buyer the details of its Service Delivery Plan.

Any changes to the Service Delivery Plan and resulting changes to Call-Off Schedule 22 (Tender) shall be amended as agreed between the Parties at least thirty (30) days before the In-Service Date.

- ANNEX A: MOBILISATION PLAN

[Mobilisation Plan to be inserted here]

TABLE 1.  MILESTONES

- The Milestones to be achieved are identified below:

| Milestone | Deliverable Items | Milestone Date | Buyer Responsibilities | Milestone Payments [0% of mobilisation cost] |
| --- | --- | --- | --- | --- |
| 1 | Helpdesk facility ready to manage the Service Delivery (ISD) |  |  |  |
| 2 | All Supplier staff training completed to include BAMS, TAROM and MCRT |  |  |  |
| 3 | H&S policy and manual defined, reviewed and agreed with the Authority |  |  |  |
| 4 | Sufficiently functional ICT fit out started to enable performance monitoring and task reporting |  |  |  |
| 5 | BAMS and MCRT functioning and supplier staff identified and posts filled to enable activity to transfer to supplier |  |  |  |
| 6 | Upon mutual agreement of the Mobilisation Plan |  |  |  |