## TQ Spreadsheet
South West Design Services Contract
Query Ref | Document Reference | Nature of Query | Date Query Received | Date Referred | Referred to | Response | Internal Response Date | Date issued to bidders | Formal Amendment Required to Document | Tender Amendment | Tender Amendment Issued (date)
A1 | IfT Doc 3 3.7.5 | IFT Doc 3 includes a market share test in section 3.7.5, however there is no mention of the Design Services contract within the maximum number of contracts a tenderer may be appointed, as it only applies to ASC, MAC and M&R Contracts, which makes this test ineffectual. Could you please confirm how this test will be applied. | 2016-09-29 | 2016-09-29 | C&P (CD) | Market share test is going to be addressed in a tender amendment and will be removed | 2016-10-07 | 2016-10-07 | Yes | TA1 | 2016-10-07
B2 | Quality Submission Answer Book Issue 2 Rev 0 | Can you confirm do we submit the Quality Submission in the Quality Submission Answer booklet provided? If yes, can we include a header and footer? | 2016-09-30 | 2016-09-30 | C&P (PD) | Yes your quality submission must be provided in the quality submission booklet provided. Yes you can include a header and footer if you wish as long as you keep to the page count | 2016-09-30 | 2016-09-30 | N/A | N/A | N/A
B3 | Quality Submission Answer Book Issue 2 Rev 0 | Please could you confirm; a) That the ‘available space’ for each question response in the Answer Book is only provided as an indicative guide to the space that should be allocated to a quality statement? b) That the pages used to restate the individual Quality Statement Risks and Issues (provided for information purposes) are not included within the total page count? | 2016-09-30 | 2016-09-30 | C&P (PD)/OD | This will be a Tender Amendment to Vol 2A. The Quality Answer booklet is set up to allocate tenderers the page limit per process which includes Parts A & B, cross references, covers, title pages, drawings, diagrams, flow charts and annexes. The page limit does not include the question text included in the Quality Submission Answer Booklet template. Please see the revised Vol 2A In TA1 for details | 2016-10-07 | 2016-10-07 | Yes | TA1 | 2016-10-07
B4 | IfT – Vol 2B (Quality Submission B) Issue 3 Rev 0 Para 1.2.8; | 1.2.8 The Contract Overview must also include details of the following information: · Expected number of full time equivalents (FTEs) to deliver the whole of the Services, broken down between design activities and management roles… Please confirm which Staff roles (as listed in Task Schedule Appendix A Time Charge Issue 3 Revision 0 – Worksheet ‘Job Description’) and activities are to be considered as ‘Design’ and which are to be considered as ‘management’? | 2016-09-30 | 2016-09-30 | C&P C | Within the Appendix A Time Charge a tab gives full job descriptions therefore it is up to the tenderer to decide which activities are 'design' and which are 'management' functions | 2016-10-07 | 2016-10-07 | N/A | N/A | N/A
C5 | IfT Doc 1 Tender Process Para 2.6 | TOUR OF OFFICES/DEPOTS: 1. Is this a tour of the offices listed in the documents (Exeter, Saltash and Bristol) rather than the depots as indicated in the tender programme (para 2.7.1)? 2. Will the tour encompass all offices on the same day? 3. What format will the day take? 4. Is there some current uncertainty over the location of the Bristol office? | 2016-09-29 | 2016-09-29 | OD | Highways England has taken the decision to cancel the DSC Depot/Office Tour which was due to take place 17th October 2016. The reasons for this are: There were 3 premises we wished to show tenderers, however negotiations have yet to be concluded for leases on 2 of the 3 sites. We now do not envisage that these negotiations will be completed before the tender return date, so we have taken the decision to cancel the event. We recognise the uncertainty in this circumstance and we are therefore clarifying what information is available and what consequent assumptions you can make. Premises Location Staff Desks Car Spaces Ash House Exeter, EX2 7LB 29 23 see below* Depot between Saltash and Liskeard 4 3 3 North Bristol Office (TBC) Aztec West Bristol 33 26 see below* *Car parking spaces are not assigned to any particular contractor so will first come first serve. This information will be incorporated in the next TA | 2016-10-07 | 2016-10-07 | Yes | TA1 | 2016-10-07
B6 | Extension | Given that the risks and issues have not yet been released for 3 of the quality responses, we request an extension of 3 weeks to the tender period. | 2016-10-03 | 2016-10-03 | OD | The risks you refer to have now been added via TA1. Since the documents have only recently been released your request for a tender extension is denied | 2016-10-07 | 2016-10-07 | Yes | TA1 | 2016-10-07
B7 | Technical Envelope Q2.1.5 and SW DSC IfT - Vol 1B Supporting Information | Technical Envelope Q2.1.5 requests "Evidence of competence for the role and confirming our willingness to act as Principal Designer under the Construction (Design and Management) Regulations 2015." where as point 1.9 page 5 of the SW DSC IfT - Vol 1B Supporting Information states: "Statement confirming willingness, if awarded the contract, to accept the appointment and duties of principal designer" Can you confirm which is correct Q2.1.5 or point 1.9? Do we provide evidence or just a statement? | 2016-10-03 | 2016-10-03 | C&P (PD) | 2.1.5 of the Technical Envelope and 1.9 of Vol 1B are one and the same. The 'Evidence' is your statement that you attach to the technical envelope. | 2016-10-07 | 2016-10-07 | N/A | N/A | N/A
C8 | IfT Vol2A Table 2A.2 | As part of Quality Submission A we note that the "Process Risks" and "Issues to be addressed" for questions 3, 5 and 6 are all "to be issued as a tender amendment". Can you provide an update as to when this tender amendment will be issued to all tenderers please? | 2016-10-04 | 2016-10-04 | OD | Please see B3 & B6 | 2016-10-07 | 2016-10-07 | N/A | N/A | N/A
D9 | Hinckley Nuclear investment programme | We note the recent announcement of the Hinckley Nuclear investment programme, the impact of this project could be such that demand on the resources in the area will be severe which could result in availability ,commercial and cost pressures. This will cut across recruitment and retention of people and procurement of resources. Please can you advise whether these risks are to be included. | 2016-10-05 | 2016-10-05 | OD/C&P (C) | A number of process risks refer to resource, labour, plant and material supply chain shortages and resilience. These risks could potentially occur as a consequence of major infrastructure projects e.g. Hinckley Point Power Station and could be included in your submission. However, there may be other equally valid examples of far lesser scale that tenderers can consider and have good quality practical knowledge and experience and which information can be provided describing how issues / risks occurred and how these were satisfactorily mitigated covering the specific bullet points within the "issues to be addressed" table. | 2016-10-14 | 2016-10-14 | N/A | N/A | N/A
D10 | Indexation Mechanism in Option X1 | We note the Indexation Mechanism in Option X1 for the DSC Contract, and following our assessment of this, we believe that the actual inflation that would be experienced would be significantly higher than that provided for by this mechanism, EARN03 Tab 5 Column K5EY. Could you please advise as to how tenderers should allow for the high likelihood of this risk materialising and therefore under recovery of costs considering the requirements detailed in SW DSC IfT - Vol 3 Commercial Submission clause 1.2.4. | 2016-10-05 | 2016-10-05 | C&P (C) | The index is as stated in the contract and will not be changed. If the tenderer assesses their submission is inadequate within the staff rate table an allowance could be made in table 3 of the business and sub contract overhead build-up document | 2016-10-07 | 2016-10-07 | N/A | N/A | N/A
TC11 | Depot/Offices | Will the design services contractor take the desks you make available or were you saying that any of the differential buyers can take the desks? | 2016-10-04 | 2016-10-04 | OD | Please refer to response to C5. it is for each tenderer to decide how they wish to utilise the provided desks | 2016-10-05 | 2016-10-07 | N/A | N/A | N/A
TC12 | Depot/Offices | So the implication for us is that when our staff are in your offices there is a certain overhead that we would incur. When they are in our offices there is a different overhead. So it is actually important we know what desks are definitively available rather than might be because it has an impact on the commercial approach. | 2016-10-04 | 2016-10-04 | OD | Please refer to response in C5 as this gives clarity of the desks available | 2016-10-05 | 2016-10-07 | N/A | N/A | N/A
TC13 | Renewal Works | You talked about £65,000,000 of renewal work it terms of the stuff that we have got, in terms of the full programme, that tends to be on the capital renewals is that also included designated fund or improvements | 2016-10-04 | 2016-10-04 | OD | The £65M was an indicative works value. Please refer to the OJEU notice and the IfT for the anticipated value of spend through this contract | 2016-10-05 | 2016-10-07 | N/A | N/A | N/A
TC14 | Surveys | on one of the slides (at the tender presentation) reference was made to environmental support including surveys. Do you see that as the primary deliverer of surveys or within Highways | 2016-10-04 | 2016-10-04 | OD | We envisage survey work to be carried out by the DSC via instruction from Highways England | 2016-10-05 | 2016-10-07 | N/A | N/A | N/A
TC15 | Surveys | in reference to TC14 in terms of identifying, scoping by yourselves, surveys by consultants, actual interpretation do you include that within the consultancy agreement. | 2016-10-04 | 2016-10-04 | OD | We are not sure we captured the question correctly, please resubmit as written TQ | 2016-10-05 | 2016-10-07 | N/A | N/A | N/A
TC16 | Principal Designer | Principal designer Role there is a handover from Highways England to the DSC provider what happens at pre construction into construction does the DSC maintain that role? | 2016-10-04 | 2016-10-04 | OD | Yes, it's Highways England's intention that the principal designer role as referenced in CDM will remain with the DSC until completion of the scheme | 2016-10-05 | 2016-10-07 | N/A | N/A | N/A
TC17 | Market Share Test | I noticed in IfT you have a market share test in there can you let us know how that will be applied | 2016-10-04 | 2016-10-04 | C&P (CD/PD) | Please refer to the response to A1 | 2016-10-05 | 2016-10-07 | N/A | N/A | N/A
TC18 | OJEU | The OJEU notice is £25 – £40 million when you look at the detail that’s been provided around the forward programmes it’s a different order of magnitude in terms of the forward programme, how will that be square up. | 2016-10-04 | 2016-10-04 | OD | Please refer to the response to TC13 | 2016-10-05 | 2016-10-07 | N/A | N/A | N/A
TC19 | Forward Programme | If you look at the forward program information that has been provided the pricing does not reach that figure. | 2016-10-04 | 2016-10-04 | OD | Please refer to the response to TC13 | 2016-10-05 | 2016-10-07 | N/A | N/A | N/A
TC20 | Mobilisation | The contracts start at the end of Feb, with a 4 month mobilisation is it possible that we could issue task orders in between that time? Or do we have to wait? | 2016-10-04 | 2016-10-04 | C&P (C) | We do not envisage asking the DSC to carry out any other work other than mobilisation until the 1st July as the existing contracts will still be in place. | 2016-10-05 | 2016-10-07 | N/A | N/A | N/A
TC21 | Quality Part A & B | You mentioned about the marking, can you confirm you mentioned it is possible to score higher in part A and part B | 2016-10-04 | 2016-10-04 | C&P (PD) | It is possible but it will be the lower mark that goes forward, so you might have a not so great approach but lots of evidence to support that approach so you could get an 8 for evidence and a 5 for you approach but it will be the 5 that is taken forward. | 2016-10-05 | 2016-10-07 | N/A | N/A | N/A
TC22 | Risk Register | I saw on Bravo a Risk Register but I did not see it get called for in the OMT/OFT is that right? | 2016-10-04 | 2016-10-04 | C&P (PD) | We are not sure we captured the question correctly, and are unsure which document you refer to. Please can you ldentify the document title and confirm the question via a new TQ | 2016-10-14 | 2016-10-14 | N/A | N/A | N/A
TC23 | Quality Submission Risks | On the subject of Risks, one the new questions that have been introduced the risks are awaited, the teams are eager to get hold of them. Do you have a timescale for releasing the risks | 2016-10-04 | 2016-10-04 | OD | Please refer to the response to B3 & B6 | 2016-10-05 | 2016-10-07 | N/A | N/A | N/A
TC24 | Overheads | Irrespective of any deficit. Pensions any business that has a deficit needs to record it elsewhere, are you happy for it to sit in the business overhead? | 2016-10-04 | 2016-10-04 | C&P (C) | You may make an allowance in your business overhead to recover these costs | 2016-10-05 | 2016-10-07 | N/A | N/A | N/A
TC25 | Overheads | I am just checking you will not fail a validation for this (TC24) | 2016-10-04 | 2016-10-04 | C&P (C) | If you are taken forward to validation all costs must be verifiable | 2016-10-05 | 2016-10-07 | N/A | N/A | N/A
TC26 | Mobilisation | You mentioned on mobilisation and demobilisation of staff if there are costs that would otherwise be expenses do you want to see it in mobilisation and demobilisation or is that just time | 2016-10-04 | 2016-10-04 | C&P (C) | People costs in the Lump Sum pricing need to be in accordance with the schedule of the costs components and include for business overhead, office overhead and profit | 2016-10-05 | 2016-10-07 | N/A | N/A | N/A
TC27 | Mobilisation | For arguments sake let’s say you want to purchase a load of PC’s the intention is that you could put that in there if you wanted to (TC26) | 2016-10-04 | 2016-10-04 | C&P (C) | Please refer to response to TC26 | 2016-10-05 | 2016-10-07 | N/A | N/A | N/A
E28 | Selection Questionnaire 1.8.9 | Selection Questionnaire 1.8.9 'Would your Parent Company be willing to provide a Parent Company Guarantee if necessary' allows only three responses - Yes, No and N/A - no Parent Company. These responses do not cover where the tender is willing to provide a Parent Company Guarantee and is also able to confirm that they pass the financial standing tests detailed in IfT Document 3 (cl.2.4.2, 2.4.3, 2.4.6, 2.4.7 and 2.4.8). Can a further option be added - Yes and pass financial standing test. | 2016-10-07 | 2016-10-07 | C&P (PD) | If you company will be willing to provide a PCG at this stage just answer 'yes' to 1.8.9 of the Selection Questionnaire | 2016-10-07 | 2016-10-07 | N/A | N/A | N/A
E29 | IfT Volume 2B 1.2 Contract Overview | Currently the page count for the Contract Overview is limited to 8 pages (16 sides) and is required to cover the overall management and resourcing of the contract and include key people CVs, role profiles, organisation structure and FTE schedules. To allow tenderers to provide adequate details of their management approach and resources required to support Highways England and the Community to deliver this commission we request that the page limit is increased to 10 pages (20 sides). | 2016-10-07 | 2016-10-07 | OD | Tenderers must remain within the limits defined within the IfT | 2016-10-07 | 2016-10-07 | N/A | N/A | N/A
E30 | Quality Submission Answer Book | A template for Schedule of Reference Projects have been provided in the Answer Book. Please confirm if the Schedule of Reference Projects is included in the page limit of 16 sheets (32 sides). | 2016-10-07 | 2016-10-07 | OD | Please see B3 above | 2016-10-07 | 2016-10-07 | N/A | N/A | N/A
E31 | NEC3 Professional Services Contract | Cl 1.2 requires the Project Bank Account to be provided within 3 weeks of the Contract Date. Can you please advise if there is flexibility in the timeframe of opening the PBA for example to be within the mobilisation period. | 2016-10-07 | 2016-10-07 | C&P (PD) | The PBA will take time and effort to get set up. Numerous parties are involved. The contract needs to be signed before it can be set up. Payments can only be made to the PBA. | 2016-10-07 | 2016-10-07 | N/A | N/A | N/A
E32 | Contract Data Part 1 Clause X1 | In Contract Data Part 1, Option X1 states that the index will be EARN03 but in the IfT Document 3 Clause 3.5.1 (d) states 'An inflationary allowance calculated using the Office for Budget Responsibility (OBR) forecast for inflation over the service period, as published at the base date, applied in accordance with clause X1 of the Conditions of Contract.' For the avoidance of doubt please confirm that for Option X1 the index is EARN03. | 2016-10-07 | 2016-10-07 | C&P (C)/(PD) | The index is EARN03. | 2016-10-07 | 2016-10-07 | N/A | N/A | N/A
E33 | Scope Table 1 | Please confirm that the premises, equipment and facilities supplied by the Employer will be available for use by the Design Services Consultant 24/7 | 2016-10-07 | 2016-10-07 | OD | The Consultant will have 24/7 access to the premises, equipment and facilities of the Northern Office (Bristol Area), Ash House and Depot between Saltash and Liskeard | 2016-10-14 | 2016-10-14 | N/A | N/A | N/A
E34 | Scope Table 1 | Please confirm that the premises, equipment and facilities supplied by the Employer will be provided free of any charges for heating, lighting, business rates, etc. | 2016-10-07 | 2016-10-07 | OD | All utility payments and business rates for the Northern Office (Bristol Area), Ash House and Depot between Saltash and Liskeard will be made by Highways England. All IT hardware, software and specialist equipment is the Consultant's responsibility to provide and maintain. | 2016-10-14 | 2016-10-14 | N/A | N/A | N/A
E35 | Scope Table 1 | Please confirm that suitable, secure and air-conditioned storage accommodation will be provided in the premises supplied by the Employer to house IT equipment (servers). | 2016-10-07 | 2016-10-07 | OD | Provision will be made to accommodate servers at the three locations | 2016-10-14 | 2016-10-14 | N/A | N/A | N/A
E36 | IfT Volume 2B: Quality Submission B | Cl.1.2.7 refers to the submission of role profiles for key people as part of the Contract Overview, would you please confirm role profiles are only required for the General Manager and Commercial Manager roles identified in 1.2.6. | 2016-10-07 | 2016-10-07 | OD | Yes, only these roles are required. | 2016-10-14 | 2016-10-14 | N/A | N/A | N/A
E37 | Task Schedule Appendix A Time Charge Issue 3 Rev 0 | To assist with the completion of the Task Schedule Appendix A Staff Rate Tables for the defined roles can additional information on the qualifications, experience and skills required be added to the Job Descriptions. This would ensure that all tenderers provide rates for staff with similar level of qualifications, skills and experience for each post and would assist the Tender Assessment panel during the evaluation of the financial submission. | 2016-10-07 | 2016-10-07 | OD/CD | The Job Descriptions that have been issued as part of the Appendix A Time Charge will not be amended. | 2016-10-07 | 2016-10-07 | N/A | N/A | N/A
E38 | Contract Data Part 1 Clause X18 | Limitation of Liability (X18) – Following our review of Contract Data Part One we have identified that a limitation of liability provision has not been incorporated which is a widely accepted standard clause. Can you please confirm that this will be included as a Secondary Option? | 2016-10-07 | 2016-10-07 | C&P (C) | Highways England is considering introducing a cap on liability and amending the insurance requirements to reflect any cap. This work is currently underway with our advisers. We invite bids to be submitted on the basis of the current tender documents. Highways England will, on or before 4 November, notify all bidders of its decision on the cap on liability and any changes to the insurance requirements. Tenderers will be given the opportunity to amend their bids and resubmit within a specified timescale. | 2016-10-21 | 2016-10-21 | N/A | N/A | N/A
E39 | Forecast for Forward Programmes | As the level of programmed expenditure in the 5yr Forward Programmes for Area 1 and 2 does not cover all disciplines, is not fully populated for all years and differs from the information provided at the tender conference please provide details of the historic spend on schemes for Area 1 and 2. The incumbents for each area will already have this information available as they will have been responsible for the delivery of the historic scheme programmes. To avoid the incumbents having an unfair advantage over other tenderers please provide a detailed breakdown of the historic spend on schemes for the last three years including the current year by year and activity for both Areas 1 and 2. | 2016-10-07 | 2016-10-07 | OD | Historic data is not necessarily a robust guide to future works programmes. Not only do funding levels change but internal and external guidance changes. In the SW we are currently operating 2 contracts which have specific funding. Therefore we will not be issuing anything further. | 2016-10-21 | 2016-10-21 | N/A | N/A | N/A
E40 | Task Schedule Appendix A and Appendix B | The guidance provided for completion of the Task Schedules in Appendix A and B state that tenderers are not to leave cells blank, where there is no value to be entered a 0 (zero) is to be entered. When a 0 (zero) is entered the auto format alters this to leave the cell blank. Please provide further guidance. | 2016-10-07 | 2016-10-07 | C&P (C) | When a cell is populated in column B (People) of the Appendix B (Task Schedule Lump Sum) then a zero value should not be used as a person in column B will mean a price needs to be entered. If the row has no data in Column B please leave rest of row blank. | 2016-10-14 | 2016-10-14 | N/A | N/A | N/A
E41 | Scope Table 2 | For the premises supplied by the Employer at Ash House (Exeter), Notter Bridge Depot and Bristol please confirm: a) if the Employer will provide the broadband connections to the proposed (Notter Bridge Depot and Bristol) for the Design Services Consultant b) will any IT infrastructure/network cabling in the proposed offices be available for the Design Services Consultant | 2016-10-07 | 2016-10-07 | OD | A) It is for the Consultant to provide their own broadband service. B) It is for the Consultant to install all necessary cabling to their IT and communication systems. | 2016-10-14 | 2016-10-14 | N/A | N/A | N/A
E42 | Contract Data Part 1 | Please confirm when the Consultant will be able to access the offices at Ash House, Notter Bridge Depot and Bristol during the mobilisation period to commence the installation of any IT network cabling and associated network connections required. | 2016-10-07 | 2016-10-07 | OD | The office refits are due to commence early 2017 and access will be notified to the Consultant. Office accomdation is currently occupied by the incumbents and we are reviewing lead-in period prior to the access date. | 2016-10-14 | 2016-10-14 | N/A | N/A | N/A
E43 | Scope - CDM Guidance | Scope NDD CDM Guidance Table 2 Reg. 4 Client duties for managing projects states that the Principal Designer will undertake duties to review the construction phase plan. This is an additional duty to those required by the CDM Regulations and the Principal Designer Appointment letter also details a list on additional duties that the Principal Designer will undertake. Please confirm that all the listed additional services detailed in Table 2 and the Appointment letter will be required and what payment mechanism will be used when additional services are required as the rate to be included in the Task Schedule Appendix A is for Principal Designer undertaking the duties required by CDM. | 2016-10-07 | 2016-10-07 | OD | The specific scope of work required for each project will be set out in the Task Order. Time spent on relevant activities will be reimbursed through the appropriate Time Charge. | 2016-10-26 | 2016-10-26 | N/A | N/A | N/A
E44 | TUPE | Kier - It is stated that all staff have a pay review on 1st Oct of each year, please confirm the current salary, post 1st Oct 2016 review, of all staff are included on the TUPE list. | 2016-10-07 | 2016-10-07 | HR | Kier has provided their latest ELI Data including revised salaries. This has been uploaded to the TUPE folder on Bravo - 'Area 1 TUPE - 14 10 16 - without names_DSC_received from Kier 141016.xlsx' | 2016-10-21 | 2016-10-21 | N/A | N/A | N/A
E45 | Tender Conference | During the tender conference it was stated that TQ responses would be provided weekly every Friday, with the short tender period can Highways England increase the frequency of providing TQ responses to twice per week. | 2016-10-07 | 2016-10-07 | C&P (PD) | Highways England requires suffient time in order to respond to queries. At this time increasing the frequency of the TQ sheet issue will not result in any benefit. If we believe there will be a future benefit we will review this | 2016-10-07 | 2016-10-07 | N/A | N/A | N/A
E46 | TUPE | Skanska - • For the “0100 CA2010 Pension” and “FPP BMS (Atkins)” schemes please confirm that the employees are ex-public sector, what date they transferred out of the public sector and what public sector pension scheme they were in at the point of transfer | 2016-10-07 | 2016-10-07 | HR | Skanska state - Response re FPP BMS - Each of the three individuals in the FPP BMS (Atkins) scheme are all ex public sector employees whose pensionable service originated in the LGPS. All of them were TUPE transferred out of the LGPS prior to 6 April 2008. At the point these individuals TUPE transferred to Skanska, they were already third or fourth generation ex LGPS employees who had been put into their respective employers’ GAD approved pension scheme. Membership to Skanska’s GAD approved pension scheme commenced on 1 August 2013 with continued rights. (i.e. NRD age 60 was retained.) With the exception of employee 145, neither of the other two individuals transferred any of their previous (ex LGPS) pensionable service into the scheme. Employee 145 transferred in ex LGPS service of 1 year 26 days. | 2016-10-21 | 2016-10-21 | N/A | N/A | N/A
E47 | TUPE | Skanska - • For the “0100 CA2010 Pension” and “FPP BMS (Atkins)” members please confirm what date they joined the schemes, whether any members transferred benefits from previous pension schemes and what date is used for any continuous service date for scheme membership purposes | 2016-10-07 | 2016-10-07 | HR | Please see the response to E46 | 2016-10-21 | 2016-10-21 | N/A | N/A | N/A
E48 | TUPE | Skanska - • For the “0100 CA2010 Pension” and “FPP BMS (Atkins)” schemes please provide details of Cash Equivalent Transfer Values by individual, including the actuarial assumptions in use for the Cash Equivalent Transfer Value basis, the scheme Technical Provisions basis, and the Technical Provisions funding level. | 2016-10-07 | 2016-10-07 | HR | Skanska state - Response Re FPP BMS - At the point of TUPE transfer from Skanska, the three individuals in the FPP BMS (Atkins) scheme will be offered one opportunity on an individual basis of a past service reserve transfer value to enable them to transfer out their accrued benefits to the new employer’s GAD pension scheme (or to the LGPS, if the Admission Body route applies). | 2016-10-21 | 2016-10-21 | N/A | N/A | N/A
E49 | TUPE | Skanska - • 43 employees are noted with rights to the “DC2013” pension scheme. Please confirm: 1) if the members are active in this scheme or just eligible, 2) whether the scheme is an occupational or personal pension scheme, 3) details of the range of employer contributions to which the individuals have a contractual right (e.g. matching percentage up to a cap, fixed rate linked to grade etc.). | 2016-10-07 | 2016-10-07 | HR | Skanska state- not sure of the question, however if it relates to DC2013 cases where they ‘refused to join’ / ‘opted out’ / ‘decision o/s’, 1) there are still eligible for DC2013 scheme, 2) an occupational DC scheme 3) Employer DC match % range is as follows EE% 3% gets 6% match/ 4% gets 7% / 5% gets 8% / and 6% gets 9%. Maximum match of 9%. | 2016-10-21 | 2016-10-21 | N/A | N/A | N/A
E50 | TUPE | Skanska - • a number of members of the DC2013 scheme are described as “Protected X/Y (TUPE)”. Please explain the nature of this protection | 2016-10-07 | 2016-10-07 | HR | Skanska state - previous Atkins DC scheme rates were age related so in some cases we protected the higher Employer match eg 4/8 and 5/10 where they were better than the standard Skanska match table. | 2016-10-21 | 2016-10-21 | N/A | N/A | N/A
E51 | TUPE | Kier - • for those in the WorkSave pension plan, please detail 1) whether the scheme is an occupational or personal pension scheme, 2) details of the range of employer contributions to which the individuals have a contractual right (e.g. matching percentage up to a cap, fixed rate linked to grade etc.). | 2016-10-07 | 2016-10-07 | HR | Kier has stated: 1. Occupational Pension Scheme 2. Matched contributions start at 1% up to a maximum matched contribution of 6% | 2016-10-21 | 2016-10-21 | N/A | N/A | N/A
E52 | Task Schedule Appendix A Time Charge Issue 3 Revision 0 | Task Schedule Appendix A allows tenderers to insert Consulting Office Overheads and Client Office Overheads, thereby calculating rates for staff in either of these offices. This allows tenderers to nominate a location but only for the names listed that apply to the 14 designated grades it does not allow tenderers to nominate a location for the other staff that are not named but make up the total list of FTE’s. There is nothing binding the pricing to the intended delivery solution and the pricing will not differentiate between tenderers planning to co-locate staff with those who do not plan to co-locate. Please confirm how the intended delivery solution will be reflected in the Quality and Financial Assessment models and how Highways England intend to ensure it will be delivered in contract. | 2016-10-07 | 2016-10-07 | C&P (C)/CD | In Schedule Appendix A Time Charge table 3 identifies 3 options for a fee percentage for any member of staff working on the contract, therefore every tender submission could be potentially different. Please note staff rate table prices are the upper bound for all job descriptions. Highways England are not minded to explain how tenders are assessed other than the information given in the IfT. | 2016-10-07 | 2016-10-07 | N/A | N/A | N/A
F53 | Design Services Contract Scope Issue 3 Rev. 0 | Please confirm whether the Designer/tenderer is required to solely provide the scope of service listed under clause 1.1.2 or whether there will be other consultants providing some of these services. Eg. Lighting/air quality, traffic signals as these are specialist areas not currently resorced within our company | 2016-10-11 | 2016-10-11 | C&P (PD) | The Scope of the service is set out in the document refered to. The Consultant must be able to deliver the whole service, this can be delivered as a sole provider, as part of a consortium/JV or by utilising subcontractors. | 2016-10-14 | 2016-10-14 | N/A | N/A | N/A
F54 | Extent of Designer resource allocation | Please can you indicate the number of staff that the Designer is expected to allocate as a percentage of the 29 staff allocated for Ash House, 4 staff in the Area 1 depot and 33 staff in the North Bristol office. | 2016-10-11 | 2016-10-11 | OD | Please refer to response C5 | 2016-10-14 | 2016-10-14 | N/A | N/A | N/A
B55 | SW DSC Quality Submission Answer Book Issue 3 Revision 1 | ‘Deliver Schemes’ has 8 issues to address, but only 2 pages have been provided for the full response. Allowing for evidence to be provided, this only allows a maximum of 1.5 pages for the Part A response. This makes it difficult to provide a meaningful response to the issues, when compared with ‘ICT’ which has 3 pages but only 4 issues to address. Could you either reduce the number of issues that need to be addressed, or provide additional space on this particular response? | 2016-10-12 | 2016-10-12 | OD | Highways England conducted a detailed analysis in regards to page limits and a Tender Amendment was made (TA1) as a result.The page limit is propotional to the weightings. So although 'Deliver Schemes' has 2 pages it only equates to 5% of the overall quality mark where as 'ICT' has 3 pages but 10% of the overall quality mark. | 2016-10-14 | 2016-10-14 | N/A | N/A | N/A
B56 | SW DSC Task Schedule Issue 3 SW DSC Task Schedule Appendix A Time Charge | Total Hours per Annum & Total Annual Hours Available calculations seem to working incorrectly. i.e. An Individual on 40 Hr week contract (8 Hrs per day) would have Total Hours Per Annum of (40*52 = 2080), also to calculate Total Annual Hours assuming, for example 8 Bank Holidays, 20 Days Annual Leave and 2 Sickness Training Days (2080 – ((8+20+2)*8)) = 1840. However by typing these figures into the areas in column AB the numbers calculated are the following, Total Hours Per Annum – 2024 & Total Annual Hours Available - 1848. The Total Annual Hours available stated on the HE sheet assume a larger divisor number leading to a potential under recovery in the rates calculated in the schedule. Can the HE please re-issue Appendix A with the correct calculation? | 2016-10-12 | 2016-10-12 | C&P (C) | The calculations are based on 365 days per calendar year rather than 52 weeks. On that basis : The total hours per annum is (365 - 104 - 8) = 253 x 8 = 2024hrs The available hours per annum is (253 - 20 - 2) = 231 x 8 = 1848hrs The calculations are therefore correct. | 2016-10-21 | 2016-10-21 | N/A | N/A | N/A
B57 | IfT Document 3: Tender Assessment | The Commercial Envelope requires the Submission of Appendix A & B Time Charge and Lump Sum respectively. Can the HE confirm how the tenderers prices will be evaluated and how the total Contract Value of £28,960,000 (paragraph 2.4.10) will be used as a method to compare all tenderer’s? | 2016-10-12 | 2016-10-12 | C&P (PD)/(CD) | Document 3 of the IfT provides the extent of the assessment information that Highways England is prepared to provide | 2016-10-14 | 2016-10-14 | N/A | N/A | N/A
B58 | SW DSC Task Schedule | 1. Work Items [Items 1-24] have incorrect Scope References. Can the HE please re-issue revised Task Schedule documentation with the corrected Scope references? | 2016-10-12 | 2016-10-12 | C&P (CD)/(C) | An updated Task Schedule will be issued as a tender amendment. | 2016-10-21 | 2016-10-21 | Yes | TA3 | 2016-10-25
B59 | SW DSC Scope | 2.1.1 “The Consultant designs and documents a mobilisation process in a mobilisation plan in accordance with the requirements of Annex 16, and submits it to the Employer for acceptance within two weeks of the starting date”. Having referred to Annex 16 - APPENDIX C – THE EXECUTIVE PROCESS OWNER ROLE paragraph 6 – “Process measures are identified during the Mobilisation Period in accordance with Annex 18, implemented and used to manage the on-going performance of the Process” and having reviewed Annex 18 – Continual Improvement and Innovation, it does not refer a specific process relating to the activities to be carried out in accordance with Scope 2.1.1. Can the HE please clarify this? | 2016-10-12 | 2016-10-12 | C&P (CD)\OD | Scope section 2.1.1 requires the consultant to develop a mobilisation process. Annex 16 Appendix C requires the Consultant to develop process measures for each process during the mobilisation period. These process measures are to be in accordance with the requirements of Annex 18. The requirements for the mobilisation period are detailed in Annex 16 Appendix B. | 2016-10-21 | 2016-10-21 | N/A | N/A | N/A
B60 | SW DSC Scope | Paragraph 11.1.1 “The Consultant prepares and maintains a robust information security plan complying with the Employer’s security policy and submits it to the Employer for acceptance” however within Mobilisation 2.1.2 (5) “a date for submission of an information security plan that is no later than four weeks after the starting date, and” refers to submission of the Information Security Plan. Can the HE confirm which payment mechanism will be applicable to the preparation of the Information Security Plan? | 2016-10-12 | 2016-10-12 | C&P (CD) | This should be allowed for in the mobilisation costs | 2016-10-21 | 2016-10-21 | N/A | N/A | N/A
B61 | SW DSC Scope | Paragraph 4.1.1 “The Consultant complies with the requirements in Annex 16 for the preparation, implementation and ongoing updating of its Quality Plan” however within Mobilisation 2.1.3 (3) “prepares and issues the Quality Plan to the Employer no later than four weeks after the starting date,” also refers to the preparation of the Quality Plan. Can the HE confirm which payment mechanism will be applicable to the preparation of the Quality Plan? | 2016-10-12 | 2016-10-12 | C&P (CD) | This should be allowed for in the mobilisation costs | 2016-10-21 | 2016-10-21 | N/A | N/A | N/A
B62 | SW DSC Scope | Paragraph 13.1.1 – Confidentially and Security “The Consultant arranges for staff requiring access to Employer’s premises, including offices, Regional Control Centres, the National Traffic Operations Centre and any outstations owned and/or operated by the Employer and usage of the Employer’s Information Systems to be vetted in accordance with the procedures in Part 2 of Annex 8 whether this be during or after mobilisation, and for the performance of the Consultant’s duties”. This item is not referred to within the Task Schedule. Can the HE confirm if this scope item is covered under Mobilisation duties within the contract? | 2016-10-12 | 2016-10-12 | C&P (CD) | Yes this will be covered within the mobilisation Any new member of staff that is required to work on the contract must have security clearance this will be covered in the overhead percentage tendered. | 2016-10-21 | 2016-10-21 | N/A | N/A | N/A
B63 | SW DSC Task Schedule Appendix B Lump Sum | Can the HE please confirm that any potential redundancy costs, associated with the change in scope and contract type, should be priced into the mobilisation charge? | 2016-10-12 | 2016-10-12 | C&P (C) | Severance costs are listed within the Business Overhead - item 12 - and should be included therein. | 2016-10-21 | 2016-10-21 | N/A | N/A | N/A
B64 | SW DSC Scope | Can the HE confirm, what payment mechanism will be used to recover tasks undertaken for the Transition (Scope 10.6) element post mobilisation? | 2016-10-12 | 2016-10-12 | C&P (C) | There does not appear to be any specific work for the Consultant to undertake associated with either the Transition Plan (Scope paragraph 10.6 sub-paragraph 1.7.1(1)) or the Employer's assessment of Consultant performance (Scope paragraph 10.6 sub-paragraph 1.7.1(3)). The Consultant may, with the agreement of the Employer, complete mobilisation duties not completed during the Mobilisation Period, however these would already have been priced for within the lump sum for Mobilisation. As such, we do not consider that there are any Transition tasks for which the Consultant needs to be separately reimbursed. | 2016-10-21 | 2016-10-21 | N/A | N/A | N/A
B65 | SW DSC Task Schedule Appendix A Time Charge | It is described in Table 1. column G (Total Cost of People) should correspond with office location in either Consultant’s or Highways England Office within tab 3. Office Overhead. Can HE confirm: 1)the reference to column G is incorrect (in fact column D) 2)How the tenderers are able to ensure the correct Office OH % is carried through to the calculation in column X or Z in the Staff Rate Table. Can the HE re-issue Appendix A enabling tenderers to populate the office overhead % from table 3 to the corresponding location in Table 1 column D | 2016-10-12 | 2016-10-12 | C&P (C) | 1) This appears to be correct - Guidance tab, cell C16 should reference Column D rather than Column G. 2) Tenderers should be able, if necessary, to check the calculation of Office Overheads in Tab 1 Columns X and Z based on the hourly cost of people derived in Column V. Tenderers should note that the calculations in those cells take account of the upper bound values only from Tab 3 Rows 17 and 31 - different percentages for different Consultant or HE office locations are not considered. | 2016-10-21 | 2016-10-21 | N/A | N/A | N/A
B66 | IfT Document 3: Tender Assessment | IFT Document 3: Tender Assessment Paragraph 3.5.1 – Financial Scoring “A Financial Assessment Panel will determine a total price for each Tenderer on the following basis: (a) The lump sum amounts in Schedule A (b) The total of the Schedule of rate items amounts in Schedule C tested against expected SoR work (c) An allowance for cost reimbursable items” Tenderers are only required to price Appendix A and B (Time Charge & Lump Sum respectively) can the HE confirm that this statement is not applicable as part of this tender exercise And re-issue an amendment to the Tender Assessment document. | 2016-10-13 | 2016-10-13 | C&P (CD) | A tender amendment will be issued to reflect the following changes to IfT Doc 3: (a) The rates scheduled in Task Schedule Appendix A tested against expected Time Charge work (b) The total of the Lump Sum prices in Task Schedule Appendix B (c) NOT USED | 2016-10-14 | 2016-10-14 | Yes | TA2 | 2016-10-17
D67 | IfT Document 3 (tender assesment) Issue 3 Rev 1 | Section 3.5 Financial Scoring details the method to be used by Highways England to determine the total price for each Tenderer. Please confirm this is correct as the Appendix Reference and titles don’t appear to tie into those listed in the Task Schedule. | 2016-10-13 | 2016-10-13 | C&P (CD) | Please see response B66 | 2016-10-14 | 2016-10-14 | N/A | N/A | N/A
D68 | IfT Volume 2A (Quality Submission A) Issue 3 Rev 1 | Tender amendment 1 removed the overall page/side allowance for the quality statement and replaced it with a table with individual side limits per question – refer paragraph 1.2.2. The sides allocated to the questions equals 32 sides. In paragraph 1.4.4 it states that the project schedule is to be included within the page limit, however, the overall side limit has been removed. Could Highways England permit tenderers to provide a project schedule outside the 32 sides, provided that the project schedule does not exceed 1 side. | 2016-10-13 | 2016-10-13 | C&P (PD) | The schedule of Project References is included in the page limit for the Quality Submission. This is because it is part of your evidence. We have not specified the size that this schedule should be, or that it should be on its own separate page. It is logical that this schedule be included at the end of the Quality Submission as opposed to anywhere else. This will not be changed. | 2016-10-14 | 2016-10-14 | N/A | N/A | N/A
D69 | IfT Volume 1A (Selection Questionnaire) Issue 3 Rev 1 | Paragraph 1.2.1 - 1.2.6 details the evidence that tenderers are required to provide in respect of a PCG. It is implied that this is required to be provided as part of the tender submission. On bravo Section A point 1.8.9 asks tenderers to confirm that they are willing to provide a PCG (if required). As this question is in Section A, and IfT Volume 1A paragraph 1.20 states that evidence is only required for Section C, D, G and H of the selection questionnaire, please confirm that with the tender submission we do not need to provide evidence (letter or board minute) of our willingness to provide a PCG. | 2016-10-13 | 2016-10-13 | C&P (CD) | The information requested in IfT Volume 1A paragraphs 1.21 to 1.26 specifically the board minutes or letter and/or legal opinion about the PCG from the guarantor is correct and all tenderers are required to submit these. The Bravo question 1.8.9 does not ask for this prior to tender return however circumstances are such we will now require information shortly after tender submission. Highways England will write to all tenderers shortly via a broadcast note and again at tender return to remind tenderers this will need to be submitted. | 2016-10-26 | 2016-10-26 | N/A | N/A | N/A
C70 | TUPE | Are the named staff all currently undertaking detailed design and so are anticipated to transfer to the Design Services Contract or does this include any of the design staff expected to transfer to Highways England? | 2016-10-18 | 2016-10-18 | HR | Kier state - The staff that are designated as being in the Design Services Contract are identified on the ELI data that has been provided. It is expected that these staff will transfer into the provider of the Design Services Contract and not Highways England. Please see E44 for reference | 2016-10-26 | 2016-10-26 | N/A | N/A | N/A
C71 | TUPE | Please could you provide approximate geography of home locations for the staff operating out of Bridgend and Ipswich given that these staff will need to relocate to our offices, and we need to assess reasonable travel. Eg. anonamised by provision of first three digits of the postcode, or otherwise simply by identifying whether they travel from the North/East/South/West of Ipswich and Bridgend. | 2016-10-18 | 2016-10-18 | HR | Kier have no obligation to provide any personal data in relation to individuals at this stage. The assumption would have to be that they are relatively local | 2016-10-26 | 2016-10-26 | N/A | N/A | N/A
B72 | TUPE (Kier) | Kier Staff TUPE List - Can you please provide contractual redundancy terms for all staff? | 2016-10-19 | 2016-10-19 | HR | Kier state the redundancy terms are in line with statutory guidelines only. | 2016-10-28 | 2016-10-28 | N/A | N/A | N/A
B73 | TUPE (Kier) | Kier - Please can the Annual Leave entitlement for EM Staff - 524781A be provided? This refers to a missing document? | 2016-10-19 | 2016-10-19 | HR | Please refer to document '4 Ex PB staff T and C's - received from Kier 300616.pdf' which states 24-27 days depending on contract | 2016-10-26 | 2016-10-26 | N/A | N/A | N/A
B74 | Appendix A | Appendix A Time Charge – due to varying responsibilities and accountabilities for each grade on the Schedule, please can the Appendix A be re-issued allowing tenderer’s to determine individual productive hours (utilisation levels) per Staff Grade within columns T and U (Total Hours Per Annum and Total Annual Hours Available) rather than assuming an average Utilisation for all Grades (as per the current calculations)? | 2016-10-19 | 2016-10-19 | C&P (C) | Appendix A will not be re-issued. The “Total annual hours available” figure calculated in column U is intended to reflect the maximum number of standard working hours per annum for which an individual is available to undertake work on the Framework. As the total “Annual Costs of People” shown in column S is divided by the “Total annual hours available” to provide an hourly rate for each individual, it would be inappropriate to make any adjustment for the presumed non-productive time being referred to in the query which is assumed to be included within the Fee. | 2016-10-26 | 2016-10-26 | N/A | N/A | N/A
C75 | Depot/Offices | Which ISP provides the connections to your current and proposed collocated offices? | 2016-10-20 | 2016-10-21 | OD | All Highways England network services are provided from our contract with Thales. | 2016-10-26 | 2016-10-26 | N/A | N/A | N/A
C76 | Depot/Offices | Is there a structured wired network in that office and are we able to utilise your structured cabling? | 2016-10-20 | 2016-10-21 | OD | Highways England will run the cables from the server rooms to the design contractors area for them to hook up to during the refits | 2016-10-26 | 2016-10-26 | N/A | N/A | N/A
C77 | Depot/Offices | Is there any other information you can provide which will facilitate our IT mobilisation estimate? | 2016-10-20 | 2016-10-21 | OD | Highways England can only answer specific questions | 2016-10-26 | 2016-10-26 | N/A | N/A | N/A
B78 | Scope of Service | Within the scope of services the DSC includes the provision of Environmental Surveys. Please could it be confirmed whether it is the intention this will be a “top up” service to supplement Highways England ordered surveys or whether the DSC will be the primary route for delivery. | 2016-10-20 | 2016-10-21 | OD | Highways England anticipate that they will carry out initial surveys to provide a business case (value for money) and also asset surveys to inform this process. Highways England would expect the Consultant to provide technical input beyond this requirement and reserve the right to request additional support for the activities that Highways England will lead on. | 2016-10-26 | 2016-10-26 | N/A | N/A | N/A
B79 | Scope of Service | Within the scope of services the DSC includes the provision of Development Control advice. Please could it be confirmed whether it is the intention this will be a “top up” service to supplement Highways England on an ad-hoc basis or whether the DSC will be the primary route for delivery of this advice. | 2016-10-20 | 2016-10-21 | OD | We assume you are referring to 7.1.2(4) of the Scope. The extent of such work will be as detailed in any task order. This work should not be confused with and does not replace the existing Highways England spatial planning arrangements. | 2016-10-27 | 2016-10-28 | N/A | N/A | N/A
E80 | Contract Data Part 1 (Depots) | For the avoidance of doubt in relation to the response to E42, please can you provide a further confirmation of your requirements. As the dates for access to the three Highways England offices to undertake broadband connections and installation of IT infrastructure cannot be confirmed at this stage, please confirm if tenderers are to allow for a temporary broadband solution for each office to ensure operational readiness for the Access Date. | 2016-10-20 | 2016-10-21 | OD | UPDATED ANSWER: Highways England will provide the Consultant access to premises for the following: From 22nd Feb (or the first working day following award, whichever is later) - access to server rooms to identify IT requirements during mobilisation in liaison with Highways England From 1st April – access to server room for installation in liaison with Highways England 1st July – full access. | 2016-10-26 | 2016-10-26 | Yes | TA4 | 2016-10-28
E81 | IfT Document 3: Tender Assessment | As per Tender Amendment 2, we note that clause 3.5.1 (c) now states that the total price for each tenderer will be determined on the basis of “An inflationary allowance calculated using the Office for Budget Responsibility (OBR) forecast for inflation over the service period, as published at the base date, applied in accordance with clause Z45 of the Conditions of Contract”. Can you please confirm: a) The exact indices published by OBR that is intended to be used for this evaluation. b) For the avoidance of doubt, that even though it is HE’s intention to use OBR forecast for inflation to determine a total price for each Tenderer as part of the Financial Assessment, is it still the intention to use EARN03 during the contract period for actual indexation increases as defined in Contract Data Part 1 | 2016-10-20 | 2016-10-21 | C&P (PD) | Paragraph 3.5.1 actually states the following: An inflationary allowance calculated using the Office for Budget Responsibility (OBR) forecast for inflation over the service period, as published at the base date, applied in accordance with clause X1 of the Conditions of Contract. in answer to your 2 points: a) please see response to B57 b) Yes - please see response to E32 | 2016-10-26 | 2016-10-26 | N/A | N/A | N/A
E82 | Task Schedule Appendix B Lump Sum | There are incorrect formulas in this spreadsheet Mob - Demob Lump Sum Tab a) The Mobilisation costs are entered for 4 months, but the columns only summate Month 1, 2 and 4 and not Month 3 b) Cell N40 appears to link to another cell as it has a value in it but no data above it. c) The Expenses section rows 43 downwards uses the rate inserted in D15 to calculate the expenses amounts. It should use the rate / amount inserted into cells, D43 downwards and multiply by the quantities inserted in E-K. d) The expenses section also has the same issue as a) as the columns only summate Month 1, 2 and 4 and not Month 3. | 2016-10-20 | 2016-10-21 | C&P (C) | Task Schedule Appendix B has been amended as part of TA3 | 2016-10-25 | 2016-10-26 | Yes | TA3 | 2016-10-25
E83 | Scope Annex 4 - Insurance Requirements | Section 2 - Professional Indemnity Insurance includes a requirement that 'An inner limit of one million pounds (£1,000,000) in respect of any one claim and in the annual aggregate applies in respect of asbestos.' Please provide details of any pre-existing asbestos risks that Highways England are aware of. | 2016-10-20 | 2016-10-21 | OD | Please see documents 'Area 1 Asbestos Management Plan 2016-17 - Issue 10 (approved).pdf' & 'Area 2 Asbestos Management Plan 16-17.pdf' which have been uploaded to Bravo in the Tender Documents folder | 2016-10-26 | 2016-10-26 | N/A | N/A | N/A
D84 | IfT Volume 2A Quality Submission | Table 2A.2 Deliver Schemes includes the issue to be addressed of “Availability of suitable resources including specialist IT and site based equipment”. In the context of Deliver Schemes please could you identify the specialist IT and site based equipment that you envisaged the design services partner providing. | 2016-10-21 | 2016-10-21 | OD | Highways England will look to the tenderers to provide an approach and evidence that satisfies and innovates such that the Consultant can provide IT systems that link with both the systems used by Highways England and those of the other Asset Delivery suppliers. | 2016-10-26 | 2016-10-26 | N/A | N/A | N/A
D85 | Volume 3 | Please could you confirm the correct revision for Volume 3. When using the front issued issued with TA2 the link tries to take you to Volume 3 revision 1. Having looked through the TA issued it appears Vol 3 Revision 1 does not exisit. Please can you confirm. | 2016-10-21 | 2016-10-21 | C&P (PD) | Highways England has not amended IfT Vol 3 during this tender period therefore the document that should be used is the issue version 'SW DSC IfT - Vol 3 (Commercial Submission) Issue 3 Rev 0.pdf' | 2016-10-21 | 2016-10-21 | Yes | TA3 | 2016-10-25
Tender Query Deadline (21/10/16 12:00) has now passed. Any further queries will be logged but Highways England does not guarantee to answer them prior to Tender Return
C86 | TUPE (Kier) | Are there any pension rights that are not old age, invalidity or survivor’s benefits which will transfer to the successful bidder as a result of TUPE (for example, early retirement benefits which are contingent upon dismissal)? | 2016-10-21 | 2016-10-21 | HR | None that Kier are aware of | 2016-10-26 | 2016-10-26 | N/A | N/A | N/A
C87 | TUPE (Kier) | Do any of the employees on the list have early retirement options? If so please advise which, and the extent of those options. | 2016-10-21 | 2016-10-21 | HR | No specific entitlements that Kier are aware of. Retirement options are all in line with the scheme rules | 2016-10-26 | 2016-10-26 | N/A | N/A | N/A
C88 | TUPE (Kier) | Do any of employees on the list benefit from any fair deal provisions? If so please advise which, and the extent of those provisions. | 2016-10-21 | 2016-10-21 | HR | None that Kier are aware of | 2016-10-26 | 2016-10-26 | N/A | N/A | N/A
C89 | TUPE (Kier) | Please advise where transferring employees are currently members of, or gain admitted body status to, their existing pension scheme. | 2016-10-21 | 2016-10-21 | HR | Kier state - Confirmation that there is no requirement for any Kier based employees. | 2016-10-28 | 2016-10-28 | N/A | N/A | N/A
C90 | TUPE (Kier) | Please advise if any employee on the TUPE lists are working here on a visa. | 2016-10-21 | 2016-10-21 | HR | None that Kier are aware of | 2016-10-26 | 2016-10-26 | N/A | N/A | N/A
C91 | TUPE | RE E44: We have had a quick look on the TUPE folder for the updated information from Kier with the revised salaries but cannot see it. When will it be uploaded? We have checked the previous Kier staff list but the salary information is the same | 2016-10-24 | 2016-10-25 | HR | Attachment now uploaded and answer E44 updated. Please see 'Area 1 TUPE - 14 10 16 - without names_DSC_received from Kier 141016.xlsx' in the TUPE folder | 2016-10-26 | 2016-10-26 | N/A | N/A | N/A
C92 | IfT Doc 1 | We submitted Tender Queries C86-C90 on 21st October 2016 but note that these have been identified as being submitted after the Tender Query Deadline. Upon reviewing the Instructions for Tender, Document 1 Tender Process, we note that paragraph 2.3.1 refers to the ‘date stated in Section 2.7’; which states a date of 21st October 2016 but no reference to a time deadline. May we respectfully request that Tender Queries C86-C90 are treated as Tender Queries submitted before the Tender Query deadline? | 2016-10-24 | 2016-10-25 | C&P (PD) | The deadline for TQ's is specified on the Bravo ITT and is visible to all tenderers. Although your question came in after the deadline it has still been logged and we will try to answer it, however as stated already Highways England cannot guarantee an answer prior to tender return. | 2016-10-26 | 2016-10-26 | N/A | N/A | N/A
E93 | TUPE | TQ response E44 indicates that new TUPE data relating to revised salaries for Area 1 has been uploaded to TUPE data. Please can yu indicate where this data is as we are unable to locate this following the upload of 19.10.16 | 2016-10-24 | 2016-10-25 | HR | Please see response to C91 | 2016-10-26 | 2016-10-26 | N/A | N/A | N/A
E94 | TUPE (Skanska) | Following the response to TQ E46, please confirm whether the 19 members of the CA2010 pension scheme listed in the “DD.Design. TUPE List (FINAL)” spreadsheet have a protected right to the LGPS, as if so the pension liabilities associated with these employees could be several million pounds. If they do have a right to the LGPS, please confirm what date is used for calculating their continuous service within the scheme. | 2016-10-26 | 2016-10-26 | HR | Skanska state the one FPP member would be entitled to an unreduced pension if made redundant thus an associated employer cost implication. | 2016-11-01 | 2016-11-01 | N/A | N/A | N/A
E95 | IfT Volume 1A paragraphs 1.21 to 1.26 | Further to your message relating to the Parent Company Guarentee and TQ D69, for the avoidance of doubt please can you confirm if tenderers passing the financial standing tests detailed in IfT Document 3 (cl.2.4.2, 2.4.3, 2.4.6, 2.4.7 and 2.4.8) will be requested to provide Board minutes or letter and/or legal opinion relating to the PCG. | 2016-10-27 | 2016-10-27 | C&P (PD) | All tenderers regardless of whether or not they will pass the financial standing test as detailed in IfT Document 3 must still provide Board minutes or letter and/or legal opinion relating to the PCG as per the broadcast note and response to D69 | 2016-10-27 | 2016-10-28 | N/A | N/A | N/A
D96 | SW DSC Task Schedule Appendix B Lump Sum Issue 3 Revision 1 | Whilst completing the submission document “SW DSC Task Schedule Appendix B Lump Sum Issue 3 Revision 1” we note that there is an error in that the values for any costs inserted for Mobilisation for Month 3 do not carry forward to the summary at the top of the worksheet in cell N7. Please advise as to course of action you would like tenderers to follow. | 2016-10-28 | 2016-10-28 | C&P (C) | Task Schedule Appendix B has been amended as part of TA5 | 2016-10-31 | 2016-11-01 | Yes | TA5 | 2016-11-01
B97 | Contract Data Part 1 | Contract Data Part 1 does not include Option X2 which we believe to be an omission by HE. Can HE please confirm that Option X2 will be incorporated into the Contract Data Part 1 at Contract Stage? | 2016-11-02 | 2016-11-02 | C&P (CD) | There are no plans to use Option X2 for this contract | 2016-11-03 | 2016-11-03 | N/A | N/A | N/A