## 2018-19
[5 empty] | Tenderers | [9 empty] | PCSS intermediate period |  |  |  | PCSS 17/18
2017 Planned maintenance tasks | Department | PCS number | Purchase order | Periodicy |  |  | Due Date | NMRN | H&S checks | Movement | Electrical checks | Tools and Workshop H&S | Painting | External surveys | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01
Survey Carved entry points | HS | PCS5024 |  | 2 yearly | in house |  | 2017-07-02 | bar: 2018-07-01
To document and remove fruiting bodies | HS | PCS5039 |  | Monthly | in house |  | x | bar: 2017-12-01 to 2019-03-01
To document wood boring insects | HS | PCS5039aV |  | Monthly | in house |  | x | bar: 2017-12-01 to 2019-03-01
Load test Port ceremonial brow and visually survey bottle screws | Sub Con | PCS5067 |  | yearly |  |  | 2018-03-26 | bar: 2018-03-01; 2019-03-01
Load test stbd ceremonial brow and visually survey bottle screws | Sub Con | PCS5068 |  | yearly |  |  | 2019-03-04 | bar: 2018-03-01; 2019-03-01
Load test Port after emergency brow | Sub Con | PCS5069 |  | yearly |  |  | 2019-03-04 | bar: 2018-03-01; 2019-03-01
Load test Port forward emergency brow | Sub Con | PCS5070 |  | yearly |  |  | 2019-03-04 | bar: 2018-03-01; 2019-03-01
Load test emergency brow to escape tower | Sub Con | PCS5071 |  | yearly |  |  | 2019-03-04 | bar: 2018-03-01; 2019-03-01
Load test emergency escape tower | Sub Con | PCS5072 |  | yearly |  |  | 2019-03-04 | bar: 2018-03-01; 2019-03-01
Load test emergency brow to grand magazine | Sub Con | PCS5073 |  | yearly |  |  | 2019-03-04 | bar: 2018-03-01; 2019-03-01
Visual survey of all brows and brow tower - 6 monthly | Sub Con | PCS5074 |  | 6 Monthly |  |  | 2019-03-04 | bar: 2018-03-01; 2018-09-01; 2019-03-01
Survey of Poop deck caulking | HS | PCS5075 |  | Yearly | in house |  | 2017-07-01 | bar: 2018-07-01
Survey of Forecastle deck caulking | HS | PCS5076 |  | 6 Monthly | in house |  | 2017-02-01 | bar: 2018-02-01; 2018-08-01; 2019-02-01
Survey of beck deck caulking | HS | PCS5077 |  | Yearly | in house |  | 2017-07-01 | bar: 2018-07-01
Survey of Quarter deck caulking | HS | PCS5078 |  | 6 Monthly | in house |  | 2017-02-01 | bar: 2018-02-01; 2018-08-01; 2019-02-01
Survey Port waist deck caulking | HS | PCS5079 |  | 6 Monthly | in house |  | 2017-02-01 | bar: 2018-02-01; 2018-08-01; 2019-02-01
Survey stbd waist deck caulking | HS | PCS5080 |  | 6 Monthly | in house |  | 2017-02-01 | bar: 2018-02-01; 2018-08-01; 2019-02-01
Survey of Upper Gun Deck Caulking | HS | PCS5081 |  | 2 Yearly |  |  | 2017-07-20 | bar: 2018-07-01
Survey Middle Gun Deck Caulking | HS | PCS5082 |  | 2 Yearly | in house |  | 2017-07-20 | bar: 2018-07-01
Survey Lower Gun Deck Caulking | HS | PCS5083 |  | 2 Yearly | in house |  | 2017-07-20 | bar: 2018-07-01
Survey all ladders and handrails checking for security of fittings and condition of nosings, repaint nosing as required | HS | PCS5095 |  | Yearly | in house |  | 2017-03-12 | bar: 2018-03-01; 2019-03-01
Turn gun trucks on exposed carriages | HS | PCS5101a |  | Yearly | in house |  | 2017-08-02 | bar: 2018-08-01
Survey Jeer Capstan | Conservation team | PCS5105a |  | 2 Yearly | in house |  | 2017-08-03 | bar: 2018-08-01
Survey all Guardrails and hammock cranes | HS | PCS5106 |  | Yearly | in house |  | 2017-01-26 | bar: 2018-01-01; 2019-01-01
Survey all sinks associated drains and domestic water supplies | HS | PCS5107 |  | Yearly | in house |  | 2017-01-02 | bar: 2018-01-01; 2019-01-01
Survey all scuppers | HS | PCS5108 |  | Yearly | in house |  | 2017-01-19 | bar: 2018-01-01; 2019-01-01
Scupper and Sink Waste Drainage Cleaning |  | PM5108a |  | Yearly |  |  | 2017-06-10 | bar: 2018-06-01
Survey all canvas covers and leather buckets | HS | PCS5109 |  | Yearly | in house |  | 2017-04-10 | bar: 2018-04-01
Check tension of all canvas covers, carryout minor corrective actions | HS | PCS5110 |  | 6 Monthly | in house |  | 2017-05-06 | bar: 2018-05-01; 2018-11-01
Survey breast stem and transom shores and packing pieces for security and decay. check drip bands on gun barrels | HS | PCS5114 |  | 2 Monthly | in house |  | 2017-01-11 | bar: 2017-12-01; 2018-02-01; 2018-04-01; 2018-06-01; 2018-08-01; 2018-10-01; 2018-12-01; 2019-02-01
Security of Inboard end of breast shores |  | PM5114a |  | 6 Monthly |  |  | 2017-03-07 | bar: 2018-03-01; 2018-10-01
Inspect Rudder Pennants and Securing Arrangements |  | PM5114b |  | Yearly |  |  | 2017-09-10 | bar: 2018-10-01
Survey Inboard end of breast shores |  | PCS5114A |  | 6 Monthly |  |  | 2017-03-15 | bar: 2018-10-01
Survey rudder pendants |  | PCS5114B |  | Yearly |  |  | 2017-10-15 | bar: 2018-10-01
Survey Keel blocks, Keel sole pieces and mast suppost pillers | HS | PCS5115 |  | 5 Yearly | in house |  | 2019-05-22 | bar: 2018-05-01
Take movement monitoring and mast alignment readings |  | PCS5117 |  | 2 Monthly |  |  | 2017-01-27 | bar: 2018-01-01; 2018-03-01; 2018-05-01; 2018-07-01; 2018-09-01; 2018-11-01; 2019-01-01; 2019-03-01
Annual Calibration of monitoring equiPCSent |  | PCS5117a |  | Yearly |  |  | 2017-10-01 | bar: 2018-10-01
Annual movement monitoring calibration Visit |  | PCS5117b |  | Yearly |  |  | 2017-06-09 | bar: 2018-06-01
Web hosting costs |  | PCS5117c |  | Monthly |  |  | Monthly | bar: 2018-04-01 to 2019-03-01
Fire Suppression System service - biannual service only |  | PCS5119 |  | bi annual |  |  | 2018-04-01 | bar: 2018-02-01; 2018-08-01; 2019-02-01
Fire Suppression System - full test, fill and drain down |  | PCS5119 |  | Annual | bar: 2018-08-01
Annual UPS service check |  | PCS5120 |  |  |  |  | 2019-06-21 | bar: 2018-08-01
Portable Electrical Testing Annually | Electrical | PCS5123 |  | Yearly | in house |  | 2019-06-04 | bar: 2018-06-01
Periodical Inspection & Test (whole ship) | Electrical | PCS5124 |  | Yearly |  |  | 2019-05-06 | bar: 2018-05-01
PA System Check | Electrical | PCS5124a |  | Yearly |  |  | 2018-09-01 | bar: 2018-09-01
2 dock & Survey shore side electrical installation | Electrical | PCS5125 |  | Yearly |  |  | 2017-01-24 | bar: 2017-12-01; 2018-12-01
Survey of dockside stanchions, chains, 103 nets, non slip strips, mini mast and tabernacle |  | PCS5126 |  | Yearly | in house |  | 2017-05-19 | bar: 2018-05-01
Survey of Mess Tables and Benches on all Decks |  | PCS5127 |  | 2 Yearlly | in house |  | 2017-03-04 | bar: 2018-03-01
Annual aloft shore stay survey |  | PM5130 |  | Yearly |  | open tender | 2017-09-15 | bar: 2018-10-01
6 monthly lower shore stay survey |  | PM5130a |  | Yearly |  | open tender | 2017-03-15 | bar: 2018-03-01; 2018-10-01
Check service loading of shore stays |  | PCS5130b |  | 6 monthly | in house |  | 2017-03-15 | bar: 2018-03-01; 2018-09-01; 2019-03-01
Load cells annual check |  | PCS5130c |  | yearly |  |  | 2018-08-10 | bar: 2018-08-01
Overhaul 3 x fall arrest devices |  | PM5132 | NOT REQD | 6 Monthly |  |  | 2017-02-13 | bar: 2018-03-01; 2018-09-01; 2019-03-01
Aloft lower mast survey |  | PCS5132A |  | 6 Monthly | in house | bar: 2018-03-01; 2018-09-01; 2019-03-01
Survey of davits from chain platforms |  | PCS5158A |  | 2 Yearly | in house | bar: 2018-02-01 to 2018-03-01; 2018-09-01; 2019-03-01
Survey gun port lanyard lines & tackles |  | PCS5159 |  | 2 Yearly | in house |  | 2017-03-21 | bar: 2018-03-01
Visual survey of all masts, spar rigging from dockside and deck |  | PCS5160 |  | 2 Weekly | in house |  | ongoing
Survey trafalgar day signal halyards |  | PM5161 |  | Yearly | Bell | open tender | 2017-10-17 | bar: 2018-10-01
Survey all Visitor barrier ropes |  | PCS5162 |  | Yearly | in house |  | 2017-04-12 | bar: 2018-04-01
Survey all anchor ropes |  | PCS5163 |  | 2 Yearly | in house |  | 2017-11-08 | bar: 2018-11-01
Survey all hammock netting |  | PCS5165 |  | Yearly | in house |  | 2017-11-03 | bar: 2018-11-01
Survey and Paint 34ft launch internally and externally |  | PCS5167 |  | 3 Yearly | in house |  | 2017-04-01 | bar: 2018-11-01
Survey and Paint 32ft Admirals barge internally and externally |  | PCS5167 |  | 3 Yearly | in house |  | 2017-11-01 | bar: 2018-11-01
Survey and Paint 28ft Pinnace internally and externally |  | PCS5167 |  | 3 Yearly | in house |  | 2017-11-01 | bar: 2018-11-01
Survey and Paint Yawl internal & external |  | PCS5167 |  | 3 Yearly | in house |  | 2017-11-01 | bar: 2018-11-01
Survey and Paint 18 ft cutter internally and externally |  | PCS5167 |  | 3 Yearly | in house |  | 2017-11-01 | bar: 2018-11-01
Paint Ship Side now to include Tompions, deadeyes and davits |  | PM5177 |  | 2 Yearly |  |  | 2018-06-01 | bar: 2018-06-01
Annual dehumidifier service |  | PCS5178 |  | Yearly |  |  | 2019-05-03 | bar: 2018-05-01
Paint Stbd ceremonial brow 2019 |  | PCS5198 |  |  |  |  | 2017-06-01
Paint port LGD brow |  | PCS5198A |  |  |  |  | 2017-06-01
Paint Port ceremonial brow 2014 |  | PM5198B |  | 3 Yearly |  |  | 2017-06-01
Paint Fwd Port Emergency Brow 2014 |  | PM5198C |  | 3 Yearly |  |  | 2017-01-06
Paint Emergency Brow to tower 2017 |  | PCS5198D |  | 3 Yearly
Paint Emergency Brow Tower 2018 |  | PCS5198E |  | 3 Yearly
Paint hold exit Brow 2018 |  | PCS5198F |  | 3 Yearly
Tar shroud caps and canvas rope collars |  | PCS5199 |  | 6 Monthly | in house |  | 2017-05-04 | bar: 2018-05-01; 2018-11-01
Battery change of Fire detection call points and detector heads (1566) |  | PCS5200 |  | 3 Yearly | in house |  | 2017-10-03 | bar: 2018-03-01
Lightning Protection (Annually) |  | PM5201 |  | 11 monthly |  |  | 2017-02-02 | bar: 2018-02-01; 2019-01-01
Fore topsail maintenance contract with Mary Rose Trust |  | PM5202 |  | Monthly | in house |  |  | X
Survey fire detection system |  | PCS5203 |  | 3 Monthly |  |  | 2017-02-03 | bar: 2018-01-01; 2018-04-01; 2018-07-01; 2018-10-01; 2019-01-01
Check for ingress of water and document |  | PCS5207 |  | Monthly | in house |  | 2016-12-01
Produce quarterly report for the NMRN |  | PCS5210 |  | 3 Monthly | in house |  | 2017-01-01 | bar: 2018-01-01; 2018-04-01; 2018-07-01; 2018-10-01; 2019-01-01
Annual Sorbus decay detector drill service |  | PCS5211 |  | Yearly |  |  | 2017-06-01 | bar: 2018-06-01
Planning & Supervision |  | PCS5230 |  | Monthly | in house |  | x
Validate PCSS & update documents |  | PCS5231 |  | Yearly | in house |  | 2017-11-01 | bar: 2018-11-01
Remove ships boat covers and frame work |  | PCS5232 |  | Yearly | in house |  | 2017-04-04 | bar: 2018-04-01
Replace ships boat covers and frame work |  | PCS5233 |  | Yearly | in house |  | 2017-10-10 | bar: 2018-10-01
Launder boat & GRP canvas covers |  | PM5233A |  | Yearly | in house | Mike Williams | 2017-04-04 | X | bar: 2018-04-01
Paint all paintwork on Upper deck inc fittings, cabin faces hatch coamings, mast Bitts and gratings |  | PM5235 |  | 2 Yearly |  |  | 2017-06-01 | bar: 2018-04-01
Represerve upper deck guns 10 x 12lb & 2 x 68lb carronades |  | PCS5235a |  | 2 yearly | Volunteers |  | 2018-04-01 | bar: 2018-04-01
Survey & report on all paintwork on Upper gundeck inc fittings |  | PCS5236 |  | Yearly | in house |  | 2019-06-01 | bar: 2018-06-01
Survey & report on all paintwork on Middle gundeck inc fittings |  | PCS5237 |  | Yearly | in house |  | 2019-06-01 | bar: 2018-06-01
Survey & report on all paintwork on Lower gundeck inc fittings |  | PCS5238 |  | Yearly | in house |  | 2019-06-01 | bar: 2018-06-01
Survey & report on all paintwork on Orlop deck inc fittings |  | PCS5239 |  | Yearly | in house |  | 2019-06-01 | bar: 2018-06-01
Survey & report on all paintwork of hold and grand magazine inc fittings |  | PCS5240 |  | Yearly | in house |  | 2019-06-01 | bar: 2018-06-01
Survey & Report Shipside Paintwork .Plus allowance for 10m2 of repairs |  | PCS5242 |  | Yearly | in house |  | 2019-05-01 | bar: 2018-05-01
Prepare HMS Victory Safety, Health & Environment Plan (SHE Plan) |  | PM5244 |  | Yearly | in house |  | 2017-09-01 | bar: 2018-09-01
Wash Down 2 Dock and clean Grey water handling system carry out electrical safety check |  | PCS5247 |  | Yearly |  |  | 2017-01-11 | bar: 2018-04-01
Treat 2 dock cobbles with weed killer FEB - NOV |  | PCS5247A |  | Monthly |  |  | ongoing | bar: 2018-02-01 to 2018-11-01
Re tar rudder coat by rope access |  | PM5248 |  | 2 Yearly |  | open tender | 2017-06-01 | bar: 2018-06-01
Check shot for security and report Refix as required |  | PCS5249 |  | Yearly | in house |  | 2019-06-10 | bar: 2018-06-01
Re test 2 dock wire access system |  | PCS5250 |  | Yearly |  |  | 2018-10-24 | bar: 2018-10-01
Certification of Racking and portable ladders |  | PCS5252 |  | 6 Monthly |  |  | 2018-10-20 | bar: 2018-04-01; 2018-10-01
Review Fire Risk Assessment | H & S | PM5253 |  | Yearly |  |  | 2017-09-01 | bar: 2018-09-01
Survey shore stay ground anchors |  | PCS5254 |  | Yearly | in house |  | 2017-10-05 | bar: 2018-03-01; 2019-03-01
Drill/Mortice Machine (M) - 6 Monthly E100893 |  | PCS5259 |  | 6 Monthly |  |  | 2016-12-01 | bar: 2017-12-01
Drill/Mortice Machine (E) - 6 Monthly |  | PCS5260 |  | 6 Monthly |  |  | 2016-12-01 | bar: 2018-06-01; 2018-12-01
WADKIN SRV 762 Circular Saw E100894 |  | PCS5261 |  | 6 Monthly |  |  | 2016-12-01 | bar: 2017-12-01
WADKIN SRV 762 Circular Saw |  | PCS5262 |  | 6 Monthly |  |  | 2016-12-01 | bar: 2018-06-01; 2018-12-01
FELL Model FO Dowelling Rod Machine M 6 monthly E100900 |  | PCS5266 |  | 6 Monthly |  |  | 2016-12-01 | bar: 2017-12-01; 2018-12-01
FELL Model FO Dowelling Rod Machine E 6 monthly |  | PCS5267 |  | 6 Monthly |  |  | 2016-12-01 | bar: 2018-06-01
DUSTRACTION Dust Extraction System E100902 |  | PCS5268 |  | 3 Monthly |  |  | 2016-12-01 | bar: 2017-12-01; 2018-03-01; 2018-06-01; 2018-09-01; 2018-12-01; 2019-03-01
DUSTRACTION Dust Extraction System E annual |  | PM5269 |  | Yearly |  |  | 2017-07-01 | bar: 2018-07-01
DUSTRACTION Dust Extraction System M annual |  | PM5270 |  | Yearly |  |  | 2017-07-01 | bar: 2018-07-01
WADKIN 32" DiscSander/BobbinMoulder E 6 monthly E101345 |  | PCS5271 |  | 6 Monthly |  |  | 2016-12-01 | bar: 2017-12-01; 2018-06-01; 2018-12-01
WADKIN 32" DiscSander/BobbinMoulder M 6 monthly |  | PCS5272 |  | 6 Monthly |  |  | 2016-12-01 | bar: 2017-12-01; 2018-06-01; 2018-12-01
WILSON Model 36/DNP Bandsaw M 6 monthly E103483 |  | PCS5273 |  | 6 Monthly |  |  | 2016-12-01 | bar: 2017-12-01; 2018-06-01; 2018-12-01
WILSON Model 36/DNP Bandsaw E 6 monthly |  | PCS5274 |  | 6 Monthly |  |  | 2016-12-01 | bar: 2017-12-01; 2018-06-01; 2018-12-01
DOMINION Surfacer & Thicknesser E 6 monthly E103484 |  | PCS5275 |  | 6 Monthly |  |  | 2016-12-01 | bar: 2017-12-01; 2018-06-01; 2018-12-01
DOMINION Surfacer & Thicknesser M 6 monthly |  | PCS5276 |  | 6 Monthly |  |  | 2016-12-01 | bar: 2017-12-01; 2018-06-01; 2018-12-01
Compressor Air Receiver Test Pressure 165 bar E103751 |  | PCS5277 |  | 2 yearly |  |  | 2016-12-01
DRILL - Bench E 6 monthly E113469 |  | PCS5278 |  | 6 Monthly |  |  | 2016-12-01 | bar: 2017-12-01; 2018-06-01; 2018-12-01
DRILL - Bench M 6 monthly |  | PCS5279 |  | 6 Monthly |  |  | 2016-12-01 | bar: 2017-12-01; 2018-06-01; 2018-12-01
Compressor Rollair 25 Rotary Screw E 3 monthly |  | PCS5281 |  | 3 Monthly
Compressor Rollair 25 Rotary Screw Check LP air |  | PCS5282 |  | Monthly
Saw - Chop - Scheppach Capas 3 E 6 monthly E136977 |  | PCS5283 |  | 6 Monthly |  |  | 2016-12-01 | bar: 2017-12-01; 2018-06-01; 2018-12-01
Saw - Chop - Scheppach Capas 3 M 6 monthly |  | PCS5284 |  | 6 Monthly |  |  | 2016-12-01 | bar: 2017-12-01; 2018-06-01; 2018-12-01
Grinder Bench Mounted- monthly safety check E141656 |  | PCS5285 |  | Monthly
Grinder Bench Mounted E 6 monthly |  | PCS5286 |  | 6 Monthly |  |  | 2016-12-01 | bar: 2017-12-01; 2018-06-01; 2018-12-01
Grinder Bench Mounted M 6 monthly |  | PCS5287 |  | 6 Monthly |  |  | 2016-12-01 | bar: 2017-12-01; 2018-06-01; 2018-12-01
Emergency Lighting | Electrical | PCS5288 |  | Monthly
Emergency Lighting - 3 hour drain test | Electrical | PCS5289 |  | Yearly |  |  | 2017-06-01 | bar: 2018-06-01
Check Water System Temperature | Sub Con | PCS5290 |  | Monthly |  |  | ongoing
Check Water System Temperature |  | PCS5291 |  | 6 Monthly |  |  | 2017-06-06
Fire Extinguishers | Sub Con | PCS5292 |  | Yearly |  |  | 2018-05-17 | bar: 2018-05-01
Fire Extinguishers | Sub Con | PCS5293 |  | 6 Monthly |  |  | 2017-03-22 | bar: 2018-03-01; 2018-09-01; 2019-03-01
Fire Extinguishers – 9 Litre Water | Sub Con | PCS5294 |  | 5 Yearly |  |  | 2018-03-22 | bar: 2019-03-01
Fire Extinguishers – 9 Litre Foam | Sub Con | PCS5295 |  | 5 Yearly |  |  | 2018-03-22 | bar: 2019-03-01
Fire Extinguishers – CO2 | Sub Con | PCS5296 |  | 10 Yearly |  |  | 2018-03-22 | bar: 2019-03-01
Internal Whole Ships Survey |  | PM5300 |  | 5 Yearly |  |  | 2017-04-01
External Whole Ships Survey |  | PM5301 |  | 5 Yearly |  |  | 2017-04-01
Overhead gantry crane 6 monthly E + M | Sub Con | PCS5302 |  | Yearly |  |  | 2017-03-10
Overhead gantry crane LOLA inspection | Sub Con | PCS5303 |  | Yearly |  |  | 2019-09-27
Lifting applance safety check | Sub Con | PCS5304 |  | 6 monthly |  |  | 2017-03-10
Life jacket servicing x 4 | Sub Con | PCS5305 |  |  |  |  | 2018-10-11
Replace coir mat underlay | Conservators | PCS5306 |  | Yearly |  |  | 2018-10-01
Replace great cabin underlay | Conservators | PCS5307 |  | Yearly |  |  | 2018-10-01
Scaffolding
middle gun deck repainting |  |  |  |  | open tender |  | 2017-01-16 | bar: 2018-01-01
lower gun deck repainting |  |  |  |  | open tender |  | 2016-02-01 | bar: 2018-02-01
Remove and repaint the port aft brow (to tower)
Workshop cleaning
Replacement Pilisters
Dock clean during new support contract | [6 empty] | ongoing
Health and Safety
Plant
Service Charge
|  | Key |  |  |  |  | Cash flow totals | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | in house team activities | [10 empty] | 2017-12-01: Total to end of FY 2016; 2018-02-01: 0; 2018-12-01: Total for FY 2017/2018; 2019-02-01: 0
NMRN FM activities
Contractor works < £25k
contractor works > £25k
costs paid as a monthly sum
Note on F6: Roy Smith: PO raised 5% increase for 2018
Note on H6: Roy Smith: price valid for 2018 except hire charges
Note on I6: Roy Smith: PO 10529 raised
Note on T6: VICKERSTAFF Peter: SWL quote 3.11.16 ref 01-29799 prices set to 2018 15 BAE hours SWL £5727 ML £4360 PM5067 to PM5074
Note on AF6: Smith, Roy (UK): 15 blue collar hours Plant hire £1620.00
Note on T7: Smith, Roy (UK): 15 BAE hours SWL quote 3.11.16 ref 01-29799 prices set to 2018
Note on AF7: Smith, Roy (UK): 15 blue collar hours
Note on T8: Smith, Roy (UK): 15 BAE hours SWL quote 3.11.16 ref 01-29799 prices set to 2018
Note on AF8: Smith, Roy (UK): 15 blue collar hours
Note on T9: Smith, Roy (UK): 15 BAE hours SWL quote 3.11.16 ref 01-29799 prices set to 2018
Note on AF9: Smith, Roy (UK): 15 blue collar hours
Note on T10: Smith, Roy (UK): 29 BAE hours SWL quote 3.11.16 ref 01-29799 prices set to 2018
Note on AF10: Smith, Roy (UK): 29 blue collar hours
Note on T11: Smith, Roy (UK): 33 BAE hours SWL quote 3.11.16 ref 01-29799 prices set to 2018 £1380
Note on AF11: Smith, Roy (UK): 33 blue collar hours
Note on T12: Smith, Roy (UK): 15 BAE hours SWL quote 3.11.16 ref 01-29799 prices set to 2018
Note on AF12: Smith, Roy (UK): 15 blue collar hours
Note on G13: Roy Smith: Does not include hire costs @£3K
Note on H13: Roy Smith: Sept visual survey
Note on T13: Smith, Roy (UK): 63 BAE hours £2634 - Katherine Haigh email 10.11.16 SWL £454
Note on Z13: Smith, Roy (UK): ML
Note on AF13: Smith, Roy (UK): 63 blue collar hours Twice a year £2634 - Katherine Haigh email 10.11.16
Note on AM13: Smith, Roy (UK): 63 blue collar hours
Note on L29: Smith, Roy (UK): Jon Hanson 01226 737317
Note on W29: Smith, Roy (UK): Marlin scupper clean 14 x Scupper and 3 x Sink Waste Drainage Cleaning
Note on AI29: Smith, Roy (UK): Marlin scupper clean 14 x Scupper and 3 x Sink Waste Drainage Cleaning Marlin quote 006220 Rcvd
Note on T33: VICKERSTAFF Peter: Bell rigging quote 31.10.16
Note on U33: VICKERSTAFF Peter: Bell rigging quote 31.10.16
Note on AA34: VICKERSTAFF Peter: Bell rigging quote 31.10.16
Note on I35: Roy Smith: PO issued £672
Note on T35: Roy Smith: Bell PO raised
Note on G38: Roy Smith: Visit 27th Feb
Note on R38: Smith, Roy (UK): BAE quote requested by PV 62 white collar hours £21751 annually - Katherine Haigh email 10.11.16
Note on T38: Smith, Roy (UK): 62 white collar hours £21751 annually - Katherine Haigh email 10.11.16
Note on V38: Smith, Roy (UK): 62 white collar hours £21751 annually - Katherine Haigh email 10.11.16
Note on X38: Smith, Roy (UK): 62 white collar hours £21751 annually - Katherine Haigh email 10.11.16
Note on Z38: Smith, Roy (UK): 62 white collar hours £21751 annually - Katherine Haigh email 10.11.16
Note on AB38: Smith, Roy (UK): 62 white collar hours £21751 annually - Katherine Haigh email 10.11.16
Note on AD38: Smith, Roy (UK): 62 white collar hours £21751 annually - Katherine Haigh email 10.11.16
Note on AF38: Smith, Roy (UK): 62 white collar hours £21751 annually - Katherine Haigh email 10.11.16
Note on AH38: Smith, Roy (UK): 62 white collar hours £21751 annually - Katherine Haigh email 10.11.16
Note on AJ38: Smith, Roy (UK): 62 white collar hours £21751 annually - Katherine Haigh email 10.11.16
Note on AL38: Smith, Roy (UK): 62 white collar hours £21751 annually - Katherine Haigh email 10.11.16
Note on AN38: Smith, Roy (UK): Smith, Roy (UK): 62 white collar hours
Note on F39: VICKERSTAFF Peter: Roy to contact
Note on L39: Smith, Roy (UK): 023 9232 1712
Note on AA39: Smith, Roy (UK): Absolute calibration
Note on AM39: Smith, Roy (UK): Absolute calibration
Note on L40: Smith, Roy (UK): Katrina Crask 01923 664236
Note on M40: Smith, Roy (UK): Sheridon elliot 07769728309
Note on W40: VICKERSTAFF Peter: ITM quote 20th October ref 02816 2018 £1615
Note on AI40: VICKERSTAFF Peter: ITM quote 20th October ref 02816
Note on F41: Roy Smith: PO 10417 raised
Note on Q41: VICKERSTAFF Peter: ITM quote 20th October ref 02816 £350 per monthe until mar 2019
Note on S42: VICKERSTAFF Peter: Orange Fire Protection quote PO 10536 raised
Note on AE42: VICKERSTAFF Peter: Orange Fire Protection quote
Note on A43: VICKERSTAFF Peter: Air test first to verify no leaks
Note on Y43: VICKERSTAFF Peter: Orange Fire Protection Extra over cost for normal bi-annual service
Note on W45: Smith, Roy (UK): 54 blue collar hours £2257 - Katherine Haigh email 10.11.16
Note on AI45: Smith, Roy (UK): 54 blue collar hours £2257 - Katherine Haigh email 10.11.16
Note on V46: Smith, Roy (UK): 160 blue collar hours £6689 - Katherine Haigh email 10.11.16
Note on AH46: Smith, Roy (UK): 160 blue collar hours
Note on M47: Smith, Roy (UK): 08708 791112
Note on N47: Smith, Roy (UK): Richard Hollis 07775 631707
Note on Z47: VICKERSTAFF Peter: Sound advice quote 1/11/16 £502 2018 Need to get quote changed to NMRN
Note on AM47: VICKERSTAFF Peter: Sound advice quote 1/11/16 Need to get quote changed to NMRN
Note on Q48: Smith, Roy (UK): 24 blue collar hours £1003 BAE Katherine Haigh email 10.11.16
Note on AC48: Smith, Roy (UK): 24 blue collar hours £1003 - Katherine Haigh email 10.11.16
Note on AO48: Smith, Roy (UK): 24 blue collar hours
Note on AA51: VICKERSTAFF Peter: Bell rigging quote 31.10.16
Note on AA52: VICKERSTAFF Peter: Bell rigging quote 31.10.16
Note on T53: VICKERSTAFF Peter: See email from Ian Bell dated 7.11.16
Note on Y54: Smith, Roy (UK): 8 blue collar hours £344 annually - Katherine Haigh email 10.11.16
Note on AK54: Smith, Roy (UK): 8 blue collar hours
Note on Z55: VICKERSTAFF Peter: £227.10 SWL
Note on T56: Smith, Roy (UK): Bell rigging PO 10466
Note on Q59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on R59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on S59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on T59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on U59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on V59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on W59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on X59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on Y59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on Z59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on AA59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on AB59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on AC59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on AD59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on AE59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on AF59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on AG59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on AH59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on AI59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on AJ59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on AK59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on AL59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on AM59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on AN59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on AO59: VICKERSTAFF Peter: £2174 every 2 weeks - Katherine Haigh email 10.11.16
Note on AA60: VICKERSTAFF Peter: Bell rigging quote 31.10.16
Note on AB62: Smith, Roy (UK): 4 blue collar hours £167 - Katherine Haigh email 10.11.16
Note on AH62: Smith, Roy (UK): 4 blue collar hours
Note on AJ62: Smith, Roy (UK): 4 blue collar hours
Note on AL62: Smith, Roy (UK): 4 blue collar hours
Note on AN62: Smith, Roy (UK): 4 blue collar hours
Note on AB64: VICKERSTAFF Peter: Based upon Wood Group tender return 1.11.16 with all PM5167 and PM 5235 works undertaken concurrently
Note on W69: VICKERSTAFF Peter: Based upon Wood Group tender 1.11.16 and undertaken concurrently with PM5198b and PM5198c
Note on L70: Smith, Roy (UK): 02392 268882
Note on V70: Smith, Roy (UK): Prima quote received
Note on R73: VICKERSTAFF Peter: As per Wood Group tender, to be undertaken concurrently with ship side painting
Note on R74: VICKERSTAFF Peter: As per Wood Group tender, to be undertaken concurrently with ship side painting
Note on T79: Smith, Roy (UK): Cost for battieries £500.00
Note on S80: VICKERSTAFF Peter: Bell rigging tender 31.10.16
Note on AD80: VICKERSTAFF Peter: Bell rigging tender 31.10.16
Note on F82: Roy Smith: £350 per quarter
Note on R82: Roy Smith: PO 11092 raised visit 3rd Feb
Note on N85: Smith, Roy (UK): Matt Lines 01373475540
Note on W85: Smith, Roy (UK): Quote SQ3110
Note on AI85: Smith, Roy (UK): Quote SQ3110
Note on A90: Roy Smith: GRP cover 80Kgs
Note on F91: Roy Smith: PO to be raised
Note on AB91: VICKERSTAFF Peter: Based upon Wood Group tender return 1.11.16 with all PM5167 and PM 5235 works undertaken concurrently
Note on F92: Roy Smith: Paint allowance ?????
Note on U92: VICKERSTAFF Peter: Not part of open tender. Cost based upon S&J quote 2015 to BAE
Note on F100: Roy Smith: £3.6K
Note on G100: Roy Smith: £3.7K
Note on H100: Roy Smith: PO raised
Note on I100: Roy Smith: PO raised
Note on K100: Smith, Roy (UK): James Neno 07775868611
Note on L100: Smith, Roy (UK): 02392 725473
Note on U100: VICKERSTAFF Peter: Based upon Marlins 13.5.2016 quote ref AN/MAR/008364 2 blue collar hours to check electrics Dock clean brought forward waiting for grey water system clen quote
Note on S101: VICKERSTAFF Peter: Based upon Marlins quote dated 23/2/2016 ref AN/MAR/008177
Note on K104: Smith, Roy (UK): Kelly quarmby 0121285 1670
Note on U105: Smith, Roy (UK): 3 hours blue collar
Note on AA105: Smith, Roy (UK): 3 hours blue collar
Note on AG105: Smith, Roy (UK): 3 hours blue collar
Note on AM105: Smith, Roy (UK): 3 hours blue collar
Note on D106: Roy Smith: Raised by EK against H & S
Note on F106: Roy Smith: Raised by Elizabeth Kennady
Note on M108: Smith, Roy (UK): Glen Ward 02392 633586
Note on K115: Smith, Roy (UK): Ray Nash 07973144297
Note on T123: Smith, Roy (UK): 2 hours @£45.00 per hour
Note on Q133: Peter: £1505 Katherine Haigh email 10.11.16
Note on W134: Peter: £146 annual payment - Katherine Haigh email 10.11.16
Note on K135: Smith, Roy (UK): Simon Rawsthorne 07772599620
Note on A136: Roy Smith: Not required Email in PMS folder
Note on F137: Roy Smith: email SOR 18/01
Note on G137: Roy Smith: Email SOR 18/01
Note on V137: Peter: £418 - BAE Katherine Haigh email 10.11.16
Note on G138: Roy Smith: £167 per 2 occasions
Note on T138: Peter: £167 Katherine Haigh email 10.11.16
Note on Z138: Peter: £167 - Katherine Haigh email 10.11.16
Note on AF139: Peter: £1045 - BAE Katherine Haigh email 10.11.16
Note on AF140: Peter: Assumed same cost as PM5294
Note on AF141: Peter: £293 - BAE Katherine Haigh email 10.11.16
Note on U143: VICKERSTAFF Peter: Excludes MEWP cost
Note on F144: Roy Smith: 6 monthly due March and Sept
Note on G144: Roy Smith: 0126436499 visit 08/02
Note on H144: Roy Smith: 01142431142
Note on F145: Roy Smith: SWL visit 20/02/17
Note on S145: Roy Smith: SWL quote received
Note on T155: VICKERSTAFF Peter: Email budget from Gary at Oakworks. Excludes MEWP cost
Note on Q156: VICKERSTAFF Peter: Estimated costs
Note on AD159: Peter: 3% inflation added
Note on AE159: Peter: 3% inflation added
Note on AF159: Peter: 3% inflation added