## Summary Page
Multidisciplinary Design Team (MDDT) Scope of Services
CLIENT: Pirbright Innovations Limited
PROGRAMME: [ DRAFT rev. 29/03/22 ]
PROJECT: Vet-VMIC
INTRODUCTION Project & Programme Overview The Multi-Disciplinary Design Team for The Pirbright Institute (Pirbright) Veterinary Vaccine Manufacturing and Innovation Centre (Vet-VMIC) will interface with the PMO and assigned Pirbright representatives The Client Project Team and user groups are not a dedicated resource for the Vet-VMIC project and as such their contribution to the Vet-VMIC project needs to be planned in advance. As such the Multidisciplinary Design Team will provide suitable notice of and a plan of the input foreseen from these groups. Purpose: The purpose of this Scope of Works is to establish requirements.
Services to be undertaken by the Multi-Disciplinary Design Team: • Design Lead; • Architectural Design (including interior design and space planning); • Civil (including geotechnical and dewatering design) & Structural Design; • Building Services Design; • Principal Designer; • Sustainability / BREEAM Consultant and Assessor; • Landscape Architect; • Acoustic Consultant; • Information Management Consultant / BIM Consultant; • Building Control; • Fire Strategy Consultant; • Noise and Vibration Consultant; • Clerk of Works (Architectural, Structural&Civil) • Commissioning Validation and Verification (CVV) Consultant.
Note: The Multi-Disciplinary Design Team are to incorporate Bio-Containment, Good Manufacturing Practice (GMP), Net Carbon-Zero, Commissioning, Verification & Validation (CVV) and Equity, Diversity and Inclusion (EDI) expertise to all service lines as appropriate and any other discipline or specialist that may be required to execute and complete the works. All consultant services are arranged generally over the RIBA Plan of Works Stages, as outlined below. Some consultants may be appointed at different stages through the project lifecycle, dependent upon the need and their specialism. Please note that a number of non-standard services have been included, careful and considered attention to the schedules is highly recommended.
Format: The Scope is organised in to two parts: • Part One: General Scope [policies, standards, processes and procedures that are in use by the Client that the Consultant must comply with when providing the services. • Part Two: Specific Scope
Form of Contract: NEC4
INDEX
Summary
1.0 Part One - General Scope
2.0 Part Two - Specific Scope
2.1 Definitions (for Specific Scope)
2.2 All Stages
2.3 RIBA Stage 0 - Strategic Definition
2.4 RIBA Stage 1 - Preparation and Briefing
2.5 RIBA Stage 2 - Concept Design
2.6 RIBA Stage 3 - Spatial Co-ordination
2.7 RIBA Stage 4 - Technical Design
2.8 RIBA Stage 5 - Manufacturing and Construction
2.9 RIBA Stage 6 - Handover
2.10 RIBA Stage 7 - Use
2.11 Design Responsibility Matrix (DRM)
2.12 Minimum Deliverables
Note on A14: Procurement Strategy - need to define what stages MDT is to be appointed? And any role outside of this? E.g. reviewer role?

## 1.0 Part One - General Scope
Part One: General Scope*
Back to Summary Page
Part One: General Scope
The Multidisciplinary Design Team for Vet-VMIC will interface with the Client, Funder and Project Team which includes:
· BBSRC: Landlord, Funder, Programme Sponsor, Programme Director & Programme Management Office (PMO);
· The Pirbright Institute: Internal Project Mangers, PSO and MEP Clerk of Works;
· Client User Groups: Including Subject Matter Experts, Science, Health Safety & Biosafety, Estates Management Services, plus others as required;
· Project Manager;
· Cost Manager;
· Client Procurement Group;
· Planning Consultant;
· Approved Inspector / Building Regulations (to be novated to Main Contractor).
The Client Project Team and user groups are not a dedicated resource for the Vet-VMIC project and as such their contribution to the Vet-VMIC project needs to be planned in advance. As such the Multidisciplinary Design Team will provide suitable notice of and a plan of the input foreseen from these groups.
The Multidisciplinary Design Team will work closely with the Client and their expert advisors, Project Manager, Cost Manager, other consultants, contractors and all others involved with the project to foster a partnering culture. The culture will embody the principles of mutual trust and co-operation with an overall aim of delivering a successful project on time and to budget.

## 2.0 Part Two - Specific Scope
Part Two: Specific Scope
Back to Summary Page
Part Two: Specific Scope - The Specific Scope provides additional information to specify and describe the service and any additional constraints on how the Consultant provides the services, that are only relevant to the Consultant for whom the Specific Scope is written.

## 2.1 Definitions
Definitions (for Specific Scope)
Back to Summary Page
Reference | Definition
BBSRC | Biotechnology and Biological Sciences Research Council: Project funding partner; the BBSRC is a major funder of Biosciences research
BMGF | Bill & Melinda Gates Foundation: Project funding partner
BSL | Biosafety level / Containment Level: refers to the biocontainment precautions required to isolate dangerous biological agents in an enclosed laboratory facility. The levels of containment range from the lowest (BSL/CL 1) to the highest (BSL/CL 4)
CL
COSHH | Control of Substances Hazardous to Health (regulations): Refers to the 2002 Parliamentary Act of the same name and relevant guidance about management of dangerous materials; often used as shorthand for the materials themselves
CVV | Commissioning, Verification & Validation
DDA | Disabled Access Audit
DRM | Design Responsibility Matrix
FCDO | Foreign, Commonwealth and Development Office: Project funding partner
GMP | Good Manufacturing Practice: GMP is a set of standards around medicines manufacture and production processes, which directly influence lab design and layout.
HEPA | High efficiency particulate air: HEPA is a set of efficiency standards for air filters. HEPA filters are designed to capture pollen, dirt, dust, moisture, bacteria, virus and submicron liquid aerosols.
LMICs | Low- and Middle-Income Countries: LMIC is a categorisation of countries’ economies, applied by the World Bank, based on Gross National Income (GNI) per capita; LMIC is the second-lowest of the four categories
MHRA | Medicines and Healthcare Products Regulatory Agency: The MHRA is responsible for ensuring that medicines and medical devices work and are acceptably safe. MHRA carries out inspections to check compliance with GMP (see above)
SAPO | Specific animal pathogen order: SAPO refers to a set of regulations around animal pathogens, the handling and management therein and licensing for their use
VHP | Vapourised Hydrogen Peroxide: VHP is an anti-microbial vapour used to decontaminate enclosed and sealed areas (e.g. labs)
Vet-VMIC | Veterinary Vaccine Manufacturing and Innovation Centre
WHO | World Health Organisation

## 2.2 All Stages
Applies to all RIBA Stages
Back to Summary Page
RIBA Stage | Item No. | Scope | Bidder Comment / Clarification / Addition | c
All | 1 | To provide the following service in addition to following the RIBA plan of works at each of the 7 RIBA stages
ALL | 2 | Support the Planning Consultant in secure planning permission and provide a complete and appropriately detailed, integrated and fully co-ordinated Design, to satisfy the requirements of the Client Brief at each design stage for activities such as Client/ 3rd Party review, comment, analysis and sign off, being suitable for use at the various design stages for cost checking, market testing, functionality, code compliance, alignment with selected procurement route, bidding, contracting, etc. Design coverage to include the following core design disciplines plus any additional specialist design or analysis work necessary to provide a complete and functioning facility: Design Lead; Architectural Design; Civil & Structural Design; Building Services Design; Principal Designer; Health & Safety Consultant; Environmental Consultant; Sustainability / BREEAM Consultant; BREEAM Assessor; Landscape Architect; Acoustic Consultant; Information Management Consultant / BIM Consultant; Security Consultant; Building Control; Laboratory Planning; Biocontainment Specialist; Interior Design; Design Review / Monitoring role; Fire Strategy Consultant; Noise and Vibration Consultant; Lighting Consultant; IT / AV Consultant; Waste Consultant; Ecology Consultant; FF&E Consultant; Planning and Environmental Impact Assessment - Various Supporting Consultants.
ALL | 3 | Implement a clear and transparent management process to ensure compliance with Design Responsibility Matrix (DRM), time, cost and quality requirements. Provide a detailed Design Management Plan identifying key personnel, including those with management responsibilities, details of contractual arrangements between all members of the Consultant’s team (including JV / Consortium partners and sub-consultants), organisation charts showing names with roles and responsibilities for each discipline / specialism, communications plan (internal and with Client’s team/ other consultants), methods for planning, monitoring and progress reporting of design activities, key decision and information exchange timing / methods / responsibilities, QA / QC procedures, meeting schedules and locations and any other relevant or required information.
ALL | 4 | Facilitate pre-engagement with any specialist equipment suppliers and ensure provision is included within the design to accommodate said specialist equipment.
ALL | 5 | Assist the Employer, their procurement agent and the Project Manager in the preparation of contract documentation and act as an evaluation team member for other procurements including construction works contracts.
ALL | 6 | Provide information necessary for the Client to engage specialist firms to carry out the following, including specifications, scope, and tender/ contract documents. Upon completion carry out a full analysis of the information provided, advise of any discrepancies, suspicious data, data gaps and / or further work necessary: Structural and contamination surveys, Noise survey, including background noise, Topographical surveys, Drainage CCTV survey, Structural Engineering site investigation, Contamination survey.
ALL | 7 | Complete all necessary activities to ensure that the Design is comprehensive, complete, cost effective and buildable in a safe manner, meeting the Client’s objectives.
ALL | 8 | Advise the Employer on current Government Policies and Best Practice pertinent to the project, the impact this may have on design and cost and recommendations for implementation.
ALL | 9 | Incorporate within the Design, all Client Information Requirements, Client Standard Specifications, Client Code/ Specific requirements and all relevant published design standards, manuals and any other requirements related to such a CL2/CL3 and GMP facility.
ALL | 10 | All deliverables, including drawings, specifications, reports, etc. to be produced and delivered in a co-ordinated format which together combine and describe every element of the works to the appropriate level of detail, which the Client can rely upon as representing the full Design solution. Each Stage Report shall include input from other consultants (i.e. those working under direct appointment by the Client), so as to provide a single and complete project document. Separate volumes from various members of the Consultant's team in different formats, using different terminology, formats, nomenclature, language, standards, fonts, etc. will not be acceptable. All such deliverables to be fully co-ordinated without duplication or contradiction between volumes/ chapters/ sections. All such deliverables to be fully co-ordinated with other sections of the Client's Requirements (e.g. Contract Conditions, Preliminaries, etc.) produced by others to avoid duplication and contradiction between the various documents.
ALL | 11 | Provide an appropriate design programme for each design stage showing planned key activities, key decision points, information exchange points, client decision requirements, etc. all in compliance with the requirements of the Client’s overall Master Programme prepared by others. Amend as necessary to ensure that key dates are met. The design programme should include all stakeholder consultation meetings, design team meetings, Client meetings/ presentations, issue dates for draft and final RIBA Stage report, as well as any other information which demonstrates the design process, key decision and information exchange dates. Keep the design programme up to date through all design stages and show progress against that actually achieved. Take appropriate action to rectify any delays to avoid time slippage.
ALL | 12 | Where required provide early “packages” of design information to suit the Client’s procurement strategy, e.g. decontamination, demolition, substructures, fit-out, etc. Such "packaged" information may ultimately become part of the Main Construction Contract.
ALL | 13 | Ensure that the Design fully complies with all legal and regulatory requirements, including those related to health and safety, planning, fire, Building Control, specific Client and specialist healthcare. Requirements, etc. Rectify any deficiencies.
ALL | 14 | Complete the Design on time and within the stated cost targets.
ALL | 15 | Carry out regular Risk Assessment exercises during each design stage, and participate in regular Risk Assessment workshops with the Client and other consultants.
ALL | 16 | Participate in value management and value engineering workshops and exercises during each design stage. Undertake scheme revisions to assist in value engineering exercises and update the Design as necessary.
ALL | 17 | Attend regular design and project progress meetings with the Client and the Client Team/ 3rd Parties and verbally/ visually present a detailed report on progress, issues, etc. for discussion.
ALL | 18 | Organise and invite Client Team representation to all Consultant "internal" design team meetings with sub-consultants, and other parties.
ALL | 19 | Complete the Design within the legal site boundary as defined by the title deed.
ALL | 20 | Provide a buildability report at each stage of the design process confirming proposals for construction, including analysis of access particularly in relation to adjoining owners’ land and Guildford Borough Council land (Permissions and Licences).
ALL | 21 | Take into account the proximity of adjoining buildings above and below ground, in both temporary and permanent conditions, without any adverse effect on the Design.
ALL | 22 | Allow for reapplications (i.e. MMA & NMA) and/ or any amendments that require resubmission or new submission to gain planning approval or to amend the approved planning application.
ALL | 23 | Comply with BS EN ISO 19650-2:2018 Organization and digitization of information about buildings and civil engineering works, including building information modelling (BIM) - information management using building information modelling. Delivery phase of the assets (Incorporating corrigendum February 2021) (+ Revised NA)
ALL | 24 | Design in accordance with the Building Information Model Level 2 (BIM L2). Comply with BIM Protocol: the CIC Building Information Modelling Protocol. Provide a detailed BIM Execution Plan and Design Execution Plan in collaboration with the Client team.
ALL | 25 | From the commencement of Stage 2 Design, provide an accredited professional BREEAM consultant to provide all necessary and relevant information and expertise to enable target credits to be secured. Exercise reasonable skill, care and attention to ensure that the project BREEAM requirements and Client’s Environmental Sustainability Requirements are met and fully co-ordinated into the Design, construction and post occupancy permanent operations. Where action is required by the Client, provide assistance to take that action, including providing all evidence necessary to the BREEAM Assessor.
ALL | 26 | Advise the Client on his duties under the CDM regulations and undertake the Consultant’s duties under the CDM regulations.
ALL | 27 | Produce design risk assessments in accordance with CDM Regulations. Exercise reasonable skill, care and attention to ensure they are issued to the CDM Co-ordinator for review.
ALL | 28 | Assist the Project Manager and other consultants in undertaking active risk management and value management exercises including for whole life cycle costing for all principle elements of the construction.
ALL | 29 | Employer’s Operational Requirements: Assist the Employer in developing the operational requirements for the proposed facility, collate them into a document and manage changes to that document and version control. The Employer’s Operational Requirements Document shall include, but shall not be limited to, the following elements: i. Description of all operational procedures to be undertaken within the proposed facility, including maintenance; ii. Standard operating procedures for all procedures within the proposed facility; iii. Hazard identification and operational risk assessments for all procedures to be undertaken within the proposed facility; iv. ACDP and SAPO categorisation for pathogens to be used within the proposed facility; v. Biological containment level requirements; vi. Requirements for functional operational testing demonstration and proving of the proposed facility; vii. Requirements for witnessing and approval of systems and equipment or other elements of the proposed facility by the Employer. viii. Good Manufacturing Practice (GMP) requirements.
ALL | 30 | Validation, Commissioning and Testing Strategy: During the early stages of concept design, Support the CVV Consultant to provide a report describing the overall approach and methodology for commissioning and verification activities during the design, construction / installation and post-construction periods for the project. The report shall include a description of the roles and responsibilities of all parties and the deliverables to be produced. The report shall define the performance acceptance criteria for each element of the proposed facility, subject to the actual elements, products, construction materials and methods of installation chosen.
ALL | 31 | Assist and support for client through the HAZOPS processes
ALL | 32 | Develop the scope for the Contractor design element to be undertaken at RIBA 4B. Review of the contractor design portion at RIBA 4B and provide feedback to inform and advise the client. Work collaboratively with the Contractor and the Client in agreeing and signing off the 4B stage of works
Note on C7: Sabrina Nicholas: [TPI to add to brief the requirement to avoid nomination within the performance spec]

## 2.4 RIBA 1
Applies to RIBA Stage 1 - Preparation and Briefing
Back to Summary Page
RIBA Stage | Item No. | Scope | Bidder Comment / Clarification / Addition
REFER TO "ALL STAGES" OF THIS SCOPE OF WORKS
1 | 1 | Receive an initial brief from the Client and agree general objectives: i. Project organisation and structure. ii. Communication procedures. iii. Objectives and challenges. iv. Project timescales. v. Project budget. vi. Approach to explanation/ flexibility. vii. Image and style. viii. Content of outline brief. ix. Amenity requirements. x. Technology approach and standards. xi. M&E strategy, including Security/ IT/ Communications/ AV strategy. xii. Procurement strategy and effect on design approach. xiii. Assist Client in determining a demolition strategy and phasing
1 | 2 | Advise the Client on the need to obtain statutory approvals.
1 | 3 | Advise the Client on their duties under the CDM regulations and undertake the Consultant’s duties under the CDM regulations.
1 | 4 | Consult, as necessary, with any local or other authority on matters relating to the proposed works, including obtaining such information as is reasonably available from documents on the existence and extent of public utility services and comment to the Client on any effect that these may have on the works.
1 | 5 | Advise the Client on any site investigations required to facilitate/ complete the design, and provide all and any necessary information/ documentation/ contacts for surveys to be the carrying out. Receive and interpret the results and make recommendations to the Client as necessary.
1 | 6 | Make recommendations to the Client on the need for any site investigations or tests to be undertaken, including any tests to ascertain the presence of contaminated ground and assist in implementing any decision taken by the Client.
1 | 7 | Make recommendations to the Client on the need for specialist sub-consultants and/ or contractors necessary to design and execute any sections of the works or for specialist suppliers to provide any materials or equipment. Obtain the Client’s agreement and take any action necessary to implement the Client’s decision. Such specialist sub-consultants, with design responsibility, are to be clearly indicated on the DRM.
1 | 8 | Review the briefing information regarding site logistics, site clearance and site set-up. Advise and put forward proposals to the Client. Update as necessary and include in the Stage 1 report.
1 | 9 | Work closely with the Client, Client Team and relevant 3rd Parties in the development of the Design to ensure compliance with the Brief and any amendments thereto. Provide alternative design solutions for consideration, review and further development with the Client and Client Team. Carry out any necessary studies to determine the feasibility of the Client’s Brief/ requirements in liaison with the Client and Client Team. Undertake such further studies as may be necessary, in order to submit proposals and options to the Client, including an anticipated programme and costs and make recommendations.
1 | 10 | Attend all meetings and workshops requested by the Client with all project stakeholders, including in-house service providers, to clarify and develop brief requirements as necessary to inform the Design.
1 | 11 | Regularly liaise with and provide regular information/ support to the Client's Cost Consultant for cost planning purposes.
1 | 12 | Review the Project Execution Plan and feed back to the Client information required to update the document relevant to the proceeding stage.
1 | 13 | Obtain the Client’s confirmation of Brief, budget and programme compliance.
1 | 14 | Provide necessary and agreed deliverables for Stage 1.
1 | 15 | Client approvals required at this stage: • Project Budget. • Project Programme. • Instruction to proceed to Stage 2.

## 2.5 RIBA 2
Applies to RIBA Stage 2 - Concept Design
Back to Summary Page
RIBA Stage | Item No. | Scope | Bidder Comment / Clarification / Addition
REFER TO "ALL STAGES" OF THIS SCOPE OF WORKS
2 | 1 | With the Client and the Client's team, review and to agree and/or reconfirm the following general objectives: i. Content of outline brief. iii. Project objectives and challenges. iv. Project timescales including key dates. v. Project budget. vi. Communication requirements. vi. Amenity requirements. viii. Technology approach and standards. x. M&E strategy, including Security / IT/ Communications / AV strategy. xi. Procurement strategy and effect on design approach. xii. Assist Client in determining a demolition strategy and phasing
2 | 2 | Carry out of an initial BREEAM assessment of the Project to indicate whether the appropriate score is achievable. Incorporate into the Design.
2 | 3 | Advise the Client on any site investigations required to facilitate / complete the design, and provide all and any necessary information/ documentation/ contacts for surveys to be the carrying out. Receive and interpret the results and make recommendations to the Client as necessary.
2 | 4 | Prepare a co-ordinated Design, including design intent, external appearance, massing, functional areas, grids, general arrangements, facade systems, structural and foundation systems, MEP systems, interior quality, etc. so as to achieve a “design freeze” suitable for completing a robust cost plan and Employer sign off.
2 | 5 | In co-operation with the Client and the Client’s Team, develop a concept Design which complies with the Brief, is within budget and submit to the Client for review, comment and acceptance.
2 | 6 | Develop the accommodation and space planning requirements and prepare the following: i. Stacking diagram to agree location of all special needs. ii. Blocking plans to test overall space planning strategy. iii. Defined locations for special areas where appropriate. iv. Test layouts showing circulation and zoning strategy.
2 | 7 | Develop the Design to include building shape/ external appearance, visual intent, quality/ type/ examples of architectural systems/ finishes, MEP strategy and initial solutions, structural methodology and initial solutions, circulation, fire strategy, functionality and other specialist input to determine the overall appearance, functionality and quality of the Project for pricing and Client acceptance.
2 | 8 | Provide information and input to assist in the preparation of a cost plan based on the project budget and anticipated start and completion dates. Monitor the Concept Design against the cost plan and report any anticipated difficulty to the Client, including proposals for overcoming that difficulty and obtain the Client’s instructions in sufficient time to allow corrective action to be taken.
2 | 9 | Exercise the reasonable skill, care and attention to ensure that the Design fully complies with all Client, legal and regulatory requirements, including but not limited to health and safety requirements, planning, fire, escape, use, Building Control, etc. and take any action necessary to rectify deficiencies. Where necessary, act as a witness at any hearing or planning enquiry or the like, subject to additional fee as defined under the Contract.
2 | 10 | Where the Client has indicated the possibility of a change to the agreed brief during the Concept Design phase, inform the Client of any cost and/ or programme implications and seek the Client’s instructions.
2 | 11 | Review with the Client and other consultants alternative design and construction approaches.
2 | 12 | Review with the Client and other consultants the briefing information regarding site logistics, site clearance and site set-up, in order to advise and put forward proposals to the Client. Update as necessary and include in the stage report.
2 | 13 | Develop general arrangement layouts, including preliminary partition layouts, ceiling concepts and generic furniture layouts.
2 | 14 | Prepare a project outline specification to inform the cost plan.
2 | 15 | Exercise reasonable skill, care and attention to ensure that the Client's BREEAM requirements are met and fully co-ordinated into the Design and advise where action by the Client is required to maintain such during construction and use. Assist the Client to take any action necessary, including providing all evidence, etc. to the BREEAM Assessor.
2 | 16 | Attend and participate in workshops to assist the Client to define and check Brief and Code compliance and achieving design quality.
2 | 17 | Assist the Cost Consultant in evaluation of the Design and adopt solutions which take into consideration life cycle costing and environmental assessments undertaken by others giving the best overall value. If such considerations threaten to increase the budget make recommendations to the Client and obtain instructions before proceeding.
2 | 18 | Do not include deleterious materials in the Design.
2 | 19 | Provide regular relevant/ detailed information to assist and liaise with the Cost Consultant. Provide such information in a timely manner to allow sufficient time for the production of the Stage 2 cost report to be completed in accordance with the programme. Liaise with the Cost Consultant in advance to agree the durations required.
2 | 20 | Regularly review and update the design programme at all stages of the design process to reflect actual progress achieved and immediately report to the Client any issue or item that may affect the project master programme. Take action and amend the design programme as necessary to rectify any delay.
2 | 21 | Attend all meetings/ workshops with the Client, other consultants and all project stakeholders, including in-house service providers, to clarify and develop brief requirements, as necessary, to inform the Design. Regularly update the Client with regard information requirements/ deadlines and issues which the Consultant deem to be a change. Advise the Client of the effect on time or budget of any change identified.
2 | 22 | Produce design risk assessments in accordance with CDM Regulations and exercise reasonable skill, care and attention to ensure they are issued to the CDM Co-ordinator for review. Advise any design changes as the Design is progressed.
2 | 23 | Liaise with the Client team and participate in any meetings necessary to consider suitable options for the procurement of the works and make recommendations to the Client in respect of how it may affect the Design, quality and functionality highlighting any potential associated risks.
2 | 24 | Make recommendations to the Client on the suitability of potential contractors and specialist sub-contractors. Incorporate such information on the DRM as appropriate. It is essential that the Client is made aware of any element or part of the Design for which the Consultant is not able to complete a full set of working, construction or fabrication drawings and specifications.
2 | 25 | Exercise reasonable skill, care and attention to ensure that the design is fully co-ordinated and continuously tested throughout the design phase against the Brief and cost plan, and that it fully complies with all legal and regulatory requirements, including but not confined to requirements concerning health and safety, planning, fire, Building Control, etc. and take any action necessary to rectify deficiencies.
2 | 26 | Develop the access and maintenance strategy, exercising reasonable skill, care and attention to ensure that the finished building, including services, is fully accessible for maintenance purposes. FM strategies should be clearly defined to facilitate economic maintenance during normal working hours using access equipment readily available to the Client’s maintenance team.
2 | 27 | Prepare structural and MEP design options reflecting the architectural intent, for incorporation in and development of the Concept Design, including calculations, sketches, diagrams, models, drawings, reports or specifications necessary to clearly describe the design intent. Take special care when considering the MEP design concepts to incorporate the special equipment needs of a specialist healthcare facility and demonstrate such to the Client.
2 | 28 | Carry out a full analysis and report on the availability of power sources at the site and the possibility of using alternative energy sources. Maximise the use of clean energy for the project and provide the Client with appropriate alternatives for consideration.
2 | 29 | Undertake regular and thorough reviews of the Client's environmental policies, targets and objectives which need to be incorporated in the Design. Regularly update the Client on how this is being done and provide any specialists necessary to carry out this task. Highlight on the DRM any specialist suppliers needed to provide materials or equipment to deliver the compliant works as part of the Main Contract.
2 | 30 | Prepare outline performance based work schedules to clearly identify the construction, operation and maintenance requirements for the services installations. Provide a specialist FM consultant to incorporate these requirements into the Design.
2 | 31 | Develop and advise the Client on design standardisation, maintenance management procedures and on construction handover procedures in respect of maintenance.
2 | 32 | Commence the thermal modelling for the Project.
2 | 33 | Apply environmental assessment techniques to the Design and adopt solutions giving the best overall value for money, and where this may result in the cost limit for the project being exceeded, make recommendations to the Client and obtain instructions.
2 | 34 | Client approvals required at this stage: • Concept Design. • Space Standards. • Project Budget. • Project Programme. • Instruction to proceed to Stage 3.

## 2.6 RIBA 3
Applies to RIBA Stage 3 - Spatial Co-ordination
Back to Summary Page
RIBA Stage | Item No. | Scope | Bidder Comment / Clarification / Addition
REFER TO "ALL STAGES" OF THIS SCOPE OF WORKS
3 | 1 | Exercise reasonable skill, care and attention to ensure that the Developed Design is fully co-ordinated and tested throughout the design phase for compliance with the cost plan requirements and all legal and regulatory requirements, including but not confined to requirements concerning health and safety, planning, fire, Building Control, etc. and take any action necessary to rectify deficiencies.
3 | 2 | Prepare the Design in compliance with the Project Brief, Stage 2 Design and planning requirements.
3 | 3 | Prepare the Design based on the accepted, (with amendments), Stage 2 Design and planning approval comments, maintaining quality, functionality and cost parameters, all in compliance with the evolving Client Brief.
3 | 4 | Work closely with the Client, Client Team and other consultants to finalise and incorporate their requirements into the Design. Provide information and advice, as necessary, to solve design and detailed functional requirements for discussion.
3 | 5 | Co-ordinate, consult and exchange information with the CDM Co-ordinator, keeping them updated with any design changes or key decisions made, which may affect their input and responsibilities.
3 | 6 | Formulate a strategy to deal with Building Control and other statutory approvals related to the Design, including a programme of submissions for relevant legal and regulatory approvals/assessments.
3 | 7 | Continue regular dialogue and consultation with Statutory Authorities and other relevant bodies/ authorities.
3 | 8 | Provide information to assist with: i. Finalisation of the detailed Cost Plan prepared by others. ii. Updating the project Master Programme, including pre-purchase recommendations for potential long lead and specialist items included in the Design.
3 | 9 | Regularly review and update the design programme at all stages of the design process to reflect actual progress achieved and immediately report to the Client any issue or item that may affect the project Master Programme. Take action and amend the design programme as necessary to rectify any delay.
3 | 10 | Attend all meetings and workshops with the Client, other consultants and all project stakeholders, including 3rd party service providers to finalise the Brief requirements for incorporation in the Design. Regularly update the Client with regard information requirements/deadlines and issues which the Consultant deem to be a change. Advise the Client of the effect on time or budget of any change.
3 | 11 | Review and finalise space planning and functional requirements solutions for incorporation in the Design.
3 | 12 | Produce FF&E layouts, specifications and samples of colours, materials and finishes in consultation with stakeholders for review by the Client and for stakeholder sign off.
3 | 13 | Complete the computer model, including ‘fly through’, or by agreement with the Client static visualisations, where more appropriate to the scheme for presentation to the Client, who may use them to publish and promote the scheme.
3 | 14 | Complete a set of fully co-ordinated drawings, specifications, schedules and any other relevant documents to the necessary level of detail maintaining the requirements of the current Brief, amendments thereto and any further changes confirmed by the Client on time and on budget.
3 | 15 | Assist the Cost Consultant to finalise the detailed elemental cost plan. The Developed Design is to be within the cost plan.
3 | 16 | Based on the accepted Developed Design and detailed elemental cost plan, provide suitable information (drawings, specifications reports, etc.) to discuss with and co-ordinate input of other consultants. Provide advice to the Client regarding suitability of documentation for tender according to the selected procurement route.
3 | 17 | Prepare a fully detailed and co-ordinated Specification. The Specification shall reflect the selected procurement process, be co-ordinated with the Preliminaries and Contract Conditions produced by others, be a single document covering all design disciplines and clarify clearly the extent of specialist design and build sub-contractors to be appointed by the Contractor to complete the Detailed Design of predetermined elements of the works. The Specification shall: 1. Be fully co-ordinated. 2. Use the same nomenclature, font and style. 3. Use the same contractual language throughout reflecting that determined by the main construction contract. 4. Clearly identify elements that the Contractor will be required to appoint a specialist design and build sub-contractor to produce Working Drawings for review and comment only by the Consultant.
3 | 18 | Where necessary, produce information for tender in advance packages to suit the Client’s procurement process.
3 | 19 | In collaboration with the Cost Consultant and Client answer any design enquiries from tenderers satisfactorily during the procurement process.
3 | 20 | Advise the Client on tenderers recommended for interview. Attend interviews, assist in compiling and agreeing interview agenda and questions. Provide feedback following interviews to enable necessary appointments.
3 | 21 | Attend any mid-tender workshops as may be necessary with tenderers, the Client and other consultants. Attend reference visits to exemplar projects and compile a report on observations made regarding the workshop and visit.
3 | 22 | Assist with tender appraisals and contribute to the tender recommendation reports.
3 | 23 | Finalise the Client’s Brief clearly identifying any changes and amendments.
3 | 24 | Advise the Client on the need for any special conditions of contract relevant to the works.
3 | 25 | The Developed Design shall include general arrangement drawings, elevations, sections, typical details, structural solutions/ details, MEP solutions/ details, specifications and other information considered to be appropriate to clearly define the scope and quality required. A contractor may be invited to submit proposals in response, in order to maximise the benefits of his expertise in buildability and his/her knowledge of the market/ supply.
3 | 26 | Develop integrated energy efficient strategies for the fabric and engineering services.
3 | 27 | Update the thermal modelling for the Project.
3 | 28 | Support the environmental specialist in the carrying out of an initial BREEAM assessment of the Project to indicate whether the appropriate score is achievable. Incorporate into the design.
3 | 29 | Design the building services systems in accordance with the acoustic and other specialist consultants' requirements.
3 | 30 | Key design deliverables to be included in the Client’s Requirements: • Updated schedules of accommodation and areas. • Floor plans for all areas. • Reflected ceiling plans for all areas. • Elevations, sections and details of selected areas. • Finishes schedule and samples of colours, materials and finishes. • Furniture schedules and tender review. • Fixtures and fittings schedule. • Construction specifications. • Submissions for statutory approvals. • CDM and access statement. • Statutory issues statement. • Provision of information in relation to any party wall and right to light issues. • BREEAM appraisal. • Employer’s brief showing updates.
3 | 31 | Provide information in support of an application for detailed planning consent for the proposed facility made by the Planning Consultant on behalf of the Employer.
3 | 32 | Production information for mechanical and electrical services shall include, but shall not be limited to, process and instrumentation diagrams, schematic drawings, detailed design drawings, co-ordination drawings, builders work and fixing schedules, plant and equipment schedules, specifications, design criteria and calculations. Production information drawings shall include detailed integrated component drawings of elements forming or penetrating the containment barrier and any other elements critical to biological containment or operational procedures.
3 | 33 | Production information drawings shall include co-ordinated spatial design of all pipework, ductwork containment and plant within spaces which require access for routine maintenance.
3 | 34 | Production information of architectural or building work shall include, but shall not be limited to, location drawings, general arrangement drawings, construction details assembly drawings, interface and co-ordination details, schedules, specifications, calculations and integrating information from specialists.
3 | 35 | Production information of architectural building work shall include integrated component drawings including structural design for all elements forming, supporting or otherwise affecting the containment barrier or other elements critical to biological containment.
3 | 36 | Where the containment barrier is formed by or relies upon the integrity of proprietary elements or applied finishes the limiting physical capacities, including strength under the ultimate loading conditions and resistance to cracking under serviceability loading conditions or other physical conditions shall be determined, if necessary from primary investigation, and included within the design calculations.
3 | 37 | Production information for all internal areas of the proposed facility shall include detailed layout plans at a scale not less than 1:50 and detailed wall elevations at a scale not less than 1:25. These drawings shall be fully co-ordinated to include all physical features within the internal space including mechanical and electrical fittings, Employer supplied loose and fixed equipment to accurately represent all surface features visible to the Employer when the facility is occupied.
3 | 38 | Provide rendered BIM data model and three dimensional visualisations (BIM Level 2) of all internal areas of the proposed facility include all physical features within the internal space including mechanical and electrical fittings, Employer supplied loose and fixed equipment to accurately represent all surface features visible to the Employer when the facility is occupied.
3 | 39 | Provide information in support of SWIFT and HAZOP studies undertaken by the Employer. Attend workshops and actively participate in the SWIFT and HAZOP exercises. Respond to the output recommendations of the SWIFT and HAZOP studies providing additional information or making amendments to the design as appropriate and as required.
3 | 40 | Provide information in support of the Design Qualification, Installation Qualification and Operation Qualification to be undertaken by the CVV Consultant.
3 | 41 | During the detailed design stage, develop the Commissioning and Testing Plan in consultation with the Employer and the CVV Consultant. The plan shall identify the following: i. Each element of the systems or equipment which is to be commissioned and/or tested, ii. A detailed description of the commissioning and/or testing activity required. iii. The performance acceptance criteria and the method by which the parameters shall be measured, iv. Requirements for specialist instrumentation including accuracy. v. Requirements for witnessing by the Employer’s CVV Consultant and the Employer’s staff. vi. Requirements for documentation defining the commissioning activities in further detail.
3 | 42 | Client approvals required at this stage: • Developed Design Report. • Project Cost Plan. • Project Programme. • Instruction to proceed to Stage 4.

## 2.7 RIBA 4
Applies to RIBA Stage 4 - Technical Design
Back to Summary Page
RIBA Stage | Item No. | Scope | Bidder Comment / Clarification / Addition
REFER TO "ALL STAGES" OF THIS SCOPE OF WORKS
4 | 1 | Complete the Technical Design maintaining the accepted Developed Design, incorporating input from all design disciplines, specialist design and build sub-contractors and the Contractor. The Consultant is to maintain the quality, functionality and operational aspects of the Design as set out in the Brief and accepted Stage 3 Design throughout this stage and through any value engineering exercises undertaken for budget control
4 | 2 | Review and comment on Working Drawings/ detailed technical specifications prepared by the specialist design and build sub-contractors for adherence to and compliance with the Design and Specification contained in the Main Contract. (Note: Specialist sub- contractors are those with responsibility to complete the Technical Design, manufacture, install and warrant predetermined elements of the works).
4 | 3 | Consult statutory authorities on the Developed Design proposals. Prepare such calculations and details relating to the works as may be required for submission to any statutory authority, including the co-ordination of such information for the work submitted by specialist suppliers and/ or sub-contractors as is available, which may need to be included in such submissions.
4 | 4 | Regularly review and update the design programme at all stages of the design process to reflect actual progress achieved and immediately report to the Client
4 | 5 | Attend all meetings/ workshops with the Client, other consultants and all project stakeholders, including in-house service providers, to clarify and develop brief requirements, as necessary, to inform the Design. Regularly update the Client with regard information requirements/ deadlines and issues which the Consultant deems to be a change. Advise the Client of the effect on time or budget of any change
4 | 6 | The Technical Design is to provide the Contractor with the necessary fully co-ordinated information needed for construction, including details and comprehensive specifications related to all aspects of the works (e.g. architecture, landscaping, civil/ structural engineering, mechanical, electrical, plumbing, IT, etc.). Final Working Drawings and technical specifications will be produced by the Contractor and/ or specialist design and build sub-contractors.
4 | 7 | Advise on the consequences of any changes to the Design through the change control processes as and when such changes are identified. Consultant to clearly explain which changes are the result of changes to the Brief, Client decisions, Consultant decisions/ choices or those arising from the action of third parties.
4 | 8 | Exercise reasonable skill, care and attention to ensure that the Client's BREEAM requirements are met and fully co-ordinated into the Design and advise where action by the Client is required to maintain such during construction and use. Assist the Client to take any action necessary, including providing all evidence, etc. to the BREEAM Assessor.
4 | 9 | Finalise all details in connection with the access and maintenance strategy. Exercise reasonable skill, care and attention to ensure the building, including services is fully accessible for maintenance purposes. Strategies should allow for maintenance during normal working hours using access equipment readily available to the maintenance team.
4 | 10 | Process review, comment and return Working Drawings to the specialist sub-contractors.
4 | 11 | Exercise reasonable skill, care and attention to ensure that the Technical Design is fully co-ordinated, integrated and tested throughout the design phase against the Brief and Construction Contract so that the Technical Design is fully compliant with all legal and regulatory requirements, including but not confined to requirements concerning health and safety, planning, fire, Building Control, etc. and take any action necessary to rectify
4 | 12 | Attend regular meetings with the Contractor and other consultants, as necessary, in order to monitor the progress of the works and the delivery of final design
4 | 13 | Contribute to an Equality Analysis to incorporate into the Stage 4 report. This will require consultation with end users, including disability and wellbeing groups. All enhancements found to be necessary as part of this assessment must be incorporated in the Stage 4 Design in line with the agreed budgetary provisions.
4 | 14 | Include FF&E schedules along with specifications for tender purposes, including agreeing sample of colours, materials and finishes and consultation with stakeholders and potential
4 | 15 | Engage with the Client to determine final finishes schedule and specification.
4 | 16 | Prepare and co-ordinate submissions to comply with any Acts, Regulations or other Legal and Regulatory Requirements for the project.
4 | 17 | Prepare sufficient structural and MEP calculations, drawings, schedules and specifications to enable the Technical Design to be completed on time.
4 | 18 | Prepare the final Design, drawing attention to any significant differences from the previously agreed requirements for the works.
4 | 19 | Examine Working Drawings, bar bending schedules and specifications submitted by the Contractor and sub-contractors for the works or parts thereof, in respect of conformity with the Design and in particular in respect of general dimensions, structural adequacy of members and connections and compliance with performance criteria.
4 | 20 | Finalise the thermal model ready for design Stage 5.
4 | 21 | In conjunction with the Client, establish that all qualifications, clarifications, omissions and exclusions are satisfactorily resolved and agreed in writing.
4 | 22 | Prepare and co-ordinate the making of submissions under building acts and/ or regulations or other legal and regulatory
4 | 23 | With the other consultants, negotiate an information release schedule with the Contractor prior to the award of the Building Contract.
4 | 24 | Once the Client is ready to enter into the Building Contract, confirm to the Project Manager in writing that so far as concerns matters within your responsibility or knowledge, a state of readiness has been achieved for construction to commence and to proceed in accordance with the proposed construction programme, or notify the Project Manager of any respects in which that is not the case.
4 | 25 | Client approvals required at this stage: • Contract documents. • Elemental Cost Plan. • Statutory approvals. • Project Programme. • Instruction to proceed to Stage 5.

## 2.8 RIBA 5
Applies to RIBA Stage 5 - Manufacturing and Construction [MDT Role: NEC Supervisor]
Back to Summary Page
RIBA Stage | Item No. | Scope | Bidder Comment / Clarification / Addition
REFER TO "ALL STAGES" OF THIS SCOPE OF WORKS
This stage includes all design, construction and commissioning activities by the Contractor to achieve completion of the whole of the works. The Contractor is appointed by the Client under the NEC4 Engineering and Construction Contract at the beginning of this stage. The Consultant’s specific activities include:
5 | 1 | Monthly attendance at the following meetings: · Principal’s meeting · Integrated project team (IPT) meeting · Design Review Workshop · Risk Management · Quality Monitoring Site Inspections
5 | 2 | Provide support and advice to the Client with regard to regulatory compliance of the design information developed by the Contractor Team.
5 | 3 | Provide support to reconcile comments between the Contractor Team, TPI User Groups and the Project Manager on design information being prepared by the Contractor.
5 | 4 | Support and advice to the Client with regard to regulatory compliance of the design information developed by the Contractor Team.
5 | 5 | Provide support to reconcile comments between the Contractor Team, TPI User Team and the Client’s Project Manager on design information being prepared by the Contractor.
5 | 6 | Support the Project Manager in the Change Control Process based on input from the Client and the Contractor, where appropriate.
5 | 7 | Provide support to review and advise on issues related to reconciliation of design proposals and contractual requirements via the Request for Project Manager’s Instruction (RPMI) process.
5 | 8 | Provide support to review information issued by the Contractor.
5 | 9 | Conduct sample reviews of record drawings and O&M Manual submittals as prepared by the contractor. Such reviews will be conducted on the basis of a benchmark set of such Record Drawings and O&M Manual submittals prepared by the contractor and approved by the Client prior to any OEM Manuals and Record Drawing Reviews being conducted. Review such Record Drawings and O&M Manuals for general completeness. Such reviews will not represent a full check of the documents for accuracy (assumption that any such accuracy verification will be performed by others i.e. the Clerk of Works) and the reviews are based on the assumption that it is the contractor’s responsibility to provide a complete set of information in the manner specified under the contract.
5 | 10 | Attendance at HAZOP and other containment design related meetings conducted on the project site.
5 | 11 | Review of design information prepared by the Contractor Team and related to the containment design of the project.
5 | 12 | Review of containment related work package submittals including, but not limited to, the list below. The proposal is based on conducting one such review per work package submittal. The reviews are limited to advising the Client that the information generally complies with the design intent documented in the Client’s Requirements.
5 | 13 | Technical support and technical advice in the form of answers to Request for Information (RFI) as related to containment/ laboratory design during the anticipated construction period.
5 | 14 | Review of contractor design related work package submittals to confirm compliance with the design intent documented in the Client’s Requirements.
5 | 15 | Co-ordinate and manage production of snagging lists following site visits and assist Project Manager in monitoring rectification works to areas of non-compliance against the Clients Requirements. Use all reasonable endeavours to procure that operational-critical defects are rectified prior to operational start.
5 | 16 | Review the Contractor’s procedures for the release of design information for acceptance by the Project Manager. Notify the Project Manager of any comments, discrepancies, ambiguities, inconsistencies, errors or omissions and non-compliance.
5 | 17 | Advise the Project Manager on submissions required from the Contractor for design information.
5 | 18 | Monitor the developing design that is relevant to the services. Notify the Project Manager accordingly of any concerns and issues, discrepancies, ambiguities, inconsistencies, errors or omissions and non-compliance.
5 | 19 | Review and examine all design information submitted by the Contractor [via Conject], which is relevant to the services (including drawings, schedules, detailed designs, shop fabrication drawings, standard details, specifications, final Room Data Sheets, loaded room layout drawings and technical submittals). Confirm to the Project Manager that it is consistent and coordinated. Notify the Project Manager of any comments and non-compliance with the Works Information and any legal or statutory requirements. This will continue until such time that all Contractor submittals are approved on Aconex (prior to associated/ relevant works commencing on site).
5 | 20 | Support the Cost Manager in the assessment of their valuations, where appropriate, in terms of advising on the completeness of activities / works on site.
5 | 21 | Advise on the need for special inspections or tests during construction. Attend tests.
5 | 22 | Review quality control and testing procedures for compliance with contract requirements. Review results of performance demonstration tests.
5 | 23 | Review the Contractor’s procedures for the release of design information for submission to and approvals by the Local Planning Authority.
5 | 24 | Review samples, prototypes and benchmarks of materials, components and assemblies for conformity with contract requirements. Determine if amendments and resubmission for review needed and issue comments.
5 | 25 | Review the Contractor’s procedures for the provision of samples for submission to and approvals by the Local Planning Authority before that part of development is commenced on site:
5 | 26 | Witness final testing to demonstrate performance of architectural materials, components and assemblies.
5 | 27 | Review impact of Client variations on design, assist in preparation of material to be submitted to Contractor as part of a Project Manager Instruction.
5 | 28 | Attend monthly progress, quality and technical review meetings on site and advise the Project Manager and Client of any relevant issues and concerns.
5 | 29 | In collaboration with the Project Manager and Client, review the Contractor’s preparation for Soft Landings and notify the Project Manager of any non-compliance with the Building Contract and TPI procedures.
5 | 30 | Assist the Project Manager in connection with Contractor notifications, Contractor communications, Early Warning Notification (EWN) and Notification of Compensation Events (NCE) under the Building Contract that is relevant to the services.
5 | 31 | Make regular visits to the site as appropriate (monthly as a minimum) to check on workmanship, compliance with good practice and compliance with the Works Information. Notify the Project Manager of the outcomes of these visits and whether any Defects were identified or any other concerns.
5 | 32 | When conducting site visits, check that rigorous safety policies are in place by the Contractor and that all statutory health and safety requirements are being observed by all those responsible for either designing or constructing the works. Notify the Project Manager of any concerns.
5 | 33 | Attend off-site visits to Subcontractors and review mock-up installations or samples that are relevant to the services against the Building Contract and notify the Project Manager of any comments, discrepancies, ambiguities, inconsistencies, errors or omissions and non-compliance.
5 | 34 | Review and inspect samples submitted by the Contractor that are relevant to the services. Notify the Project Manager of any comments, discrepancies, ambiguities, inconsistencies, errors or omissions and non-compliance.
5 | 35 | In collaboration with the Project Manager and Client, review the preparation of the Energy Performance Certificate by the Contractor and notify the Project Manager of any non-compliance.
5 | 36 | In conjunction with the Project Manager and Client, review in draft and final form all handover documentation, including As-Built Information and the operation and maintenance manuals for the works that are relevant to the services. Notify the Client and Project Manager of any comments as to its adequacy and non-compliances with the Building Contract and TPI procedures.
5 | 37 | In conjunction with the Project Manager and Client, examine the first 12 months’ maintenance proposal, comment on the adequacy of this that are relevant to the services and notify the Client and Project Manager of any comments and non-compliances with the Building Contract.
5 | 38 | Attend witness commissioning of the works relevant to the services. Notify the Project Manager of any Defects or non-compliance with the Building Contract.
5 | 39 | Support the Commissioning, Verification & Validation (CVV) with the relevant regulatory bodies, to ensure the facilities meet the correct standards and assist the Project Manager in identifying non compliant work or defects.
5 | 40 | Attend relevant inspections and assist the Project Manager in identifying incomplete work or Defects prior to the issue of the Completion Certificate under the Building Contract.
5 | 41 | In conjunction with Project Manager and Client, inspect the works on Completion. Record and issue a list of Defects at the appropriate time.
5 | 42 | If instructed, assist the Client and Project Manager in any adjudication proceedings issued in respect of the works, in so far as they relate to matters which are relevant to the services.

## 2.9 RIBA 6
Applies to RIBA Stage 6 - Handover [MDT Role: NEC Supervisor]
Back to Summary Page
RIBA Stage | Item No. | Scope | Bidder Comment / Clarification / Addition
REFER TO "ALL STAGES" OF THIS SCOPE OF WORKS
This stage is the period from Completion of the whole of the works until the defect date, which is 12 months. The Consultant’s specific activities include:
6 | 1 | Attend the post-project Lessons Learned workshop.
6 | 2 | Review any potential defects that are relevant to the services and determine whether they are a Defect in accordance with the Building Contract and advise the Project Manager accordingly.
6 | 3 | Attend site inspections as appropriate and advise the Project Manager as necessary in connection with the Contractor correcting any Defects. Inspect the works 2 weeks prior to the defects date and notify the Project Manager of any outstanding Defects.
6 | 4 | In collaboration with the Project Manager, review and advise the Client as to the appropriateness of issuing the Defects Certificate.

## 2.10 RIBA 7
Applies to RIBA Stage 7 - Use
Back to Summary Page
RIBA Stage | Item No. | Scope | Bidder Comment / Clarification / Addition
REFER TO "ALL STAGES" OF THIS SCOPE OF WORKS
7 | 1 | Attend post occupancy lessons learnt workshop 6-12 months after practical completion is certified.
7 | 2 | Implement Client’s Soft Landings requirements, including attending meetings in accordance with the Soft Landings
7 | 3 | Attend post occupancy BREEAM and Client’s Environmental Sustainability Requirements workshop 12 months after practical completion is certified for permanent operations following completion of the project and, where action by the Client is necessary, assist the Client to take that action, including providing all evidence necessary to the BREEAM Assessor.

## 2.11 DRM
Design Responsibility Matrix
Back to Summary Page
INTRODUCTION
The Consultant is to complete this Design Responsibility Matrix (DRM) as part of the initial submission. The Consultant should amend the Consultant Team columns to reflect their proposed team, adding and deleting disciplines as necessary. The Consultant should amend the list of tasks shown for each CAWS section as necessary to suit his scope by adding or deleting from the list as necessary. The Row and Column headings shown are for guidance only and should not be taken as an indication of what may or may not be necessary to complete the Consultant's responsibilities to deliver a complete and fully coordinated Design.
DEFINITIONS:
Consultant: The Party contracted to deliver the design including all subconsultants Design: That produced by the Consultant for tender and contract purposes. Detailed Design; The final design for manufacture and installation. Working Drawings: Drawings representing the Detailed Design. SSC: A specialist (design and build) sub-contractor responsible for completing the Detailed Design reflecting the performance and design intent requirements stipulated in the Design.
KEY: P (Primary): Lead, manage, coordinate, develop and complete the Design element indicated to the required level of detail. Obtain all information required from others to achieve this in line with the programme. Finalise all interfaces. S (Secondary): Provide all required and necessary information/ input upon which the Primary depends to complete his role and the Design. C (Contribution): Provide reliable information and input to the Primary and Secondary as required.
|  | MDT Consultants | [26 empty] | Ultimate Design Responsibility
Column2 | Column1 | Design Lead | Architec tural Design | Civil & Structural Design | Building Services Design | Principal Designer | Health & Safety Consultant | Environmental Consultant | Sustainability / BREEAM Consultant | BREEAM Assessor | Landscape Architect | Acoustici Consultant | Information Management Consultant / BIM Consultant | Security Consultant | Building Control | Laboratory Planning | Biocontainment Specialist | Interior Design | Design Review / Monitoring role | Fire Strategy Consultant | Noise and Vibration Consultant | Lighting Consultant | IT / AV Consultant | Waste Consultant | Ecology Consultant | FF&E Consultant | Planning and Environmental Impact Assessment - Various Supporting Consultants | Commissioning Validation and Verification (CVV) Consultant | 100% Detailed Design by the Consultant | Completion of Detailed Design and Working Drawings by SSC.
Name of Company
A | Existing Site Buildings and Services
1 | Demolition Scope
2 | Utilities - power, water and communications connections
3 | Utilities - foul and surface water connection
4 | Utilities diversions
5 | Utility Temporary provisions
6 | Site Investigation (Geotechnics and hydrology)
7 | Topographical survey Scope
8 | Transport/traffic Survey scopes
9 | Building Survey scopes (Fabric Demolition)
10 | Acoustic survey scopes
11 | Building Services survey scopes
12 | Utilities surveys scopes
13 | Structural & Contamination Survey scope
14 | Asbestos Survey Scope
15 | Archaeological Baseline Review
16 | Archaeological Report
17 | Ecology Survey and Report
18 | Transport Temporary Works
19 | Party wall temporary retention
B | Groundwork
1 | Soil stabilisation
2 | Underpinning
3 | Retaining Structures / Sheet piling
4 | Excavation & groundwork
5 | Permanent Dewatering (Feasibility)
6 | Landscape Temporary Works
7 | Sleeves for services
8 | Sleeves for drainage
9 | Re routing & disconnections of underground drainage services
10 | Underground (beneath lowest slab level and bearing on earth) service trenching, pits, ducts etc. Integral with the primary structure.
C | In situ concrete and precast concrete.
1 | Dimensional co-ordination, setting out and tolerances
2 | Piling and foundation Structures
3 | Sub-Structure inc pilecaps, pressure slabs, ground beams etc
3a | Gas protection systems - passive
3b | Gas protection systems - active
3c | Waterproofing - Concrete additives & rebar crack control
3d | Waterproofing - membranes or internal drained cavity
4 | Sub bases
5 | Below ground insulation
6 | In-situ concrete elements (reinforced)
7 | Structural Pre-cast and pre stressed & post tensioned concrete elements
8 | Non Structural pre-cast concrete elements (sills/copings including material colour, composition, form shape and visual intent)
9 | Structral movement, deflection, jointing and tolerances
10 | Ground retention
11 | Structural Load requirements
12 | Structural Slab profiles
13 | Related details of lift pits sumps, trenches, services pop ups
14 | Structural Penetrations
15 | Slab edge, beam, step details >20mm
16 | Reinforcement design - foundations and superstructure
17 | Vibration Design Criteria
18 | Cast-in conduits, pipes and sleeves
19 | Access Chambers covers on lowest slab level - full spec - in connection with drainage
20 | Access Chambers covers on lowest slab level - performance spec - in connection with other non drainage related services.
D | Masonry
1 | Free standing Structures (walls, fences etc)
2 | Free standing Structures foundations
3 | Masonry loadbearing Structures
4 | Loadbearing partitions
5 | Lintels
6 | Windposts, masonry support, support angles, secondary structure, cladding support and restraint systems
7 | Load bearing natural stone walling
8 | Accessories for masonry walling - ties & straps
9 | Accessories for masonry walling - vapour barriers
10 | Accessories for masonry walling - insulation
11 | Metal sills
12 | Bracing
13 | Panels forming perimeter cladding or internal partitions
14 | Exposed Internal masonry walling - visual appearance
15 | Exposed external masonry - visual appearance
E | Structural carcassing, metal and timber.
1 | Metal decking
2 | Structural steel framing (Primary)
3 | Structural steel framing (Secondary)
4 | Structural aluminium framing (Secondary)
5 | Isolated Structural metal members (Secondary)
6 | Timber Structures (Primary)
7 | Timber Structures (Secondary)
8 | Pre-fabricated timber unit decking
9 | Steel and timber connection design
10 | Structural movement, deflection and tolerances
11 | Corrosion protection
12 | Steelwork provision for concealed specialist masonry / envelope support
13 | Plinths / propping / supports for plant and plant screens
F | Facades and Cladding.
1 | Loading design criteria: dead and imposed, dynamic & wind.
2 | Secondary Steelwork to cladding
3 | Daylight and Sunlight - design implementation
4 | Thermal performance and airtightness (setting performance)
5 | Thermal performance and airtightness (meeting performance)
6 | Acoustic performance
7 | Cladding/Curtain walling - traditional and systems
8 | Patent glazing
9 | Structural movement, deflection and tolerances
10 | Penetrations
11 | Podium penetration elements (ventilation grills etc)
12 | External Walls Power Supply, Security And Protection
13 | Supports and fixings and adhesives
14 | Access and maintenance platforms/systems
15 | Louvres and plant screens
16 | Canopies Structural design
17 | Canopies drainage
18 | Canopies
19 | Facade access installations
20 | Rooflights, vents and overhead glazing elements
21 | Green Roofs
22 | Roof build-up and terraces
23 | Balustrade, barriers and guarding - Structural design
24 | Balustrades, barriers and guarding - Design Intent
25 | Balconies Soffit Coverings
26 | Balconies Finishes
27 | Structural glass assemblies
28 | Pavement lights
29 | Rainscreen cladding
30 | Sheet / board cladding elements
31 | Profiled / flat sheet cladding / covering / siding
32 | Panel cladding elements
33 | Pre-cast Concrete cladding - fixings
34 | Pre-cast Concrete cladding - Design Intent
35 | Natural stone slab cladding
36 | Tiled cladding
37 | Lead sheet coverings / flashings
38 | Aluminium / copper / zinc sheet coverings / flashings
39 | Stainless steel sheet coverings / flashings
40 | Tensile fabric elements
41 | Sealants, mastic, backing rods etc
42 | Mortar
43 | Timber Cladding
44 | Lightweight Framed Systems
G | Waterproofing
1 | Cementitious coatings
2 | Mastic Asphalt roofing / insulation / coatings
3 | Liquid applied coatings
4 | Retaining wall retention
5 | Cut / Fill studies
6 | Waterproofing above ground generally (except pools)
7 | Cladding water proofing
8 | Flexible sheet waterproofing
9 | Single Layer polymeric roof coverings
10 | Concrete water retaining structures
H | Linings, sheathing and dry partitioning.
1 | Internal plasterboard dry wall partitioning
2 | Internal plasterboard dry lining to masonry walls
3 | Internal panels - metal, timber, GRP, GRC etc
4 | Fixings and connections
5 | Proprietary partitioning - solid, glazed
6 | Joinerywork, carpentry - skirtings, architraves, etc
7 | Partition setting out
8 | Plasterboard / GRP / GRC ceilings
9 | Miscellaneous lined soffits
10 | Rigid sheet flooring
11 | Framed panel cubicles
12 | Demountable suspended ceilings
13 | Raised access flooring
14 | Insulation - acoustic
15 | Insulation - fire
16 | Bracing
17 | Metal Stud partition holing
18 | Suspended ceiling fixing and support
I | Windows, doors and stairs.
1 | Thermal performance and airtightness (including calculations)
2 | Proprietary doors, shutters, hatches
3 | Windows & glazing
4 | Rooflights / roof windows
5 | Internal doors / architraves / frames
6 | Ironmongery and security accessories
7 | External louvres
8 | Stairs / walkways / balustrades - Arch metalwork
9 | Bespoke Doors / shutters / hatches
10 | Stair design
11 | Stair Structure (including auditorium / theatre seating)
J | Surface finishes.
1 | Structure Protective finishes - fire
2 | Structure Protective finishes - moisture
3 | Structure Aesthetic finishes
4 | Exposed Concrete finishes
5 | Specialist Cement screeds / toppings / trowelled flooring
6 | Internal Wall finishes
7 | External Wall finishes
8 | Epoxy resin flooring
9 | Plastered / rendered / roughcast coatings
10 | Insulation with rendered finish
11 | Sprayed monolithic coatings
12 | Resin bound mineral coatings
13 | Internal Ceiling finishes
14 | External soffit finishes
15 | Miscellaneous metalwork finishes
16 | Architectural metalwork finishes
17 | Joinery work / carpentry finishes
18 | Internal Door finishes
19 | External door finishes
20 | Window/ curtain walling finishes
21 | Render / stucco / roughcast / pebbledash finishes
22 | Services components finishes
23 | Work related to plastered coatings - mesh lathing, anchored reinforcement
24 | Rigid tiles - ceramic / stone / terrazzo etc
25 | Flexible sheet / tile coverings - rubber, plastics, cork, carpet
26 | Painting / clear finishing
27 | Internal floor finishes (inc skirtings)
28 | Trowelled bitumen / resin / rubber - latex flooring
K | Furniture and equipment.
1 | General purpose fixtures / furnishings / equipment
2 | Domestic kitchen fittings
3 | Catering equipment
4 | Sanitary appliances / fittings
5 | Plant containers
6 | Signage / notices
7 | Special purpose fixtures / furnishings / equipment
8 | Sports Equipment
L | Building fabric sundries.
1 | External signage illumination
2 | Miscellaneous metalwork
3 | Sundry proofing / insulation - fire stopping
4 | Foamed / fibre / beaded wall insulation
5 | External Door / Window Ironmongery
6 | Internal Sealant/mastic joints
M | Paving, planting, fencing and site furniture.
1 | Flood Risk Analysis
2 | Hard landscaping inc finishes, build-up details
3 | Site external works setting out & levels
4 | Balustrade, barriers and guarding - Structural design
5 | Balustrades, barriers and guarding
6 | Soft landscaping / planting
7 | Green wall design
8 | Fences, gates
9 | Fences, gates supporting Structure
10 | Public art
11 | Landscape / street furniture & base details
12 | Services to water features
13 | Kerbs / edgings / channels/ paving accessories
14 | Granular sub bases to roads / pavings / parking area s/ kerbs
15 | In situ concrete roads / pavings / parking areas / kerbs bases
16 | Coated macadam / asphalt roads / pavings
17 | Gravel roads / pavings
18 | Interlocking brick/block roads/pavings
19 | Sett/cobble pavings
20 | Seeding / turfing
21 | Planting
22 | Landscape maintenance
N | Disposal systems.
1 | Roof gutters and external rainwater goods
2 | Spillage / leakage containment to basement
3 | Internal rainwater downpipes
4 | Waste handling and collection strategy
5 | Surface water drainage, harvesting and disposal
6 | Below ground foul and surface water drainage (inc. connection to extg sewers)
7 | Above ground foul and surface water drainage
8 | Sewage pumping not within below ground foul and surface water drainage
9 | Refuse chutes
10 | Compactors / macerators
11 | Automated refuse systems
12 | Testing and commissioning of disposal systems
13 | Condensate drainage
14 | Positioning of gutters and rainwater goods
15 | Petrol interceptors
16 | Below ground SUDS devices
17 | Pump units, rising mains, sump sizes - below ground system
18 | Rising mains - above ground
19 | Drainage to rainwater tanks
20 | Soft Landscaping drainage
O | Piped supply systems.
1 | Cold water supply, storage and distribution
2 | Hot water production and distribution
3 | Irrigation systems
4 | Irrigation storage / supply
5 | Water features and fountains
6 | Treated de-ionised distilled water supply
7 | Natural gas
8 | Retaining wall retention
9 | Cut / Fill studies
10 | Dry risers
11 | Sprinklers / drencher systems
12 | Deluge
13 | Fire hydrants
14 | Gas fire fighting supply
15 | Pumps
16 | Water tanks / cisterns
17 | Heat exchangers
18 | Storage cylinders / calorifier
19 | Trace heating
20 | Cleaning and chemical treatment
21 | Testing and commissioning of piped supply systems
24 | Pipework identification
25 | Speacialst gas systems
P | Mechanical heating, cooling and refrigeration systems.
1 | Gas/oil fired boilers / flues
2 | Direct electric boilers
3 | Heat pumps
4 | Solar collectors
5 | Alternative fuel boilers
6 | Primary heat distribution
7 | Low temperature hot water heating
8 | Warm air heating
9 | Local heating units
10 | Heat recovery
11 | Central refrigeration plant
12 | Local cooling units
13 | Cold rooms
14 | Under floor heating - water based
15 | Air diffusers/grilles
16 | Chilled ceilings
17 | Testing and commissioning of heating, cooling and Refrigeration systems
18 | Mechanical identification
Q | Ventilation and air conditioning systems.
1 | Plant room and Services riser sizes and positions
2 | Secondary plant support for Services and equipment
3 | Acoustic attenuation of plant items
4 | Acoustic advice - noise levels, noise break out, attenuation
5 | General ventilation
6 | Toilet ventilation
7 | Smoke extract / smoke control
8 | Low velocity air conditioning
9 | Air conditioning (all air) - VAV, Dual duct / multi
10 | Air conditioning (air / water)
11 | Air conditioning - hybrid
12 | Local Air conditioning units
13 | Air curtains
14 | Air handling units
15 | Air filtration
16 | Air treatment
17 | Grilles / diffusers / louvres
18 | Testing and commissioning of mechanical Services
19 | Vibration Isolation mounting
20 | Control components
21 | Mechanical identification
R | Electrical systems.
1 | Electricity generation plant
2 | LV supply / distribution / general lighting / general power
3 | Electrical substations and switchgear
4 | LV electrical and small power distribution
5 | Backup power systems (generation)
6 | Containment for all Services systems distribution
7 | Lightning protection and earthing
8 | External lighting design intent
9 | External lighting design implementation
10 | Internal lighting design intent
11 | Internal lighting engineering design implementation & scheduling
12 | Emergency and escape lighting
13 | Extra low voltage supply
14 | DC supply
15 | Uninterrupted power supply
16 | Testing and commissioning of electrical Services
17 | Photovoltaic arrays
S | Communications, security, safety and protection systems.
1 | External security systems
2 | Security risk assessment and strategy
3 | Access control and video entry systems
4 | CCTV systems & monitoring
5 | Security lighting
6 | Intruder detection and alarm
7 | Incoming communications connections
8 | IT containment, cabling & termination
9 | Estate IT equipment (pc's, printers, Servers, switches, office telephone system)
10 | Public address systems
11 | Wireless communications - Radio and telephone signal
12 | Radio / TV / satellite / cable
13 | Projection
14 | Information / advertising display
15 | Data systems / transmission
16 | Estate IT room cooling
17 | Fire strategy
18 | Design implementation of fire strategy
19 | Fire suppression / smoke control installations
20 | Retaining wall retention
21 | Cut / Fill studies
22 | Earthing and bonding
23 | Lightning protection
24 | Gas detection alarms
25 | Electronic bird / vermin control
26 | Central control / building management systems
27 | AV Strategy
28 | AV Design / product specification
T | Transport systems.
1 | Servicing, deliveries and removals strategy
2 | Road markings & signage
3 | Secure by Design
4 | Travelling cradles / gantries / façade maintenance
5 | Passenger and goods lifts
6 | Lift car finishes design intent
7 | Lift car finishes design implementation
8 | Kerb setting out / turning circle diagrams
U | General Engineering Services.
1 | Temporary works design
2 | Statutory Services negotiations
3 | Energy Strategy
4 | Sustainability Strategy
5 | Renewable energy installations
6 | BWIC (builders work in connection)
7 | Building Services controls
8 | Provision for tenants' plant
9 | Testing and Commissioning Strategy
V | Interiors
1 | Interiors/fit-out concepts
2 | Common areas interiors/fit-out concepts
3 | Interiors/fit-out dimensional co-ordination
4 | Interiors/fit-out design implementation
5 | Interiors/fit-out Services design implementation
6 | Statutory signage
7 | Wayfinding and building signage
8 | AV strategy
9 | AV implementation
11 | Purpose made joinery
12 | Purpose made metalwork
13 | Preservative / fire retardant coatings for timber
14 | Fixings / adhesives
16 | Sealants
17 | Specialist flooring - Sports Facilities
18 | Performance criteria - Sports facilities
19 | Sports facilities building fabric
20 | Specialist flooring - Performance Spaces
Note on B29: Do we want survey scope included? or is that a separate scope?
Note on B66: Project sepecific?
Note on B119: Not required?
Note on B184: Not rerquired?
Note on B237: Not required?
Note on B240: Not required?
Note on B382: Not required?
Note on B413: Repeat from earlier section? Or separate as interior??

## 2.12 Minimum Deliverables
Minimum Deliverables
Back to Summary Page
Minimum Deliverables | RIBA 0 | RIBA 1 | RIBA 2 | RIBA 3 | RIBA 4 | RIBA 5 | RIBA 6 | RIBA 7
3-D Fly through model | bar: RIBA 3
All relevant information / drawings uploaded to the Employer’s Information Management system. | bar: RIBA 0 to RIBA 7
Application for statutory approvals. | bar: RIBA 4
Concept Design of chosen Option – to include drawings and report for Employer sign-off. | bar: RIBA 2
Contribution to / agreement of KPIs. | bar: RIBA 1
Contribution to appraising tenders. | bar: RIBA 4
Contribution to Cost Plan. | bar: RIBA 0 to RIBA 7
Contribution to identification and evaluation of potential contractors and/or specialists for the project. | bar: RIBA 4
Contribution to issuing of information to the Contractor. | bar: RIBA 5 to RIBA 7
Contribution to Lessons Learned Workshop and Report. | bar: RIBA 5 to RIBA 7
Contribution to Procurement Strategy. | bar: RIBA 1
Contribution to Risk Register, Risk Management and Mitigation | bar: RIBA 0 to RIBA 7
Contribution to submission of recommendations to the Employer. | bar: RIBA 4
Contribution to Value Management plan. | bar: RIBA 0 to RIBA 7
Coordinated RIBA Stage 3 Design of chosen Option – Report and coordinated drawings to include structural and building services systems and updated outline specifications for development into Stage 1 Tender Document Employers Requirements. | bar: RIBA 3
Design Meeting Schedule (regularly reviewed and updated). | bar: RIBA 0 to RIBA 7
Detailed Planning Permission Application. | bar: RIBA 3
Draft NBS specifications for Architectural, Civil & Structural and Building Services elements | bar: RIBA 3
Draft of Planning Permission Application. | bar: RIBA 2
Draft Options Report (minimum of 3 options to be provided with initial design concepts). | bar: RIBA 1
Employer Meeting Schedule (regularly reviewed and updated). | bar: RIBA 0 to RIBA 7
End of Stage Report. | bar: RIBA 0 to RIBA 7
Final Options Report (with developed design concepts and recommended Option). | bar: RIBA 1
Information for statutory standards and construction safety. | bar: RIBA 4
Initial acoustics strategy | bar: RIBA 3
Initial interior design strategy including finishes and door schedules | bar: RIBA 3
Initial wayfinding and signage strategy | bar: RIBA 1
Outline proposals for structural and building services systems and outline specifications. | bar: RIBA 2
Planning Strategy. | bar: RIBA 2
Preparation of Employers Requirements in sufficient detail to enable a tender or tenders to be obtained. | bar: RIBA 4
Preparation of Employers Requirements in sufficient detail to enable a tender or tenders to be obtained. | bar: RIBA 4
Preparation of further information for construction required under the building contract. | bar: RIBA 4
Progress and KPI performance reports (monthly). | bar: RIBA 0 to RIBA 7
Rendered computer generated images | bar: RIBA 3
Review of existing brief and any existing project and site information. | bar: RIBA 1
Technical appraisal of contractor’s tender proposals | bar: RIBA 4
Scale drawings
Initial 1:100 civil & structural engineering drawings
Initial 1:100 electrical services schematic drawings
Initial 1:100 General Arrangement Drawings
Initial 1:100 mechanical services schematic drawings
Initial 1:100 public health schematic drawings
Initial 1:200 external works plan
Initial 1:50 Room Data Sheets.
Initial 1:50 sections and elevations
Initial 1:500 Site Locality Plan
Revised 1:100 General Arrangement Drawings
Revised 1:200 external works plan
Revised 1:50 Room Data Sheets, fully loaded including Room Elevations.
Revised 1:50 Room Data Sheets.
Revised 1:50 sections and elevations
Revised 1:500 Site Locality Plan
Logistics / Circulation Strategy
Initial Logistics/ Circulation Strategy for the site and facility.
Draft Logistics / Circulation Strategy for the site and facility.
Revised Logistics/ Circulation Strategy for the site and facility.
Final Logistics/ Circulation Strategy for the site and facility.
Biosecurity and Biosafety
Initial Bio-security and Biosafety Report.
Draft Bio-Security and Biosafety Report.
Revised Bio-Security and Biosafety Report.
Final Bio-Security and Biosafety Report.
Phasing Plan
Initial Phasing Plan.
Draft Phasing Plan.
Revised Phasing Plan.
Final Phasing Plan.
BREEAM
Initial BREEAM assessment, followed by a BREEAM Report recommending an approach to achieve XXXX
Revised BREEAM assessment, including revision of the BREEAM Report.
Revised BREEAM assessment.
BIM
BIM data drop
BIM data for Detailed Planning Permission Application.
BIM data for environmental performance and area analysis.
BIM Inputs and Outputs.
BIM Specification.
Key BIM model elements and concept level parametric objects.
End of Construction BIM record model data.
4D or 5D BIM Assessment
Room Data Sheets
Initial Room Data Sheets.
Revised Room Data Sheets.
Final Room Data Sheets.
Building Control
Initial Building Control Report.
Draft Building Control Report.
Revised Building Control Report.
Final Building Control Report.
Security Strategy
Initial Security Strategy.
Draft Security Strategy.
Revised Security Strategy.
Final Security Strategy.
DDA
Draft DDA Report.
Revised DDA Report.
Final DDA Report.
Site Waste Disposal
Initial Site Waste Disposal Report.
Draft Site Waste Disposal Report.
Revised Site Waste Disposal Report.
Final Site Waste Disposal Report.
Facilities Management Strategy
Initial Facilities Management Strategy.
Revised Facilities Management Strategy.
Final Facilities Management Strategy.
Sustainability Strategy
Initial Sustainability Strategy.
Draft Sustainability Strategy
Revised Sustainability Strategy.
Final Sustainability Strategy.
Fire Strategy
Draft Strategy
Revised Fire Strategy.
Final Fire Strategy.
Whole Life Cost
Contribution to Whole Life Cost information
Agendas
Agendas and Minutes for Design Meetings (issue within 2 working days of meeting).
Contribution to Agendas for Client Meetings.
Contribution to Agendas for Employer Meetings.
Landscape Strategy
Initial Landscape Strategy.
Draft Landscape Strategy.
Revised Landscape Strategy.
Final Landscape Strategy.
Bidder to List Any Additional / Intended Deliverables

## Lookup
DRM
P
S
C