## Summary Sheet - Lot 3
Pirbright Innovations Limited
Veterinary Vaccine Manufacturing and Innovation Centre (Vet VMIC)
Lot 3 - Multi-Disciplinary Design Team
Tender Evaluation Quality Criteria
Name of Tenderer:
Ref | Subject Area |  | Weighting for Section
1 | General Management & Resources |  | 19%
2 | Project Understanding |  | 31%
3 | Presentation |  | 20%
|  | Quality Evaluation Total | 70%

## Method Statement
Pirbright Innovations Limited
Veterinary Vaccine Manufacturing and Innovation Centre (Vet VMIC)
Lot 3 - Multi-Disciplinary Design Team
Tender Evaluation Method Statement
Name of Tenderer:
Ref | Question | Page limit | % age Weight-ing | Scoring Criteria
1 | General Management & Resources
1.1 | Provide the names, qualifications and experience of your proposed delivery team presented as an individual 1-page profile per person (including their proposed role, responsibilities and added value, as applicable to this project) for each of your key personnel in your team. Please also provide an organogram setting out the consortium structure proposed for this project including the key account manager. | 1 page per profile | 5% | 5 – Substantial evidence of a proposed team appropriate to deliver the works required that exceeds the requirements 4 – Good evidence of a proposed team appropriate to deliver the works required that slightly exceeds the requirements 3 – Generally provides evidence of a proposed team appropriate to deliver the works required that meets the requirements 2 – Partial evidence of a proposed team appropriate to deliver the works required but fails to meet the requirements 1 – Substantially fails to evidence a proposed team appropriate to deliver the works required 0 – Does not meet the requirement, fails to respond or to provide supporting evidence
1.2 | Identify 5x facilities / case studies of a similar technical nature that your company/key individuals or consortium identified in question 1 have been directly engaged with and have either completed or are currently on site / post contract post 2010. Project examples from the following sectors would be considered:- 1. Government / institutional research GLP/GMP laboratories / clean rooms 2. Higher education research / teaching GLP/GMP laboratories / clean rooms 3. Pharmaceutical / commercial research GLP/GMP laboratories / clean rooms 4. Healthcare support GLP/GMP laboratories / clean rooms The following information should be provided for each facility: Client, GIFA, start and completion dates, procurement route, construction cost, components of facility, services provided / role, containment level (if applicable), members of the proposed team directly involved in the project. Please identify what added value your team/individuals brought to the project and lessons learnt that could be applied to this project. Please identify where your supply chain/consortium have successfully delivered projects together, either as an integrated team or as separate direct appointments. | 1 page per case study | 8% | 5 – Substantial evidence of previous case history that exceeds the requirements 4 – Good evidence of previous case history that slightly exceeds the requirements 3 – Generally provides evidence of previous case history that meets the requirements 2 – Partial evidence of previous case history but fails to meet the requirements 1 – Substantially fails to evidence previous case history to deliver the works required 0 – Does not meet the requirement, fails to respond or to provide supporting evidence
1.3 | Please set out how your specific company / personal behaviours and interpersonal skills will be applied positively throughout the duration of the project. You should concentrate on no more than TEN key behaviours and provide evidence related to your case history/experience | 2 pages | 3% | 5 - Substantial evidence of how specific company/ personal behaviours and interpersonal skills will be applied throughout the duration of the project that exceeds the requirements 4 - Good evidence of how specific company/ personal behaviours and interpersonal skills will be applied throughout the duration of the project that slightly exceeds the requirements 3 - Generally provides evidence of how specific company/ personal behaviours and interpersonal skills will be applied throughout the duration of the project that meets the requirements 2 - Partial evidence of how specific company/ personal behaviours and interpersonal skills will be applied throughout the duration of the project but fails to meet the requirements 1 - Substantially fails to evidence how specific company/ personal behaviours and interpersonal skills will be applied throughout the duration of the project 0 - Does not meet the requirement, fails to respond or to provide supporting evidence
1.4 | Based on your previous relevant experience, please set out how you propose to apply your experience/lessons learned in undertaking the required services and delivering added value to the project. | 1 page | 3% | 5 - Substantial evidence of approach to applying experience and lessons learned in undertaking the required services and delivering added value that exceeds the requirements 4 - Good evidence of applying experience and lessons learned in undertaking the required services and delivering added value that slightly exceeds the requirements 3 - Generally provides evidence of applying experience and lessons learned in undertaking the required services and delivering added value that meets the requirements 2 - Partial evidence of applying experience and lessons learned in undertaking the required services and delivering added value but fails to meet the requirements 1 - Substantially fails to evidence applying experience and lessons learned in undertaking the required services and delivering added value 0 - Does not meet the requirement, fails to respond or to provide supporting evidence
Sub-Total for Section |  |  | 19%
2 | Project Understanding
2.1 | The Authority is keen to ensure that the entire delivery team performs well and in accordance with their full scope of duties. To assist, the Authority would like you to propose suitable Key Performance Indicators to monitor your own performance. Please therefore provide the following:- - Proposed KPIs and targets - How data will be collected and analysed - What rectification measures you propose in the event of failure to achieve targets. | 1 page | 2% | 5 - Provides substantial evidence of KPIs and targets suitable to monitoring own performance. The response identifies routes for collecting and analysing data and measures to rectify in the event of failure to achieve targets that exceeds the requirements 4 - Good evidence of KPIs and targets suitable to monitoring own performance. The response identifies routes for collecting and analysing data and measures to rectify in the event of failure to achieve targets that slightly exceeds the requirements 3 - Generally provides evidence of KPIs and targets suitable to monitoring own performance. The response identifies routes for collecting and analysing data and measures to rectify in the event of failure to achieve targets that meets the requirements 2 - Partial evidence of KPIs and targets suitable to monitoring own performance. The response also fails to identify routes for collecting and analysing data and measures to rectify in the event of failure to achieve targets but fails to meet the requirements 1 - Substantially fails to evidence KPIs and targets suitable to monitoring own performance. The response also substantially fails to identify routes for collecting and analysing data and measures to rectify in the event of failure to achieve targets 0 - Does not meet the requirement, fails to respond or to provide supporting evidence
2.2 | Please set out your approach and leadership strategy for delivering the project in your role as MDDT through RIBA stages 1-4a, this should include how you will integrate the professional teams, internal teams/stakeholders. | 3 pages | 5% | 5 – Provides evidence of an appropriate approach for delivering the project through RIBA stages 1-4a that exceeds the requirements 4 – Provides evidence of an appropriate approach for delivering the project through RIBA stages 1-4a that slightly exceeds the requirements 3 – Provides evidence of an appropriate approach for delivering the project through RIBA stages 1-4a that meet the requirements 2 – Provides evidence of an appropriate approach for delivering the project through RIBA stages 1-4a that slightly fails to meet the requirements 1 – Substantially fails to provide evidence of an appropriate approach for delivering the project through RIBA stages 1-4a 0 – Does not meet the requirement, fails to respond or does not provide supporting evidence
2.3 | Please set out your approach and leadership strategy for delivering the project in your role as MDDT through RIBA stages 4b -6 , this should include how you will ensure the building meets the approved design | 3 pages | 5% | 5 – Provides evidence of an appropriate approach for delivering the project through RIBA stages 4b-6 that exceeds the requirements 4 – Provides evidence of an appropriate approach for delivering the project through RIBA stages 4b-6 that slightly exceeds the requirements 3 – Provides evidence of an appropriate approach for delivering the project through RIBA stages 4b-6 that meet the requirements 2 – Provides evidence of an appropriate approach for delivering the project through RIBA stages 4b-6 that slightly fails to meet the requirements 1 – Substantially fails to provide evidence of an appropriate approach for delivering the project through RIBA stages 4b-6 0 – Does not meet the requirement, fails to respond or does not provide supporting evidence
2.4 | The Authority has set out a "Design To Budget" principle and has a clearly defined budget and target operational costs for this project. Please set out your management processes and procedures to ensure that the project is delivered in line with the budget, set out how you will ensure that the design stays within cost plan/target operational costs and set out how you will manage and mitigate any issues that may arise during the design development. | 2 pages | 5% | 5 – Provides substantial evidence of effective cost management procedures that exceed the requirements 4 – Provides good evidence of effective cost management procedures that slightly exceeds the requirements 3 – Provides evidence of effective cost management procedures that meets the requirements 2 – Partially provides evidence of effective cost management procedures but fails to meet the requirements 1 – Substantially fails to provide evidence of effective cost management procedures that meets the requirements 0 – Does not meet the requirement, fails to respond or does not provide supporting evidence
2.5 | Please produce a project "Risk Register" identifying the top 10 TECHNICAL DESIGN Risks you expect to encounter on this project specifically. Tenderers are required to consider the risks on the project and complete accordingly, with due regard to:- - Identification of the risk including both the cause and consequence; - Proposed mitigation measures to minimise the impact of the risk; - Identification of the Risk Owner and Action Owner for each identified risk; - Assessment of the "Impact Severity", "Likelihood" and "Proximity"" to provide an overall assessment of risk. Your response should be presented in an Excel (or equivalent) table, colour coded (and scored) to illustrate the overall risks. | 1 page excel or equivalent | 4% | 5 – Substantial evidence of effective risk management strategies and understanding of potential risks to the project that exceeds the requirements 4 – Good evidence of effective risk management strategies and understanding of potential risks to the project that slightly exceeds the requirement 3 – Generally provides evidence of effective risk management strategies and understanding of potential risks to the project that meets the requirements 2 – Partial evidence of effective risk management and understanding of potential risks to the project but fails to meet the requirements 1 – Substantially fails to evidence effective risk management strategies and understanding of potential risks to the project 0 – Does not meet the requirement, fails to respond or to provide supporting evidence
2.6 | Please provide details of how you intend to engage proactively with the risk management process, focusing on identification of technical or design specific risks and the monitoring and controlling of mitigating actions. Please detail how you will engage with the Project Manager as the leader of the Risk Management process | 2 pages | 3% | 5 – Substantial evidence of effective risk management strategies and interpretation of the developed register in place that exceeds the requirements 4 – Good evidence of effective risk management strategies and interpretation of the developed register in place that slightly exceeds the requirements 3 – Generally provides evidence of effective risk management strategies and interpretation of the developed register in place that meets the requirements 2 – Partial evidence of effective risk management and interpretation of the developed register strategies in place but fails to meet the requirements 1 – Substantially fails to evidence effective risk management strategies and interpretation of the developed register are in place 0 – Does not meet the requirement, fails to respond or to provide supporting evidence
2.7 | Please provide details of your resilience plans that you have in place should key team members be unavailable during the project for a significant period due to illness, injury or permanently unavailable should they move from, or within, your company. This should include as a minimum: - Specific named individuals - Supporting systems | 1 page | 2% | 5 – Provides evidence of an efficient & effective resilience plan to ensure business continuity in the absence of a key staff member that exceeds the requirements 4 – Provides evidence of an efficient & effective resilience plan to ensure business continuity in the absence of a key staff member that slightly exceeds the requirements 3 – Provides evidence of an efficient & effective resilience plan to ensure business continuity in the absence of a key staff member that meets the requirements 2 – Provides evidence of an efficient & effective resilience plan to ensure business continuity in the absence of a key staff member that slightly fails to meet the requirements 1 – Substantially fails to provide evidence an efficient & effective resilience plan to ensure business continuity in the absence of a key staff member that meets the requirements 0 – Does not meet the requirement, fails to respond or does not provide supporting evidence
2.8 | The Authority works in a highly regulated and licenced environment. Please set out how you will ensure that the project delivers to the required standards (GLP/GMP/SAPO). | 2 pages | 5% | 5 - Substantial evidence of maintaining business continuity at all times that exceeds the requirements 4 - Good evidence of maintaining business continuity at all times that slightly exceeds the requirements 3 - Generally provides evidence of maintaining business continuity at all times that meets the requirements 2 - Partial evidence of maintaining business continuity at all times but slightly fails to meet the requirements 1 - Substantially fails to evidence maintaining business continuity at all times 0 - Does not meet the requirement, fails to respond or to provide supporting evidence
Sub-Total for Section |  |  | 31%
Total for Section (To Summary) |  |  | 50%

## Presentation
Pirbright Innovations Limited
Veterinary Vaccine Manufacturing and Innovation Centre (Vet VMIC)
Lot 3 - Multi-Disciplinary Design Team
Tender Evaluation Quality Criteria
Name of Tenderer:
Ref | Question | % age Weight-ing | Scoring Criteria
3 | Presentation
3.1 | Overview of the proposed team and in particular the Lead Individual heading up the ‘Multi-Disciplinary Design Team’. | 1% | 5 – Substantial evidence of a proposed team appropriate to deliver the works required that exceeds the requirements 4 – Good evidence of a proposed team appropriate to deliver the works required that slightly exceeds the requirements 3 – Generally provides evidence of a proposed team appropriate to deliver the works required that meets the requirements 2 – Partial evidence of a proposed team appropriate to deliver the works required but fails to meet the requirements 1 – Substantially fails to evidence a proposed team appropriate to deliver the works required 0 – Does not meet the requirement, fails to respond or to provide supporting evidence
3.2 | Overview of your leadership of the design process in your role as MDDT for delivering the project. | 5% | 5 – Substantial evidence of a 'Leadership Strategy' appropriate to deliver the works required that exceeds the requirements 4 – Good evidence of a 'Leadership Strategy' appropriate to deliver the works required that slightly exceeds the requirements 3 – Generally provides evidence of a 'Leadership Strategy' appropriate to deliver the works required that meets the requirements 2 – Partial evidence of a 'Leadership Strategy' appropriate to deliver the works required but fails to meet the requirements 1 – Substantially fails to evidence a 'Leadership Strategy' appropriate to deliver the works required 0 – Does not meet the requirement, fails to respond or to provide supporting evidence
3.3 | Overview of how you will ensure that the commissioning and verification is captured during the design phase and delivered during the build stage | 5% | 5 – Substantial evidence of an approach that exceeds the requirements 4 – Good evidence of an approach that slightly exceeds the requirements 3 – Generally provides evidence of an approach that meets the requirements 2 – Partial evidence of an approach but fails to meet the requirements 1 – Substantially fails to evidence an approach appropriate for the requirements 0 – Does not meet the requirement, fails to respond or to provide supporting evidence
3.4 | During the design phase it is noted that the scope of the project is increasing - what do you do? | 3% | 5 – Substantial evidence of a response that exceeds the requirements 4 – Good evidence of a response that slightly exceeds the requirements 3 – Generally provides evidence of a response that meets the requirements 2 – Partial evidence of a response but fails to meet the requirements 1 – Substantially fails to evidence a of a response appropriate for the requirements 0 – Does not meet the requirement, fails to respond or to provide supporting evidence
3.5 | It is noted that the project is not getting the engagement form the stakeholders resulting in delays and prolongation - how will you address this issue? | 3% | 5 – Substantial evidence of a response that exceeds the requirements 4 – Good evidence of a response that slightly exceeds the requirements 3 – Generally provides evidence of a response that meets the requirements 2 – Partial evidence of a response but fails to meet the requirements 1 – Substantially fails to evidence a of a response appropriate for the requirements 0 – Does not meet the requirement, fails to respond or to provide supporting evidence
3.6 | You have been invited to witness a the performance test of a critical system that has failed the performance test twice already – what do you do? | 3% | 5 – Substantial evidence of a response that exceeds the requirements 4 – Good evidence of a response that slightly exceeds the requirements 3 – Generally provides evidence of a response that meets the requirements 2 – Partial evidence of a response but fails to meet the requirements 1 – Substantially fails to evidence a of a response appropriate for the requirements 0 – Does not meet the requirement, fails to respond or to provide supporting evidence
Sub-Total for Section |  | 20%
Total for Section (To Summary) |  | 20%

## Sheet1 (hidden)
0
1
2
3
4
5