## Sheet1
CLARIFICATION LOG
Tender: | Park Gerry - Modular Building
Tender Reference:
Published Date: | 2023-04-06
Version number: | 0.4
Number | Clarification | Response | Reply date
1 | Within the tender documents of Vol 1 ITT, the client states they have undertaken a number of surveys. If possible, please provide reports from the surveys undertaken to aide the tender submission. | Following documents have been added for information purposes: South West Water Ltd Drainage & Water Search (Commercial Premium); FLOOD_RISK_ASSESSMENT-7134911; HERITAGE_STATEMENT-7126774; PA22_11292-PRELIMINARY_ECOLOGICAL_APPRAISAL-7126696; TRANSPORT_STATEMENT-7126734; Phase I Preliminary Risk Assessment (PRA) - Park Gerry 21441 | 2023-03-16
2 | Please can you advise where on the park/field the building will be positioned? | This is indicated in the concept designs that are included in the tender pack. Final location will be agreed with the succesful supplier and specified in the fullplanning application | 2023-04-03
3 | Who is responsible for bringing supplies to the building? | During the construction phase, the succesful supplier will be expected to manage all of their own materials to site. This will be via the Trannance Road entrance. | 2023-04-03
4 | Further to Q2 in terms of supplies we are referring to services supplies such as electric water etc? | All service connections are to be included in this tender | 2023-04-06
5 | Will this be awarded through crown commercial services? | No, the contract will be a looking to appoint as a direct result of this tender process. | 2023-04-06
6 | Could you provide a copy of the Contract Particulars, we are assuming that the JCT Conditions have no special amendments | The contract will be a standard JCT D&B, as agreed by both parties on signing. We do not expect there to be any amendments. If there are any specific concerns or recommendations then we will be happy to respond to those. | 2023-04-06
Clarifications will be published against the Contract Notice on Find a Tender and Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: