# Annex A

| Title of Project | Delivering Global Coral Reef Monitoring Network Monitoring (GCRMN) training to the UK OTs |
| --- | --- |
| Date and Time for Return of Bids | Friday 3 December 2021 @ 16:00 hours |
| Contract Reference Number | C21-0481-1615 |
| Address for Bid Submission | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND BIDS DIRECTLY TO BRYONY MEAKINS OR DORA IANTOSCA VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the individuals below, in the following order: Sue Wenlock (00 44 1733 866880) Chris Downes (00 44 1733 866877) |
| Contacts for Technical Information relating to this Project Specification | Joint Nature Conservation Committee Name: Bryony Meakins Email: bryony.meakins@jncc.gov.uk Telephone: OR Joint Nature Conservation Committee Name: Abbie Dosell Email: abbie.dosell@jncc.gov.uk Telephone: |
| Contact for Queries Regarding the Procurement Procedure | Dora Iantosca Finance Team Joint Nature Conservation Committee Email: Dora.Iantosca@jncc.gov.uk or contractqueries@jncc.gov.uk Telephone: 01733 866894 |
| Proposed Start Date | 10/12/2021 |
| Proposed End Date | 31/03/2022 |

Delivering Global Coral Reef Monitoring Network Training to the UKOTs

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Aims	3

3.	Project Background	3

4.	Project Objectives	5

5.	Project Objectives: Detailed Tasks 	5

6.	Potential Follow-On Work	7

7.	Outputs	7

8.	Product Specification	8

9.	Dissemination	8

10.	Timescale	8

11.	Health and Safety	9

12.	Project Management	9

13.	Instructions for Bid Submission	10

14.	Evaluation Criteria	11

15.	Payment	12

16.	Additional Requirements	12

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation

Our role is to provide scientific evidence, information, and advice to inform decisions to protect the natural environment. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally, by:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/

## Project Aims

The aim of this project is to build capacity in the UK Overseas Territories (OTs) to carry out coral reef monitoring activities that align with Global Coral Reef Monitoring Network (GCRMN) standards to better understand the health of coral reefs in Caribbean and Western Atlantic UK OT waters.

The project will deliver in-person training in Anguilla, British Virgin Islands, Montserrat and the Turks and Caicos Islands and online training in the 4 aforementioned OTs, Bermuda and the Cayman Islands.

## Project Background

UK OT Coral Reef Initiative

The Department for Environment, Food and Rural Affairs (Defra) in collaboration with the Joint Nature Conservation Committee (JNCC), the Centre for Environment, Fisheries and Aquaculture Science (Cefas) and the Foreign, Commonwealth and Development Office (FCDO) are developing a collaborative initiative with Overseas Territories (OTs) to improve understanding of the status of coral reefs, the pressures affecting them, the current national and regional policies in place and the actions necessary to ensure their long-term protection.

Through this initiative, Caribbean and Western Atlantic UK OTs have developed coral reef Action Plans that outline tailored priority areas for coral reef conservation within the OTs and at a regional level that help to underpin conservation efforts.

Implementing the Action Plans

JNCC is working with the UK OTs to implement the coral reef action plans in individual OTs and, where it makes sense to do so, work collaboratively to share skills and knowledge.  Current high priority activities include:

- sharing knowledge and experience responding to stony coral tissue loss disease (SCTLD), in particular in-water management interventions;

- proactive education and outreach to raise awareness of SCTLD and the risks it poses to reefs and the many benefits reefs provide to local communities and economies;

- data collection on the status and health of coral reefs through monitoring;

- Identifying management options available to individual OTs that will assist with improving the resilience of coral reefs through reducing pressures from human activities on land and in the sea;

Funding has been secured through the UK Government’s Conflict, Stability and Security Fund to support implementation of the Action Plans in 2021/22.

This contract

Management decisions require data and evidence before appropriate actions can be taken.  Coral reef monitoring programmes across the OTs range from fully in place, to recently re-started or soon to be established.  The rapidly emerging threat of SCTLD has increased the requirement for people capable of undertaking coral reef surveys, designing monitoring programmes and implementing adaptive management strategies to support coral reef conservation.

Global Coral Reef Monitoring Network

Monitoring methods vary in the Caribbean region and across the OTs. The contractor is requested to deliver training to a single standard, so that data can be shared locally, regionally and globally, thus supporting a wider understanding of the status of coral reefs.  The contractor is expected to tailor the training to enable attendees to use GCRMN-Caribbean guidelines.

GCRMN was established by the International Coral Reef Initiative (ICRI) in 1995, initially with the primary task of reporting on the condition of the world’s coral reefs in the context of the development of the International Coral Reef Initiative ‘Call to Action’. Since then, GCRMN has produced a range of global, regional and thematic reports on coral reef status and trends, supported countries globally to set up regional hubs, and developed a comprehensive range of guidelines and protocols for coral reef monitoring.

The contractor should have previous experience in the Caribbean region and expertise in GCRMN monitoring methodologies and training.  They will work with the Caribbean UK OT Governments, stakeholders, JNCC, and the UK OTs Coral Reef Initiative partners to organise and facilitate bio-physical and socio-economic coral reef monitoring training workshops in the UK OTs.

Logistics and Information to note

Given the ongoing Covid-19 pandemic, travel and gatherings of people are subject to changes in restrictions. As a result JNCC are requesting the contractor to consider the potential for changing restrictions in their proposal and to provide contingency plans should circumstances change as a result of Covid-19.

Contractors may bid for one or any of the following proposed objectives. We would particularly welcome bids from consortiums to cover shared delivery. We welcome suggestions from potential contractors on how to structure the training and outputs to maximise the educational experience of attendees and provide value for money by combining tasks.

## Project Objectives

To meet the overall aims of this project (Section 2), the objectives are:

- Work with the Caribbean UK OT Governments, stakeholders, JNCC, and the UK OT Coral Reef Initiative partners to organise and facilitate bio-physical coral reef monitoring training workshops in four OTs (Montserrat, Anguilla, British Virgin Islands and Turks and Caicos Islands).

- (We would welcome proposals to run a single event in a central Caribbean location, to include facilitation of travel of attendees from all four locations)

- Work with the six aforementioned Caribbean UK OT Governments, stakeholders, JNCC, and the UK OT Coral Reef Initiative partners to organise and facilitate an online workshop introducing socioeconomic coral reef monitoring methodology

## Project Objectives: Detailed Tasks

- Work with the Caribbean UKOT Governments, stakeholders, JNCC, and the UK OTs Coral Reef Initiative partners to organise and facilitate bio-physical coral reef monitoring training workshops in four OTs (Montserrat, Anguilla, British Virgin Islands and Turks and Caicos Islands). (Please note bidders are encouraged to bid for one or any elements of Objectives 1 & 2)

- We envisage that this will take the format of four separate training events in each OT, however, the proposal could present a suggestion of how events could be combined e.g. combining training events with multiple OTs, running individual events, or delivering elements online remotely.

- Develop a training agenda with JNCC and OT governments to meet requirements of each OT including: biophysical monitoring, data interpretation and data management. It is expected that there will be between 6 and 10 attendees from each OTs, with existing dive training.

- Book travel and subsistence for training events to align with JNCC Policies.

- Liaise with lead OT contacts to organise appropriate venues, facilities, and dive equipment and vessels as necessary. (Any costs associated with these should (e.g., boat hire costs) not be included in the quote).

- Submit event H&S risk assessment to JNCC prior to each event, including proof of appropriate insurance, where required.

- Facilitate liaison and regional communication with SPAW-RAC and other relevant agencies including invitation to speak at the event if appropriate.

- Work with JNCC and OTs to draft social media and other promotional materials around the event.

- Supply training materials to OTs for future coral reef monitoring training.

- Deliver 5-day training workshop. It is expected that there will be between 6 and 10 attendees at each event, with existing dive training.

- Design and circulate pre- and post-event questionnaires to measure change in understanding of participants and inform design of future training.

- Produce workshop reports following training events to include workshop summary and recommendations for each on successful implementation of a GCRMN monitoring programme.

- Provide support post-workshop to guide data interpretation and advise on data management.

- Work with the six aforementioned Caribbean and Western Atlantic UKOT Governments, stakeholders, JNCC, and the UK OTs Coral Reef Initiative partners to organise and facilitate an online workshop introducing socioeconomic coral reef monitoring methodology

  - Work alongside JNCC and OTs to design and deliver an introductory 1-day online workshop on socioeconomic coral reef monitoring methodology, including case studies of use and interactive sessions, or delivering elements online remotely).

  - Host the workshop using a chosen online platform, distribute invitations and track participant’s attendance.

  - Design and circulate pre- and post-event questionnaires to measure change in understanding of participants and inform design of future training.

  - Work with JNCC and OTs to draft social media and other promotional materials around the event.

  - Produce workshop report to include details of attendance, analysis of pre and post workshop questionnaires and suggestions for future training.

  - Provide recording of the online workshop for future training for the UK OTs.

## Potential Follow-On Work

Bidders should be aware that there is the potential for the successful bidder to be requested by JNCC to undertake additional work on this contract into the financial year 2021/22 or 2022/2023 (please indicate year) as follows:

- Deliver further GCRMN training workshops into 2022/2023

Please note that the potential for additional work to be undertaken is subject to a continuing need, availability of funds and satisfactory contractor performance. For the avoidance of doubt, no guarantee can be given that the selected contractor will be asked to undertake the potential additional work outlined within this Annex A document. Bidders are not asked to provide detailed project plans for these follow-on aspects at this stage.

## Outputs

Any products or outputs submitted to JNCC should adhere to JNCC’s house-style, in CSSF Programme templates, and should be produced in an accessible format (see Section 8, Product Specification for more information).

It is expected that this contract will produce the following outputs:

- Workshop Reports for four GCRMN training events to be completed in templates provided by JNCC.

- Hard and digital copies of training materials used in GCRMN training events, including recordings of online training workshops.

- After-workshop data management and interpretation support.

## Product Specification

JNCC is committed to making its publicly available resources and documents accessible, in accordance with the Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.

Making material accessible means making sure it can be used by as many people as possible.  This includes those with:

- impaired vision

- motor difficulties

- cognitive impairments or learning disabilities

- deafness or impaired hearing

The outputs and material that JNCC publishes should be compliant with the Web Content Accessibility Guidelines version 2.1 AA standard.

To meet this standard, all reports and other documentation which are to be made publicly available must adhere to JNCC’s house-style (to be provided) and be produced using a JNCC CSSF template (to be provided), unless otherwise stated.  All reports (draft and final) should be provided electronically via email both as a Microsoft Word document and an Adobe PDF.  Templates will be supplied to the successful bidder.

Copies of documentation associated with case studies should be provided in electronic format with an associated reference catalogue.

For any other outputs or products which are to be made publicly available through JNCC, evidence regarding how the accessibility standard will be reached should be included.

(Note for author if research project/contract: see EQA Policy Appendix 4 (Communicating Evidence Quality). Ensure that data management and storage requirements are stipulated taking into account relevant policy for data access. See https://jncc.gov.uk/about-jncc/corporate-information/evidence-quality-assurance/

## Dissemination

The products/outputs produced under this contract will be the property of JNCC and shall not be published or disseminated without the written permission of JNCC. Outputs may at some point be published on the JNCC website and all material supplied as part of this contract shall remain copyright of JNCC. The findings from this contract will also be made available to staff within JNCC, Defra, FCDO, The International Coral Reef Initiative Steering Group and the UKOT Collaborative Coral Reef Working Group.

## Timescale

Provisional dates for delivery of the contact outputs are set out below. Exact dates are to be agreed at the start-up meeting based on Contractor and JNCC staff availability.

| Output | Provisional Date |
| --- | --- |
| Start-up meeting (Online) | W/E 10th December 2021 |
| Online and in-person training schedules agreed | end of December 2021 |
| Online training workshops | January – March 2022 (exact dates to be confirmed with UKOTs and JNCC, based upon OT availability) |
| In-person training events conducted | January – March 2022 (exact dates to be confirmed with UK OTs and JNCC). |

In agreeing exact dates, please note that the potential for work under this contract to be funded into 2022/23 is subject to availability of funds.

## Health and Safety

The successful bidder is expected to follow appropriate Health & Safety procedures including adhering to JNCC’s policy on safeguarding. For further information  https://jncc.gov.uk/about-jncc/corporate-information/safeguarding/ and to be able to undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by the JNCC H&S Advisor).

Any incidents occurring within the contract should be immediately reported to JNCC.

The contractor is expected to provide their own travel insurance, Diver Alert Network (DAN) insurance and public indemnity insurance.

## Project Management

The successful Contractor shall nominate a project manager who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Name: Bryony Meakins

Email: Bryony.meakins@jncc.gov.uk

Telephone: +44(0)1733  866950

Name: Abbie Dosell

Email:  abbie.dosell@jncc.gov.uk

Telephone: +44 (0)1733 866930

## Instructions for Bid Submission

The bid submission should include the following:

A brief summary of the bidder’s experience in relation to the requirements of this contract (including SCUBA diving certifications);

Details of which elements of the project the proposal covers (the bidder may submit proposals that deliver any or all elements of the above Annex A. If bidder proposes to deliver multiple elements, suggestions for streamlining activities, such as the workshop reports, are welcome.);

A proposed approach for achieving the objectives of the contract and delivering the detailed tasks identified within each objective. This should be sufficiently detailed to allow assessment against the evaluation criteria (Section 14);

A detailed project plan (including Gantt chart) with proposed work programme and training schedules and an estimate of time required to achieve each objective;

A draft Table of Contents for the workshop report;

Details of Quality Control procedures to be followed

Details of the bidder’s own internal Quality Management System;

Details of the Project Team including their roles and experience, an estimate of their time input into each task and CVs of all personnel who will be involved in the contract/project;

Availability of the Project Team for a virtual start-up meeting in the W/C 6th December 2021 to align with GMT.

Overall quote for the contract to include:

  - Day rates (in GBP) for all members of the Project Team;

  - Costs and time allocation should be clearly allocated to specific tasks within this contract/project; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and if so, provide their VAT registration number.

The following documentation:

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates;

  - Copies of any appropriate risk assessments; and

  - Copies of any environmental policies should you have them.

In addition, note that the bid submission should provide sufficient information to allow assessment against the evaluation criteria outlined in Section 14.

## Evaluation Criteria

JNCC is not bound to accept the lowest priced or any bid. Having the technical expertise and experience to complete the work to a high standard and being able to complete it within the timescale are of the essence for this contract.

The bid evaluation may be undertaken by a panel consisting of JNCC staff and members of the UKOT Coral Reef Project Management Group.

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Maximum Score | Score |
| --- | --- | --- | --- |
| 1. Quality of Bid (50% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal particularly work programme and deliverables | 10 |  |
|  | Understanding of, and relevance to, the requirements in particular the adequacy of outputs and understanding of and familiarity with GCRMN methodologies, conducting training in small-island settings, dive certifications and data management. | 10 |  |
|  | Soundness and logicality of methods | 5 |  |
|  | Realism and measurability of outputs | 5 |  |
|  | Evidence provided of how accessibility standards will be met | 5 |  |
|  | Identification and proposed solutions to potential risks/issues | 5 |  |
|  | Serious weaknesses which threaten success | 5 |  |
|  | Probability of success | 5 |  |
|  | Sub Total | 50 |  |
| 2. Details of Contractor (20% of the total for the three assessment categories) |  |  |  |
|  | Expertise, experience, and balance of team | 9 |  |
|  | Risks if important team members drop out | 5 |  |
|  | Adequacy of subcontractors if any | 6 |  |
|  | Sub Total | 20 |  |
| 3. Cost (30% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation what does presentation mean here in relation to cost? | 10 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 6 |  |
|  | Appropriateness of ratio of senior to junior staff time | 6 |  |
|  | Clarity of each team member’s contribution and value added | 8 |  |
|  | Sub Total | 30 |  |
| Total Score |  | 100 |  |

## Payment

Payments will be split. 20% of contract value will be paid upon approval of training schedules, following the submission of invoice(s). The remaining amount will be paid upon completion of the objectives following the submission of invoice(s) and based on the satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key outputs.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates/fees given.

The bidder is expected to supply all necessary equipment, software, licences, insurance, etc. to carry out the obligations required under the contract.