# Annex A

| Title of project: | Technical assistance in developing a Method for Producing Soil Health Indicators for England |
| --- | --- |
| Date and time for return of tenders: | Monday 12 April 2021 @16:00 hours |
| Contract Reference No: | C20-0171-1550 |
| Address for tender submission: | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND TENDERS DIRECTLY TO HANNAH HOSKINS, LAWRENCE WAY OR DORA IANTOSCA VIA THEIR PERSONAL EMAIL ADDRESSES, AS THIS WILL INVALIDATE YOUR TENDER Tender responses must be less than 10 MB in size. On receipt of your tender, you will receive an automated e-mail to confirm receipt by JNCC Support Co. If you do not receive this automated email, please contact, in the following order: Sue Wenlock (00 44 1733 866880) Chris Downes (00 44 1733 866877) |
| Contacts for technical information relating to this project specification: | Hannah Hoskins Joint Nature Conservation Committee Email: hannah.hoskins@jncc.gov.uk Tel: 01733 866953 OR Lawrence Way Joint Nature Conservation Committee Email: Lawrence.Way@jncc.gov.uk Tel: 01733 866860 |
| Contact for any queries regarding the tendering procedure: | Dora Iantosca Finance Team Joint Nature Conservation Committee Email: Dora.Iantosca@jncc.gov.uk Tel: 01733 866894 |
| Proposed start-date: | 26 April 2021 |
| Proposed end-date: | 24 September 2021 |

Contents

1.	Joint Nature Conservation Committee	3

2.	Introduction	3

3.	Background to the Overall Project	3

4.	Aims of the Overall Project	5

5.	Objectives of this Contract	6

6.	Detailed tasks	6

7.	Outputs Required From Contractor	10

8.	Dissemination	11

9.	Governance and Management of the Overall Project	11

10.	Timescale	12

11.	Health and safety	12

12.	Product specification	13

13.	Instructions for tender submission	13

14.	Evaluation Criteria	14

15.	Payment	15

16.	Additional Contractor requirements	15

17.	References	15

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation. Its work contributes to maintaining and enriching biological diversity, conserving geological features and sustaining natural systems.

Our role is to provide evidence, information and advice so that decisions are made that protect natural resources and systems. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminate knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on the JNCC intranet: https://jncc.gov.uk/about-jncc/

## Introduction to Project and Research Service Required

Indicators of soil health are required by Defra and other key stakeholders, including Natural England, Environment Agency, and Forest Research/Forestry England. Additionally, these will make an important contribution to the 25 Year Environment Plan (25 YEP), both through tracking changes in soil health across England and through understanding the effectiveness of interventions.

JNCC is co-ordinating a project funded by Defra to develop a method for producing soil health indicators. JNCC expertise includes developing indicators for use by policymakers, facilitating stakeholder input, and conceptual ecological models. As such, a contractor with complementary expertise – particularly technical understanding of soil systems – is required to provide a research service and form a partnership with JNCC to co-develop the method for producing soil health indicators. Key areas in which the contractor would contribute include reviewing existing soil health indicators, developing a conceptual model, and linking model outputs with soil health. These roles are described in more detail below.

- Sections 3-4 describe the Background and Aims for the overall project.

- Section 5 describes the Objectives for this contract (i.e. what the involvement of the contractor is expected to provide to the overall project).

- Sections 6-7 provides more detail on the tasks that will be required from the contractor, including suggested time allocations and how the work programme would be divided with JNCC.

## Background to the Overall Project

The overall project being co-ordinated by JNCC is to develop soil health indicators. A better understanding of soil health and how it can be improved is a priority within the 25 YEP because of the importance of soils to farming and forestry and because soil health underpins a range of ecosystem functions and services across all land use types. Key uses of soil health indicators include designing and evaluating interventions as well as providing national-level monitoring of trends in soil health. However, although the importance of soil health indicators is widely acknowledged, developing suitable indicators must also address several challenges, including:

- Uncertainties and knowledge gaps over links between interventions/pressures, soil variables, and ecosystem services.

- Inherent differences in the ecosystem services that different soils are expected to provide, as a result of underlying factors that are outside management control (e.g. topography, climate, parent material). This makes it potentially difficult to develop indicators that are comparable across all soils in England.

- A potential need for trade-offs in the ecosystem services that can be provided by soils (e.g. managing to optimise agricultural production might reduce effectiveness for carbon storage)

- The wide range of potential users of soil health indicators with different interests and working at different spatial scales.

- There are potentially many approaches to developing indicators, which may result in competing or incompatible systems.

- The need to develop a monitoring programme, including e.g. sampling strategy and field protocols, data processing and reporting etc.

The overall project will focus on developing methods for producing soil health indicators and so relates to the first five of the above challenges. The overall project will involve the following work packages (WP):

WP1:	Reviewing soil health metrics already in use in the UK and internationally.

(WP2:) 	Reviewing approaches used to produce metrics that capture complexity in other systems (e.g. water quality metrics, site condition assessments) to determine whether any can be usefully adapted for soils. NB: this is a relatively small piece of work that will be carried out by JNCC – the contractor is not expected to contribute, and so further details are not provided in this specification.

WP3:	Producing a conceptual framework that allows determination of the expected optimum and range for ecosystem services provided by soils with any given set of underlying environmental variables. The conceptual framework should also show what data need to be collected to understand soil health.

WP4:	Using outputs from WP1-3 to interpret the data collected and produce indicators that are comparable across land uses and ecosystem services drawing on insights from wider stakeholder engagement.

An overview of the intended involvement of JNCC, the contractor, and other stakeholders is shown in Table 1. Plans to develop a soil monitoring programme are being designed by Natural England (NE), who will be closely involved as one of the key stakeholders for this project.

Table 1: Outline of key participants in the overall project and approximate involvement in the four activities listed above

| Organisation | Main role | Involvement in WP |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Review soil indicators | Review other indicators | Conceptual model | Developing indicators |
| JNCC | Co-ordinating overall project | ✓ | ✓✓✓ | ✓✓✓ | ✓✓✓ |
| Contractor | Provide soil science expertise | ✓✓✓ | N/A | ✓✓✓ | ✓✓ |
| Defra, Natural England, Environment Agency, Forestry England | End users of indicators. Main involvement through steering direction of project | ✓ | ✓ | ✓ | ✓✓ |
| Wider stakeholders (e.g. NGOs, NFU) | Provide perspectives and priorities to inform indicator development | N/A | N/A | N/A | ✓ |
| Independent experts | Provide constructive challenge and expert review | N/A | N/A | ✓ | ✓ |

Definitions

For this project, ‘soil health’ is defined as:

The ability of the soil to perform its functions. The range of functions and ecosystem services provided should reflect the different capabilities of different soils – a ‘healthy’ soil is therefore one in which ecosystem services are provided at an acceptable level given inherent underlying constraints and the purpose of the land.

A ‘soil health indicator’ is defined as:

A measure that can be used by policymakers and other stakeholders to understand soil health and if/how it is changing. Indicators should be interpretable by users e.g. in terms of where soil health is currently good or bad.

This is not the same as a variable that is used to directly measure or indicate ecosystem functions or processes (e.g. C:N ratio), which then requires further interpretation and/or information to make an assessment of soil health.

## Aims of the Overall Project

The project will be co-ordinated by JNCC, and the overall aim is to develop a method (framework) for producing indicators that can be used to assess changes in soil health across England and to understand the effectiveness of interventions. It should be feasible to provide at least a basic level of monitoring and mapping of these indicators across England using current data and protocols, although additional approaches will probably be needed for a fully comprehensive measure. Indicators should be applicable across all soils in England and should reflect the aims of the 25 Year Environment Plan, e.g. in relation to ecosystem services and natural capital, biodiversity conservation, and sustainable soil management. Soil health indicators should also be produced and agreed collaboratively with input from a range of stakeholders in the public, private and NGO sectors as well as the research community.

## Objectives of this Contract

This contract is to contribute expertise to help meet the aims of the overall project. The objectives for the contractor in relation to the four work packages described in Section 3 are as follows:

- Lead on carrying out a review and evaluation of existing soil health indicators being used in the UK and internationally (WP1).

- With JNCC, jointly discuss and agree on the approaches for producing a conceptual model of the soil system, in particular how it relates to ecosystem services and mechanisms for reporting on service delivery. The contractor should then lead on populating the resulting model using soil science expertise e.g. of relevant soil properties, processes and functions. As far as possible, the contractor should ensure that this model is scientifically robust and provides a credible framework for the wider research community interested in soil health (WP3).

- With JNCC, agree and carry out a programme of work that uses the outputs from WP1-3 to develop a method for producing soil health indicators. As far as possible, the contractor should ensure that this method is scientifically robust and credible to the wider research community (WP4).

## Project Objectives: Detailed tasks

This section describes the research service the contractor is expected to provide for WP1, WP3, and WP4. An approximate suggestion is given below of what proportion of the contract value should be allocated. However, proposals are free to suggest alternative allocations if these are felt to be more appropriate. (The contractor is not required to contribute to WP2, which will be carried out by JNCC).

Contractor contribution to WP1: Lead on carrying out a review and evaluation of existing soil health indicators being used in the UK and internationally. (~20% of overall contract)

A brief review of existing and in-development metrics is important for identifying (i) any soil health indicators that could be adapted for use in England, (ii) any metrics already in use in England for which there is a risk that new indicators might create conflicts, and (iii) any general lessons and strengths and weaknesses in relation to existing or in-development indicators.

Scope of Review

- For this exercise, relevant indicators are restricted to those that specifically refer to soil health (or a closely related term, e.g. ‘quality’). The definition of ‘soil health indicators’ emphasises measures that are used to understand (for example) whether soil health is good or bad. Measures that are solely indicating the level of ecosystem functions or processes (e.g. C:N ratio) and then require further interpretation and/or information to make an assessment of soil health are not a priority.

- The review should include indicators that are:

  - specific to particular habitats, land uses or soil types as well as more general indicators;

  - assessed nationally as well as indicators that are used at smaller spatial scales;

  - in use in the UK as well as those used internationally.

- The review should include peer-reviewed literature and grey literature where appropriate. Direct discussions with relevant organisations may be necessary where key information is not easy to find using conventional academic databases or websites.

Contents of the Review

The review should contain descriptive information for each relevant indicator. This can be discussed and refined to ensure feasibility, but is likely to involve at least some of the following:

- Which variables are measured to produce each indicator..

- What habitat, land use or soil types are covered.

- How each indicator is intended to be used, including how it links to soil functions and ecosystem services.

The review should highlight key indicators that could be adapted for use in England and any that could conflict with any new soil health indicators produced for England. It should also provide commentary on general problems in existing indicators and if/how these have been tackled. Findings from this exercise should inform WP4.

Required information from prospective contractor proposal

The main purpose of the review is to identify and describe the most important and relevant existing indicators in the UK and internationally. As such, a comprehensive list of all possible soil health indicators is not required. However, tender responses should describe the methodology behind the process for ensuring that key indicators are found, including the approach to literature searching and additional discussions with relevant organisations. Proposals should also state how the information about soil health indicators will be presented.

Contractor and JNCC responsibilities

The contractor is expected to lead this work with minor input from JNCC (e.g. to clarify scope and outputs).

Contractor contribution to WP3: Jointly discuss and agree on the appropriate approaches for modelling the soil system with JNCC. The contractor should then lead on populating the resulting model using soil science expertise e.g. of relevant soil properties, processes and functions. As far as possible, the contractor should ensure that this model is scientifically robust and credible to the wider research community. (~50% of overall contract)

WP3 aims to develop a conceptual model of the soil system (e.g. Figure 1). The model should describe how environmental variables (e.g. pH, climate, topography, hydrology etc.) influence soil properties and processes and, in turn, ecosystem functions and services.

The model has three purposes:

- To determine the expected optimum and range for ecosystem services provided by soils with a given set of underlying environmental variables.

- To identify what data to collect to monitor soil health; these recommendations should take into account practicality.

- To plan and evaluate the effects of interventions, alongside other evidence.

The model should be relevant to all soils across England, and any areas of uncertainty should be stated.

Figure 1: Example network-diagram type systems model. Note that this form of model is not the only acceptable approach, and that the example provided here is for illustrative purposes only.

Required information from prospective contractor proposal

The conceptual model will be developed collaboratively with JNCC during the project. As such, proposals are not expected to provide extensive details on the modelling approach that would be used. However, proposals should indicate:

- Whether the contractor would favour any existing soil models and/or general modelling approaches.

- How the contractor would identify variables to include in the model, and how the relationships between these variables would be determined. Approaches to generating the information to construct the model might include a literature review, analysing existing datasets, expert judgement/workshop etc.

- How the model could be validated and quality assured.

- Key potential challenges with producing a conceptual model of the soil system and the feasibility of overcoming these.

Contractor and JNCC responsibilities

JNCC and the contractor will jointly agree on the eventual modelling approach, with JNCC leading if the contractor has limited expertise in conceptual models. JNCC will be responsible for guiding the process to ensure the model meets requirements of end users in public bodies. The contractor will be responsible for ensuring that the model contains all relevant components and accurately describes the links between environmental variables, soil properties and processes, ecosystem functions, and ecosystem services. The contractor will also be responsible for validating the model and ensuring an appropriate level of quality assurance and peer-review from the wider research community is attained.

Contractor contribution to WP4: Support JNCC in co-developing measures of soil health that are comparable across all soils in England. (~30% of overall contract)

JNCC and the contractor will agree and carry out a joint programme of work that uses the outputs from WP1-3 to develop soil health indicators that are comparable across all soils in England. As such, the contractor should allocate at least 30% of the contract value to WP4, with the details of the work involved to be agreed in June of 2021.

The purpose of WP4 is to develop soil health indicators that show how closely currently delivered ecosystem services relate to the expected optimum given underlying constraints such as climate, soil type etc. The indicators therefore need to account for inherent differences between soils where these arise from factors outside management control. For example, the carbon stored by degraded peatland might be high relative to other habitats but low relative to the expected optimum for peat and so soil health would be low. The soil indicators also need to account for trade-offs between outcomes, such that the provision of different ecosystem services is given appropriate weight when assessing soil health relative to the expected optimum.

In addition to being scientifically robust, it is important to be able to map the soil health indicators using existing data sources and/or data that are relatively straightforward to collect. Soil health indicators also need to be acceptable and usable by a range of stakeholders. As such, WP4 will require consultation to understand needs of key end users (e.g. soil health policy leads in public bodies) and consensus-building to ensure acceptability to wider stakeholders (e.g. NGOs, farmers, foresters etc.). This will largely be achieved through a workshop that will be organised and led by JNCC (with contractor attendance/participation).

Required information from prospective contractor proposal

JNCC and the contractor will work closely to co-develop soil health indicators using the outputs from WP1-3. As such, proposals are not expected to contain a detailed method for producing indicators. However, proposals should include:

- A brief outline of any approaches to producing soil health indicators that would be favoured by the contractor.

- Key potential challenges with developing indicators that are comparable across soils.

- Suggested approach to stakeholder consultation and quality assurance/peer-review of outputs.

- Any experience in producing indicators to understand complex systems (not necessarily soil-related) and/or meet the needs of multiple stakeholders.

- Any required adjustments to proposed timeline including a timeline (with justification of changes where needed) for alternative provisional dates.

Contractor and JNCC responsibilities

JNCC will oversee the process and provide expertise in developing policy-relevant indicators and engaging end users with government. The contractor will be responsible for ensuring that the soil health indicators are correct from a technical perspective and for organising independent peer-review and quality assurance. Both JNCC and the contractor are expected to contribute to stakeholder engagement.

Potential follow-on work

Tenderers should be aware that there is the potential for the successful contractor to be requested by JNCC to undertake additional work on this contract, up to financial year 2021/2022, as follows:

- Contribute to design and execution of case studies to assess the comparability of the designed framework.

- Contribute to adjustments and improvements to methodology as they arise from case study assessments.

- Provide input to the content of and attend additional stakeholder engagement events run by JNCC, which will aim to educate and consult a wide range of stakeholders with an interest in the adoption of framework for interpreting soil health.

Please note however that the potential for additional work to be undertaken is subject to a continuing need, availability of funds, and satisfactory contractor performance. For the avoidance of doubt, no guarantee can be given, that you will be asked to undertake the potential additional work outlined within this Annex A document. Tenderers are not asked to provide detailed project plans for these follow-on aspects at this stage.

## Outputs Required From Contractor

The key outputs are:

- A brief review of the most relevant soil health indicators. This should include strengths, weaknesses, potential applicability, and risk of conflicting with a new soil health indicator.

- Incorporation of relevant soil properties, processes and relationships into a conceptual ecological model that links environmental variables, ecosystem functions, and ecosystem services. Use of the model to assess the expected ecosystem services for a given set of underlying environmental variables. Use of the model to identify what data to collect in order to monitor soil health.

- Ensure external per review is conducted of technical recommendations prior to their use in forming a framework for soil health indicator development.

- A demonstrable contribution (approx. 30% of the contract value) to support JNCC in developing provisional soil health indicators including workshop attendance and support.

## Dissemination

The report produced under this contract will be a JNCC product and shall not be published or disseminated without the written permission of JNCC. It may at some point be published on the JNCC website and all material supplied as part of this contract shall remain copyright of JNCC. The findings from this contract will also be made publicly available.

## Governance and Management of the Overall Project

JNCC are responsible for delivering the ‘Developing a soil health indicator for England Project’ for Defra.  This project has the following Governance:

Steering Group

The project will have a steering group comprised of representatives from Defra, Natural England, Environment Agency, and Forestry Commission England.  The Steering Group will provide technical direction, evaluating project proposals and outputs at key milestones.  Currently these would be inception, model approach and workshop design, workshops outcomes, and draft final project outputs.  The JNCC project manager would lead project team engagement with the steering group and JNCC would provide secretariat to the steering group.  The contractor would attend relevant steering group meetings and lead agenda items relevant to their discrete work package responsibilities and contribute on others.

Stakeholder Groups

The project will provide briefings and collect feedback from established Defra stakeholder groups that have an interest in soils.  The Steering Group will advise the project team on the composition and best ways of engaging with stakeholders to ensure good participation of the relevant soils expertise, and those with a strong interest in using and applying soil indicators in the activities of the project.  JNCC will take responsibility for the logistics of communicating with stakeholders (meetings, virtual meetings, calls for input etc). The contractor will participate in stakeholder engagement activities (leading where input is needed on work packages where the contractor leads or is contributing to others).

Project team

The JNCC Project Manager will hold regular short checkpoint meetings for the whole team, JNCC staff and contractor staff, working on the project to coordinate and shape delivery.

Contractor project management

The contractor will have a single point of responsibility able to track and report on their progress, and who is responsible for all contractor deliver, and the quality of the delivery.

## Timescale

Provisional dates for delivery of the contract outputs are set out below. Exact dates are to be agreed at start-up meeting based on Contractor and JNCC staff availability. The Contractor should suggest additional milestones that are relevant to the approach that will be taken, and proposed revised timescale as required (please see related evaluation criteria score in Section 14 below).

| Milestones | Provisional dates |
| --- | --- |
| Start-up meeting | w/c 26th April 2021 |
| Complete review of soil health metrics Mid-project workshop / discussion with key stakeholders in public bodies (Defra, Natural England etc.) | by 5th June 2021 |
| Draft conceptual model produced Work programme for WP4 produced | 18th June 2021 |
| Conceptual model finalised with external expert input and quality assurance (potentially for workshop) | 2nd July 2021 |
| Draft soil metrics approach and illustrative examples developed | 16th July 2021 |
| Soil health metrics approach finalised with external input and quality assurance (potentially via workshop) | 13th August 2021 |
| Final outputs provided | By 24th September 2021 |

## Health and safety

The Contractor is expected to follow appropriate Health & Safety procedures and undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by JNCC H&S advisor).

Any incidents occurring within the contract should be immediately reported to JNCC.

## Product specification

Any reports must adhere to the JNCC report template and house style guidance unless stated otherwise. The draft and final reports should be provided electronically via email both as a Microsoft Word document and an Adobe PDF. Outputs should comply with JNCC Evidence Quality Assurance policy (https://jncc.gov.uk/about-jncc/corporate-information/evidence-quality-assurance/), including in relation to Communicating Evidence Quality (Appendix 4).

## Instructions for tender submission

The tender submission should include the following:

A brief summary of the potential Contractor’s (and any proposed subcontractors where relevant) experience in relation to the requirements of this contract, in particular (i) soil science expertise, (ii) experience with developing indicators for complex systems and/or conceptual ecological models, (iii) experience working with multiple stakeholders with differing priorities;

A proposed approach for achieving the objectives of the contract, including any subcontracting, and identification of potential challenges for the overall project. This should be sufficiently detailed allow assessment against the evaluation criteria (Section 14);

A project plan (including Gantt chart) and estimate of the time required for WP1, WP3 and WP4, and a proposed work programme for WP1 and for WP3;

Details of Quality Control procedures to be followed. This should be in accordance with JNCC Evidence Quality Assurance policies;

Details of the Contractor’s own internal Quality Management System;

Details of the Project Team, including their roles and experience (including relevant publication records), an estimate of their time input into each task, and CVs of all personnel (including any subcontractors) involved in the contract;

Availability of the Project Team for a start-up meeting in mid-late April;

Overall quote for the contract, to include:

  - Daily rates for all members of the Project Team;

  - Rates for attending start-up, interim and final meetings remotely;

  - Costs and time allocation should be clearly allocated to specific tasks within this contract including any subcontracting; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and to provide their company’s VAT registration number.

The following documentation:

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates; and

  - Copies of any appropriate risk assessments.

  - Copies of any environmental policies should you have them.

In addition, note that the tender submission should provide sufficient information to allow assessment against the criteria outlined in Section 14.

For information on how we handle personal data please see our Privacy Notice at http://jncc.defra.gov.uk/privacypolicy.

## Evaluation Criteria

JNCC are not bound to accept the lowest priced or any tender.  Having the technical expertise and experience to complete the work to a high standard, and being able to complete it within the timescale, are of the essence for this contract.

The tender evaluation will be undertaken by a panel consisting of JNCC staff and staff members from Natural England, Defra, and the Environment Agency.  Unless otherwise stated in your tender submission will be forwarded to these agencies for evaluation purposes only.

Tenders will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Max Score | Score |
| --- | --- | --- | --- |
| 1. Quality of proposal, (45% of the total for the three assessment categories) |  |  |  |
|  | Overall clarity of proposal (particularly work plan, milestones, and deliverables) and availability within our desired timeframe | 10 |  |
|  | Suitability of methods and outputs for WP1 and probability of success | 5 |  |
|  | Suitability of response for WP3 and probability of success | 15 |  |
|  | Suitability of response for WP4 and probability of success | 10 |  |
|  | Identification of potential problems/risks and proposed solutions | 5 |  |
|  | Sub Totals | 45 |  |
| 2. Details of Contractor (30% of the three assessment categories) |  |  |  |
|  | Demonstration of suitable expertise and experience (including any subcontractors) with examples of successful work in any of the following areas: soils monitoring, complex systems, conceptual models, indicator development, working with multiple stakeholders | 22 |  |
|  | Risks if important team members drop out | 8 |  |
|  | Sub Totals | 30 |  |
| 3. Cost (25% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation | 8 |  |
|  | Fairness/reasonableness of costs for the level of work and expertise required | 12 |  |
|  | Clarity of each team member’s contribution and value added | 5 |  |
|  | Sub Totals | 25 |  |
| Total score |  | 100 |  |

## Payment

Payment will be made on completion of the objectives, following the submission of an invoice(s); and based on satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Contractor requirements

All tenderers are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key milestones.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates and fees given.

The Contractor is expected to supply all necessary equipment, software, licences etc. to carry out the obligations required under the contract.

## References

https://www.parliament.uk/business/committees/committees-a-z/commons-select/environmental-audit-committee/inquiries/parliament-2015/soil-health/