## Priority 1 Programme
| Project | Comments/Description of Works | Estimated Project Duration | Contractor | Contractor | Contractor | Contractor | Contractor | Contractor | Contractor | Contractor | Contractor | Contractor | Contractor | W/C 29.07.2019 | [6 empty] | W/C 05.08.2019 | [6 empty] | W/C 12.08.2019 | [6 empty] | W/C 19.08.2019 | [6 empty] | W/C 26.08.2019
[15 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
[15 empty] | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1
1 | CONSTRUCTION BUILDING - 1ST FLOOR | Construction first floor corridor and classrooms Decoration Flooring Ceiling tiles | 2 weeks | Classic | Ian Williams |  | Bell | CLC
2 | CONSTRUCTION BUILDING - CONVERSION TO AUTOMOTIVE | Demolition, supply and fit roller door Decorate Electrical services for ramp | 2 weeks | Classic | Ian Williams |  |  |  | DAB
3 | CREATION OF NEW ART ROOM IN HOSPITALITY | Knock 2 x classrooms in to 1 - 211A and 211B New vinyl flooring Make good ceiling Decoration Installation of new sink | 2 weeks | Classic | Ian Williams |  |  | CLC
4 | CRIME SCENE ROOM | Flooring, ceiling, decoration and removal of shelving | 1 week | Classic | Ian Williams |  |  |  |  | TEC
5 | DANCE STUDIO WALL REMOVAL | Combine two rooms to include wall removal, making good to floor and ceiling and move power installations | 1 week | Classic | Ian Williams |  |  |  |  | TEC
6 | DELI ENTRANCE STEPS | Resurface/refit | 1 week | Classic | Ian Williams |  |  |  |  | TEC
7 | IOT ROOM KI204 SW CAD SUITE | Refurbish and new furniture | 2 weeks | Classic |  | Purdy |  | CLC |  |  | Rogers
8 | MAIN CORRIDOR REFURBISHMENT | To reflect STEM building image | 4 weeks | Classic |  | Purdy |  | CLC | [5 empty] | Mercury
9 | STUDENT HUB REFURBISHMENT | Refurbish Student Hub to create zones. Removal of offices to increase space. Uplift flooring and recover, decorate. Fit out furnish. | 4 weeks | Classic |  | Purdy |  | CLC | [5 empty] | Mercury
10 | THEATRE AND SPORTS HALL | Redecoration works | 3 weeks | Classic | Ian Williams |  | Bell
11 | IOT ROOMS KS227-KS229 DIGITAL SUITE CONVERSION | Conversion to Computer rooms. Power and data installation - inc small cab Furniture to be reviewed Relocate radiator | 1 week |  |  | Purdy | [5 empty] | Rowe Elec | Bonnett
12 | NEW NAIL ROOM | Flooring, decoration, relocate nail bar and new power installations | 1 week |  |  | Purdy |  | CLC |  |  |  | Rowe Elec
13 | HE CORRIDOR REFURB | Decoration of corridor | 2 weeks | Classic | Ian Williams |  | Bell